## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 64 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 76 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 84 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 84 | 420000 | ACTION | 84 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 87.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 87.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 84.0008 | 875008.6892 | ACTION | 87.2441 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 96 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 104 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 124 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 136 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 144 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 147.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 152.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 153.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 156 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 163.6607 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 164 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 164.3838 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 164.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 165.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 166.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 167.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 167.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 176.5871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 177.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 178.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 182.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 186.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 189.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 195.0037 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 197.0037 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 257.0037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 262.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 263.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 273.4204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 274.1435 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 274.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 275.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 276.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 286.3467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 287.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 288.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 292.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 297.7634 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 357.7634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 363.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 364.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 374.18 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 374.9031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 374.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 375.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 377.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 387.1064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 388.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 389.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 393.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 398.523 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 458.523 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 463.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 464.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 474.9397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 475.6628 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 475.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 476.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 477.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 487.866 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 400.6219 | 2003109.644 | ACTION | 487.866 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 487.8668 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 488.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 489.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 491.1101 | MonopileInstallation
| Feeder 1 | Queue | 323.866 | 1619330.0311 | ACTION | 491.1101 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 493.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 499.2827 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 503.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 511.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 523.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 531.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 543.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 551.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 559.2827 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 563.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 564.6993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 565.6993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 571.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 574.3533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 574.3542 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 575.6993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 576.4224 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 576.4257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 577.4257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 578.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 588.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 589.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 590.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 594.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 600.0423 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 660.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 665.459 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 666.459 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 676.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 677.1821 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 677.1853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 678.1853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 679.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 689.3853 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 690.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 691.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 695.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 700.802 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 760.802 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 766.2186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 767.2186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 777.2186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 777.9417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 777.945 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 778.945 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 780.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 790.145 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 791.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 792.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 796.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 801.5616 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 861.5616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 866.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 867.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 877.9783 | MonopileInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 884.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 885.7014 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 885.7046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 886.7046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 887.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 897.9046 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 406.7945 | 2033972.5903 | ACTION | 897.9046 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 897.9054 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 898.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 899.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 901.1487 | MonopileInstallation
| Feeder 0 | Queue | 326.7945 | 1633972.5903 | ACTION | 901.1487 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 903.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 909.3213 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 913.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 921.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 933.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 941.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 953.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 961.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 969.3213 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 973.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 974.7379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 975.7379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 981.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 984.3919 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 984.3928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 985.7379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 986.461 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 986.4643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 987.4643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 988.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 998.6643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 999.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1000.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1004.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1010.0809 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1070.0809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1075.4976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1076.4976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1086.4976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1087.2206 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1087.2239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1088.2239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1089.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1099.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1100.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1101.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1105.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1110.8406 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1170.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1176.2572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1177.2572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1187.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1187.9803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1187.9835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1188.9835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1190.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1200.1835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1201.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1202.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1206.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1211.6002 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1271.6002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1277.0169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1278.0169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1288.0169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1288.7399 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1288.7432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1289.7432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1290.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1300.9432 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 1300.9432 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1300.944 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1301.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1302.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1304.1873 | MonopileInstallation
| Feeder 1 | Queue | 319.7945 | 1598972.5903 | ACTION | 1304.1873 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1306.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1312.3599 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1316.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1324.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1336.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1344.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1356.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1364.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1372.3599 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1376.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1377.7765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1378.7765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1384.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1387.4305 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1387.4314 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1388.7765 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1389.4996 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1389.5028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1390.5028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1391.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1401.7028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1402.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1403.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1404.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1409.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1413.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1419.1195 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1479.1195 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1484.5362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1485.5362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1495.5362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1496.2592 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1496.2625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1497.2625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1498.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1508.4625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1509.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1510.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1514.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1519.8792 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1579.8792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1585.2958 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1586.2958 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1596.2958 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1597.0189 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1597.0221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1598.0221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1599.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1609.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1610.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1611.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1615.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1620.6388 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1680.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1686.0555 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1687.0555 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1697.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1697.7785 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1697.7818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1698.7818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1699.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1709.9818 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 405.7945 | 2028972.5903 | ACTION | 1709.9818 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1709.9826 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1710.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1711.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1713.2259 | MonopileInstallation
| Feeder 0 | Queue | 325.7945 | 1628972.5903 | ACTION | 1713.2259 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1715.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1721.3985 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1725.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1733.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1745.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1753.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1765.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1773.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1781.3985 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1785.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1786.8151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1787.8151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1793.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1796.4691 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1796.4699 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1797.8151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1798.5382 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1798.5414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1799.5414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1800.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1810.7414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1811.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1812.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1816.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1822.1581 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1882.1581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1887.5748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1888.5748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1898.5748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1899.2978 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1899.3011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1900.3011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1901.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1911.5011 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1912.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1913.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1917.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1922.9178 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1982.9178 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1988.3344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1989.3344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1999.3344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2000.0575 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2000.0607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2001.0607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2002.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2012.2607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2013.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2014.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2018.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2023.6774 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2083.6774 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2089.0941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2090.0941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2100.0941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2100.8171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2100.8204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2101.8204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2103.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2113.0204 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 2113.0204 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2113.0212 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2114.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2115.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2116.2645 | MonopileInstallation
| Feeder 1 | Queue | 319.7945 | 1598972.5903 | ACTION | 2116.2645 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2119.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2124.4371 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2128.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2136.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2148.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2156.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2168.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2176.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2184.4371 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2188.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2189.8537 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2190.8537 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2196.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2199.5077 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2199.5085 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2200.8537 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2201.5768 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2201.58 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2202.58 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2203.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2213.78 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2214.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2215.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2219.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2225.1967 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2285.1967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2290.6134 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2291.6134 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2301.6134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2302.3364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2302.3397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2303.3397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2304.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2314.5397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2315.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2316.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2320.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2325.9564 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2385.9564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2391.373 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2392.373 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2402.373 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2403.0961 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2403.0993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2404.0993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2405.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2415.2993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2416.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2417.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2421.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2426.716 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2486.716 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2492.1327 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2493.1327 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2503.1327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2503.8557 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2503.859 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2504.859 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2506.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2516.059 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 2516.059 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2516.0598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2517.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2518.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2519.3031 | MonopileInstallation
| Feeder 0 | Queue | 319.7945 | 1598972.5903 | ACTION | 2519.3031 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2522.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2527.4757 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2531.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2539.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2551.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2559.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2571.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2579.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2587.4757 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2591.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2592.8923 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2593.8923 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2599.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2602.5463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2602.5471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2603.8923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2604.6154 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2604.6186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2605.6186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2606.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2616.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2617.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2618.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2622.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2628.2353 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2688.2353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2693.652 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2694.652 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2704.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2705.375 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2705.3783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2706.3783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2707.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2717.5783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2718.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2719.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2723.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2728.9949 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 42 | 437500 | ACTION | 2770.9949 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2830.9949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2836.4116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2837.4116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2847.4116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2848.1347 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2848.1379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2849.1379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2850.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2860.3379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2861.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2862.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2866.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2871.7546 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2931.7546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2937.1713 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2938.1713 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2948.1713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2948.8943 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2948.8976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2949.8976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2951.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2961.0976 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 441.7945 | 2208972.5903 | ACTION | 2961.0976 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2961.0984 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2962.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2963.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2964.3417 | MonopileInstallation
| Feeder 1 | Queue | 361.7945 | 1808972.5903 | ACTION | 2964.3417 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2967.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2972.5142 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2976.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2984.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2996.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3004.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 60 | 625000 | ACTION | 3032.5142 | MonopileInstallation
| Feeder 0 | Delay | 37 | 185000 | ACTION | 3041.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3053.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3061.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3073.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3081.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3084.5849 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3084.5857 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3092.5142 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3097.9309 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3098.9309 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3108.9309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3109.654 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3109.6572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3110.6572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3111.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3121.8572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3122.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3123.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3127.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3133.2739 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3193.2739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3198.6906 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3199.6906 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3209.6906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3210.4136 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3210.4169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3211.4169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3212.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3222.6169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3223.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3224.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3228.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3234.0335 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3294.0335 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3299.4502 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3300.4502 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3310.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3311.1733 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3311.1765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3312.1765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3313.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3323.3765 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3324.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3325.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3329.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3334.7932 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3394.7932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3400.2099 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3401.2099 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3411.2099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3411.9329 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3411.9362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3412.9362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3414.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3424.1362 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 459.7945 | 2298972.5903 | ACTION | 3424.1362 | MonopileInstallation | [14 empty] | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3425.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3426.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3430.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 11 | 55000 | ACTION | 3435.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3435.137 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3435.5528 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3438.3803 | MonopileInstallation
| Feeder 0 | Queue | 353.7945 | 1768972.5903 | ACTION | 3438.3803 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 2.8274 | 29452.1953 | ACTION | 3438.3803 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3450.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3458.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3470.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3478.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3490.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3498.3803 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3498.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3503.7969 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3504.7969 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3510.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3514.7969 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3515.52 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3515.5232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3516.5232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3517.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3518.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3521.6235 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3521.6243 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3527.7232 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3528.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 3535.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3536.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3538.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3542.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3548.1399 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3608.1399 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3613.5566 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3614.5566 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3624.5566 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3625.2796 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3625.2829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3626.2829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3627.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3637.4829 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3638.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3639.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3643.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3648.8995 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 113 | 1177083.3333 | ACTION | 3761.8995 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3821.8995 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3827.3162 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3828.3162 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3838.3162 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3839.0393 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3839.0425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3840.0425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3841.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3851.2425 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3852.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3853.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3857.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3862.6592 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3922.6592 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3928.0759 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3929.0759 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3939.0759 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3939.7989 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3939.8022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3940.8022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3942.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3952.0022 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 513.6219 | 2568109.644 | ACTION | 3952.0022 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3952.003 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3953.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3954.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3955.2463 | MonopileInstallation
| Feeder 1 | Queue | 433.6219 | 2168109.644 | ACTION | 3955.2463 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3958.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3963.4188 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3967.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3975.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3987.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3995.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4007.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4015.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 80 | 833333.3333 | ACTION | 4043.4188 | MonopileInstallation
| Feeder 0 | Delay | 37 | 185000 | ACTION | 4052.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4064.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4072.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4075.4895 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4075.4903 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4103.4188 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4108.8355 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4109.8355 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4119.8355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4120.5586 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4120.5618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4121.5618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4122.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4132.7618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4133.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4134.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4138.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4144.1785 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4204.1785 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4209.5952 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4210.5952 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4220.5952 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4221.3182 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4221.3215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4222.3215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4223.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4233.5215 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4234.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4235.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4239.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4244.9381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4304.9381 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4310.3548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4311.3548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4321.3548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4322.0779 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4322.0811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4323.0811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4324.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4334.2811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4335.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4336.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4340.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4345.6978 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4405.6978 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4411.1145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4412.1145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4422.1145 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4422.8375 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4422.8408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4423.8408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4425.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4435.0408 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 479.7945 | 2398972.5903 | ACTION | 4435.0408 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4435.0416 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4436.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4437.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4438.2849 | MonopileInstallation
| Feeder 0 | Queue | 362.7945 | 1813972.5903 | ACTION | 4438.2849 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4441.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4446.4574 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4450.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4458.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4470.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4478.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4490.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4498.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 98 | 490000 | ACTION | 4596.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4608.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 250 | 2604166.6667 | ACTION | 4696.4574 | MonopileInstallation
| Feeder 1 | Delay | 99 | 495000 | ACTION | 4707.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4715.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4718.5281 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4718.5289 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4756.4574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4761.8741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4762.8741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4772.8741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4773.5972 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4773.6004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4774.6004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4775.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4785.8004 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4786.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4787.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4791.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4797.2171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4829.2171 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4889.2171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4894.6338 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4895.6338 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4905.6338 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4906.3568 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4906.3601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4907.3601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4908.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4918.5601 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4919.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4920.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4924.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4929.9767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4989.9767 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4995.3934 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4996.3934 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5006.3934 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5007.1165 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5007.1197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5008.1197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5009.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5019.3197 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5020.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5021.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 5027.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5031.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5036.7364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5096.7364 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5102.1531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5103.1531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5113.1531 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5113.8761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5113.8794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5114.8794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5116.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5126.0794 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 687.7945 | 3438972.5903 | ACTION | 5126.0794 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5126.0802 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5127.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5128.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5129.3234 | MonopileInstallation
| Feeder 1 | Queue | 410.7945 | 2053972.5903 | ACTION | 5129.3234 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5132.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5137.496 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5141.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5149.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 24 | 250000 | ACTION | 5161.496 | MonopileInstallation
| Feeder 0 | Delay | 19 | 95000 | ACTION | 5168.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5180.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5188.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5221.496 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5226.9127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5227.9127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5237.9127 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5238.6358 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5238.639 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5239.639 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5240.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5250.839 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5251.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5252.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5256.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5262.2557 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 17 | 177083.3333 | ACTION | 5279.2557 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5339.2557 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5344.6724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5345.6724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5355.6724 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5356.3954 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5356.3987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5357.3987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5358.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5368.5987 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5369.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5370.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5374.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5380.0153 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 102 | 1062500 | ACTION | 5482.0153 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5542.0153 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5547.432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5548.432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5558.432 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5559.1551 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5559.1583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5560.1583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5561.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5571.3583 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5572.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5573.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5577.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5582.775 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 47 | 489583.3333 | ACTION | 5629.775 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5689.775 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5695.1917 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5696.1917 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5706.1917 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5706.9147 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5706.918 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5707.918 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5709.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5719.118 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 589.7945 | 2948972.5903 | ACTION | 5719.118 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5719.1188 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5720.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5721.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5722.362 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5725.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5730.5346 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 5730.5346 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 5730.5346 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 5730.5346 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5732.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5733.7779 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5734.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5736.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5738.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5740.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5741.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5742.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5742.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 12.25 | 61250 | ACTION | 5742.7846 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5744.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5746.0279 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 5746.0287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 12.2508 | 127612.8559 | ACTION | 5746.0287 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5746.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5748.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 58 | 604166.6667 | ACTION | 5804.0287 | TurbineInstallation
| Feeder 1 | Delay | 58 | 290000 | ACTION | 5806.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5808.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5810.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5811.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5812.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5813.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5816.2779 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 5816.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5864.0287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5869.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5870.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5870.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5872.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5873.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5874.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5876.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5877.5854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5878.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5880.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5881.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5883.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5885.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5886.2454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5887.2454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5888.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5890.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5891.7454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5892.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5893.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5895.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5895.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5897.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5898.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5899.2454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 153.2167 | 766083.3333 | ACTION | 5899.2454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 82.9667 | 414833.3333 | ACTION | 5899.2454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5899.2462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5900.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5902.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5902.4895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5904.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5906.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5907.662 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5908.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5910.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5912.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5913.2395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5913.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5914.7395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5917.9827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 5917.9835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5967.662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5973.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5974.0787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5974.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5976.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5977.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5978.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5980.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5981.2187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5982.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5984.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5985.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5986.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5988.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5989.8787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5990.8787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5992.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5994.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5995.3787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5995.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5997.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5998.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5999.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6000.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6002.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6002.8787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 6002.8787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 6002.8787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6002.8795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6004.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6005.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6006.1228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6008.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6010.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6011.2954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6012.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6014.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6016.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6016.8728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6017.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6018.3728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6021.616 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6021.6169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6071.2954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6076.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6077.712 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 6081.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6082.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6084.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6085.092 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6085.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6087.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6088.852 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 6094.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6095.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6097.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6098.992 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6100.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6102.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6103.512 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6104.512 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6106.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6108.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6109.012 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6109.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6111.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6112.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6113.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6114.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6116.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6116.512 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 113.6333 | 568166.6667 | ACTION | 6116.512 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 94.8952 | 474475.8926 | ACTION | 6116.512 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6116.5129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6118.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6119.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6119.7561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6121.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6123.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6124.9287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6125.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6127.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6129.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6130.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6131.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6132.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6135.2494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6135.2502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 458333.3333 | ACTION | 6168.9287 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6228.9287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6234.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6235.3454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6235.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 6238.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6240.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6241.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6242.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6244.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6245.4854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6246.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6248.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6249.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6251.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6253.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6254.1454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6255.1454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6256.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6258.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6259.6454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6260.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6261.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6263.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6263.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6265.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6266.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6267.1454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 150.6333 | 753166.6667 | ACTION | 6267.1454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 131.8952 | 659475.8926 | ACTION | 6267.1454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6267.1462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6268.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6270.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6270.3895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6272.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6274.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6275.562 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6276.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6278.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6280.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6281.1395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6281.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6282.6395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6285.8827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6285.8835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 38 | 395833.3333 | ACTION | 6313.562 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6373.562 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6378.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6379.9787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6380.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 6383.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6385.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6386.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6387.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6389.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6390.1187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6391.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6393.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6394.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6395.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6397.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6398.7787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6399.7787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6401.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6403.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6404.2787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6404.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6406.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6407.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6408.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6409.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6411.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6411.7787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 144.6333 | 723166.6667 | ACTION | 6411.7787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 125.8952 | 629475.8926 | ACTION | 6411.7787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6411.7795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6413.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6414.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6415.0228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6417.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6419.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6420.1954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6421.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6423.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6425.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6425.7728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6426.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6427.2728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6430.516 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6430.5169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6480.1954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6485.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6486.612 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6486.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6488.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6489.992 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6490.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6492.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6493.752 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6494.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6496.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6498.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6499.892 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 6514.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6516.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6518.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6519.412 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6520.412 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6521.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6523.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6524.912 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6525.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6526.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6528.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6528.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6530.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6531.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6532.412 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 120.6333 | 603166.6667 | ACTION | 6532.412 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 101.8952 | 509475.8926 | ACTION | 6532.412 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6532.4129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6533.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6535.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6535.6561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6537.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6539.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6540.8287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6541.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6543.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6545.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6546.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6547.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6547.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6551.1494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6551.1502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6600.8287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6606.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6607.2454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6607.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6609.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6610.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6611.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6613.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6614.3854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6615.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6617.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6618.5254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6620.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6622.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6623.0454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6624.0454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6625.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6627.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6628.5454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6629.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6630.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6632.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6632.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6634.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6635.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6636.0454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 6636.0454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 6636.0454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6636.0462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6637.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6639.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6639.2895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6641.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6643.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6644.462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6645.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6647.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6649.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6650.0395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6650.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6651.5395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6654.7827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6654.7835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 187500 | ACTION | 6662.462 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6722.462 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6727.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6728.8787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6729.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6731.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6732.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6733.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6735.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6736.0187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6737.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6754.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6756.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6757.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6758.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6760.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6761.6787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6762.6787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6764.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6766.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6767.1787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6767.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6769.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6770.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6771.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6772.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6774.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6774.6787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 138.6333 | 693166.6667 | ACTION | 6774.6787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 119.8952 | 599475.8926 | ACTION | 6774.6787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6774.6795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6776.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6777.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6777.9228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6779.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6781.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6783.0954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6783.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6785.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6787.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6788.6728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6789.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6790.1728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6793.416 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6793.4169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 38 | 395833.3333 | ACTION | 6821.0954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6881.0954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6886.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6887.512 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6887.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6889.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6890.892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6891.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6893.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6894.652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6895.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6897.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6898.792 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6900.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6902.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6903.312 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6904.312 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6905.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6906.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6908.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6909.812 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6910.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6911.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6913.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6913.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6915.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6916.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6917.312 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 142.6333 | 713166.6667 | ACTION | 6917.312 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 123.8952 | 619475.8926 | ACTION | 6917.312 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6917.3129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6918.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6920.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6920.5561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6922.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6924.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6925.7287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6926.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6928.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6930.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6931.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6932.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6932.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6936.0494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6936.0502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 39 | 406250 | ACTION | 6964.7287 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7024.7287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7030.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7031.1454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7031.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7033.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7034.5254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7035.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7037.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7038.2854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7039.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7041.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7042.4254 | TurbineInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 7085.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7086.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7087.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7089.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7090.9454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7091.9454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7093.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7095.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7096.4454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7096.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7098.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7099.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7100.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7101.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7103.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7103.9454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 186.6333 | 933166.6667 | ACTION | 7103.9454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 167.8952 | 839475.8926 | ACTION | 7103.9454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7103.9462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7105.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7106.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7107.1895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7109.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7111.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7112.362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7113.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7115.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7117.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7117.9395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7118.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7119.4395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7122.6827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7122.6835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7172.362 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7177.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7178.7787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7179.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7181.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7182.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7182.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7184.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7185.9187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7187.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7189.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7190.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7191.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7193.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7194.5787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7195.5787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7197.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7199.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7200.0787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7200.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7202.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7203.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7204.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7205.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7207.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7207.5787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 7207.5787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 7207.5787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7207.5795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 218750 | ACTION | 7228.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7230.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7231.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 24 | 120000 | ACTION | 7231.5795 | TurbineInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7234.8228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7236.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7236.9954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7238.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7240.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7242.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7244.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7245.5728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7246.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7247.0728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7250.316 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7250.3169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 55 | 572916.6667 | ACTION | 7291.9954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7351.9954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7357.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7358.412 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7358.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7360.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7361.792 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7362.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7364.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7365.552 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7366.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7368.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7369.692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7371.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7373.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7374.212 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7375.212 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7376.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7378.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7379.712 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7380.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7381.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7383.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7383.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7385.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7386.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7387.212 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 179.6333 | 898166.6667 | ACTION | 7387.212 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 136.8952 | 684475.8926 | ACTION | 7387.212 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7387.2129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7388.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7390.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7390.4561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7392.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7394.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7395.6287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7396.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7398.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7400.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7401.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7401.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7402.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7405.9494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7405.9502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 63 | 656250 | ACTION | 7458.6287 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7518.6287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7524.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7525.0454 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 7541.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7541.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7543.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7544.4254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7545.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7547.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7548.1854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7549.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7551.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7552.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7553.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7555.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7556.8454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7557.8454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7559.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7561.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7562.3454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7562.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7564.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7565.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7566.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7567.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7569.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7569.8454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 182.6333 | 913166.6667 | ACTION | 7569.8454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 163.8952 | 819475.8926 | ACTION | 7569.8454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Delay | 1 | 5000 | ACTION | 7570.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7570.8462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7571.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7572.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7574.0895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7576.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7578.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7578.262 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7580.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7582.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7584.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7584.8395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7585.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7586.3395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7589.5827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7589.5835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7638.262 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7643.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7644.6787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7645.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7647.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7648.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7648.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7650.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7651.8187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7652.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7654.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7655.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7657.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7659.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7660.4787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7661.4787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7662.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7664.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7665.9787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7666.4787 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7669.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7670.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7672.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7672.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7674.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7675.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7676.4787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 106.6333 | 533166.6667 | ACTION | 7676.4787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 86.8952 | 434475.8926 | ACTION | 7676.4787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7676.4795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7677.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7679.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7679.7228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7681.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7683.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7684.8954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7685.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7687.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7689.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7690.4728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7691.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7691.9728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7695.216 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7695.2169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7744.8954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7750.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7751.312 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7751.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7753.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7754.692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7755.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7757.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7758.452 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7759.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7761.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7762.592 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7764.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7766.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7767.112 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7768.112 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7769.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7771.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7772.612 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7773.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7774.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7776.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7776.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7778.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7779.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7780.112 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 7780.112 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 7780.112 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7780.1129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7781.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7783.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7783.3561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7785.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7787.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7788.5287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7789.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7791.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7793.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7794.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7794.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7795.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7798.8494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7798.8502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7848.5287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7853.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7854.9454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7855.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7857.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7858.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7859.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7861.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7862.0854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7863.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7865.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7866.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7867.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7869.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7870.7454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7871.7454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7873.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7875.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7876.2454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7876.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7878.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7879.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7880.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7881.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7883.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7883.7454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 7883.7454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 7883.7454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7883.7462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7885.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7886.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7886.9895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7888.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7890.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7892.162 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7892.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7894.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7896.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7897.7395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7898.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7899.2395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7902.4827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7902.4835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7952.162 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7957.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7958.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7958.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7960.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7961.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7962.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7964.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7965.7187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7966.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7968.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7969.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7971.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7973.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7974.3787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7975.3787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7976.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7978.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7979.8787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7980.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7981.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7983.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7983.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7985.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7986.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7987.3787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 7987.3787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 7987.3787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7987.3795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7988.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7990.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7990.6228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7992.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7994.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7995.7954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7996.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7998.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8000.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8001.3728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8002.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8002.8728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8006.116 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8006.1169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8055.7954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8061.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8062.212 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8064.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8064.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8066.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8067.592 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8068.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8070.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8071.352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8072.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8074.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8075.492 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8077.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 8080.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8082.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8083.012 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8084.012 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8085.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8087.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8088.512 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8089.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8090.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8092.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8092.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8094.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8095.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8096.012 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 108.6333 | 543166.6667 | ACTION | 8096.012 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 89.8952 | 449475.8926 | ACTION | 8096.012 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8096.0129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8097.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8099.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8099.2561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8101.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8103.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8104.4287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8105.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8107.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8109.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8110.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8110.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8111.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8114.7494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8114.7502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 635416.6667 | ACTION | 8165.4287 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8225.4287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8230.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8231.8454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8232.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8234.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8235.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8235.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8237.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8238.9854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8240.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8242.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8243.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8244.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8246.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8247.6454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8248.6454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8250.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8252.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8253.1454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8253.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8255.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8256.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8257.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8258.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8260.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8260.6454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 164.6333 | 823166.6667 | ACTION | 8260.6454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 145.8952 | 729475.8926 | ACTION | 8260.6454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8260.6462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8262.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8263.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8263.8895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8265.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8267.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8269.062 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8269.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8271.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8273.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8274.6395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8275.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8276.1395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8279.3827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8279.3835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8329.062 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8334.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8335.4787 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 8339.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8339.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8341.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8342.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8343.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8345.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8346.6187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8347.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8349.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8350.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8352.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8354.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8355.2787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8356.2787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8357.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8359.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8360.7787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8361.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8362.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8364.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8364.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8366.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8367.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8368.2787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 107.6333 | 538166.6667 | ACTION | 8368.2787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 88.8952 | 444475.8926 | ACTION | 8368.2787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8368.2795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8369.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8371.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8371.5228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8373.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8375.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8376.6954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8377.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8379.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8381.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8382.2728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8383.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8383.7728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8387.016 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8387.0169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 66 | 687500 | ACTION | 8442.6954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8502.6954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8508.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8509.112 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8509.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8511.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8512.492 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8513.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8515.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8516.252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8517.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8519.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8520.392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8521.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8523.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8524.912 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8525.912 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8527.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8529.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8530.412 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8530.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8532.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8533.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8534.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8535.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8537.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8537.912 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 169.6333 | 848166.6667 | ACTION | 8537.912 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 150.8952 | 754475.8926 | ACTION | 8537.912 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8537.9129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8539.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8540.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8541.1561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8543.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8545.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8546.3287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8547.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8549.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8551.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8551.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8552.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8553.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8556.6494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8556.6502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8606.3287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8611.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8612.7454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8613.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8615.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8616.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8616.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8618.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8619.8854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8621.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8623.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8624.0254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8625.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8627.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8628.5454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8629.5454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8631.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8633.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8634.0454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8634.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8636.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8637.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8638.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8639.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8641.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8641.5454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 8641.5454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 8641.5454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8641.5462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8643.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8644.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8644.7895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8646.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8648.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8649.962 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8650.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8652.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8654.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8655.5395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8656.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8657.0395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8660.2827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8660.2835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 635416.6667 | ACTION | 8710.962 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8770.962 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8776.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8777.3787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8777.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8779.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8780.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8781.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8783.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8784.5187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8785.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8787.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8788.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8790.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8792.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8793.1787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8794.1787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8795.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8797.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8798.6787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8799.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8800.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8802.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8802.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8804.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8805.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8806.1787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 164.6333 | 823166.6667 | ACTION | 8806.1787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 145.8952 | 729475.8926 | ACTION | 8806.1787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8806.1795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8807.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8809.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8809.4228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8811.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8813.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8814.5954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8815.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8817.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8819.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8820.1728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8820.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8821.6728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8824.916 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8824.9169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8874.5954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8880.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8881.012 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8881.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8883.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8884.392 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8885.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8887.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8888.152 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8889.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8891.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8892.292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8893.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8895.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8896.812 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8897.812 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8899.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8901.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8902.312 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8902.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8904.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8905.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8906.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8907.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8909.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8909.812 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 8909.812 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 8909.812 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8909.8129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8911.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8912.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8913.0561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8915.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8917.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8918.2287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8919.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8921.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8923.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8923.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8924.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8925.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8928.5494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8928.5502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8978.2287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8983.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8984.6454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8985.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8987.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8988.0254 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8993.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8993.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 6 | 62500 | ACTION | 8999.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9001.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9002.7854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9003.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9005.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9006.9254 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 9015.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9017.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9019.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9020.4454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9021.4454 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 9026.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9027.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9029.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9030.9454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9031.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9032.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9034.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9034.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9036.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9037.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9038.4454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 128.6333 | 643166.6667 | ACTION | 9038.4454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 109.8952 | 549475.8926 | ACTION | 9038.4454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9038.4462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9039.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9041.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9041.6895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9043.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9045.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9046.862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9047.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9049.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9051.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9052.4395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9053.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9053.9395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9057.1827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9057.1835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9106.862 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9112.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9113.2787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9113.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9115.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9116.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9117.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9119.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9120.4187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9121.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9123.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9124.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9126.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9128.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9129.0787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9130.0787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9131.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9133.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9134.5787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9135.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9136.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9138.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9138.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9140.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9141.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9142.0787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9142.0787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 9142.0787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9142.0795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9143.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9145.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9145.3228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9147.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9149.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9150.4954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9151.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9153.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9155.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9156.0728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9156.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9157.5728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9160.816 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9160.8169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9210.4954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9215.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9216.912 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9217.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9219.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9220.292 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9221.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9223.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9224.052 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9225.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9227.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9228.192 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9229.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9231.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9232.712 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9233.712 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9235.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9237.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9238.212 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9238.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9240.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9241.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9242.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9243.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9245.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9245.712 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9245.712 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 9245.712 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9245.7129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9247.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9248.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9248.9561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9250.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9252.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9254.1287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9254.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9256.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9258.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9259.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9260.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9261.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9264.4494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9264.4502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9314.1287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9319.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9320.5454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9320.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9322.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9323.9254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9324.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9326.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9327.6854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9328.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9330.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9331.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9333.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9335.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9336.3454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9337.3454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9338.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9340.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9341.8454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9342.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9343.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9345.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9345.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9347.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9348.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9349.3454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9349.3454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 9349.3454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9349.3462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9350.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9352.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9352.5895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9354.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9356.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9357.762 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9358.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9360.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9362.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9363.3395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9364.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9364.8395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9368.0827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9368.0835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9417.762 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9423.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9424.1787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9424.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9426.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9427.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9428.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9430.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9431.3187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9432.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9434.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9435.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9436.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9438.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9439.9787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9440.9787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9442.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9444.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9445.4787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9445.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9447.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9448.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9449.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9450.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9452.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9452.9787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9452.9787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 9452.9787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9452.9795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9454.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9455.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9456.2228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9458.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9460.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9461.3954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9462.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9464.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9466.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9466.9728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9467.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9468.4728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9471.716 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9471.7169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9521.3954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9526.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9527.812 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9529.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9530.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9532.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9533.192 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9533.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9535.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9536.952 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9538.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9540.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9541.092 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9542.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9544.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9545.612 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9546.612 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9548.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9550.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9551.112 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9551.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9553.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9554.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9555.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9556.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9558.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9558.612 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 105.6333 | 528166.6667 | ACTION | 9558.612 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 86.8952 | 434475.8926 | ACTION | 9558.612 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9558.6129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9560.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9561.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9561.8561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9563.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9565.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9567.0287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9567.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9569.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9571.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9572.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9573.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9574.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9577.3494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9577.3502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9627.0287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9632.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9633.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9633.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9635.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9636.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9637.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9639.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9640.5854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9641.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9643.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9644.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9646.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9648.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9649.2454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9650.2454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9651.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9653.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9654.7454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9655.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9656.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9658.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9658.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9660.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9661.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9662.2454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9662.2454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 9662.2454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9662.2462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9663.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9665.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9665.4895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9667.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9669.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9670.662 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9671.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9673.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9675.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9676.2395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9676.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9677.7395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9680.9827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9680.9835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9730.662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9736.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9737.0787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9737.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9739.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9740.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9741.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9743.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9744.2187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9745.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9747.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9748.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9749.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9751.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9752.8787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9753.8787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9755.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9757.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9758.3787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9758.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9760.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9761.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9762.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9763.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9765.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9765.8787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9765.8787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 9765.8787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9765.8795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9767.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9768.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9769.1228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9771.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9773.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9774.2954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9775.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9777.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9779.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9779.8728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9780.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9781.3728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9784.616 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9784.6169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9834.2954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9839.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9840.712 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9841.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9843.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9844.092 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9844.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9846.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9847.852 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9848.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9850.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9851.992 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9853.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9855.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9856.512 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9857.512 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9859.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9861.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9862.012 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9862.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9864.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9865.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9866.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9867.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9869.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9869.512 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9869.512 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 9869.512 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9869.5129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9871.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9872.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9872.7561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9874.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9876.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9877.9287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9878.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9880.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9882.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9883.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9884.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9885.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9888.2494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9888.2502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9937.9287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9943.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9944.3454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9944.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9946.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9947.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9948.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9950.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9951.4854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9952.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9954.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9955.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9957.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9959.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9960.1454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9961.1454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9962.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9964.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9965.6454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9966.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9967.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9969.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9969.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9971.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9972.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9973.1454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 9973.1454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 9973.1454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9973.1462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9974.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9976.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9976.3895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9978.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9980.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9981.562 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9982.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9984.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9986.3895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9987.1395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9987.8895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9988.6395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9991.8827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9991.8835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10041.562 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10046.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10047.9787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10048.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10050.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10051.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10052.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10054.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10055.1187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10056.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10058.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10059.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10060.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10062.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10063.7787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10064.7787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10066.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10068.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10069.2787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10069.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10071.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10072.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10073.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10074.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10076.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10076.7787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10076.7787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 10076.7787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10076.7795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10078.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10079.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10080.0228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10082.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10084.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10085.1954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10086.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10088.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10090.0228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10090.7728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10091.5228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10092.2728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10095.516 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10095.5169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10145.1954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10150.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10151.612 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10151.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10153.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10154.992 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10155.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10157.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10158.752 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10159.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10161.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10162.892 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10164.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10166.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10167.412 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10168.412 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10169.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10171.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10172.912 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10173.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10174.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10176.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10176.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10178.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10179.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10180.412 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10180.412 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 10180.412 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10180.4129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10181.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10183.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10183.6561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10185.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10187.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10188.8287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10189.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10191.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10193.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10194.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10195.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10195.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10199.1494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10199.1502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10248.8287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10254.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10255.2454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10255.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10257.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10258.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10259.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10261.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10262.3854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10263.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10265.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10266.5254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10268.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10270.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10271.0454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10272.0454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10273.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10275.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10276.5454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10277.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10278.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10280.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10280.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10282.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10283.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10284.0454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10284.0454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 10284.0454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10284.0462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10285.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10287.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10287.2895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10289.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10291.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10292.462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10293.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10295.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10297.2895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10298.0395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10298.7895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10299.5395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10302.7827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10302.7835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10352.462 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10357.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10358.8787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10359.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10361.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10362.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10363.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10365.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10366.0187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10367.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10369.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10370.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10371.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10373.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10374.6787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10375.6787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10377.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10379.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10380.1787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10380.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10382.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10383.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10384.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10385.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10387.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10387.6787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10387.6787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 10387.6787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10387.6795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10389.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10390.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10390.9228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10392.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10394.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10396.0954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10396.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10398.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10400.9228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10401.6728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10402.4228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10403.1728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10406.416 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10406.4169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10456.0954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10461.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10462.512 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10462.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10464.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10465.892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10466.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10468.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10469.652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10470.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10472.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10473.792 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10475.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10477.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10478.312 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10479.312 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10480.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10482.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10483.812 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10484.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10485.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10487.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10487.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10489.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10490.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10491.312 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10491.312 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 10491.312 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10491.3129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 10494.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10494.5561 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10495.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10496.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10497.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10498.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10500.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10502.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10502.7287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10504.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10505.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10506.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10506.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10510.0494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10510.0502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10562.7287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10568.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10569.1454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10569.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10571.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10572.5254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10573.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10575.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10576.2854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10577.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10579.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10580.4254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10581.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10583.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10584.9454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10585.9454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10587.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10589.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10590.4454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10590.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10592.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10593.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10594.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10595.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10597.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10597.9454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 106.6333 | 533166.6667 | ACTION | 10597.9454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 87.8952 | 439475.8926 | ACTION | 10597.9454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10597.9462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10599.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10600.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10601.1895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10603.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10605.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10606.362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10607.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10609.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10611.1895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10611.9395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10612.6895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10613.4395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10616.6827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10616.6835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10666.362 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10671.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10672.7787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10673.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10675.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10676.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10676.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10678.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10679.9187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10681.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10683.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10684.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10685.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10687.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10688.5787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10689.5787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10691.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10693.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10694.0787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10694.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10696.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10697.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10698.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10699.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10701.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10701.5787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10701.5787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 10701.5787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10701.5795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10703.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10704.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10704.8228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10706.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10708.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10709.9954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10710.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10712.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10714.8228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10715.5728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10716.3228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10717.0728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10720.316 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10720.3169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10769.9954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10775.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10776.412 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10776.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10778.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10779.792 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10780.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10782.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10783.552 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10784.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10786.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10787.692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10789.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10791.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10792.212 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10793.212 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10794.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10796.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10797.712 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10798.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10799.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10801.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10801.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10803.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10804.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10805.212 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10805.212 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 10805.212 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10805.2129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10806.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10808.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10808.4561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10810.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10812.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10813.6287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10814.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10816.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10818.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10819.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10819.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10820.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10823.9494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10823.9502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10873.6287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10879.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10880.0454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10880.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10882.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10883.4254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10884.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10886.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10887.1854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10888.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10890.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10891.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10892.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10894.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10895.8454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10896.8454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10898.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10900.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10901.3454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10901.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10903.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10904.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10905.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10906.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10908.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10908.8454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 10908.8454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 10908.8454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10908.8462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10910.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10911.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10912.0895 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10914.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10916.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10917.262 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10918.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10920.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10922.0895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10922.8395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10923.5895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10924.3395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10927.5827 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10927.5835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10977.262 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10982.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10983.6787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10984.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10986.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10987.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10987.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10989.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10990.8187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10991.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10993.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10994.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10996.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10998.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10999.4787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11000.4787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11001.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11003.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11004.9787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11005.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11006.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11008.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11008.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11010.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11011.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11012.4787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11012.4787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 11012.4787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11012.4795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11013.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11015.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11015.7228 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11017.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11019.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11020.8954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11021.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11023.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11025.7228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11026.4728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11027.2228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11027.9728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11031.216 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11031.2169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11080.8954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11086.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11087.312 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11087.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11089.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11090.692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11091.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11093.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11094.452 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11095.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11097.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11098.592 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11100.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11102.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11103.112 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11104.112 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11105.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11107.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11108.612 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11109.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11110.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11112.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11112.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11114.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11115.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11116.112 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11116.112 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 11116.112 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11116.1129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11117.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11119.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11119.3561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11121.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11123.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11124.5287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11125.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11127.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11129.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11130.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11130.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11131.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11134.8494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11134.8502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11184.5287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11189.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11190.9454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11191.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11193.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11194.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11195.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11197.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11198.0854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11199.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11201.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11202.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11203.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11205.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11206.7454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11207.7454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11209.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11211.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11212.2454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11212.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11214.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11215.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11216.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11217.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11219.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11219.7454 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11219.7454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 11219.7454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11219.7462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11221.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11222.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11222.9895 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11224.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11226.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11228.162 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11228.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11230.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11232.9895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11233.7395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11234.4895 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11235.2395 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11238.4827 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11238.4835 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11288.162 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11293.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11294.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11294.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11296.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11297.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11298.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11300.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11301.7187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11302.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11304.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11305.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11307.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11309.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11310.3787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11311.3787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11312.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11314.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11315.8787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11316.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11317.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11319.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11319.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11321.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11322.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11323.3787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11323.3787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 11323.3787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11323.3795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11324.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11326.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11326.6228 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11328.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11330.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11331.7954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11332.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11334.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11336.6228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11337.3728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11338.1228 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11338.8728 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11342.116 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11342.1169 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11391.7954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11397.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11398.212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11398.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11400.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11401.592 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11402.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11404.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11405.352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11406.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11408.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11409.492 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11411.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11413.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11414.012 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11415.012 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11416.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11418.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11419.512 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11420.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11421.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11423.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11423.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11425.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11426.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11427.012 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11427.012 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 84.8952 | 424475.8926 | ACTION | 11427.012 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11427.0129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11428.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11430.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11430.2561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11432.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11434.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11435.4287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11436.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11438.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11440.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11441.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11441.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11442.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11445.7494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11445.7502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11495.4287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11500.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11501.8454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11502.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11504.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11505.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11505.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11507.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11508.9854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11510.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11512.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11513.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11514.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11516.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11517.6454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11518.6454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11520.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11522.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11523.1454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11523.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11525.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11526.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11527.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11528.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11530.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11530.6454 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 103.6333 | 518166.6667 | ACTION | 11530.6454 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 84.8952 | 424475.8926 | ACTION | 11530.6454 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11530.6462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11532.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11533.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11533.8895 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11539.062 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11599.062 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11604.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11605.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11605.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 38 | 395833.3333 | ACTION | 11643.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11645.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11646.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11647.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11649.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11650.6187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11651.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11653.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11654.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11656.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11658.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11659.2787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11660.2787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11661.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11663.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11664.7787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11665.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11666.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11668.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11668.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11670.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11671.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11672.2787 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 141.6333 | 708166.6667 | ACTION | 11672.2787 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11672.2795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11673.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11675.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11675.5228 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11680.6954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 11683.9386 | TurbineInstallation