## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 64 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 76 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 84 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 84 | 420000 | ACTION | 84 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 87.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 87.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 84.0008 | 875008.6892 | ACTION | 87.2441 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 96 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 104 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 124 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 136 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 144 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 147.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 152.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 153.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 156 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 163.6607 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 164 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 164.3838 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 164.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 165.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 166.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 167.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 167.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 176.5871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 177.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 178.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 182.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 186.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 189.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 195.0037 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 197.0037 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 257.0037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 262.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 263.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 273.4204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 274.1435 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 274.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 275.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 276.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 286.3467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 287.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 288.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 292.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 297.7634 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 357.7634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 363.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 364.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 374.18 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 374.9031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 374.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 375.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 377.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 387.1064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 388.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 389.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 393.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 398.523 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 458.523 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 463.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 464.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 474.9397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 475.6628 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 475.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 476.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 477.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 487.866 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 400.6219 | 2003109.644 | ACTION | 487.866 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 487.8668 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 488.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 489.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 491.1101 | MonopileInstallation
| Feeder 1 | Queue | 323.866 | 1619330.0311 | ACTION | 491.1101 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 493.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 499.2827 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 503.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 511.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 523.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 531.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 543.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 551.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 559.2827 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 563.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 564.6993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 565.6993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 571.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 574.3533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 574.3542 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 575.6993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 576.4224 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 576.4257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 577.4257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 578.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 588.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 589.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 590.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 594.6257 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 600.0423 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 660.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 665.459 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 666.459 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 676.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 677.1821 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 677.1853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 678.1853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 679.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 689.3853 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 690.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 691.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 695.3853 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 700.802 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 760.802 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 766.2186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 767.2186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 777.2186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 777.9417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 777.945 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 778.945 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 780.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 790.145 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 791.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 792.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 796.145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 801.5616 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 861.5616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 866.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 867.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 877.9783 | MonopileInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 884.9783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 885.7014 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 885.7046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 886.7046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 887.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 897.9046 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 406.7945 | 2033972.5903 | ACTION | 897.9046 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 897.9054 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 898.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 899.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 901.1487 | MonopileInstallation
| Feeder 0 | Queue | 326.7945 | 1633972.5903 | ACTION | 901.1487 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 903.9046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 909.3213 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 913.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 921.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 933.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 941.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 953.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 961.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 969.3213 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 973.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 974.7379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 975.7379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 981.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 984.3919 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 984.3928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 985.7379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 986.461 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 986.4643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 987.4643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 988.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 998.6643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 999.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1000.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1004.6643 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1010.0809 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1070.0809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1075.4976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1076.4976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1086.4976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1087.2206 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1087.2239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1088.2239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1089.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1099.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1100.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1101.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1105.4239 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1110.8406 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1170.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1176.2572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1177.2572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1187.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1187.9803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1187.9835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1188.9835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1190.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1200.1835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1201.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1202.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1206.1835 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1211.6002 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1271.6002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1277.0169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1278.0169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1288.0169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1288.7399 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1288.7432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1289.7432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1290.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1300.9432 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 1300.9432 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1300.944 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1301.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1302.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1304.1873 | MonopileInstallation
| Feeder 1 | Queue | 319.7945 | 1598972.5903 | ACTION | 1304.1873 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1306.9432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1312.3599 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1316.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1324.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1336.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1344.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1356.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1364.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1372.3599 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1376.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1377.7765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1378.7765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1384.1873 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1387.4305 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1387.4314 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1388.7765 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1389.4996 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1389.5028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1390.5028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1391.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1401.7028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1402.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1403.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1404.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1409.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1413.7028 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1419.1195 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1479.1195 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1484.5362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1485.5362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1495.5362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1496.2592 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1496.2625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1497.2625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1498.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1508.4625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1509.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1510.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1514.4625 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1519.8792 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1579.8792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1585.2958 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1586.2958 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1596.2958 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1597.0189 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1597.0221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1598.0221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1599.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1609.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1610.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1611.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1615.2221 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1620.6388 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1680.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1686.0555 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1687.0555 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1697.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1697.7785 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1697.7818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1698.7818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1699.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1709.9818 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 405.7945 | 2028972.5903 | ACTION | 1709.9818 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1709.9826 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1710.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1711.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1713.2259 | MonopileInstallation
| Feeder 0 | Queue | 325.7945 | 1628972.5903 | ACTION | 1713.2259 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1715.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1721.3985 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1725.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1733.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1745.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1753.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1765.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1773.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1781.3985 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1785.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1786.8151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1787.8151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1793.2259 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1796.4691 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1796.4699 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1797.8151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1798.5382 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1798.5414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1799.5414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1800.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1810.7414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1811.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1812.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1816.7414 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1822.1581 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1882.1581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1887.5748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1888.5748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1898.5748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1899.2978 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1899.3011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1900.3011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1901.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1911.5011 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1912.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1913.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1917.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1922.9178 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1982.9178 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1988.3344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1989.3344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1999.3344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2000.0575 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2000.0607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2001.0607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2002.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2012.2607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2013.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2014.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2018.2607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2023.6774 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2083.6774 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2089.0941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2090.0941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2100.0941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2100.8171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2100.8204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2101.8204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2103.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2113.0204 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 2113.0204 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2113.0212 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2114.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2115.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2116.2645 | MonopileInstallation
| Feeder 1 | Queue | 319.7945 | 1598972.5903 | ACTION | 2116.2645 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2119.0204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2124.4371 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2128.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2136.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2148.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2156.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2168.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2176.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2184.4371 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2188.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2189.8537 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2190.8537 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2196.2645 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2199.5077 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2199.5085 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2200.8537 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2201.5768 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2201.58 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2202.58 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2203.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2213.78 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2214.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2215.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2219.78 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2225.1967 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2285.1967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2290.6134 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2291.6134 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2301.6134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2302.3364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2302.3397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2303.3397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2304.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2314.5397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2315.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2316.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2320.5397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2325.9564 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2385.9564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2391.373 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2392.373 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2402.373 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2403.0961 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2403.0993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2404.0993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2405.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2415.2993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2416.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2417.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2421.2993 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2426.716 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2486.716 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2492.1327 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2493.1327 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2503.1327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2503.8557 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2503.859 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2504.859 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2506.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2516.059 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 399.7945 | 1998972.5903 | ACTION | 2516.059 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2516.0598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2517.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2518.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2519.3031 | MonopileInstallation
| Feeder 0 | Queue | 319.7945 | 1598972.5903 | ACTION | 2519.3031 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2522.059 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2527.4757 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2531.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2539.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2551.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2559.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2571.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2579.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2587.4757 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2591.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2592.8923 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2593.8923 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2599.3031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2602.5463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2602.5471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2603.8923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2604.6154 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2604.6186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2605.6186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2606.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2616.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2617.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2618.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2622.8186 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2628.2353 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2688.2353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2693.652 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2694.652 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2704.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2705.375 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2705.3783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2706.3783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2707.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2717.5783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2718.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2719.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2723.5783 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2728.9949 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 42 | 437500 | ACTION | 2770.9949 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2830.9949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2836.4116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2837.4116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2847.4116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2848.1347 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2848.1379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2849.1379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2850.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2860.3379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2861.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2862.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2866.3379 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2871.7546 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2931.7546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2937.1713 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2938.1713 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2948.1713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2948.8943 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2948.8976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2949.8976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2951.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2961.0976 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 441.7945 | 2208972.5903 | ACTION | 2961.0976 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2961.0984 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2962.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2963.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2964.3417 | MonopileInstallation
| Feeder 1 | Queue | 361.7945 | 1808972.5903 | ACTION | 2964.3417 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2967.0976 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2972.5142 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2976.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2984.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2996.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3004.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 60 | 625000 | ACTION | 3032.5142 | MonopileInstallation
| Feeder 0 | Delay | 37 | 185000 | ACTION | 3041.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3053.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3061.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3073.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3081.3417 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3084.5849 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3084.5857 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3092.5142 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3097.9309 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3098.9309 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3108.9309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3109.654 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3109.6572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3110.6572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3111.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3121.8572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3122.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3123.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3127.8572 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3133.2739 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3193.2739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3198.6906 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3199.6906 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3209.6906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3210.4136 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3210.4169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3211.4169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3212.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3222.6169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3223.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3224.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3228.6169 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3234.0335 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3294.0335 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3299.4502 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3300.4502 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3310.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3311.1733 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3311.1765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3312.1765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3313.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3323.3765 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3324.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3325.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3329.3765 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3334.7932 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3394.7932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3400.2099 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3401.2099 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3411.2099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3411.9329 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3411.9362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3412.9362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3414.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3424.1362 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 459.7945 | 2298972.5903 | ACTION | 3424.1362 | MonopileInstallation | [14 empty] | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3425.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3426.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3430.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 11 | 55000 | ACTION | 3435.1362 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3435.137 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3435.5528 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3438.3803 | MonopileInstallation
| Feeder 0 | Queue | 353.7945 | 1768972.5903 | ACTION | 3438.3803 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 2.8274 | 29452.1953 | ACTION | 3438.3803 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3450.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3458.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3470.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3478.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3490.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3498.3803 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3498.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3503.7969 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3504.7969 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3510.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3514.7969 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3515.52 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3515.5232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3516.5232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3517.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3518.3803 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3521.6235 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3521.6243 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3527.7232 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3528.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 3535.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3536.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3538.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3542.7232 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3548.1399 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3608.1399 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3613.5566 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3614.5566 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3624.5566 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3625.2796 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3625.2829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3626.2829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3627.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3637.4829 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3638.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3639.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3643.4829 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3648.8995 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 113 | 1177083.3333 | ACTION | 3761.8995 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3821.8995 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3827.3162 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3828.3162 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3838.3162 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3839.0393 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3839.0425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3840.0425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3841.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3851.2425 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3852.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3853.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3857.2425 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3862.6592 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3922.6592 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3928.0759 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3929.0759 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3939.0759 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3939.7989 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3939.8022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3940.8022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3942.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3952.0022 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 513.6219 | 2568109.644 | ACTION | 3952.0022 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3952.003 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3953.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3954.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3955.2463 | MonopileInstallation
| Feeder 1 | Queue | 433.6219 | 2168109.644 | ACTION | 3955.2463 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3958.0022 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3963.4188 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3967.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3975.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3987.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3995.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4007.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4015.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 80 | 833333.3333 | ACTION | 4043.4188 | MonopileInstallation
| Feeder 0 | Delay | 37 | 185000 | ACTION | 4052.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4064.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4072.2463 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4075.4895 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4075.4903 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4103.4188 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4108.8355 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4109.8355 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4119.8355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4120.5586 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4120.5618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4121.5618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4122.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4132.7618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4133.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4134.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4138.7618 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4144.1785 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4204.1785 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4209.5952 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4210.5952 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4220.5952 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4221.3182 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4221.3215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4222.3215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4223.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4233.5215 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4234.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4235.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4239.5215 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4244.9381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4304.9381 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4310.3548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4311.3548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4321.3548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4322.0779 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4322.0811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4323.0811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4324.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4334.2811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4335.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4336.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4340.2811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4345.6978 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4405.6978 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4411.1145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4412.1145 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4422.1145 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4422.8375 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4422.8408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4423.8408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4425.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4435.0408 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 479.7945 | 2398972.5903 | ACTION | 4435.0408 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4435.0416 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4436.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4437.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4438.2849 | MonopileInstallation
| Feeder 0 | Queue | 362.7945 | 1813972.5903 | ACTION | 4438.2849 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4441.0408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4446.4574 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4450.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4458.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4470.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4478.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4490.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4498.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 98 | 490000 | ACTION | 4596.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4608.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 250 | 2604166.6667 | ACTION | 4696.4574 | MonopileInstallation
| Feeder 1 | Delay | 99 | 495000 | ACTION | 4707.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4715.2849 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4718.5281 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4718.5289 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4756.4574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4761.8741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4762.8741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4772.8741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4773.5972 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4773.6004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4774.6004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4775.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4785.8004 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4786.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4787.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4791.8004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4797.2171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4829.2171 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4889.2171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4894.6338 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4895.6338 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4905.6338 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4906.3568 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4906.3601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4907.3601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4908.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4918.5601 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4919.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4920.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4924.5601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4929.9767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4989.9767 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4995.3934 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4996.3934 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5006.3934 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5007.1165 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5007.1197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5008.1197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5009.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5019.3197 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5020.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5021.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 5027.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5031.3197 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5036.7364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5096.7364 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5102.1531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5103.1531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5113.1531 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5113.8761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5113.8794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5114.8794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5116.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5126.0794 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 687.7945 | 3438972.5903 | ACTION | 5126.0794 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5126.0802 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5127.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5128.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5129.3234 | MonopileInstallation
| Feeder 1 | Queue | 410.7945 | 2053972.5903 | ACTION | 5129.3234 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5132.0794 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5137.496 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5141.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5149.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 24 | 250000 | ACTION | 5161.496 | MonopileInstallation
| Feeder 0 | Delay | 19 | 95000 | ACTION | 5168.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5180.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5188.3234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5221.496 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5226.9127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5227.9127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5237.9127 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5238.6358 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5238.639 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5239.639 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5240.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5250.839 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5251.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5252.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5256.839 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5262.2557 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 17 | 177083.3333 | ACTION | 5279.2557 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5339.2557 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5344.6724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5345.6724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5355.6724 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5356.3954 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5356.3987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5357.3987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5358.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5368.5987 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5369.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5370.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5374.5987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5380.0153 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 102 | 1062500 | ACTION | 5482.0153 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5542.0153 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5547.432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5548.432 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5558.432 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5559.1551 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5559.1583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5560.1583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5561.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5571.3583 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5572.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5573.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5577.3583 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5582.775 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 47 | 489583.3333 | ACTION | 5629.775 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5689.775 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5695.1917 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5696.1917 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5706.1917 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5706.9147 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5706.918 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5707.918 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5709.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5719.118 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 589.7945 | 2948972.5903 | ACTION | 5719.118 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5719.1188 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5720.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5721.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5722.362 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5725.118 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5730.5346 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 5730.5346 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 5730.5346 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 5730.5346 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5732.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5733.7779 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5734.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5736.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5738.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5740.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5741.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5742.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5742.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5744.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5746.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5748.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 58 | 290000 | ACTION | 5806.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5808.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5810.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5811.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5812.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5813.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5815.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5817.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5819.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5821.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5823.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5823.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5824.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5825.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 94.75 | 473750 | ACTION | 5825.2846 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5827.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5828.5279 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 5828.5287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 94.7508 | 986987.8559 | ACTION | 5828.5287 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5829.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5831.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5833.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5835.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5836.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5836.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5837.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5839.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5841.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5843.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5845.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5847.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5848.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5849.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5849.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5851.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5853.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5855.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5857.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5859.7846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5860.5346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5861.2846 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5862.0346 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5865.2779 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 5865.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5888.5287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5893.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5894.9454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5895.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5897.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5898.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5899.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5901.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5902.0854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5903.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5905.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5906.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5907.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5909.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5910.7454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5911.7454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5913.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5915.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5916.2454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5916.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5918.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5919.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5920.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5921.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5923.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5923.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5925.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5926.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5932.162 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5992.162 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5997.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5998.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5998.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6000.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6001.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6002.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6004.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6005.7187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6006.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6008.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6009.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6011.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6013.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6014.3787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6015.3787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6016.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6018.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6019.8787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6020.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6021.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6023.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6023.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6025.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6026.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6027.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6028.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6030.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6035.7954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6095.7954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6101.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6102.212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6102.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6104.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6105.592 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6106.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6108.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6109.352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6110.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6112.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6113.492 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6115.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6117.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6118.012 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6119.012 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6120.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6122.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6123.512 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6124.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6125.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6127.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6127.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6129.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6130.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6131.012 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 302.4833 | 1512416.6667 | ACTION | 6131.012 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 265.7333 | 1328666.6667 | ACTION | 6131.012 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6131.0129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6132.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6134.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6134.2561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6136.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6138.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6139.4287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6140.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6142.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6144.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6145.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6145.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6146.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 30 | 312500 | ACTION | 6169.4287 | TurbineInstallation
| Feeder 0 | Delay | 28 | 140000 | ACTION | 6174.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6176.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6178.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6180.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6182.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6184.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6185.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6186.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6186.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6188.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6190.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6192.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6194.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6196.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6197.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6198.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6199.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6202.2494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6202.2502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6229.4287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6234.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6235.8454 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 6238.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6239.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6241.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6242.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6242.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6244.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6245.9854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6247.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6249.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6250.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6251.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6253.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6254.6454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6255.6454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6257.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6259.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6260.1454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6260.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6262.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6263.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6264.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6265.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6267.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6267.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6269.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6270.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6276.062 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 38 | 395833.3333 | ACTION | 6314.062 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6374.062 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6379.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6380.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6380.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6382.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6384.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6385.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6386.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6388.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6389.6187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6390.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6392.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6393.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6395.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6397.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6398.2787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6399.2787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6400.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6402.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6403.7787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6404.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6405.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6407.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6407.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6409.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6410.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6411.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6412.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6414.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6419.6954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6479.6954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6485.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6486.112 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6486.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6488.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6489.492 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6490.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6492.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6493.252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6494.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6496.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6497.392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6498.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6514.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6516.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6517.912 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6518.912 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6520.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6522.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6523.412 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6523.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6525.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6526.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6527.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6528.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6530.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6530.912 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 399.9 | 1999500 | ACTION | 6530.912 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 328.6618 | 1643309.2259 | ACTION | 6530.912 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6530.9129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6532.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6533.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6534.1561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6536.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6538.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6539.3287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6540.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6542.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6544.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6544.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6545.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6546.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6548.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6550.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6552.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6554.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6556.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6557.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6557.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6558.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6560.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6562.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6564.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6566.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6568.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6569.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6570.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6570.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6574.1494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6574.1502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6599.3287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6604.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6605.7454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6606.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6608.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6609.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6609.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6611.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6612.8854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6614.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6616.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6617.0254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6618.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6620.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6621.5454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6622.5454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6624.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6626.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6627.0454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6627.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6629.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6630.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6631.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6632.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6634.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6634.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6636.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6637.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6642.962 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 19 | 197916.6667 | ACTION | 6661.962 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6721.962 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6727.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6728.3787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6728.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6730.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6731.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6732.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6734.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6735.5187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6736.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6753.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6755.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6756.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6758.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6760.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6761.1787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6762.1787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6763.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6765.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6766.6787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6767.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6768.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6770.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6770.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6772.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6773.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6774.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6775.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6777.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6782.5954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 38 | 395833.3333 | ACTION | 6820.5954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 6880.5954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6886.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6887.012 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6887.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6889.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6890.392 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6891.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6893.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6894.152 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6895.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6897.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6898.292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6899.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6901.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6902.812 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6903.812 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6904.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6906.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6908.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6909.312 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6909.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6911.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6912.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6913.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6914.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6916.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6916.812 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 385.9 | 1929500 | ACTION | 6916.812 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 342.6618 | 1713309.2259 | ACTION | 6916.812 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6916.8129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6918.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6919.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6920.0561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6922.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6924.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6925.2287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6926.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6928.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6930.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6930.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6931.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6932.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6934.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6936.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 6940.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6942.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6944.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6946.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 40 | 416666.6667 | ACTION | 6965.2287 | TurbineInstallation
| Feeder 0 | Delay | 26 | 130000 | ACTION | 6972.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6973.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6973.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6974.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6976.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6978.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6980.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6982.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6984.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6985.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6986.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6986.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6990.0494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6990.0502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7025.2287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7030.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7031.6454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7032.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7034.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7035.0254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7035.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7037.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7038.7854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7039.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7041.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7042.9254 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 7084.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7086.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7088.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7090.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7091.4454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7092.4454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7093.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7095.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7096.9454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7097.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7098.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7100.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7100.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7102.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7103.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7104.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7105.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7107.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7112.862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7172.862 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7178.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7179.2787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7179.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7181.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7182.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7183.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7185.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7186.4187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7187.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7189.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7190.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7192.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7194.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7195.0787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7196.0787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7197.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7199.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7200.5787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7201.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7202.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7204.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7204.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7206.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7207.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7208.0787 | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 7229.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7230.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7232.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7237.4954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 55 | 572916.6667 | ACTION | 7292.4954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7352.4954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7357.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7358.912 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7359.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7361.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7362.292 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7363.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7365.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7366.052 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7367.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7369.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7370.192 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7371.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7373.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7374.712 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7375.712 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7377.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7379.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7380.212 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7380.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7382.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7383.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7384.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7385.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7387.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7387.712 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 470.9 | 2354500 | ACTION | 7387.712 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 397.6618 | 1988309.2259 | ACTION | 7387.712 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7387.7129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7389.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7390.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7390.9561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7392.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7394.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7396.1287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7396.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7398.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7400.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7401.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7402.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7403.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7405.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7407.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7409.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7411.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7413.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7413.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7414.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7415.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7417.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7419.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7421.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7423.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7425.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7426.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7426.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7427.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7430.9494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7430.9502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 63 | 656250 | ACTION | 7459.1287 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7519.1287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7524.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7525.5454 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 7540.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7540.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7542.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7543.9254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7544.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7546.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7547.6854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7548.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7550.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7551.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7553.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7555.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7556.3454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7557.3454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7558.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7560.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7561.8454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7562.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7563.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7565.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7565.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7567.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7568.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7569.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7570.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7572.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7577.762 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7637.762 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7643.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7644.1787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7644.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7646.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7647.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7648.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7650.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7651.3187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7652.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7654.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7655.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7656.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7658.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7659.9787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7660.9787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7662.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7664.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7665.4787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7665.9787 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7668.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7670.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7671.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7672.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7673.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7675.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7675.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7677.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7678.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7684.3954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7744.3954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7749.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7750.812 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7751.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7753.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7754.192 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7754.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7756.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7757.952 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7759.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7761.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7762.092 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7763.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7765.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7766.612 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7767.612 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7769.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7771.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7772.112 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7772.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7774.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7775.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7776.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7777.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7779.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7779.612 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 391.9 | 1959500 | ACTION | 7779.612 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 348.6618 | 1743309.2259 | ACTION | 7779.612 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7779.6129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7781.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7782.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7782.8561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7784.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7786.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7788.0287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7788.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7790.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7792.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7793.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7794.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7795.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7797.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7799.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7801.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7803.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7805.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7805.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7806.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7807.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7809.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7811.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7813.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7815.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7817.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7818.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7818.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7819.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7822.8494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7822.8502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7848.0287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7853.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7854.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7854.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7856.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7857.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7858.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7860.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7861.5854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7862.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7864.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7865.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7867.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7869.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7870.2454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7871.2454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7872.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7874.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7875.7454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7876.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7877.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7879.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7879.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7881.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7882.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7883.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7884.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7886.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7891.662 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 7951.662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7957.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7958.0787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7958.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7960.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7961.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7962.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7964.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7965.2187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7966.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7968.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7969.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7970.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7972.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7973.8787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7974.8787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7976.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7978.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7979.3787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7979.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7981.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7982.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7983.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7984.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7986.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7986.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7988.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7989.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7995.2954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8055.2954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8060.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8061.712 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8063.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8064.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8066.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8067.092 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8067.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8069.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8070.852 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8071.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8073.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8074.992 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8076.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8078.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8079.512 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8080.512 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8082.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8084.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8085.012 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8085.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8087.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8088.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8089.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8090.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8092.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8092.512 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 312.9 | 1564500 | ACTION | 8092.512 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 269.6618 | 1348309.2259 | ACTION | 8092.512 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8092.5129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8094.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8095.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8095.7561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8097.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8099.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8100.9287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8101.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8103.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8105.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8106.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8107.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8108.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8110.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8112.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8114.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8116.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8118.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8118.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8119.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8120.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8122.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8124.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8126.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8128.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8130.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8131.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8131.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8132.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8135.7494 | TurbineInstallation
| WTIV | Delay | 64 | 666666.6667 | ACTION | 8164.9287 | TurbineInstallation
| Feeder 1 | Delay | 36 | 180000 | ACTION | 8171.7494 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8171.7502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8224.9287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8230.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8231.3454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8231.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8233.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8234.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8235.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8237.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8238.4854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8239.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8241.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8242.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8244.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8246.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8247.1454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8248.1454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8249.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8251.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8252.6454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8253.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8254.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8256.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8256.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8258.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8259.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8260.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8261.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8263.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8268.562 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8328.562 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8333.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8334.9787 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 8338.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8339.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8341.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8342.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8343.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8345.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8346.1187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8347.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8349.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8350.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8351.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8353.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8354.7787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8355.7787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8357.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8359.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8360.2787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8360.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8362.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8363.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8364.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8365.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8367.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8367.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8369.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8370.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8376.1954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 67 | 697916.6667 | ACTION | 8443.1954 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8503.1954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8508.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8509.612 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8509.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8511.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8512.992 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8513.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8515.752 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8516.752 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8517.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8519.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8520.892 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8522.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8524.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8525.412 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8526.412 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8527.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8529.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8530.912 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8531.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8532.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8534.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8534.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8536.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8537.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8538.412 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 445.9 | 2229500 | ACTION | 8538.412 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 366.6618 | 1833309.2259 | ACTION | 8538.412 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8538.4129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8539.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8541.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8541.6561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8543.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8545.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8546.8287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8547.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8549.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8551.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8552.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8553.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8553.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8555.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8557.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8559.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8561.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8563.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8564.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8565.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8566.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8568.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8570.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8572.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8574.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8576.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8576.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8577.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8578.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8581.6494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8581.6502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8606.8287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8612.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8613.2454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8613.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8615.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8616.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8617.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8619.3854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8620.3854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8621.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8623.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8624.5254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8626.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8628.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8629.0454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8630.0454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8631.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8633.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8634.5454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8635.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8636.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8638.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8638.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8640.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8641.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8642.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8643.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8645.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8650.462 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 61 | 635416.6667 | ACTION | 8711.462 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8771.462 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8776.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8777.8787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8778.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8780.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8781.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8782.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8784.0187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8785.0187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8786.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8788.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8789.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8790.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8792.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8793.6787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8794.6787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8796.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8798.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8799.1787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8799.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8801.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8802.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8803.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8804.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8806.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8806.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8808.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8809.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8815.0954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8875.0954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8880.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8881.512 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8881.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8883.892 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8884.892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8885.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8887.652 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8888.652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8889.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8891.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8892.792 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8894.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8896.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8897.312 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8898.312 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8899.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8901.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8902.812 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8903.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8904.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8906.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8906.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8908.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8909.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8910.312 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 371.9 | 1859500 | ACTION | 8910.312 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 328.6618 | 1643309.2259 | ACTION | 8910.312 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8910.3129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8911.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8913.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8913.5561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8915.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8917.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8918.7287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8919.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8921.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8923.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8924.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8925.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8925.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8927.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8929.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8931.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8933.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8935.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8936.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8937.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8938.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8940.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8942.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8944.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8946.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8948.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8948.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8949.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8950.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8953.5494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8953.5502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8978.7287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8984.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8985.1454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8985.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8987.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8988.5254 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8993.5254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8994.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 6 | 62500 | ACTION | 9000.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9002.2854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9003.2854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9004.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9006.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9007.4254 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 9016.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9017.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 8 | 83333.3333 | ACTION | 9025.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9027.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9028.9454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9029.9454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9031.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9033.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9034.4454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9034.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9036.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9037.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9038.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9039.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9041.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9041.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9043.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9044.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9050.362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9110.362 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9115.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9116.7787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9117.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9119.1587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9120.1587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9120.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9122.9187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9123.9187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9125.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9127.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9128.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9129.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9131.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9132.5787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9133.5787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9135.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9137.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9138.0787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9138.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9140.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9141.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9142.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9143.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9145.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9145.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9147.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9148.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9153.9954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9213.9954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9219.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9220.412 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9220.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9222.792 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9223.792 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9224.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9226.552 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9227.552 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9228.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9230.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9231.692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9233.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9235.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9236.212 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9237.212 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9238.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9240.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9241.712 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9242.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9243.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9245.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9245.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9247.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9248.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9249.212 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 338.9 | 1694500 | ACTION | 9249.212 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 295.6618 | 1478309.2259 | ACTION | 9249.212 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9249.2129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9250.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9252.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9252.4561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9254.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9256.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9257.6287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9258.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9260.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9262.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9263.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9263.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9264.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9266.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9268.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9270.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9272.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9274.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9275.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9276.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9276.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9278.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9280.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9282.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9284.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9286.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9287.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9288.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9289.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9292.4494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9292.4502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9317.6287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9323.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9324.0454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9324.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9326.4254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9327.4254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9328.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9330.1854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9331.1854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9332.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9334.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9335.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9336.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9338.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9339.8454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9340.8454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9342.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9344.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9345.3454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9345.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9347.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9348.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9349.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9350.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9352.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9352.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9354.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9355.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9361.262 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9421.262 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9426.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9427.6787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9428.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9430.0587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9431.0587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9431.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9433.8187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9434.8187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9435.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9437.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9438.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9440.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9442.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9443.4787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9444.4787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9445.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9447.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9448.9787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9449.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9450.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9452.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9452.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9454.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9455.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9456.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9457.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9459.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9464.8954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9524.8954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9530.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9531.312 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9531.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9533.692 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9534.692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9535.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9537.452 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9538.452 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9539.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9541.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9542.592 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9544.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9546.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9547.112 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9548.112 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9549.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9551.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9552.612 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9553.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9554.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9556.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9556.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9558.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9559.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9560.112 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 9560.112 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 267.6618 | 1338309.2259 | ACTION | 9560.112 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9560.1129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9561.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9563.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9563.3561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9565.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9567.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9568.5287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9569.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9571.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9573.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9574.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9574.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9575.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9577.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9579.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9581.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9583.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9585.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9586.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9587.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9587.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9589.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9591.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9593.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9595.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9597.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9598.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9599.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9600.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9603.3494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9603.3502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9628.5287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9633.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9634.9454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9635.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9637.3254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9638.3254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9639.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9641.0854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9642.0854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9643.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9645.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9646.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9647.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9649.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9650.7454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9651.7454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9653.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9655.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9656.2454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9656.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9658.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9659.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9660.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9661.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9663.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9663.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9665.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9666.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9672.162 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9732.162 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9737.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9738.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9738.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9740.9587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9741.9587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9742.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9744.7187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9745.7187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9746.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9748.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9749.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9751.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9753.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9754.3787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9755.3787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9756.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9758.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9759.8787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9760.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9761.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9763.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9763.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9765.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9766.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9767.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9768.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9770.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9775.7954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9835.7954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9841.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9842.212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9842.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9844.592 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9845.592 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9846.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9848.352 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9849.352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9850.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9852.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9853.492 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9855.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9857.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9858.012 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9859.012 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9860.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9862.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9863.512 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9864.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9865.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9867.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9867.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9869.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9870.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9871.012 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 310.9 | 1554500 | ACTION | 9871.012 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 267.6618 | 1338309.2259 | ACTION | 9871.012 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9871.0129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9872.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9874.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9874.2561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9876.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9878.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9879.4287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9880.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9882.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9884.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9885.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9885.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9886.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9888.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9890.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9892.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9894.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9896.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9897.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9898.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9898.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9900.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9902.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9904.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9906.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9908.7561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9909.5061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9910.2561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9911.0061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9914.2494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9914.2502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9939.4287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9944.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9945.8454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9946.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9948.2254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9949.2254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9949.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9951.9854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9952.9854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9954.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9956.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9957.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9958.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9960.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9961.6454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9962.6454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9964.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9966.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9967.1454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9967.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9969.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9970.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9971.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9972.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9974.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9974.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9976.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9977.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9983.062 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10043.062 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10048.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10049.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10049.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10051.8587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10052.8587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10053.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10055.6187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10056.6187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10057.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10059.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10060.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10062.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10064.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10065.2787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10066.2787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10067.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10069.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10070.7787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10071.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10072.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10074.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10074.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10076.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10077.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10078.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10079.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10081.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10086.6954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10146.6954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10152.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10153.112 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10153.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10155.492 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10156.492 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10157.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10159.252 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10160.252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10161.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10163.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10164.392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10165.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10167.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10168.912 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10169.912 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10171.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10173.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10174.412 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10174.912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10176.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10177.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10178.412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10179.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10181.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10181.912 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 10181.912 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 267.6618 | 1338309.2259 | ACTION | 10181.912 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10181.9129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10183.412 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10184.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10185.1561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10187.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10189.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10190.3287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10191.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10193.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10195.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10195.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10196.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10197.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10199.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10201.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10203.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10205.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10207.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10208.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10208.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10209.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10211.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10213.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10215.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10217.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10219.6561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10220.4061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10221.1561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10221.9061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10225.1494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10225.1502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10250.3287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10255.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10256.7454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10257.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10259.1254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10260.1254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10260.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10262.8854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10263.8854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10265.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10267.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10268.0254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10269.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10271.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10272.5454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10273.5454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10275.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10277.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10278.0454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10278.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10280.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10281.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10282.0454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10283.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10285.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10285.5454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10287.0454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10288.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10293.962 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10353.962 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10359.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10360.3787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10360.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10362.7587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10363.7587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10364.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10366.5187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10367.5187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10368.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10370.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10371.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10373.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10375.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10376.1787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10377.1787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10378.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10380.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10381.6787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10382.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10383.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10385.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10385.6787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10387.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10388.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10389.1787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10390.6787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10392.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10397.5954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10457.5954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10463.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10464.012 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10464.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10466.392 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10467.392 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10468.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10470.152 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10471.152 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10472.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10474.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10475.292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10476.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10478.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10479.812 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10480.812 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10482.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10484.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10485.312 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10485.812 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10487.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10488.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10489.312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10490.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 10493.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10495.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10495.812 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 313.9 | 1569500 | ACTION | 10495.812 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 270.6618 | 1353309.2259 | ACTION | 10495.812 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10495.8129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10497.312 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10498.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10499.0561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10501.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10503.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10504.2287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10505.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10507.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10509.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10509.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10510.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10511.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10513.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10515.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10517.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10519.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10521.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10522.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10522.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10523.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10525.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10527.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10529.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10531.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10533.5561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10534.3061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10535.0561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10535.8061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10539.0494 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10539.0502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10564.2287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10569.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10570.6454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10571.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10573.0254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10574.0254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10574.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10576.7854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10577.7854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10578.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10580.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10581.9254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10583.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10585.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10586.4454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10587.4454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10588.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10590.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10591.9454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10592.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10593.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10595.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10595.9454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10597.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10598.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10599.4454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10600.9454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10602.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10607.862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10667.862 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10673.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10674.2787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10674.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10676.6587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10677.6587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10678.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10680.4187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10681.4187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10682.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10684.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10685.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10687.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10689.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10690.0787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10691.0787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10692.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10694.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10695.5787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10696.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10697.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10699.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10699.5787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10701.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10702.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10703.0787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10704.5787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10706.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10711.4954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10771.4954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10776.912 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10777.912 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10778.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10780.292 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10781.292 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10782.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10784.052 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10785.052 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10786.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10788.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10789.192 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10790.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10792.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10793.712 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10794.712 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10796.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10798.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10799.212 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10799.712 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10801.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10802.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10803.212 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10804.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10806.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10806.712 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 10806.712 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 267.6618 | 1338309.2259 | ACTION | 10806.712 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10806.7129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10808.212 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10809.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10809.9561 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10811.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10813.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10815.1287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10815.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10817.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10819.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10820.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10821.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10822.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10824.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10826.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10828.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10830.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10832.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10832.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10833.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10834.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10836.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10838.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10840.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10842.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10844.4561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10845.2061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10845.9561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10846.7061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10849.9494 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10849.9502 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10875.1287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10880.5454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10881.5454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10881.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10883.9254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10884.9254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10885.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10887.6854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10888.6854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10889.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10891.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10892.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10894.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10896.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10897.3454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10898.3454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10899.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10901.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10902.8454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10903.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10904.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10906.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10906.8454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10908.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10909.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10910.3454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10911.8454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10913.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10918.762 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10978.762 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10984.1787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10985.1787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10985.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10987.5587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10988.5587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10989.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10991.3187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10992.3187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10993.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10995.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10996.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10997.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10999.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11000.9787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11001.9787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11003.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11005.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11006.4787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11006.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11008.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11009.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11010.4787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11011.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11013.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11013.9787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11015.4787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11016.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11022.3954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11082.3954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11087.812 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11088.812 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11089.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11091.192 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11092.192 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11092.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11094.952 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11095.952 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11097.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11099.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11100.092 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11101.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11103.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11104.612 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11105.612 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11107.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11109.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11110.112 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11110.612 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11112.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11113.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11114.112 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11115.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11117.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11117.612 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 310.9 | 1554500 | ACTION | 11117.612 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 267.6618 | 1338309.2259 | ACTION | 11117.612 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11117.6129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11119.112 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11120.612 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11120.8561 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11122.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11124.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11126.0287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11126.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11128.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11130.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11131.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11132.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11133.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11135.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11137.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11139.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11141.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11143.1061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11143.8561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11144.6061 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11145.3561 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11148.5994 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11148.6002 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11186.0287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11191.4454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11192.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11192.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11194.8254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11195.8254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11196.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11198.5854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11199.5854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11200.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11202.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11203.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11205.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11207.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11208.2454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11209.2454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11210.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11212.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11213.7454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11214.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11215.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11217.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11217.7454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11219.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11220.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11221.2454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11222.7454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11224.2454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11229.662 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11289.662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11295.0787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11296.0787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11296.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11298.4587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11299.4587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11300.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11302.2187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11303.2187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11304.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11306.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11307.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11308.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11310.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11311.8787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11312.8787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11314.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11316.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11317.3787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11317.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11319.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11320.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11321.3787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11322.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11324.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11324.8787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11326.3787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11327.8787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11333.2954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11393.2954 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11398.712 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11399.712 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11400.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11402.092 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11403.092 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11403.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11405.852 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11406.852 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11407.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11409.992 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11410.992 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11412.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11414.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11415.512 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11416.512 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11418.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11420.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11421.012 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11421.512 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11423.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11424.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11425.012 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11426.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11428.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11428.512 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 11428.512 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 279.9118 | 1399559.2259 | ACTION | 11428.512 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11428.5129 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11430.012 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11431.512 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11431.7561 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11436.9287 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11496.9287 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11502.3454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11503.3454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11503.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11505.7254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11506.7254 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11507.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11509.4854 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11510.4854 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11511.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11513.6254 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11514.6254 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11516.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11518.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11519.1454 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11520.1454 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11521.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11523.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11524.6454 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11525.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11526.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11528.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11528.6454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11530.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11531.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11532.1454 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11533.6454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11535.1454 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11540.562 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11600.562 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11605.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11606.9787 | TurbineInstallation
| WTIV | Delay | 37 | 385416.6667 | ACTION | 11643.9787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11644.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11646.3587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11647.3587 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11648.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11650.1187 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11651.1187 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11652.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11654.2587 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11655.2587 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11656.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11658.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11659.7787 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11660.7787 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11662.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11664.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11665.2787 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11665.7787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11667.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11668.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11669.2787 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11670.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11672.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11672.7787 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 244.2667 | 1221333.3333 | ACTION | 11672.7787 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11672.7795 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11674.2787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11675.7787 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11676.0228 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11681.1954 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 11684.4386 | TurbineInstallation