## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 43.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 64 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 76 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 84 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 84 | 420000 | ACTION | 84 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 96 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 104 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 116 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 124 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 127.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 127.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 84.0008 | 875008.6892 | ACTION | 127.2441 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 136 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 144 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 156 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 164 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 187.2441 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 189.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 194.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 195.6607 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 197.6607 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 207.6607 | MonopileInstallation
| Feeder 1 | Delay | 44 | 220000 | ACTION | 208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 208.3838 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 208.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 209.3871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 210.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 220.5871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 221.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 222.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 226.5871 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 232.0037 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 251.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 251.2441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 292.0037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 297.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 298.4204 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 308.4204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 309.1435 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 309.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 310.1467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 311.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 321.3467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 322.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 323.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 327.3467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 332.7634 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 392.7634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 398.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 399.18 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 409.18 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 409.9031 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 409.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 410.9064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 412.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 422.1064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 423.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 424.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 429.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 433.1064 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 438.523 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 498.523 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 503.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 504.9397 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 514.9397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 515.6628 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 515.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 516.666 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 517.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 527.866 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 400.6219 | 2003109.644 | ACTION | 527.866 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 527.8668 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 528.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 529.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 533.866 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 539.2827 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 571.1101 | MonopileInstallation
| Feeder 1 | Queue | 319.866 | 1599330.0311 | ACTION | 571.1101 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 571.1101 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 583.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 591.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 603.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 611.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 623.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 631.1101 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 631.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 636.5268 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 637.5268 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 643.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 647.5268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 648.2498 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 648.2531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 649.2531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 650.4531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 651.1101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 660.4531 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 661.4531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 662.4531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 666.4531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 671.8697 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 694.3533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 694.3542 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 731.8697 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 737.2864 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 738.2864 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 748.2864 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 749.0095 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 749.0127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 750.0127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 751.2127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 761.2127 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 762.2127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 763.2127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 764.2127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 768.2127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 773.6294 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 833.6294 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 839.046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 840.046 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 850.046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 850.7691 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 850.7724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 851.7724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 852.9724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 862.9724 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 863.9724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 864.9724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 868.9724 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 874.389 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 934.389 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 939.8057 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 940.8057 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 950.8057 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 951.5288 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 951.532 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 952.532 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 953.732 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 963.732 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 392.6219 | 1963109.644 | ACTION | 963.732 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 963.7328 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 964.732 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 965.732 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 969.732 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 975.1487 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1006.9761 | MonopileInstallation
| Feeder 0 | Queue | 312.6219 | 1563109.644 | ACTION | 1006.9761 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1006.9761 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1018.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1026.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1038.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1046.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1058.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1066.9761 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1066.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1072.3928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1073.3928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1078.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1083.3928 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1084.1158 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1084.1191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1085.1191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1086.3191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1086.9761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1096.3191 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1097.3191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1098.3191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1102.3191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1107.7357 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1130.2193 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1130.2202 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1167.7357 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1173.1524 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1174.1524 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1184.1524 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1184.8755 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1184.8787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1185.8787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1187.0787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1197.0787 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1198.0787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1199.0787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1203.0787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1208.4954 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1268.4954 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1273.9121 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1274.9121 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1284.9121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1285.6351 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1285.6384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1286.6384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1287.8384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1297.8384 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1298.8384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1299.8384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1303.8384 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1309.255 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1369.255 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1374.6717 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1375.6717 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1385.6717 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1386.3948 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1386.398 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1387.398 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1388.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1398.598 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 391.6219 | 1958109.644 | ACTION | 1398.598 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1398.5989 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1399.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 1403.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1404.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1409.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1413.598 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1419.0147 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1441.8421 | MonopileInstallation
| Feeder 1 | Queue | 311.6219 | 1558109.644 | ACTION | 1441.8421 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 22.8274 | 237785.5286 | ACTION | 1441.8421 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1453.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1461.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1473.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1481.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1493.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1501.8421 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1501.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1507.2588 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1508.2588 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1513.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1518.2588 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1518.9818 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1518.9851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1519.9851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1521.1851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1521.8421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1531.1851 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1532.1851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1533.1851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1537.1851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1542.6017 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1565.0853 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1565.0862 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1602.6017 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1608.0184 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1609.0184 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1619.0184 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1619.7415 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1619.7447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1620.7447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1621.9447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1631.9447 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1632.9447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1633.9447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1637.9447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1643.3614 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1703.3614 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1708.7781 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1709.7781 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1719.7781 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1720.5011 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1720.5044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1721.5044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1722.7044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1732.7044 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1733.7044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1734.7044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1738.7044 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1744.121 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1804.121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1809.5377 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1810.5377 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1820.5377 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1821.2608 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1821.264 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1822.264 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1823.464 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1833.464 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 391.6219 | 1958109.644 | ACTION | 1833.464 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1833.4649 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1834.464 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1835.464 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1839.464 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1844.8807 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1876.7081 | MonopileInstallation
| Feeder 0 | Queue | 311.6219 | 1558109.644 | ACTION | 1876.7081 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1876.7081 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1888.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1896.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1908.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1916.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1928.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 1936.7081 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1936.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1942.1248 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1943.1248 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1948.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1953.1248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1953.8478 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1953.8511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1954.8511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1956.0511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1956.7081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1966.0511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1967.0511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1968.0511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1972.0511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1977.4678 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1999.9513 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1999.9522 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2037.4678 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2042.8844 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2043.8844 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2053.8844 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2054.6075 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2054.6107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2055.6107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2056.8107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2066.8107 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2067.8107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2068.8107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2072.8107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2078.2274 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2138.2274 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2143.6441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2144.6441 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2154.6441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2155.3671 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2155.3704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2156.3704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2157.5704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2167.5704 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2168.5704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2169.5704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2173.5704 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2178.987 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2238.987 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2244.4037 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2245.4037 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2255.4037 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2256.1268 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2256.13 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2257.13 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2258.33 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2268.33 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 391.6219 | 1958109.644 | ACTION | 2268.33 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2268.3309 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2269.33 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2270.33 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2274.33 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2279.7467 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2311.5741 | MonopileInstallation
| Feeder 1 | Queue | 311.6219 | 1558109.644 | ACTION | 2311.5741 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2311.5741 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2323.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2331.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2343.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2351.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2363.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2371.5741 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2371.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2376.9908 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2377.9908 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2383.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2387.9908 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2388.7138 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2388.7171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2389.7171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2390.9171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2391.5741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2400.9171 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2401.9171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2402.9171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2406.9171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2412.3338 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2434.8174 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2434.8182 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2472.3338 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2477.7504 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2478.7504 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2488.7504 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2489.4735 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2489.4767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2490.4767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2491.6767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2501.6767 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2502.6767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2503.6767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2507.6767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2513.0934 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2573.0934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2578.5101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2579.5101 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2589.5101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2590.2331 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2590.2364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2591.2364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2592.4364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2602.4364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2603.4364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2604.4364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2608.4364 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2613.8531 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2673.8531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2679.2697 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2680.2697 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2690.2697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2690.9928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2690.996 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2691.996 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2693.196 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2703.196 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 391.6219 | 1958109.644 | ACTION | 2703.196 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2703.1969 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2704.196 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2705.196 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2709.196 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2714.6127 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 73 | 365000 | ACTION | 2776.1969 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2819.4401 | MonopileInstallation
| Feeder 0 | Queue | 384.6219 | 1923109.644 | ACTION | 2819.4401 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 104.8274 | 1091952.1953 | ACTION | 2819.4401 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2831.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2839.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2851.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2859.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2871.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2879.4401 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2879.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2884.8568 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2885.8568 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2891.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2895.8568 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2896.5798 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2896.5831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2897.5831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2898.7831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2899.4401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2908.7831 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2909.7831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2910.7831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2914.7831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2920.1998 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2942.6834 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2942.6842 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 2980.1998 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2985.6164 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2986.6164 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2996.6164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2997.3395 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2997.3427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2998.3427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2999.5427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3009.5427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3010.5427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3011.5427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 30 | 312500 | ACTION | 3041.5427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3045.5427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3050.9594 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3110.9594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3116.3761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3117.3761 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3127.3761 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3128.0991 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3128.1024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3129.1024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3130.3024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3140.3024 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3141.3024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3142.3024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3146.3024 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3151.7191 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3211.7191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3217.1357 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3218.1357 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3228.1357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3228.8588 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3228.862 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3229.862 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3231.062 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3241.062 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 421.6219 | 2108109.644 | ACTION | 3241.062 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3241.0629 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3242.062 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3243.062 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3247.062 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3252.4787 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3284.3061 | MonopileInstallation
| Feeder 1 | Queue | 341.6219 | 1708109.644 | ACTION | 3284.3061 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 3284.3061 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3296.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3304.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3316.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3324.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3344.3061 | MonopileInstallation
| Feeder 0 | Delay | 21 | 105000 | ACTION | 3345.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3349.7228 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3350.7228 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3357.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3360.7228 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3361.4459 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3361.4491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3362.4491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3363.6491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3365.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3373.6491 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3374.6491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3375.6491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3377.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3379.6491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3385.0658 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3385.3061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 50 | 250000 | ACTION | 3435.3061 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3445.0658 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3450.4824 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3451.4824 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3461.4824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3462.2055 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3462.2088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3463.2088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3464.4088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3474.4088 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3475.4088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3476.4088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3478.5494 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3478.5502 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3480.4088 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3485.8254 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3545.8254 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3551.2421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3552.2421 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3562.2421 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3562.9652 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3562.9684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3563.9684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3565.1684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3575.1684 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3576.1684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3577.1684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3581.1684 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3586.5851 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3646.5851 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3652.0017 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3653.0017 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3663.0017 | MonopileInstallation
| WTIV | Delay | 39 | 406250 | ACTION | 3702.0017 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3702.7248 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3702.728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3703.728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3704.928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3714.928 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 430.6219 | 2153109.644 | ACTION | 3714.928 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3714.9289 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3715.928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3716.928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3720.928 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3726.3447 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 55 | 275000 | ACTION | 3769.9289 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3813.1721 | MonopileInstallation
| Feeder 0 | Queue | 334.6219 | 1673109.644 | ACTION | 3813.1721 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 86.8274 | 904452.1953 | ACTION | 3813.1721 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3825.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 5 | 25000 | ACTION | 3830.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3838.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3850.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3858.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3870.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3873.1721 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3878.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3878.5888 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3879.5888 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3889.5888 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3890.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3890.3119 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3890.3151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3891.3151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3892.5151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3898.1721 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3902.5151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3903.5151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3904.5151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3908.5151 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3913.9318 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3941.4154 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3941.4162 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 3973.9318 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3979.3484 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3980.3484 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3990.3484 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3991.0715 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3991.0748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3992.0748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3993.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4003.2748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4004.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4005.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 4008.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4012.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 31 | 322916.6667 | ACTION | 4043.2748 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4048.6914 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4108.6914 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4114.1081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4115.1081 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4125.1081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4125.8312 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4125.8344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4126.8344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4128.0344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4138.0344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4139.0344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4140.0344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4144.0344 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4149.4511 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4209.4511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4214.8677 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4215.8677 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4225.8677 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4226.5908 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4226.5941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4227.5941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4228.7941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4238.7941 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 425.6219 | 2128109.644 | ACTION | 4238.7941 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4238.7949 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4239.7941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4240.7941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4244.7941 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4250.2107 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 38 | 190000 | ACTION | 4276.7949 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4320.0381 | MonopileInstallation
| Feeder 1 | Queue | 378.6219 | 1893109.644 | ACTION | 4320.0381 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 69.8274 | 727368.8619 | ACTION | 4320.0381 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4332.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4340.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4352.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4360.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4372.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4380.0381 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4380.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4385.4548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4386.4548 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4396.4548 | MonopileInstallation
| Feeder 0 | Delay | 17 | 85000 | ACTION | 4397.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4397.1779 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4397.1811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4398.1811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4399.3811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4409.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4409.3811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4410.3811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4411.3811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4415.3811 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4417.0381 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4420.7978 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4460.2814 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4460.2822 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4480.7978 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4486.2144 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4487.2144 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4497.2144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4497.9375 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4497.9408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4498.9408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 4506.9408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4508.1408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4518.1408 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4519.1408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4520.1408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 23 | 239583.3333 | ACTION | 4543.1408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4547.1408 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4552.5574 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 144 | 1500000 | ACTION | 4696.5574 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4756.5574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4761.9741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4762.9741 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4772.9741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4773.6972 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4773.7004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4774.7004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4775.9004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4785.9004 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4786.9004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4787.9004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4791.9004 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4797.3171 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4829.3171 | MonopileInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 4889.3171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4894.7337 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4895.7337 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4905.7337 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4906.4568 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4906.4601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4907.4601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4908.6601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4918.6601 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 598.6219 | 2993109.644 | ACTION | 4918.6601 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4918.6609 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4919.6601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4920.6601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4924.6601 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4930.0767 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4961.9041 | MonopileInstallation
| Feeder 0 | Queue | 501.6219 | 2508109.644 | ACTION | 4961.9041 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 4961.9041 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4973.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4981.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4993.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 5001.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 5013.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5021.9041 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 5021.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5027.3208 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5028.3208 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 5033.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5038.3208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5039.0439 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5039.0471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5040.0471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5041.2471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 5041.9041 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5051.2471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5052.2471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5053.2471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 15 | 75000 | ACTION | 5056.9041 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5057.2471 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5062.6638 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 5100.1474 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 5100.1482 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5122.6638 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5128.0805 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5129.0805 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5139.0805 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5139.8035 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5139.8068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5140.8068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5142.0068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 5161.0068 | MonopileInstallation
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5171.0068 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5172.0068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5173.0068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5177.0068 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5182.4234 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5242.4234 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5247.8401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5248.8401 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5258.8401 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5259.5632 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5259.5664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5260.5664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5261.7664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 18 | 187500 | ACTION | 5279.7664 | MonopileInstallation
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5289.7664 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5290.7664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5291.7664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5295.7664 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5301.1831 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5361.1831 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5366.5998 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5367.5998 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5377.5998 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5378.3228 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5378.3261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5379.3261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5380.5261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5390.5261 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 428.6219 | 2143109.644 | ACTION | 5390.5261 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5390.5269 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5391.5261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5392.5261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5396.5261 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5401.9427 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 105 | 525000 | ACTION | 5495.5269 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 5538.7701 | MonopileInstallation
| Feeder 1 | Queue | 438.6219 | 2193109.644 | ACTION | 5538.7701 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 136.8274 | 1425285.5286 | ACTION | 5538.7701 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5550.7701 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5558.7701 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 5570.7701 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 5578.7701 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5598.7701 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5604.1868 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5605.1868 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 24 | 250000 | ACTION | 5629.1868 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5639.1868 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5639.9099 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5639.9131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5640.9131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5642.1131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5652.1131 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5653.1131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5654.1131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5658.1131 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5663.5298 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5723.5298 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5728.9465 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5729.9465 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5739.9465 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5740.6695 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5740.6728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5741.6728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5742.8728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 62 | 645833.3333 | ACTION | 5804.8728 | MonopileInstallation
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5814.8728 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5815.8728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5816.8728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5820.8728 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5826.2894 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 5886.2894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5891.7061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5892.7061 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5902.7061 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5903.4292 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5903.4324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5904.4324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2855 | 29739583.3333 | ACTION | 8759.4324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8760.6324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8770.6324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8771.6324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8772.6324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8776.6324 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8782.0491 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 8842.0491 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8847.4658 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 8848.4658 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 8858.4658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 8859.1888 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 8859.1921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8860.1921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8861.3921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8871.3921 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 3332.6219 | 16663109.644 | ACTION | 8871.3921 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8871.3929 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8872.3921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8873.3921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8877.3921 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8882.8087 | MonopileInstallation | MonopileInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 8914.6362 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 8914.6362 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 8914.6362 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 8914.6362 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8916.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8918.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8920.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8922.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8924.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8925.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8926.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8926.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8928.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8930.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8932.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8934.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8936.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8937.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8938.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8939.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8941.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8943.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8945.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8947.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8949.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8949.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8950.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8951.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 36.75 | 183750 | ACTION | 8951.3862 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8953.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8955.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8957.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8957.8794 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8959.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8961.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8962.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8962.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8963.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8965.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8967.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8969.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8971.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8973.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8974.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8975.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8975.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8977.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8979.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8981.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8983.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8985.8862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8986.6362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8987.3862 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8988.1362 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8994.6294 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8994.6302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 36.7508 | 382821.1892 | ACTION | 8994.6302 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9031.3794 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9031.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9054.6302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9060.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9061.0469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9061.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9063.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9064.4269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9065.1869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9067.1869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9068.1869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9069.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9071.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9072.3269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9073.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9075.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9076.8469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9077.8469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9079.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9081.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9082.3469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9082.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9084.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9085.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9086.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9087.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9089.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9089.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9091.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9092.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9098.2636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9158.2636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9163.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9164.6802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9165.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9167.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9168.0602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9168.8202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9170.8202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9171.8202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9172.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9174.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9175.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9177.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9179.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9180.4802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9181.4802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9182.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9184.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9185.9802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9186.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9187.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9189.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9189.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9191.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9192.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9193.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9194.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9196.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9201.8969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9261.8969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9267.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9268.3136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9268.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9270.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9271.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9272.4536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9274.4536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9275.4536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9276.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9278.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9279.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9281.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9283.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9284.1136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9285.1136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9286.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9288.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9289.6136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9290.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9291.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9293.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9293.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9295.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9296.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9297.1136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 302.4833 | 1512416.6667 | ACTION | 9297.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 265.7333 | 1328666.6667 | ACTION | 9297.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9297.1144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9298.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9300.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9305.5302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9340.3576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9342.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9344.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9346.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9348.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9350.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9351.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9351.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9352.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9354.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9356.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9358.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9360.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9362.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9363.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9364.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9364.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9365.5302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9366.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9368.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9370.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9370.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9371.9469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9372.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9372.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9374.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9374.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9375.3269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9375.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9376.0869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9376.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9377.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9378.0869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9379.0869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9380.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9382.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9383.2269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9384.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9386.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9387.7469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9388.7469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9390.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9392.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9393.2469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9393.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9395.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9396.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9397.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9398.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9400.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9400.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9402.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9403.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9409.1636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9420.3509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9420.3517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9469.1636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9474.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9475.5802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9475.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9477.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9478.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9479.7202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9481.7202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9482.7202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9483.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9485.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9486.8602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9488.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9490.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9491.3802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9492.3802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9493.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9495.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9496.8802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9497.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9498.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9500.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9500.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9502.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9503.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9504.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9505.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9507.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9512.7969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9572.7969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9578.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9579.2136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9579.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9581.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9582.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9583.3536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9585.3536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9586.3536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9587.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9589.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9590.4936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9592.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9594.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9595.0136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9596.0136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9597.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9599.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9600.5136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9601.0136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9602.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9604.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9604.5136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9606.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9607.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9608.0136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 9608.0136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 187.6618 | 938309.2259 | ACTION | 9608.0136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9608.0144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9609.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9611.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9616.4302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9651.2576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9653.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9655.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9657.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9659.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9661.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9662.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9662.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9663.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9665.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9667.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9669.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9671.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9673.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9674.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9675.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9675.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9676.4302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9677.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9679.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9681.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9681.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9682.8469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9683.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9683.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9685.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9685.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9686.2269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9686.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9686.9869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9687.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9688.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9688.9869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9689.9869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9691.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9693.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9694.1269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9695.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9697.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9698.6469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9699.6469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9701.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9703.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9704.1469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9704.6469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9706.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9707.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9708.1469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9709.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9711.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9711.6469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9713.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9714.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9720.0636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9731.2509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9731.2517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9780.0636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9785.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9786.4802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9786.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9788.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9789.8602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9790.6202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9792.6202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9793.6202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9794.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9796.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9797.7602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9799.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9801.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9802.2802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9803.2802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9804.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9806.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9807.7802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9808.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9809.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9811.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9811.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9813.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9814.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9815.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9816.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9818.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9823.6969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9883.6969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9889.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9890.1136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9890.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9892.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9893.4936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9894.2536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9896.2536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9897.2536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9898.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9900.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9901.3936 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9902.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9903.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9905.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9906.9136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9907.9136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9909.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9911.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9912.4136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9912.9136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9914.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9915.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9916.4136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9917.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9919.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9919.9136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 311.9 | 1559500 | ACTION | 9919.9136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 188.6618 | 943309.2259 | ACTION | 9919.9136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9919.9144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9921.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9922.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9928.3302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9963.1576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9965.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9967.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9969.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9971.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9973.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9973.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9974.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9975.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9977.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9979.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9981.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9983.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9985.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9986.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9986.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9987.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 9988.3302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9989.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9991.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9993.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9993.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9994.7469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9995.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9995.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9997.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9997.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9998.1269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9998.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9998.8869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9999.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9999.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10000.8869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10001.8869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10003.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10005.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10006.0269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10007.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10009.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10010.5469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10011.5469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10013.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10015.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10016.0469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10016.5469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10018.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10019.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10020.0469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10021.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10023.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10023.5469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10025.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10026.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10031.9636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10043.1509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10043.1517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10091.9636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10097.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10098.3802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10098.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10100.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10101.7602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10102.5202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10104.5202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10105.5202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10106.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10108.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10109.6602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10111.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10113.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10114.1802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10115.1802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10116.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10118.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10119.6802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10120.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10121.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10123.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10123.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10125.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10126.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10127.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10128.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10130.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10135.5969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10195.5969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10201.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10202.0136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10202.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10204.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10205.3936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10206.1536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10208.1536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10209.1536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10210.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10212.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10213.2936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10214.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10216.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10217.8136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10218.8136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10220.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10222.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10223.3136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10223.8136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10225.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10226.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10227.3136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10228.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10230.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10230.8136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 10230.8136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 187.6618 | 938309.2259 | ACTION | 10230.8136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10230.8144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10232.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10233.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10239.2302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10274.0576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10276.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10278.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10280.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10282.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10284.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10284.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10285.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10286.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10288.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10290.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10292.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10294.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10296.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10297.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10297.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10298.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10299.2302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10300.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10302.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10304.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10304.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10305.6469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10306.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10306.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10308.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10308.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10309.0269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10309.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10309.7869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10310.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10310.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10311.7869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10312.7869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10313.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10315.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10316.9269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10318.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10320.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10321.4469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10322.4469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10323.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10325.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10326.9469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10327.4469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10328.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10330.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10330.9469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10332.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10333.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10334.4469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10335.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10337.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10342.8636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10354.0509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10354.0517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10402.8636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10408.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10409.2802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10409.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10411.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10412.6602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10413.4202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10415.4202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10416.4202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10417.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10419.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10420.5602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10422.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10424.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10425.0802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10426.0802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10427.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10429.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10430.5802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10431.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10432.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10434.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10434.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10436.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10437.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10438.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10439.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10441.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10446.4969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10506.4969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10511.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10512.9136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10513.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10515.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10516.2936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10517.0536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10519.0536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10520.0536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10521.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10523.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10524.1936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10525.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10527.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10528.7136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10529.7136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10531.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10533.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10534.2136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10534.7136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10536.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10537.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10538.2136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10539.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10541.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10541.7136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 310.9 | 1554500 | ACTION | 10541.7136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 187.6618 | 938309.2259 | ACTION | 10541.7136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10541.7144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10543.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10544.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10550.1302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10584.9576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10586.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10588.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10590.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10592.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10594.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10595.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10596.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10597.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10599.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10601.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10603.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10605.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10607.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10607.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10608.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10609.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10610.1302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10611.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10613.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10615.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10615.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10616.5469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10616.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10617.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10618.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10619.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10619.9269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10620.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10620.6869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10620.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10621.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10622.6869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10623.6869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10624.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10626.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10627.8269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10629.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10631.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10632.3469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10633.3469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10634.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10636.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10637.8469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10638.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10639.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10641.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10641.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10643.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 6 | 62500 | ACTION | 10649.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10650.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10651.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10652.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10654.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10659.7636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10664.9509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10664.9517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10719.7636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10725.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10726.1802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10726.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10728.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10729.5602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10730.3202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10732.3202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10733.3202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10734.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10736.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10737.4602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10738.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10740.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10741.9802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10742.9802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10744.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10746.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10747.4802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10747.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10749.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10750.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10751.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10752.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10754.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10754.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10756.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10757.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10763.3969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10823.3969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10828.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10829.8136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10830.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10832.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10833.1936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10833.9536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10835.9536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10836.9536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10838.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10840.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10841.0936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10842.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10844.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10845.6136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10846.6136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10848.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10850.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10851.1136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10851.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10853.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10854.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10855.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10856.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10858.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10858.6136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 316.9 | 1584500 | ACTION | 10858.6136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 193.6618 | 968309.2259 | ACTION | 10858.6136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10858.6144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10860.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10861.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10867.0302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10901.8576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10903.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10905.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10907.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10909.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10911.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10912.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10913.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10914.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10916.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10918.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10920.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10922.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10924.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10924.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10925.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10926.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 10927.0302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10928.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10930.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10932.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10932.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10933.4469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10933.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10934.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10935.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10936.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10936.8269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10937.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10937.5869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10937.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10938.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10939.5869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10940.5869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10941.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10943.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10944.7269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10946.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10948.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10949.2469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10950.2469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10951.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10953.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10954.7469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10955.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10956.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10958.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10958.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10960.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10961.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10962.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10963.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10965.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10970.6636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10981.8509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10981.8517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11030.6636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11036.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11037.0802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11037.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11039.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11040.4602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11041.2202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11043.2202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11044.2202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11045.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11047.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11048.3602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11049.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11051.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11052.8802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11053.8802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11055.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11057.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11058.3802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11058.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11060.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11061.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11062.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11063.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11065.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11065.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11067.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11068.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11074.2969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11134.2969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11139.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11140.7136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11141.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11143.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11144.0936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11144.8536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11146.8536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11147.8536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11148.9936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11150.9936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11151.9936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11153.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11155.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11156.5136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11157.5136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11159.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11161.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11162.0136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11162.5136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11164.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11165.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11166.0136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11167.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11169.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11169.5136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 310.9 | 1554500 | ACTION | 11169.5136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 187.6618 | 938309.2259 | ACTION | 11169.5136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11169.5144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11171.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11172.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11177.9302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 11212.7576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11214.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11216.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11218.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11220.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11222.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11223.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11224.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11225.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11227.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11229.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11231.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11233.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11235.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11235.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11236.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11237.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11237.9302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11239.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11241.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11243.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11243.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11244.3469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11244.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11245.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11246.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11247.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11247.7269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11248.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11248.4869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11248.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11249.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11250.4869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11251.4869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11252.6269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11254.6269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11255.6269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11257.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11259.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11260.1469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11261.1469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11262.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11264.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11265.6469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11266.1469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11267.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11269.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11269.6469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11271.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11272.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11273.1469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11274.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11276.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11281.5636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 11292.7509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11292.7517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11341.5636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11346.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11347.9802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11348.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11350.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11351.3602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11352.1202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11354.1202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11355.1202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11356.2602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11358.2602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11359.2602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11360.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11362.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11363.7802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11364.7802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11366.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11368.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11369.2802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11369.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11371.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11372.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11373.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11374.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11376.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11376.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11378.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11379.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11385.1969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11445.1969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11450.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11451.6136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11451.9936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11453.9936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11454.9936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11455.7536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11457.7536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11458.7536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11459.8936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11461.8936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11462.8936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11464.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11466.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11467.4136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11468.4136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11469.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11471.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11472.9136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11473.4136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11474.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11476.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11476.9136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11478.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11479.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11480.4136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 310.9 | 1554500 | ACTION | 11480.4136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 187.6618 | 938309.2259 | ACTION | 11480.4136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11480.4144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11481.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11483.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11488.8302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 11523.6576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11525.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11527.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11529.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11531.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11533.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11534.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11535.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11535.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11537.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11539.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11541.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11543.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11545.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11546.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11547.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11548.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11548.8302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11550.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11552.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11554.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11554.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11555.2469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11555.6269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11556.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11557.6269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11558.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11558.6269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11558.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11559.3869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11559.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11560.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11561.3869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11562.3869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11563.5269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11565.5269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11566.5269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11568.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11570.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11571.0469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11572.0469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11573.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11575.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11576.5469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11577.0469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11578.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11580.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11580.5469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11582.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11583.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11584.0469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11585.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11587.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11592.4636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 11603.6509 | TurbineInstallation
| WTIV | Delay | 52 | 541666.6667 | ACTION | 11644.4636 | TurbineInstallation
| Feeder 1 | Delay | 42 | 210000 | ACTION | 11645.6509 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11645.6517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11704.4636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11709.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11710.8802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11711.2602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11713.2602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11714.2602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11715.0202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11717.0202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11718.0202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11719.1602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11721.1602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11722.1602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11723.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11725.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11726.6802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11727.6802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11729.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11731.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11732.1802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11732.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11734.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11735.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11736.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11737.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11739.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11739.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11741.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11742.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11748.0969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11808.0969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11813.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11814.5136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11814.8936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11816.8936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11817.8936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11818.6536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11820.6536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11821.6536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11822.7936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11824.7936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11825.7936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11827.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11829.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11830.3136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11831.3136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11832.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11834.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11835.8136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11836.3136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11837.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11839.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11839.8136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11841.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11842.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11843.3136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 362.9 | 1814500 | ACTION | 11843.3136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 197.6618 | 988309.2259 | ACTION | 11843.3136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11843.3144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11844.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11846.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11851.7302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 11886.5576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11888.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 67 | 697916.6667 | ACTION | 11918.7302 | TurbineInstallation
| Feeder 0 | Delay | 34 | 170000 | ACTION | 11922.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11924.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11926.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11928.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11930.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11931.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11932.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11932.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11934.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11936.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11938.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11940.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11942.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11943.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11944.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11945.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11947.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11949.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11951.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11953.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11955.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11955.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11956.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11957.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 11978.7302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11984.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11985.1469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11985.5269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11987.5269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11988.5269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11989.2869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11991.2869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11992.2869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11993.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11995.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11996.4269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11997.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11999.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 12000.5509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 12000.5517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12000.9469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12001.9469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12003.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12005.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12006.4469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12006.9469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12008.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12009.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12010.4469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12011.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12013.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12013.9469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12015.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12016.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12022.3636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12082.3636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12087.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12088.7802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12089.1602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12091.1602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12092.1602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12092.9202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12094.9202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12095.9202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12097.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12099.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12100.0602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12101.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12103.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12104.5802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12105.5802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12107.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12109.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12110.0802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12110.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12112.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12113.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12114.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12115.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12117.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12117.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12119.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12120.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12125.9969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12185.9969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12191.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12192.4136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12192.7936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12194.7936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12195.7936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12196.5536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12198.5536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12199.5536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12200.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12202.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12203.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12205.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12207.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12208.2136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12209.2136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12210.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12212.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12213.7136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12214.2136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12215.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12217.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12217.7136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12219.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12220.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12221.2136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 377.9 | 1889500 | ACTION | 12221.2136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 220.6618 | 1103309.2259 | ACTION | 12221.2136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12221.2144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12222.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12224.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12229.6302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 12264.4576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12266.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12268.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12270.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12272.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12274.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12275.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12275.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12276.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12278.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12280.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12282.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12284.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12286.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12287.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12288.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12288.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12289.6302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12290.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12292.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12294.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12295.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12296.0469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12296.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12296.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12298.4269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12298.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12299.4269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12299.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12300.1869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12300.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12301.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12302.1869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12303.1869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12304.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12306.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12307.3269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12308.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12310.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12311.8469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12312.8469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12314.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12316.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12317.3469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12317.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12319.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12320.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12321.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12322.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12324.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12324.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12326.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12327.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12333.2636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 12344.4509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 12344.4517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12393.2636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12398.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12399.6802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12400.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12402.0602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12403.0602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12403.8202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12405.8202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12406.8202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12407.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12409.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12410.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12412.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12414.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12415.4802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12416.4802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12417.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12419.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12420.9802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12421.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12422.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12424.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12424.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12426.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12427.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12428.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12429.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12431.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12436.8969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12496.8969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12502.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12503.3136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12503.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12505.6936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12506.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12507.4536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12509.4536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12510.4536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12511.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12513.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12514.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12516.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12518.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12519.1136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12520.1136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12521.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12523.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12524.6136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12525.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12526.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12528.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12528.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12530.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12531.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12532.1136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 310.9 | 1554500 | ACTION | 12532.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 187.6618 | 938309.2259 | ACTION | 12532.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12532.1144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12533.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12535.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12540.5302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 12575.3576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12577.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12579.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12581.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12583.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 12585.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12586.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12586.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12587.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12589.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12591.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12593.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12595.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 12597.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12598.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12599.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12599.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12600.5302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12601.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12603.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12605.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12605.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12606.9469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12607.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 12607.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12609.3269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 12609.8576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12610.3269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12610.6076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12611.0869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12611.3576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 12612.1076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12613.0869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12614.0869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12615.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12617.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12618.2269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12619.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12621.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12622.7469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12623.7469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12625.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12627.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12628.2469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12628.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12630.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12631.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12632.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12633.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12635.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12635.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12637.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12638.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12644.1636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 12655.3509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 12655.3517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12704.1636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12709.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12710.5802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12710.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12712.9602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12713.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12714.7202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12716.7202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12717.7202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12718.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12720.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12721.8602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12723.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12725.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12726.3802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12727.3802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12728.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12730.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12731.8802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12732.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12733.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12735.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12735.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12737.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12738.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12739.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12740.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12742.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12747.7969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 40 | 416666.6667 | ACTION | 12787.7969 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12847.7969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12853.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12854.2136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12854.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12856.5936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12857.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12858.3536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12860.3536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12861.3536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12862.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12864.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12865.4936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12867.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12869.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12870.0136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12871.0136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12872.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12874.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12875.5136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12876.0136 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 12878.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12879.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12881.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12881.5136 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 12883.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12885.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12886.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12887.0136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 354.9 | 1774500 | ACTION | 12887.0136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 231.6618 | 1158309.2259 | ACTION | 12887.0136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12887.0144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 33 | 343750 | ACTION | 12920.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12921.5136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12923.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 41 | 205000 | ACTION | 12928.0144 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12928.4302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 12971.2576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12973.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12975.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12977.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12979.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12981.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12982.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12982.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12983.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12985.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12987.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 12988.4302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12989.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12991.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12993.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12993.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12994.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12994.8469 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12995.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12995.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12995.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12997.2269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12997.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12998.2269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12998.9869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12999.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13000.9869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13001.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13001.9869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13003.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13003.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13005.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 13005.7576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13006.1269 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13006.5076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13007.2576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13007.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13008.0076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13009.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13010.6469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13011.6469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13013.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13015.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13016.1469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13016.6469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13018.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13019.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13020.1469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13021.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13023.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13023.6469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13025.1469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13026.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13032.0636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 13051.2509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 13051.2517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13092.0636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13097.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13098.4802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13098.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13100.8602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13101.8602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13102.6202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13104.6202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13105.6202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13106.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13108.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13109.7602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13111.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13113.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13114.2802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13115.2802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13116.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 22 | 229166.6667 | ACTION | 13138.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13140.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13141.7802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13142.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13143.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13145.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13145.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13147.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13148.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13149.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13150.7802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13152.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13157.6969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13217.6969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13223.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13224.1136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13224.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13226.4936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13227.4936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13228.2536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13230.2536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13231.2536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13232.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13234.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13235.3936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13236.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13238.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13239.9136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13240.9136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13242.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13244.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13245.4136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13245.9136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13247.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13248.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13249.4136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13250.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13252.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13252.9136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 365.9 | 1829500 | ACTION | 13252.9136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 201.6618 | 1008309.2259 | ACTION | 13252.9136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13252.9144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13254.4136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13255.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13261.3302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 13296.1576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13298.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13300.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13302.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13304.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 13306.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13306.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13307.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13308.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13310.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13312.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13314.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13316.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 13318.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13319.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13319.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13320.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13321.3302 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13322.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13324.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13326.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13326.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13327.7469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13328.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13328.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13330.1269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 13330.6576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13331.1269 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13331.4076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13331.8869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13332.1576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13332.9076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13333.8869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13334.8869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13336.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13338.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13339.0269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13340.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13342.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13343.5469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13344.5469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13346.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13348.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13349.0469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13349.5469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13351.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13352.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13353.0469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13354.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13356.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13356.5469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13358.0469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13359.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13364.9636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 13376.1509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 13376.1517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13424.9636 | TurbineInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 13441.9636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13447.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13448.3802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13448.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13450.7602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13451.7602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13452.5202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13454.5202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13455.5202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13456.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13458.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13459.6602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13461.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13463.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13464.1802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13465.1802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13466.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13468.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13469.6802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13470.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13471.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13473.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13473.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13475.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13476.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13477.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13478.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 13480.6802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13482.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13487.5969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13547.5969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13553.0136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13554.0136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13554.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13556.3936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13557.3936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13558.1536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13560.1536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13561.1536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13562.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13564.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13565.2936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13566.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13568.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13569.8136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13570.8136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13572.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13574.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13575.3136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13575.8136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13577.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13578.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13579.3136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13580.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 13583.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13585.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13585.8136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 332.9 | 1664500 | ACTION | 13585.8136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 209.6618 | 1048309.2259 | ACTION | 13585.8136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13585.8144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13587.3136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13588.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 6 | 30000 | ACTION | 13591.8144 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13594.2302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 13635.0576 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13637.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13639.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13641.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13643.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 13645.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13645.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13646.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13647.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13649.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13651.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13653.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13654.2302 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13655.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 13657.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13658.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13658.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13659.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13659.6469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13660.6469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13661.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13661.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13663.0269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13663.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13664.0269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13664.7869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13665.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13666.7869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 13667.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13667.7869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13668.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 13669.5576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13670.3076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13670.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13671.0576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 13671.8076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13671.9269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13673.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13675.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13676.4469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13677.4469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13678.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13680.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13681.9469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13682.4469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13683.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13685.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13685.9469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13687.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13688.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13689.4469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13690.9469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13692.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13697.8636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 32 | 333333.3333 | ACTION | 13729.8636 | TurbineInstallation
| Feeder 1 | Delay | 62 | 310000 | ACTION | 13733.8076 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 13777.0509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 13777.0517 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13789.8636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13795.2802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13796.2802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13796.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13798.6602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13799.6602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13800.4202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13802.4202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13803.4202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13804.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13806.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13807.5602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13809.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13811.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13812.0802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13813.0802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13814.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13816.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13817.5802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13818.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13819.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13821.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13821.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13823.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13824.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13825.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13826.5802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13828.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13833.4969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 42 | 437500 | ACTION | 13875.4969 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 13935.4969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13940.9136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13941.9136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13942.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13944.2936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13945.2936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13946.0536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13948.0536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13949.0536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13950.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13952.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13953.1936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13954.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13956.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13957.7136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13958.7136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13960.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13962.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13963.2136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13963.7136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13965.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13966.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13967.2136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13968.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13970.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13970.7136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 384.9 | 1924500 | ACTION | 13970.7136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 193.6618 | 968309.2259 | ACTION | 13970.7136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13970.7144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13972.2136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13973.7136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13979.1302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 14013.9576 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14015.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14017.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14019.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14021.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 14023.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14024.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14025.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14026.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14028.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14030.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14032.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 14034.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 14036.2076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14036.9576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14037.7076 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 14038.4576 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 14039.1302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 14044.5469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14045.5469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 14045.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14047.9269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14048.9269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 14049.6869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14051.6869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14052.6869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 14053.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14055.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14056.8269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 14058.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14060.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 14061.3469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14062.3469 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 14078.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14079.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 42 | 210000 | ACTION | 14080.4576 | TurbineInstallation
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 14081.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14082.8469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14083.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14084.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14086.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14086.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14088.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14089.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14090.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14091.8469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14093.3469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 14098.7636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 14123.7009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 14123.7017 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 60 | 625000 | ACTION | 14158.7636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 14164.1802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14165.1802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 14165.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14167.5602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14168.5602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 14169.3202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14171.3202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14172.3202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 14173.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14175.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14176.4602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 14177.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14179.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 14180.9802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14181.9802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14183.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 14185.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14186.4802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14186.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14188.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14189.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14190.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14191.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14193.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14193.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14195.4802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14196.9802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 14202.3969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 58 | 604166.6667 | ACTION | 14260.3969 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 14320.3969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 14325.8136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14326.8136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 14327.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14329.1936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14330.1936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 14330.9536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14332.9536 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14333.9536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 14335.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14337.0936 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14338.0936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 14339.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14341.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 14342.6136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14343.6136 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 14354.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14356.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 14358.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14359.1136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14359.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14361.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14362.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14363.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14364.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14366.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14366.6136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 395.9 | 1979500 | ACTION | 14366.6136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 242.9118 | 1214559.2259 | ACTION | 14366.6136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 14366.6144 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14368.1136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14369.6136 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 14375.0302 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 31 | 322916.6667 | ACTION | 14406.0302 | TurbineInstallation
| Feeder 1 | Delay | 44 | 220000 | ACTION | 14410.6144 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 14453.8576 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 14466.0302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 14471.4469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14472.4469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 14472.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14474.8269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14475.8269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 14476.5869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14478.5869 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14479.5869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 14480.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14482.7269 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14483.7269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 14485.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14487.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 14488.2469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14489.2469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14490.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 14492.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14493.7469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14494.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14495.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14497.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14497.7469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14499.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14500.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14501.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14502.7469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14504.2469 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 14509.6636 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 65 | 677083.3333 | ACTION | 14574.6636 | TurbineInstallation
| WTIV | Position Onsite | 60 | 625000 | ACTION | 14634.6636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 14640.0802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14641.0802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 14641.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14643.4602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14644.4602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 14645.2202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14647.2202 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14648.2202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 14649.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14651.3602 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 14652.3602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 14653.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 14655.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 14656.8802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14657.8802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14659.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 14661.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14662.3802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14662.8802 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 14664.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14666.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 14668.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14669.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14670.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14671.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14673.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 14673.8802 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 307.2667 | 1536333.3333 | ACTION | 14673.8802 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 14673.8811 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14675.3802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 14676.8802 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 5 | 25000 | ACTION | 14678.8811 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 14682.2969 | TurbineInstallation | TurbineInstallation | 60 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 14722.1243 | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 14725.5401 | TurbineInstallation