## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 83.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 88.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 88.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 89.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 92.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 93.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 93.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 94.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 95.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 97.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 98.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Delay | 3 | 50000 | ACTION | 101.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 102.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 106.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 107.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 112.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 112.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 113.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 116.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 117.1426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 117.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 118.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 119.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 121.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 122.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 123.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 127.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 127.9625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 132.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 133.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 134.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 137.2792 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 142.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 143.0023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 143.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 144.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Delay | 3 | 50000 | ACTION | 147.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 148.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 150.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 151.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 152.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 156.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 156.8222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 161.8222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 162.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 163.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 166.1389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 166.8619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 166.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 167.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 169.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 171.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 172.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 173.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 177.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 177.6818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 180.9251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 192.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 203.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 211.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 223.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 231.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 243.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 251.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 263.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 271.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 275.1683 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 280.1683 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 280.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 281.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 284.485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 285.2081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 285.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 286.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 287.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 289.7113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 290.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 291.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 295.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 296.028 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 301.028 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 301.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 302.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 305.3446 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 306.0677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 306.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 307.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 308.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 310.571 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 311.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 312.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 316.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 316.8876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 321.8876 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 322.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 323.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 326.2043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 326.9274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 326.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 327.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 329.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 331.4306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 332.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 333.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 337.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 337.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 342.7473 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 343.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 344.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 347.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 347.787 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 347.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 348.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 350.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 352.2903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 353.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 354.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 358.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 358.6069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 361.8502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 373.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 381.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 393.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 401.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 413.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 421.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 433.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Delay | 6 | 100000 | ACTION | 439.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 447.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 451.0934 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 453.0934 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 458.0934 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 458.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 459.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 462.4101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 463.1331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 463.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 464.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 465.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 467.6364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 468.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 469.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 473.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 473.9531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 478.9531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 479.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 480.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 483.2697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 483.9928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 483.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 484.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 486.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 488.496 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 489.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 490.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 494.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 494.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 499.8127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 500.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 501.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 504.1294 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 504.8524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 504.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 505.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 507.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 509.3557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 510.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 511.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 515.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 515.6724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 520.6724 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 520.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 521.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 524.989 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 525.7121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 525.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 526.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 528.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 530.2153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 531.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 532.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 536.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 536.532 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 539.7752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 551.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 559.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 571.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 579.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 591.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 599.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 611.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 619.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 623.0185 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 628.0185 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 628.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 629.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 632.3352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 633.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 633.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 634.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 635.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 637.5615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 638.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 639.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 643.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 643.8781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 648.8781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 649.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 650.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 653.1948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 653.9179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 653.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 654.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 656.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 658.4211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 659.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 660.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 664.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 664.7378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 669.7378 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 670.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 671.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 674.0545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 674.7775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 674.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 675.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 677.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 679.2808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 680.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 681.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 685.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 685.5974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 690.5974 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 690.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 691.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 694.9141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 695.6372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 695.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 696.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 698.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 700.1404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 701.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 702.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 706.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 706.4571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 709.7003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 721.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 729.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 741.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 749.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 761.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 769.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 781.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 789.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 792.9436 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 797.9436 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 798.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 799.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 802.2602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 802.9833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 802.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 803.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 805.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 807.4866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 808.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 809.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 813.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 813.8032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 818.8032 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 819.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 820.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 823.1199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 823.843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 823.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 824.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 826.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 828.3462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 829.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 830.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 834.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 834.6629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 839.6629 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 839.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 840.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 843.9795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 844.7026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 844.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 845.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 847.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 849.2059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 850.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 851.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 855.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 855.5225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 860.5225 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 860.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 861.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 864.8392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 865.5622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 865.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 866.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 868.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 870.0655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 871.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 872.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 876.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 876.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 879.6254 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 885.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 897.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 905.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 917.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 925.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 937.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 945.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 957.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 965.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 968.8687 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 973.8687 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 974.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 975.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 978.1853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 978.9084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 978.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 979.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 981.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 983.4116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 984.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 985.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 989.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 989.7283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 994.7283 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 995.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 996.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 999.045 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 999.768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 999.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1000.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1002.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1004.2713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1005.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1006.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1010.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1010.588 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1015.588 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1015.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1016.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1019.9046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1020.6277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1020.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1021.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1023.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1025.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1026.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1027.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1031.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1031.4476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1036.4476 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1036.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1037.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1040.7643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1041.4873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1041.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1042.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1043.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1045.9906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1046.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1047.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1051.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1052.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1055.5505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1067.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1075.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1087.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1095.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1107.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1115.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1127.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1135.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1138.7937 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1143.7937 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1144.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1145.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1148.1104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1148.8335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1148.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1149.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1151.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1153.3367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1154.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1155.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1159.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1159.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1164.6534 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1164.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1165.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1168.9701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1169.6931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1169.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1170.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1172.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1174.1964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1175.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1176.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1180.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1180.513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1185.513 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1185.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1186.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1189.8297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1190.5528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1190.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1191.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1193.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1195.056 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1196.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1197.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1201.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1201.3727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1206.3727 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1206.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1207.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1210.6893 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1211.4124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1211.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1212.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1213.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1215.9157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1216.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1217.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1221.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1222.2323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1225.4756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1237.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1245.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1257.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1265.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1277.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1285.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1297.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1305.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1308.7188 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1313.7188 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1314.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1315.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1318.0355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1318.7585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1318.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1319.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1321.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1323.2618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1324.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1325.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1329.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1329.5785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1334.5785 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1334.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1335.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1338.8951 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1339.6182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1339.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1340.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1342.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1344.1214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1345.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1346.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1350.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1350.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1355.4381 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1355.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1356.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1359.7548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1360.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1360.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1361.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1362.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1364.9811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1365.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1366.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1370.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1371.2978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1376.2978 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1376.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1377.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1380.6144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1381.3375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1381.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1382.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1383.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1385.8407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1386.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1387.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1391.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1392.1574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1395.4007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1407.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1415.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1427.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1435.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1447.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1455.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1467.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1475.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1478.6439 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1483.6439 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1483.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1484.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1487.9606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1488.6836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1488.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1489.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1491.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1493.1869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1494.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1495.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1499.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1499.5035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1504.5035 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1504.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1505.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1508.8202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1509.5433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1509.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1510.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1512.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1514.0465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1515.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1516.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1520.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1520.3632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1525.3632 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1525.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1526.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1529.6799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1530.4029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1530.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1531.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1532.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1534.9062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1535.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1536.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1540.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1541.2228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1546.2228 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1546.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1547.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1550.5395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1551.2626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1551.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1552.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1553.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1555.7658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1556.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1557.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Delay | 3 | 50000 | ACTION | 1560.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1564.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1565.0825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1568.3257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1580.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1588.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1600.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1608.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1620.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1628.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1640.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1648.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1651.569 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1656.569 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1656.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1657.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1660.8856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1661.6087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1661.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1662.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1664.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1666.112 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1667.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1668.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1672.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1672.4286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1677.4286 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1677.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1678.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1681.7453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1682.4684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1682.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1683.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1684.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1686.9716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1687.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1688.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1692.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1693.2883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1698.2883 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1698.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1699.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1702.6049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1703.328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1703.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1704.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1705.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1707.8313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1708.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1709.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1713.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1714.1479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1719.1479 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1719.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1720.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1723.4646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1724.1877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1724.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1725.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1726.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1728.6909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1729.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1730.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1734.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1735.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1738.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1750.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1758.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1770.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1778.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1790.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1798.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1810.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1818.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1821.4941 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1826.4941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1826.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1827.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1830.8107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1831.5338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1831.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1832.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1834.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1836.037 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1837.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1838.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1842.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1842.3537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1847.3537 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1847.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1848.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1851.6704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1852.3934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1852.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1853.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1854.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1856.8967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1857.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1858.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1862.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1863.2134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1868.2134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1868.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1869.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1872.53 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1873.2531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1873.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1874.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1875.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1877.7563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1878.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1879.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1883.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1884.073 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1889.073 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1889.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1890.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1893.3897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1894.1127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1894.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1895.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1896.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1898.616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1899.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1900.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1904.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1904.9327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1908.1759 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1920.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1928.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1940.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1948.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1960.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1968.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1980.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1988.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1991.4191 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1996.4191 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1996.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1997.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2000.7358 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2001.4589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2001.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2002.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2003.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2005.9621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2006.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2007.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2011.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2012.2788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2017.2788 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2017.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2018.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2021.5955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2022.3185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2022.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2023.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2024.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2026.8218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2027.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2028.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2032.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2033.1384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2038.1384 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2038.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2039.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2042.4551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2043.1782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2043.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2044.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2045.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2047.6814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2048.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2049.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2053.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2053.9981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2058.9981 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2059.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2060.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2063.3148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2064.0378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2064.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2065.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2066.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2068.5411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2069.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2070.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2074.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2074.8577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2078.101 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2090.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2098.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2110.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2118.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2121.3442 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2126.3442 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2126.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2127.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2130.6609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2131.384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2131.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2132.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2133.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2135.8872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2136.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2137.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2141.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2142.2039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2147.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2147.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2148.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2151.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2152.2436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2152.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2153.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2154.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2156.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2157.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2158.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2162.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 2163.0635 | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2163.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2167.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2171.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2175.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2179.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2183.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2184.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2186.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2187.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2191.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2195.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2199.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2203.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2207.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2209.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2210.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2212.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2216.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2220.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2224.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2228.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2232.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2233.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2235.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2236.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2239.8068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2244.8068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2245.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2248.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2248.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2254.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2257.5034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2258.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2264.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2267.2634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2268.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2274.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2277.4034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2278.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2284.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2287.9234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2288.9234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2290.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2296.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2297.4234 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2298.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2299.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2303.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2304.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2305.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2309.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2310.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2311.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2315.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2315.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2320.7401 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2321.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2324.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2324.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2330.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2333.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2334.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2340.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2343.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2344.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2350.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2353.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2354.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2360.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2363.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2364.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2366.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2372.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2373.3568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2374.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2375.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2379.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2380.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2381.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2385.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2386.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2387.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2391.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2391.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2396.6734 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2396.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2399.9901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2400.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2406.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2409.3701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2410.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2416.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2419.1301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2420.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2426.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2429.2701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2430.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2436.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2439.7901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2440.7901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2442.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2448.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2449.2901 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2450.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2451.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2455.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2456.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2457.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2461.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2462.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2463.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2467.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2467.6068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2470.85 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2474.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2478.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2482.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2486.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2490.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2492.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2493.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2495.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2499.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2503.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2507.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2511.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2515.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2516.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2518.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2519.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2523.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2527.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2531.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2535.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2539.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2541.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2542.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2544.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2547.5933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2552.5933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2552.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2555.9099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2556.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2562.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2565.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2566.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2572.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2575.0499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2576.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2582.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2585.1899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2586.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2592.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2595.7099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2596.7099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2598.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2604.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2605.2099 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2606.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2607.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2611.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2612.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2613.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2617.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2618.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2619.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2623.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2623.5266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2628.5266 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2628.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2631.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2632.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2638.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2641.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2641.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2647.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2650.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2652.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2658.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2661.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2662.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2668.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2671.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2672.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2674.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2680.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2681.1433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2682.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2683.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2687.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2688.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2689.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2693.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2694.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2695.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2699.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2699.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2704.4599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2704.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2707.7766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2708.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2714.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2717.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2717.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2723.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2726.9166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2728.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2734.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2737.0566 | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 2769.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2770.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 9 | 150000 | ACTION | 2779.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2785.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2788.5766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2789.5766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2791.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2797.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2798.0766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2799.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2800.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2804.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2805.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2806.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2810.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2811.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2812.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2816.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2816.3933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2819.6365 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2823.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2827.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2831.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2835.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2839.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2841.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2842.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2844.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2848.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2852.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2856.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2860.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2864.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2865.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2867.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2868.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2872.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2876.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2880.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2884.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2888.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2890.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2891.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2893.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2896.3797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2901.3797 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2901.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2904.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2905.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2911.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2914.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2914.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2920.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2923.8364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2924.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2930.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2933.9764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2935.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2941.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2944.4964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2945.4964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2946.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2952.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2953.9964 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2954.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2956.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2959.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2960.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2962.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2965.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2966.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2968.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2971.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2972.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2977.3131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2977.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2980.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2981.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2987.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2990.0097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2990.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2996.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2999.7697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3000.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3006.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3009.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3011.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 21 | 350000 | ACTION | 3032.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3038.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3041.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3042.4297 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3050.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3051.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3057.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3058.9297 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3059.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3061.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3064.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3065.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3067.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3070.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3071.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3073.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3076.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3077.2464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3082.2464 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3082.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3085.5631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3085.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3091.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3094.9431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3095.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3101.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3104.7031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3105.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3111.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3114.8431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3116.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3122.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3125.3631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3126.3631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3127.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3133.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3134.8631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3135.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3137.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3140.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3141.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3143.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3146.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3147.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3149.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3152.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3153.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3156.423 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3160.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3164.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3168.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3172.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3176.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3177.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3179.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3180.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3184.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3188.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3192.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3196.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3200.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3202.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3203.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3205.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3209.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3213.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3217.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3221.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3225.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3226.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3228.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3229.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3233.1662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3238.1662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3238.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3241.4829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3241.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3247.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3250.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3251.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3257.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3260.6229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3261.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3267.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3270.7629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3272.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3278.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3281.2829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3282.2829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3283.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3289.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3290.7829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3291.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3293.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3296.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3297.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3299.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3302.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3303.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3305.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3308.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3309.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3314.0996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3314.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3317.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3317.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3323.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3326.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3327.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3333.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3336.5562 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3337.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3338.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 13 | 216666.6667 | ACTION | 3351.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3357.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3360.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3362.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3368.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3371.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3372.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3373.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3379.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3380.7162 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3381.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3383.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3386.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3387.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3389.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3392.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3393.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3395.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3398.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3399.0329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3404.0329 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3404.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3407.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3407.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3413.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3416.7296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3417.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3423.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3426.4896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3427.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3434.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3440.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3443.6296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3445.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3451.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3454.1496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3455.1496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3456.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3462.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3463.6496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3464.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3466.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3469.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3470.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3472.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3475.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3476.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3478.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3481.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3481.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3485.2095 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3489.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3493.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3497.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3501.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3505.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3506.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3508.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3509.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3513.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3517.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3521.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3525.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3529.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3531.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3532.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3534.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3538.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3542.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3546.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3550.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3554.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3555.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3557.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3558.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3561.9527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3566.9527 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3567.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3570.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3570.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3576.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3579.6494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3580.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3586.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3589.4094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3590.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3596.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3599.5494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3601.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3607.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3610.0694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3611.0694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3612.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 3629.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3635.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3636.5694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3637.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3639.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3642.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3643.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3645.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3648.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3649.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3651.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3654.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3654.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3659.886 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3660.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3663.2027 | TurbineInstallation
| WTIV | Delay | 39 | 650000 | ACTION | 3702.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3702.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3708.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3711.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3712.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3718.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3721.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3722.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3728.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3731.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3733.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3739.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3742.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3743.0027 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3768.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3769.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3775.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3776.5027 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3777.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3779.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3782.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3783.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3785.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3788.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3789.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3791.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3794.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3794.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3799.8194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3800.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3803.136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3803.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3809.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3812.516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3813.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3819.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3822.276 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3823.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3839.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3845.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3848.416 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3849.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3855.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3858.936 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3859.936 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3861.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3865.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3871.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3872.436 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3873.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3874.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3878.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3879.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3880.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3884.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3885.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3886.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3890.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3890.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3893.996 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3897.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3901.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3905.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3909.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3913.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3915.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3916.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3918.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3922.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3926.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3930.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3934.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3938.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3939.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3941.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3942.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3946.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3950.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3954.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3958.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3962.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3964.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3965.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3967.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3970.7392 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3975.7392 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3976.0559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3979.0559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3979.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3985.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3988.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3989.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3995.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3998.1959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3999.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4005.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4008.3359 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4009.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4010.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 50 | 833333.3333 | ACTION | 4060.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4066.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4069.8559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4070.8559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4072.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4078.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4079.3559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4080.3559 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4082.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4083.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4087.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4088.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4089.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4093.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4094.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4095.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4099.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4099.6725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4104.6725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4104.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4107.9892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4108.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4114.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4117.3692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4118.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4124.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4127.1292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4128.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4134.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4137.2692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4138.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4144.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4147.7892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4148.7892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4150.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4156.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4157.2892 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4158.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4159.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4163.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4164.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4165.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4169.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4170.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4171.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4175.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4175.6059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4180.6059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4180.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4183.9225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4184.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4190.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4193.3025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4194.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 9 | 150000 | ACTION | 4203.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4209.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4212.0625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4213.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4219.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4222.2025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4223.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4229.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4232.7225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4233.7225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4235.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4241.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4242.2225 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4243.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4244.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4248.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4249.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4250.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4254.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4255.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4256.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4260.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4260.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4263.7824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4267.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4271.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4275.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4277.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4281.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4285.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4287.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4288.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4290.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4294.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4298.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4302.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4306.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4310.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4311.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4313.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4314.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4318.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4322.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4326.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4330.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4334.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4336.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4337.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4339.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4342.5257 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4347.5257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4347.8424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4350.8424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4351.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4357.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4360.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4360.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4370.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4376.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4379.9824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4381.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4387.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4390.1224 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 4402.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4403.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4409.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4412.6424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4413.6424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4415.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4421.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4422.1424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4423.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4424.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4428.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4429.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4430.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4434.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4435.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4436.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4440.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4440.459 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4445.459 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4445.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4448.7757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4449.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4455.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4458.1557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4458.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4464.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4467.9157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4469.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4475.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4478.0557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4479.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4485.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4488.5757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4489.5757 | TurbineInstallation
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4552.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4558.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4559.0757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4560.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4561.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4565.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4566.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4567.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4571.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4572.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4573.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4577.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4577.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4582.3924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4582.709 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4585.709 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4586.709 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4587.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 18 | 300000 | ACTION | 4605.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4611.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4614.089 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4698.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4698.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4702.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4708.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4711.849 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4712.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4718.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4721.989 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4723.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4729.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4732.509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4733.509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4735.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4741.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4742.009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4743.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4744.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4748.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4749.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4750.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4754.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4755.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4756.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4760.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4760.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4763.5689 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4767.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4771.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4775.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4779.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4783.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4785.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4786.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4788.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4792.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4796.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4800.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4804.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4808.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4809.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4811.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4812.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4816.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4833.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4837.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4841.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4845.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4849.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4851.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4852.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4854.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4857.3122 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4862.3122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4862.6288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4865.6288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4866.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4872.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4875.0088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4875.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4881.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4884.7688 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4888.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4889.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4895.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4898.9088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4900.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4906.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4909.4288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4910.4288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4911.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4917.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4918.9288 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4919.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4921.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4924.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4925.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4927.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4930.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4931.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4933.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4936.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4937.2455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4942.2455 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4942.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4945.5622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4945.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4951.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4954.9422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4955.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4961.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4964.7022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4965.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4971.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4974.8422 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4982.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4984.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4991.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4997.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5000.3622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5001.3622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5002.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5008.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5009.8622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5010.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5012.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5015.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5016.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5018.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5021.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5022.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5024.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 6 | 100000 | ACTION | 5030.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5033.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5034.1788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5039.1788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5039.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5042.4955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5042.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5048.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5051.8755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5052.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5058.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5061.6355 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5065.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5066.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5072.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5075.7755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5077.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5083.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5086.2955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5087.2955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5088.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5094.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5095.7955 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5096.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5098.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5101.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5102.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5104.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5107.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5108.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5110.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5113.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5114.1122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5117.3554 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5121.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5125.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5129.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5133.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5137.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5138.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5140.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5141.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5145.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5149.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5153.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 1256 | 20933333.3333 | ACTION | 6409.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6413.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6417.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6419.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6420.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6422.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6426.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6430.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6434.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6438.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6442.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6443.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6445.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6446.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6450.0987 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6455.0987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6455.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6458.4153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6458.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6464.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6467.7953 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6468.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6474.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6477.5553 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6478.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6484.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6487.6953 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6489.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6495.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6498.2153 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6499.2153 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 6516.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6517.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6523.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6524.7153 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6525.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6527.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6530.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6531.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6533.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6536.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6537.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6539.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6542.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6543.032 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6548.032 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6548.3487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6551.3487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6551.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6557.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6560.7287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6561.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6567.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6570.4887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6571.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6577.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6580.6287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6582.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6588.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6591.1487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6592.1487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6593.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6599.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6600.6487 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6601.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6603.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6606.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6607.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6609.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6612.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6613.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6615.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6618.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6618.9653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6623.9653 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6624.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6627.282 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6627.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6633.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6636.662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6637.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6643.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6646.422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6647.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6653.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6656.562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6658.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 6 | 100000 | ACTION | 6664.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6670.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6673.082 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6674.082 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6675.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6681.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6682.582 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6683.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6685.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6688.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6689.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6691.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6694.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6695.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6697.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6700.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6700.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6704.1419 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6708.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6712.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6716.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6720.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6724.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6725.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6727.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6728.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6732.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6736.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6740.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6744.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6745.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6749.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6751.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6752.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6754.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6758.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6762.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6766.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6770.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6774.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6775.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6777.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6778.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6781.8851 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6786.8851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6787.2018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6790.2018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6790.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6796.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6799.5818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6800.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6806.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6809.3418 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6823.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6824.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6830.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6833.4818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6835.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6841.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6844.0018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6845.0018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6846.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6852.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6853.5018 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6854.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6856.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6859.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6860.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6862.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6865.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6866.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6868.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6871.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6871.8185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6876.8185 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6877.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6880.1351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6880.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6886.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6889.5151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6890.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6896.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6899.2751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6900.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6906.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6909.4151 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6915.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6916.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6922.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6925.9351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6926.9351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6928.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 55 | 916666.6667 | ACTION | 6983.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6989.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6990.4351 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6991.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6992.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6996.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6997.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6998.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7002.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7003.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7004.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7008.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7008.7518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7013.7518 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7014.0685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7017.0685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7017.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7023.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7026.4485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7027.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7033.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7036.2085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7037.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7043.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7046.3485 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7049.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7050.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 42 | 700000 | ACTION | 7092.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7098.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7101.8685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7102.8685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7104.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7110.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7111.3685 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7112.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7113.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7117.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7118.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7119.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7123.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7124.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7125.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7129.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7129.6851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7132.9284 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7136.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7140.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7144.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7148.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7152.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7154.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7155.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7157.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7161.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7165.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7169.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7173.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7177.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7178.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7180.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7181.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7185.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7189.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7193.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7197.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7201.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7203.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7204.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7206.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7209.6716 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 7221.6716 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7226.6716 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7226.9883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7229.9883 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7230.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7236.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7239.3683 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7240.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7246.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7249.1283 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7250.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7256.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7259.2683 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7260.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7266.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7269.7883 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7270.7883 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7272.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7278.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7279.2883 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7280.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7281.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 25 | 416666.6667 | ACTION | 7306.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7310.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7311.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7312.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7316.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7317.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7318.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7322.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7322.605 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7327.605 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7327.9216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7330.9216 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7331.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 20 | 333333.3333 | ACTION | 7351.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7357.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7360.3016 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7361.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7367.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7370.0616 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7371.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7377.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7380.2016 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7381.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7387.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7390.7216 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7391.7216 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7393.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7399.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7400.2216 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7401.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7402.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 63 | 1050000 | ACTION | 7465.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7469.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7470.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7471.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7475.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7476.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7477.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7481.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7481.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7486.5383 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7486.855 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7489.855 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7490.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7496.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7499.235 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7499.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7505.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7508.995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7510.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7516.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7519.135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7520.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 29 | 483333.3333 | ACTION | 7549.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7555.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7558.655 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7559.655 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7561.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7567.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7568.155 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7569.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7570.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7574.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7575.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7576.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 3 | 50000 | ACTION | 7579.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7583.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7584.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7585.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7589.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7589.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7592.7149 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7596.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7600.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7604.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7608.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7612.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7614.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7615.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7617.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7621.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7625.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7629.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7633.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7637.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7638.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7640.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7641.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7645.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7649.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7653.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7657.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7661.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7663.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7664.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7666.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7669.4581 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7674.4581 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7674.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7677.7748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7678.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7684.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7687.1548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7687.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7693.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7696.9148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7698.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7704.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7707.0548 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7708.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 7731.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7737.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7740.5748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7741.5748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7743.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7749.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7750.0748 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7751.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7752.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7756.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7757.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7758.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7762.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7763.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7764.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7768.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7768.3915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7773.3915 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7773.7081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7776.7081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7777.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7783.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7786.0881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7786.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7792.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7795.8481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7796.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7802.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7805.9881 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7807.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7813.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7816.5081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7817.5081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7819.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7825.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7826.0081 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7827.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7828.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7832.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7833.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7834.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7838.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7839.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7840.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7844.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7844.3248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7849.3248 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7849.6415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7852.6415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7853.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7859.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7862.0215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7862.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7868.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7871.7815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7872.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7878.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7881.9215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7883.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7889.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7892.4415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7893.4415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7894.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7900.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7901.9415 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7902.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7904.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7907.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7908.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7910.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7913.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7914.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7916.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7919.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7920.2581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7923.5014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7927.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7931.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7935.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7939.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7943.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7945.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7946.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7948.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7952.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7956.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7960.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7964.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7968.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7969.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7971.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7972.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7976.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7980.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7984.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7988.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7992.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7994.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7995.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7997.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8000.2446 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8005.2446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8005.5613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8008.5613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8008.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8014.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8017.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8018.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8024.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8027.7013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8028.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8034.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8037.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8039.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 12 | 200000 | ACTION | 8051.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8057.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8060.3613 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8061.3613 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8062.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8072.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8078.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8079.8613 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8080.8613 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8085.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8087.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8090.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8091.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8093.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8094.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8097.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8098.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8100.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8103.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8104.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8109.1779 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8109.4946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8112.4946 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8112.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8118.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8121.8746 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8122.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8128.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8131.6346 | TurbineInstallation
| WTIV | Delay | 40 | 666666.6667 | ACTION | 8171.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8172.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8178.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8181.7746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8183.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8189.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8192.2946 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8193.2946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8194.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8200.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8201.7946 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8202.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8204.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8207.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8208.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8210.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8213.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8214.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8216.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8219.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8220.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8225.1113 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8225.4279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8228.4279 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8228.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8234.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8237.8079 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8238.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8244.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8247.5679 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8248.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8254.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8257.7079 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8259.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8265.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8268.2279 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8269.2279 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8270.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8276.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8277.7279 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8278.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8280.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8283.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8284.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8286.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 31 | 516666.6667 | ACTION | 8317.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8320.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8321.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8323.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8326.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8327.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8330.2878 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8334.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8338.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8342.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8346.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8350.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8354.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8355.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8357.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8358.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8362.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8366.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8370.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8374.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8378.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8380.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8381.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8383.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8387.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8391.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8395.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8399.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8403.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8404.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8406.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8407.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8411.0311 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8416.0311 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8416.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8419.3478 | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 8451.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8451.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8457.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8460.7278 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8461.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8467.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8470.4878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8471.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8477.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8480.6278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8482.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8488.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8491.1478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8492.1478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8493.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8499.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8500.6478 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8501.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8503.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8506.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8507.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8509.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8512.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8513.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8515.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8518.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8518.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8523.9644 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8524.2811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8527.2811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8527.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8533.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8536.6611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8537.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 6 | 100000 | ACTION | 8543.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8549.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8552.4211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8553.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8559.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8562.5611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8564.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8570.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8573.0811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8574.0811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8575.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 27 | 450000 | ACTION | 8602.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8608.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8609.5811 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8610.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8612.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8615.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8616.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8618.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8621.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8622.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8624.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8627.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8627.8978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8632.8978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8633.2144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8636.2144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8636.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8642.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8645.5944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8646.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 75 | 1250000 | ACTION | 8721.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8727.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8730.3544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8731.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8737.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8740.4944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8742.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8748.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8751.0144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8752.0144 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8753.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8759.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8760.5144 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8761.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8763.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8766.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8767.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8769.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8772.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8773.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8775.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8778.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8778.8311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8782.0743 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8786.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8790.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8794.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8798.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8802.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8803.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8805.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8806.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8810.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8814.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8818.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8822.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8826.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8828.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8829.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8831.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8835.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8839.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8843.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8847.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8851.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8852.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8854.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8855.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8858.8176 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8863.8176 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8864.1342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8867.1342 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8867.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8873.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8876.5142 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8877.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8883.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8886.2742 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8887.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8893.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8896.4142 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8897.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8903.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8906.9342 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8907.9342 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8909.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8915.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8916.4342 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8917.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8918.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8922.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8923.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8924.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8928.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8929.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8930.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8934.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8934.7509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8939.7509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8940.0676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8943.0676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8943.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8949.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8952.4476 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8953.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8959.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8962.2076 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8963.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8969.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8972.3476 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8974.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8975.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 8998.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9004.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9007.8676 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9008.8676 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9010.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 9021.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9027.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9028.3676 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9029.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9030.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9034.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9035.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9036.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9040.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9041.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9042.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9046.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9046.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9051.6842 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9052.0009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9055.0009 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9055.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9061.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9064.3809 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9065.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9071.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9074.1409 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9075.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9081.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9084.2809 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9085.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9091.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9094.8009 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9095.8009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9097.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9103.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9104.3009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9105.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9106.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9110.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9111.3009 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9112.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9113.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9117.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9118.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9119.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9123.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9123.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9126.8608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9130.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9134.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9138.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9142.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9146.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9148.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9149.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9151.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9155.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9159.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9163.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9167.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9171.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9172.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9174.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9175.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9179.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9183.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9187.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9191.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9195.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9197.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9198.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9200.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9203.6041 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9208.6041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9208.9207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9211.9207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9212.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9218.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9221.3007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9222.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9228.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9231.0607 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9232.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9238.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9241.2007 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9242.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9248.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9251.7207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9252.7207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9254.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9260.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9261.2207 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9262.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9263.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9267.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9268.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9269.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9273.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9274.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9275.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9279.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9279.5374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9284.5374 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9284.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9287.8541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9288.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9294.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9297.2341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9297.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9303.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9306.9941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9308.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 20 | 333333.3333 | ACTION | 9328.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9334.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9337.1341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9338.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9344.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9347.6541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9348.6541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9350.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9356.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9357.1541 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9358.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9359.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9363.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9364.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9365.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9369.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9370.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9371.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9375.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9375.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9380.4707 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9380.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9383.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9384.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9390.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9393.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9393.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9399.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9402.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9404.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9408.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9414.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9417.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9418.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9424.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9427.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9428.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9430.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9436.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9437.0874 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9438.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9439.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9443.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9444.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9445.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9449.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9450.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9451.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9455.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9455.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9458.6473 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9462.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9466.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9470.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9474.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9478.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9480.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9481.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9483.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9487.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9491.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9495.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9499.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9503.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9504.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9506.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9507.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9510.8906 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9515.8906 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9516.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9519.2072 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 9530.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9530.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9532.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9538.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9541.5872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9542.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 9553.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9559.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9562.3472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9563.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9569.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9572.4872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9574.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9580.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9583.0072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9584.0072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9585.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9591.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9592.5072 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9593.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9595.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9598.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9599.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9601.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9604.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9605.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9607.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9610.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9610.8239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9615.8239 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9616.1406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9619.1406 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9619.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9625.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9628.5206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9629.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9635.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9638.2806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9639.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9645.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9648.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9649.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9655.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9658.9406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9659.9406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9661.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9667.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9668.4406 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9669.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9670.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9674.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9678.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9679.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9680.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9684.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9685.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9686.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9690.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9690.7572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5