## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 89 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 109 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 112.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 114.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 114.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 115.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 118.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 119.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 119.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 120.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 121.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 123.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 124.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 125.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 129.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 130.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 132.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 132.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 133.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 136.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 137.1426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 137.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 138.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 139.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 141.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 142.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 143.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 147.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 147.9625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 149.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 150.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 151.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 154.2792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 155.0023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 155.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 156.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 157.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 159.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 160.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 161.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 181.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 185.5055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 185.8222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 187.8222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 188.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 189.1389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 192.1389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 192.8619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 192.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 193.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 195.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 197.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 198.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 199.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 203.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 203.6818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 206.9251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 218.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 226.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 238.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 246.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 258.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 266.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 278.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 286.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 290.1683 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 292.1683 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 292.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 293.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 296.485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 297.2081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 297.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 298.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 299.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 301.7113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 302.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 303.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 307.7113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 308.028 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 310.028 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 310.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 311.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 314.3446 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 315.3446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 316.0677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 316.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 317.071 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 318.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 320.571 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 321.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 322.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 326.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 326.8876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 328.8876 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 329.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 330.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 333.2043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 333.9274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 333.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 334.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 336.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 338.4306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 339.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 340.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 344.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 344.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 346.7473 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 347.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 348.0639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 351.0639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 351.787 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 351.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 352.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 354.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 356.2903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 357.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 358.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 362.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 362.6069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 365.8502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 377.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 385.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 397.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 405.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 417.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 425.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 437.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 445.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 449.0934 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 451.0934 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 451.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 452.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 455.4101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 456.1331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 456.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 457.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 458.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 460.6364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 461.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 462.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 466.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 466.9531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 468.9531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 469.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 470.2697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 473.2697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 473.9928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 473.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 474.996 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 476.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 478.496 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 479.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 480.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 484.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 484.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 486.8127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 487.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 488.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 491.1294 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 491.8524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 491.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 492.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 494.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 496.3557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 497.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 498.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 93 | 1550000 | ACTION | 591.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 595.3557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 595.6724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 597.6724 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 597.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 598.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 601.989 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 602.7121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 602.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 603.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 605.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 607.2153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 608.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 609.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 613.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 613.532 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 616.7752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 628.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 636.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 648.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 656.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 668.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 676.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 688.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 696.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 700.0185 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 702.0185 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 702.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 703.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 706.3352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 707.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 710.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 710.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 711.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 712.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 714.5615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 715.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 716.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 720.5615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 720.8781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 722.8781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 723.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 724.1948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 727.1948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 727.9179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 727.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 728.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 730.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 732.4211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 733.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 734.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 738.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 738.7378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 740.7378 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 741.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 742.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 745.0545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 745.7775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 745.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 746.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 748.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 750.2808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 751.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 752.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 756.2808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 756.5974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 758.5974 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 758.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 759.9141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 762.9141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 763.6372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 763.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 764.6404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 766.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 768.1404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 769.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 770.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 774.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 774.4571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 777.7003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 789.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 797.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 809.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 817.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 829.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 837.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 849.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 857.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 860.9436 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 862.9436 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 863.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 864.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 867.2602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 867.9833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 867.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 868.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 870.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 872.4866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 873.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 874.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 878.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 878.8032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 880.8032 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 881.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 882.1199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 885.1199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 885.843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 885.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 886.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 917.8462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 919.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 921.3462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 922.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 923.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 927.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 927.6629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 929.6629 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 929.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 930.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 933.9795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 934.7026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 934.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 935.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 937.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 939.2059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 940.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 941.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 945.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 945.5225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 947.5225 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 947.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 948.8392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 951.8392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 952.5622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 952.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 953.5655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 955.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 957.0655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 958.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 959.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 963.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 963.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 966.6254 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 978.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 986.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 998.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1006.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 37 | 616666.6667 | ACTION | 1043.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1055.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1063.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1075.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 1088.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1096.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1099.8687 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1101.8687 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1102.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1103.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1106.1853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1106.9084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1106.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1107.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1109.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1111.4116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1112.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1113.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1117.4116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1117.7283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1119.7283 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1120.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1121.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1124.045 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1124.768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1124.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1125.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1127.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1129.2713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1130.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1131.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1135.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1135.588 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1137.588 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1137.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1138.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1141.9046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1142.6277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1142.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1143.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1145.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1147.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1148.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1149.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1153.1309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1153.4476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1155.4476 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1155.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1156.7643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1159.7643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1160.4873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1160.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1161.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1162.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1164.9906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1165.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 72 | 1200000 | ACTION | 1237.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1238.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1242.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1243.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1246.5505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1258.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1266.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 1283.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1295.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1303.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1315.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1323.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1335.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1343.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1346.7937 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1348.7937 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1349.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1350.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1353.1104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1353.8335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1353.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1354.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 1359.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1361.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1363.3367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1364.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1365.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1369.3367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1369.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1371.6534 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1371.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1372.9701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1375.9701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1376.6931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1376.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1377.6964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1379.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1381.1964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1382.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1383.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1387.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1387.513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1389.513 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1389.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1390.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1393.8297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1394.5528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1394.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1395.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1397.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1399.056 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1400.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1401.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1405.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1405.3727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1407.3727 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1407.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1408.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1411.6893 | MonopileInstallation
| WTIV | Delay | 68 | 1133333.3333 | ACTION | 1479.6893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1480.4124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1480.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1481.4157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1482.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1484.9157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1485.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1486.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 1492.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1496.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1497.2323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1500.4756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1512.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1520.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1532.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1540.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1552.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1560.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1572.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1580.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1583.7188 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1585.7188 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1586.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1587.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1590.0355 | MonopileInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 1616.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1616.7585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1616.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1617.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1619.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1621.2618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1622.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1623.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1627.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1627.5785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1629.5785 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1629.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1630.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1633.8951 | MonopileInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 1664.8951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1665.6182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1665.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1666.6214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1668.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1670.1214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1671.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1672.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1676.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1676.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1678.4381 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1678.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1679.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1682.7548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1683.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1683.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1684.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1685.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1687.9811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1688.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1689.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1693.9811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1694.2978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1696.2978 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1696.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1697.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1700.6144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1701.3375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1701.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1702.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1703.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1705.8407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1706.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1707.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1711.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1712.1574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1715.4007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1727.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1735.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1747.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 1779.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1787.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1799.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1807.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1819.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1827.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1830.6439 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1832.6439 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1832.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1833.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1836.9606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1837.6836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1837.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1838.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1840.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1842.1869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1843.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1844.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1848.1869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1848.5035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1850.5035 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1850.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1851.8202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1854.8202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1855.5433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1855.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1856.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1858.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1860.0465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1861.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1862.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1866.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1866.3632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1868.3632 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1868.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1869.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1872.6799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1873.4029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1873.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1874.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1875.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1877.9062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1878.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1879.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1883.9062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1884.2228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1886.2228 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1886.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1887.5395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1890.5395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1891.2626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1891.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1892.2658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1893.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1895.7658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1896.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1897.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1901.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1902.0825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1905.3257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1917.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1925.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1937.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1945.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1957.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1965.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1977.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1985.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1988.569 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1990.569 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1990.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1991.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1994.8856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1995.6087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1995.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1996.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 1998.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2000.112 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2001.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2002.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2006.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2006.4286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2008.4286 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2008.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2009.7453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2012.7453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2013.4684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2013.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2014.4716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2015.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2017.9716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2018.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2019.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2023.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2024.2883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2026.2883 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2026.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2027.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2030.6049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2031.328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2031.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2032.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2033.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2035.8313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2036.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2037.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2041.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2042.1479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2044.1479 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2044.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2045.4646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2048.4646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2049.1877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2049.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2050.1909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2051.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2053.6909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2054.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2055.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2059.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2060.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2063.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2075.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2083.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2095.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2103.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2115.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 18 | 300000 | ACTION | 2133.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2141.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2153.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2161.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2164.4941 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2166.4941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2166.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2167.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2170.8107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2171.5338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2171.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2172.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2174.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2176.037 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2177.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2178.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2182.037 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2182.3537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2184.3537 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2184.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2185.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2188.6704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2189.3934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2189.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2190.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2191.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2193.8967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2194.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2195.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2199.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2200.2134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2202.2134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2202.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2203.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2206.53 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2207.2531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2207.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2208.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2209.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2211.7563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2212.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2213.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2217.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2218.073 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2220.073 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2220.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2221.3897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2224.3897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2225.1127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2225.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2226.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2227.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2229.616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2230.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2231.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 2240.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2244.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2244.9327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2248.1759 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2260.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2268.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2280.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2288.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 47 | 783333.3333 | ACTION | 2335.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2347.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2355.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2367.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2375.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3 | 50000 | ACTION | 2378.1759 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2382.1759 | MonopileInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 2382.4191 | MonopileInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 2396.4191 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2398.4191 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2398.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2399.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2403.7358 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2406.7358 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2408.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2409.4589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2409.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2410.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2411.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2413.9621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2414.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2415.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2419.9621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2420.2788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2422.2788 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2422.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2423.5955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2426.5955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2427.3185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2427.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2428.3218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2429.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2431.8218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2432.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2433.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2437.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2438.1384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2440.1384 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2440.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2441.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2444.4551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2445.1782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2445.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2446.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2447.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2449.6814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2450.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2451.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2455.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2455.9981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2457.9981 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2458.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2459.3148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2462.3148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2463.0378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2463.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2464.0411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2465.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2467.5411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2468.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2469.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2473.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2473.8577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2477.101 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2489.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2497.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2509.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2517.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2520.3442 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2522.3442 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2522.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2523.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2526.6609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2527.384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2527.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2528.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2529.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2531.8872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2532.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2534.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2535.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2539.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2540.2039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2542.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2542.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2543.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2546.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2547.2436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2547.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2548.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 25000 | ACTION | 2549.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2551.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2552.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2553.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2557.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2558.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 2558.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2562.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2566.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2570.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2574.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2578.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2579.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2581.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2582.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2586.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 2593.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2597.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2601.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2605.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2609.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2611.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2612.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2614.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2618.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2622.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2626.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2630.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2634.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2635.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2637.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2638.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2641.8068 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2643.8068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2644.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2647.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2647.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2653.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2656.5034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2657.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2663.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2666.2634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2667.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2673.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2676.4034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2677.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 2702.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2708.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2711.9234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2712.9234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2714.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2720.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2721.4234 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2722.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2723.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2727.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2728.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2729.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2733.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2734.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2735.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2739.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2739.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2741.7401 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2742.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2745.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2745.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2751.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2754.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2755.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2761.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2764.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2765.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2771.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2774.3368 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 2789.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2790.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2796.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2799.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2800.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2802.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2808.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2809.3568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2810.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2811.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2815.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2816.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2817.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2821.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2822.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2823.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2827.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2827.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2829.6734 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2829.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2832.9901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2833.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 2839.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2845.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2848.3701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2849.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2855.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2858.1301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2859.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2865.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2868.2701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2869.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2875.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2878.7901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2879.7901 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 2904.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2906.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2912.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2913.2901 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2914.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2915.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2919.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2920.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2921.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2925.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2926.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2927.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2931.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2931.6068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2934.85 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2938.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2942.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2946.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2950.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2954.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2956.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2957.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2959.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2963.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2967.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2971.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2975.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2979.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2980.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2982.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2983.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2987.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2991.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2995.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2999.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3003.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3005.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3006.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3022.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3024.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3027.5933 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3029.5933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3029.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3032.9099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3033.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3039.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3042.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3043.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 38 | 633333.3333 | ACTION | 3081.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3087.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3090.0499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3091.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3097.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3100.1899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3101.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3107.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3110.7099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3111.7099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3113.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3119.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3120.2099 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3121.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3122.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 3136.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3140.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3141.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3142.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3146.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3147.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3148.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3152.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3152.5266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3154.5266 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3154.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3157.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3158.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3164.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3167.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3167.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3173.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3176.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3178.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3203.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3209.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3212.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3213.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3219.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3222.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3223.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3225.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3231.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3232.1433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3233.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3234.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3238.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3239.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3240.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3244.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3245.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3246.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3250.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3250.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3252.4599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3252.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3255.7766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3256.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3262.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3265.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3265.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3271.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3274.9166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3276.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3282.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3285.0566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3286.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3292.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3295.5766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3296.5766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3298.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3304.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3305.0766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3306.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3307.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3311.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3312.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3313.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3317.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3318.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3319.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3323.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3323.3933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3326.6365 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3330.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3334.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3338.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3342.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3346.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3348.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3349.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3351.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3355.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3359.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3363.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3367.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3371.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3372.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3374.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3375.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3379.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3383.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3387.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3391.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3395.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3397.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3398.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3400.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3403.3797 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3405.3797 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3405.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3408.6964 | TurbineInstallation
| WTIV | Delay | 57 | 950000 | ACTION | 3465.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3466.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 3496.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3502.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3505.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3505.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3511.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3514.8364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3515.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3521.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3524.9764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3526.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3532.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3535.4964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3536.4964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3537.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3543.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3544.9964 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3545.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3547.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3550.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3551.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3553.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3556.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3557.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3559.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3562.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3563.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3565.3131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3565.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3568.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3569.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3575.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3578.0097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3578.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3584.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3587.7697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3588.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3594.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3597.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3599.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3605.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3608.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3609.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3610.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3616.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3617.9297 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3618.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3620.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3623.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3624.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3626.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3629.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3630.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3632.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3635.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3636.2464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3638.2464 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3638.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3641.5631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3641.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3647.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3650.9431 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3655.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3656.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3658.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3664.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3667.7031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3668.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 3699.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3705.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3708.8431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3710.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3716.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3719.3631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3720.3631 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 3726.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3727.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3750.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3756.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3757.8631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3758.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3760.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3763.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3764.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3766.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3769.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3770.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3772.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3775.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3776.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3779.423 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3783.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3787.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3791.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3795.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3799.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3800.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3802.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3804.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3805.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3809.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3813.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3817.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3821.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 40 | 666666.6667 | ACTION | 3861.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3865.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3867.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3868.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3870.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3874.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3878.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3882.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3886.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3890.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3891.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3893.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3894.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3898.1662 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3900.1662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3900.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3903.4829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3903.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3909.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3912.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3913.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3919.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3922.6229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3923.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3929.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3932.7629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3934.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3940.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3943.2829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3944.2829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3945.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3951.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3952.7829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3953.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3955.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3958.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3959.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3961.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3964.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3965.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3967.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3970.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3971.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3973.0996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3973.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3976.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3976.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3982.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3985.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3986.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3992.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3995.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3996.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4002.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4005.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4007.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4013.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4016.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4017.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4018.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4024.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4025.7162 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4026.7162 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4032.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4034.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4037.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4038.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4040.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4043.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4044.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4046.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4049.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4050.0329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4052.0329 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4052.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4055.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4055.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 4070.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4076.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4079.7296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4080.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4086.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4092.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4095.4896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4096.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4102.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4105.6296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4107.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4113.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4116.1496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4117.1496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4118.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4124.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4125.6496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4126.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4128.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4131.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4132.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4134.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4137.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4138.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4140.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4143.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4143.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4147.2095 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4151.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4155.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4159.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4163.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4167.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4168.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4170.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4171.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4175.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4179.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4183.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4187.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4191.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4193.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4194.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4196.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4200.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4204.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4208.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4212.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4216.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4217.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4219.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4220.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4223.9527 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4225.9527 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4226.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4229.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4229.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4235.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4238.6494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4239.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4245.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4248.4094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4249.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4255.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4258.5494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4260.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4266.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4269.0694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4270.0694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4271.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4277.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4278.5694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4279.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4281.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4284.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4285.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4287.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4290.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4291.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4293.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4296.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4296.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4298.886 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4299.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4302.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4302.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4308.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4311.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4312.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4318.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4321.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4322.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4328.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4331.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4333.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4339.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4342.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4343.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4344.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4350.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4351.5027 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4352.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4354.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4357.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4358.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4360.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4363.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4364.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4366.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4369.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4369.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4371.8194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4372.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4375.136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4375.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4381.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4384.516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4385.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4391.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4394.276 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4395.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4401.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4404.416 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4405.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4411.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4414.936 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4415.936 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4417.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4423.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4424.436 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4425.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4426.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4430.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4431.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4432.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4436.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4437.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4438.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4442.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4442.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4445.996 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4449.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4453.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4457.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4461.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4465.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4467.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4468.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4470.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4474.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4478.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4482.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4486.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4490.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4491.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4493.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4494.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4498.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4502.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4506.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4510.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4514.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4516.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4517.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4519.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4522.7392 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4524.7392 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4525.0559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4528.0559 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4531.0559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4531.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4539.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4545.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4548.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4549.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4555.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4561.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4564.1959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4565.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4571.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4574.3359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4575.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4581.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4584.8559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4585.8559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4587.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4593.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4594.3559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4595.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4596.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4600.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4601.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4602.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4606.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4607.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4608.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4612.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4612.6725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4614.6725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4614.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4617.9892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4618.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4624.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4627.3692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4628.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 4658.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4664.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4667.1292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4668.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4674.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4677.2692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4678.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4685.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4691.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4694.7892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4695.7892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4697.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4703.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4704.2892 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4705.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4706.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4710.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4711.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4712.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 4731.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4735.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4736.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4737.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4741.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4741.6059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4743.6059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4743.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4746.9225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4747.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4753.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4756.3025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4757.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4763.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4766.0625 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4772.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4773.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 4804.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4810.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4813.2025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4814.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4820.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4823.7225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4824.7225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4826.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4832.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4833.2225 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4834.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4835.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4839.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4840.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4841.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4845.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4846.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4847.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4851.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4851.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4854.7824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4858.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4862.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4866.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4870.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4874.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4876.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4877.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4879.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4883.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4887.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4891.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4895.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4899.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4900.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4902.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4903.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4907.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4911.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4915.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4919.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4923.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4925.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4926.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4928.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4931.5257 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4933.5257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4933.8424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4936.8424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4937.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4943.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4946.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4946.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4952.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4955.9824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4957.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4963.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4966.1224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4967.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4973.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4976.6424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4977.6424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4979.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4985.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4986.1424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4987.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4988.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4992.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4993.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4994.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4998.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4999.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5000.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5004.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5004.459 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5006.459 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5006.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5009.7757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5010.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 5023.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5029.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5032.1557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5032.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5037.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5043.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5046.9157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5048.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5054.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5057.0557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5058.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5064.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5067.5757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5068.5757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5070.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5076.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5077.0757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5078.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5079.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5083.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5084.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5085.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5089.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5090.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5091.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5095.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5095.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5097.3924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5097.709 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5100.709 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5101.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5107.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5110.089 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5110.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5116.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5119.849 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5120.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5126.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5129.989 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5131.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5137.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5140.509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5141.509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5143.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5149.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5150.009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5151.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5152.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5156.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5157.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5158.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5162.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5163.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5164.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5168.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5168.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5171.5689 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5175.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5179.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5183.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5187.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5191.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5193.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5194.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5196.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5200.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5204.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5208.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5212.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5216.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5217.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5219.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5220.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5224.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5228.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5232.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5236.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5240.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5242.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5243.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5245.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5248.3122 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5250.3122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5250.6288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5253.6288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5254.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5260.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5263.0088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5263.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5269.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5272.7688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5273.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5279.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5282.9088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5284.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5290.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5293.4288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5294.4288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5295.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5301.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5302.9288 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5303.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5305.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5308.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5309.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5311.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5314.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5315.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5317.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5320.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5321.2455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5323.2455 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5323.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5326.5622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5326.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5332.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5335.9422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5336.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5342.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5345.7022 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5350.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5351.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5357.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5360.8422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5362.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5368.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5371.3622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5372.3622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5373.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5379.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5380.8622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5381.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5383.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5386.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5387.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5389.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5392.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5393.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5395.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5398.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5399.1788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5401.1788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5401.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5404.4955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5404.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5410.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5413.8755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5414.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5420.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5423.6355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5424.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5430.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5433.7755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5435.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5441.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5444.2955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5445.2955 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 5446.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5447.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5453.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5454.7955 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5455.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5457.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5460.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5461.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5463.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 5471.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5474.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5475.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5477.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5480.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5481.1122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5484.3554 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5488.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5492.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5496.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5500.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5504.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5505.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5507.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5508.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5512.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5516.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5520.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5524.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5528.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5530.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5531.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5533.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5537.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5541.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5545.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5549.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5553.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5554.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5556.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5557.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5561.0987 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5563.0987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5563.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5566.4153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5566.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5572.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5575.7953 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5576.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5582.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5585.5553 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5586.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5592.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5595.6953 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5597.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5603.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5606.2153 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5607.2153 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5608.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5614.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5615.7153 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5616.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5618.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5621.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5622.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5624.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5627.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5628.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5630.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5633.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5634.032 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5636.032 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5636.3487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5639.3487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5639.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5645.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5648.7287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5649.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5655.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5658.4887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5659.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5665.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5668.6287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5670.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5676.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5679.1487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5680.1487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5681.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5687.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5688.6487 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5689.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5691.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5694.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5695.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5697.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5700.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5701.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5703.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5706.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5706.9653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5708.9653 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5709.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5712.282 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5712.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5718.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5721.662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5722.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5728.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5731.422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5732.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5738.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5741.562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5743.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5749.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5752.082 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5753.082 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5754.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5760.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5761.582 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5762.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5764.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5767.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5768.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5770.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5773.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5774.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5776.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5779.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5779.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5783.1419 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5787.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5791.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5795.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5799.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5803.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5804.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5806.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5807.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5811.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5815.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5819.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5823.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5827.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5829.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5830.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5832.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5836.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5840.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5844.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5848.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5852.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5853.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5855.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5856.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5859.8851 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5861.8851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5862.2018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5865.2018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5865.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5871.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5874.5818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5875.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5881.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5884.3418 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5885.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5891.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5894.4818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5896.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 5902.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5908.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5911.0018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5912.0018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5913.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5919.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5920.5018 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5921.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5923.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5926.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5927.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5929.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5932.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5933.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5935.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5938.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5938.8185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5940.8185 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5941.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5944.1351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5944.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5950.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5953.5151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5954.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5960.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5963.2751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5964.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5970.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5973.4151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5974.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5980.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5983.9351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5984.9351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5986.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6000.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6006.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6007.4351 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6008.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6009.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6013.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6014.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6015.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6019.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6020.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6021.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6025.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6025.7518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6027.7518 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6028.0685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6031.0685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6031.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6037.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6040.4485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6041.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6047.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6050.2085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6051.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6057.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6060.3485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6061.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6067.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6070.8685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6071.8685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6073.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6079.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6080.3685 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6081.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6082.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6086.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6087.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6088.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6092.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6093.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6094.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6098.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6098.6851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6101.9284 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6105.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6109.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6113.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6117.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6121.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6123.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6124.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6126.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6130.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6134.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6138.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6142.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6146.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6147.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6149.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6150.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6154.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6158.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6162.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6166.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6170.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6172.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6173.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6175.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6178.6716 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6180.6716 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6180.9883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6183.9883 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6184.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6190.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6193.3683 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6194.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6200.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6203.1283 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6204.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6210.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6213.2683 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6214.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6220.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6223.7883 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6224.7883 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6226.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6232.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6233.2883 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6234.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6235.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6239.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6240.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6241.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6245.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6246.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6247.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6251.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6251.605 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6253.605 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6253.9216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6256.9216 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6257.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6263.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6266.3016 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6267.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6273.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6276.0616 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6277.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6283.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6286.2016 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6287.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6293.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6296.7216 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6297.7216 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6299.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6305.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6306.2216 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6307.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6308.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6312.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6313.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6314.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6318.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6319.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6320.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6324.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6324.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6326.5383 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6326.855 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6329.855 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6330.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6336.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6339.235 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6339.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6345.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6348.995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6350.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6356.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6359.135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6360.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6366.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6369.655 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6370.655 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6372.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6378.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6379.155 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6380.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6381.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6385.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6386.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6387.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6391.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6392.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6393.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6397.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6397.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6400.7149 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6404.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6408.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6412.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6416.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6420.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6422.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6423.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6425.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6429.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6433.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6437.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6441.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6445.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6446.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6448.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6449.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6453.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6457.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6461.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6465.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6469.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6471.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6472.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6474.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6477.4581 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6479.4581 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6479.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6482.7748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6483.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6489.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6492.1548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6492.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6498.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6501.9148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6503.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6509.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6512.0548 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6513.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6519.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6522.5748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6523.5748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6525.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6531.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6532.0748 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6533.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6534.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6538.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6539.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6540.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6544.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6545.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6546.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6550.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6554.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6554.3915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6556.3915 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6556.7081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6559.7081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6560.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6566.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6569.0881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6569.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6575.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6578.8481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6579.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6585.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6588.9881 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6590.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6596.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6599.5081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6600.5081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6602.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6606.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6612.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6613.0081 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6614.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6615.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6619.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6620.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6621.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6625.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6626.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6627.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6631.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6631.3248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6633.3248 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6633.6415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6636.6415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6637.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6643.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6646.0215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6646.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6652.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6655.7815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6656.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6662.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6665.9215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6667.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6673.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6676.4415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6677.4415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6678.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6684.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6685.9415 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6686.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6688.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6691.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6692.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6694.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6697.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6698.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6700.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6703.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6704.2581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6707.5014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6711.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6715.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6719.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6723.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6727.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6729.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6730.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6732.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6736.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6740.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6744.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6748.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6752.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6753.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6755.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6756.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6760.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6764.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6768.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6772.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6776.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6778.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6779.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6781.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6784.2446 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6786.2446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6786.5613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6789.5613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6789.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6795.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6798.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6799.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6805.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6808.7013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6809.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6815.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6818.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6820.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6826.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6829.3613 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6830.3613 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6831.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6837.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6838.8613 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6839.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6841.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6844.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6845.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6847.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6850.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6851.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6853.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6856.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6857.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6859.1779 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6859.4946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6862.4946 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6862.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6868.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6871.8746 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6872.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6878.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6881.6346 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6882.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6888.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6891.7746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6893.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6899.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6902.2946 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6903.2946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6904.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6910.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6911.7946 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6912.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6914.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6917.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6918.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6920.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6923.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6924.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6926.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6929.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6930.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6932.1113 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6932.4279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6935.4279 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6935.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6941.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6944.8079 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6945.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6951.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6954.5679 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6955.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6961.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6964.7079 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6966.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6972.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6975.2279 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6976.2279 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6977.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6983.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6984.7279 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6985.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6987.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6990.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6991.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6993.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6996.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6997.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6999.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7002.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7003.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7006.2878 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7010.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7014.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7018.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7022.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7026.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7027.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7029.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7030.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7034.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7038.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7042.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7046.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7050.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7052.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7053.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7055.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7059.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7063.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7067.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7071.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7075.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7076.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7078.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7079.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7083.0311 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7085.0311 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7085.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7088.3478 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7088.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7094.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7097.7278 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7098.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7104.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7107.4878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7108.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7114.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7117.6278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7119.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7125.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7128.1478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7129.1478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7130.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7136.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7137.6478 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7138.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7140.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7143.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7144.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7146.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7149.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7150.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7152.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7155.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7155.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7157.9644 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7158.2811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7161.2811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7161.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7167.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7170.6611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7171.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7177.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7180.4211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7181.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7187.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7190.5611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7192.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7198.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7201.0811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7202.0811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7203.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7209.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7210.5811 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7211.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7213.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7216.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7217.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7219.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7222.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7223.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7225.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7228.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7228.8978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7230.8978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7231.2144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7234.2144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7234.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7240.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7243.5944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7244.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7250.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7253.3544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7254.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7260.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7263.4944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7265.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7271.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7274.0144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7275.0144 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7276.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7282.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7283.5144 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7284.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7286.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7289.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7290.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7292.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7295.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7296.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7298.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7301.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7301.8311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7305.0743 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7309.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7313.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7317.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7321.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7323.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7327.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7334.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7335.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7337.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 7349.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7350.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7354.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7358.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7362.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7366.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7370.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7372.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7373.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7375.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7379.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7383.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7387.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7391.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7395.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7396.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7398.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7399.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7402.8176 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7404.8176 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7405.1342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7408.1342 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7408.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7414.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7417.5142 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7418.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7424.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7427.2742 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7428.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7434.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7437.4142 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7438.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7444.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7447.9342 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7448.9342 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7450.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7456.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7457.4342 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7458.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7459.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7463.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7464.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7465.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7469.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7470.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7471.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7475.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7475.7509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7477.7509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7478.0676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7481.0676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7481.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7487.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7490.4476 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7491.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7497.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7500.2076 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7501.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7507.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7510.3476 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7511.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7517.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7520.8676 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7521.8676 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7523.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7529.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7530.3676 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7531.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7532.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7536.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7537.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7538.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7542.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7543.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7544.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7548.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7548.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7550.6842 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7551.0009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7554.0009 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7554.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7560.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7563.3809 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7564.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7570.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7573.1409 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7574.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7580.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7583.2809 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7584.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7590.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7593.8009 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7594.8009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7596.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 7617.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7623.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7624.3009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7625.3009 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7635.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7636.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7640.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7641.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7642.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7646.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7647.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7648.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7652.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7652.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7655.8608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7659.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7663.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7667.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7671.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7675.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7677.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7678.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7680.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7684.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7688.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7692.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7696.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7700.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7701.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7703.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7704.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7708.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7712.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7716.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7720.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7724.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7726.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7727.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7729.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7732.6041 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7734.6041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7734.9207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7737.9207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7738.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7744.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7747.3007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7748.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7754.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7757.0607 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7758.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7764.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7767.2007 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7768.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7774.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7777.7207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7778.7207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7780.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7786.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7787.2207 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7788.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7789.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7793.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7794.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7795.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7799.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7800.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7801.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7805.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7805.5374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7807.5374 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7807.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7810.8541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7811.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7817.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7820.2341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7820.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7826.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7829.9941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7831.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7837.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7840.1341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7841.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7847.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7850.6541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7851.6541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7853.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7859.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7860.1541 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7861.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7862.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7866.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7867.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7868.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7872.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7873.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7874.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7878.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7878.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7880.4707 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7880.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7883.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7884.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7890.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7893.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7893.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7899.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7902.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7904.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7910.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7913.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7914.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 7936.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7942.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7945.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7946.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7948.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7954.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7955.0874 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7956.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7957.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7961.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7962.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7963.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7967.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7968.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7969.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7973.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7973.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7976.6473 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7980.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7984.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7988.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7992.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7996.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7998.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7999.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8001.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8005.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8009.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8013.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8017.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8021.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8022.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8024.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8025.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8028.8906 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 8030.8906 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8031.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8034.2072 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8034.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8040.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8043.5872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8044.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8050.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8053.3472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8054.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8060.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8063.4872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8065.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8071.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8074.0072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8075.0072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8076.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8082.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8083.5072 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8084.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8086.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8089.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8090.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8092.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8095.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8096.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8098.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8101.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8101.8239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 8103.8239 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8104.1406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8107.1406 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8107.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8113.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8116.5206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8117.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 8123.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8129.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8132.2806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8133.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8139.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8142.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8143.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8149.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8152.9406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8153.9406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8155.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8161.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8162.4406 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8163.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8164.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8168.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8169.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8170.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8174.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8175.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8176.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8180.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8180.7572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation