## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Delay | 32 | 160000 | ACTION | 92 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 104 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 112 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Queue | 112 | 560000 | ACTION | 112 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 115.2432 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 116.9099 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 113.6667 | 1184027.7778 | ACTION | 116.9099 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 118.9099 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 119.2266 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 120.2266 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 123.2266 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 123.9496 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 123.9529 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 124 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 124.9529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 126.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 128.4529 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 129.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 130.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 132 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 134.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 134.7696 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 136.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 137.0862 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 138.0862 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 141.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 141.8093 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 141.8125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 142.8125 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 144 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 144.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 146.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 147.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 148.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 152 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 152.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 152.6292 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 154.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 154.9459 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 155.9459 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 158.9459 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 159.9459 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 160.6689 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 160.6722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 161.6722 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 164 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 181.6722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 183.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 185.1722 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 186.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 187.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Delay | 26 | 130000 | ACTION | 190 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 191.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 191.4889 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 193.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 193.8055 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 194.8055 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 197.8055 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 198 | MonopileInstallation | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 198.5286 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 198.5318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 199.5318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 201.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 203.0318 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 86.1219 | 430609.644 | ACTION | 203.0318 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 204.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 204.6985 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 205.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 207.9417 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 209.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 209.3485 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 210 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 218 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 10.0583 | 50291.2569 | ACTION | 218 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 221.2432 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 222.9099 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 13.5614 | 141264.6305 | ACTION | 222.9099 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 224.9099 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 225.2266 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 226.2266 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 229.2266 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 229.9496 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 229.9529 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 230 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 230.9529 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 238 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 246.9529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 248.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 250 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 250.4529 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 251.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 252.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 256.4529 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 256.7696 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 258 | MonopileInstallation | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 258.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 259.0862 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 260.0862 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 263.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 263.8093 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 263.8125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 264.8125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 266.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 268.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 269.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 270 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 270.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 274.3125 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 274.6292 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 276.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 276.9459 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 277.9459 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 278 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 280.9459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 281.6689 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 281.6722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 282.6722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 284.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 286.1722 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 287.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 288.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 290 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 292.1722 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 292.4889 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 294.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 294.8055 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 295.8055 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 298 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 298.8055 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 299.5286 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 299.5318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 300.5318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 301.2432 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 302.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 302.9099 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 304.0318 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 81.1219 | 405609.644 | ACTION | 304.0318 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 305.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 305.6985 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 306.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 308.9417 | MonopileInstallation
| Feeder 0 | Queue | 6.0318 | 30159.1936 | ACTION | 308.9417 | MonopileInstallation |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 310.0318 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 310.3485 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 312.3485 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 312.6652 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 313.6652 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 316.6652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 317.3882 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 317.3915 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 318.3915 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 319.8915 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 320.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 321.8915 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 322.8915 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 323.8915 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 327.8915 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 328.2082 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 328.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 330.2082 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 330.5248 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 331.5248 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 334.5248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 335.2479 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 335.2511 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 336.2511 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 337.7511 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 339.7511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 340.7511 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 340.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 341.7511 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 345.7511 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 346.0678 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 348.0678 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 348.3845 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 348.9417 | MonopileInstallation | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 349.3845 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 352.3845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 353.1075 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 353.1108 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 354.1108 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 355.6108 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 357.6108 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 358.6108 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 359.6108 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 360.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 363.6108 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 363.9275 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 365.9275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 366.2441 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 367.2441 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 368.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 370.2441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 370.9672 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 370.9704 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 371.9704 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 373.4704 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 375.4704 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 66.5287 | 332643.4278 | ACTION | 375.4704 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 376.4704 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 377.1371 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 377.4704 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 380.3803 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 380.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 381.4704 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 381.7871 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 388.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 8.5614 | 42807.0226 | ACTION | 388.9417 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 392.185 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 393.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 12.0646 | 125672.4758 | ACTION | 393.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 395.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 396.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 397.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 400.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 400.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 400.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 400.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 401.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 403.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 405.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 406.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 407.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 408.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 411.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 411.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 413.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 414.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 415.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 418.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 418.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 418.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 419.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 420.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 421.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 423.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 424.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 425.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 428.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 429.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 429.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 431.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 431.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 432.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 435.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 436.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 436.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 437.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 439.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 440.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 441.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 442.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 443.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 447.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 447.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 448.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 449.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 449.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 450.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 453.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 454.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 454.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 455.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 456.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 458.9736 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 65.1219 | 325609.644 | ACTION | 458.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 459.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 460.6403 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 460.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 460.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 463.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 464.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 465.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 468.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Queue | 5.0583 | 25291.2569 | ACTION | 468.9417 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 472.185 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 473.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 8.5614 | 89181.2971 | ACTION | 473.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 475.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 476.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 477.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 480.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 480.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 480.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 480.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 481.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 483.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 485.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 486.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 487.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 488.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 491.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 491.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 493.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 494.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 495.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 498.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 498.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 498.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 499.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 500.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 501.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 503.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 505.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 506.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 508.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 85 | 885416.6667 | ACTION | 591.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 592.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 596.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 596.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 598.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 598.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 599.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Delay | 93 | 465000 | ACTION | 601.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 602.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 603.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 603.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 604.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 606.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 608.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 609.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 610.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 613.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 614.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 614.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 616.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 616.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 617.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 620.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 621.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 621.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 621.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 622.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 623.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 625.9736 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 152.1219 | 760609.644 | ACTION | 625.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 626.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 627.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 627.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 630.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 631.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 632.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 633.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 641.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 11.0583 | 55291.2569 | ACTION | 641.9417 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 645.185 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 646.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 14.5614 | 151681.2971 | ACTION | 646.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 648.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 649.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 650.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 653.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 653.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 653.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 653.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 654.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 656.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 658.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 659.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 660.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 661.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 664.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 664.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 666.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 667.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 668.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 671.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 671.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 671.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 672.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 673.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 674.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 676.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 677.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 678.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 681.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 682.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 682.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 684.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 684.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 685.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 688.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 689.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 689.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 690.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 692.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 693.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 694.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 695.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 696.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 700.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 700.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 701.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 702.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 702.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 703.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 706.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 707.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 710.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 710.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 711.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 712.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 713.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 714.9736 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 68.1219 | 340609.644 | ACTION | 714.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 715.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 716.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 716.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 719.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 720.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 721.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 721.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Queue | 2.0583 | 10291.2569 | ACTION | 721.9417 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 725.185 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 726.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 5.5614 | 57931.2971 | ACTION | 726.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 728.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 729.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 730.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 733.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 733.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 733.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 733.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 734.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 736.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 738.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 739.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 740.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 741.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 744.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 744.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 746.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 747.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 748.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 751.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 751.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 751.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 752.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 753.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 754.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 756.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 757.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 758.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 761.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 762.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 762.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 764.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 764.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 765.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 768.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 769.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 769.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 770.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 772.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 773.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 774.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 775.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 776.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 780.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 780.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 781.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 782.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 782.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 783.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 786.7473 | MonopileInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 790.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 791.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 791.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 792.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 793.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 793.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 795.9736 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 69.1219 | 345609.644 | ACTION | 795.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 796.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 797.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 797.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 801.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 802.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Delay | 18 | 90000 | ACTION | 815.6403 | MonopileInstallation
| Feeder 1 | Delay | 22 | 110000 | ACTION | 815.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 818.8835 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 823.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 5.0583 | 25291.2569 | ACTION | 823.9417 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 827.185 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 828.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 26.5614 | 276681.2971 | ACTION | 828.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 830.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 831.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 832.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 835.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 835.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 835.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 835.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 836.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 838.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 840.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 841.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 842.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 843.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 846.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 846.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 848.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 849.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 850.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 853.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 853.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 853.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 854.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 855.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 856.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 858.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 859.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 860.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 863.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 864.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 864.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 866.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 866.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 867.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 870.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 871.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 871.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 872.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 874.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 875.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 876.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 877.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 878.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 883.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 39 | 406250 | ACTION | 917.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Delay | 34 | 170000 | ACTION | 917.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 921.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 921.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 923.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 923.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 924.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 927.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 928.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 928.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 929.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 929.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 930.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 932.9736 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 104.1219 | 520609.644 | ACTION | 932.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 933.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 934.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 934.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 937.8835 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 937.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Queue | 0.058251 | 291.2569 | ACTION | 937.9417 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 938.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 939.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 941.185 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 942.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 3.5614 | 37097.9638 | ACTION | 942.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 944.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 945.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 946.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 949.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 949.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 949.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 949.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 950.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 952.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 954.3946 | MonopileInstallation
| Feeder 1 | Delay | 5 | 25000 | ACTION | 954.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 955.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 956.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 960.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 960.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 962.7113 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 962.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 963.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 964.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 967.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 967.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 967.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 968.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 970.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 972.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 973.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 974.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 974.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 978.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 978.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 980.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 980.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 981.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 982.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 984.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 985.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 985.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 986.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 988.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 990.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 991.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 992.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 994.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 996.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 996.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 998.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 998.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 999.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1002.7473 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1002.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1003.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1003.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1004.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1005.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1007.9736 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 65.1219 | 325609.644 | ACTION | 1007.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1008.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1009.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1009.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1012.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1013.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1014.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1014.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Delay | 32 | 160000 | ACTION | 1046.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1054.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 42.0583 | 210291.2569 | ACTION | 1054.9417 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1058.185 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1059.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 45.5614 | 474597.9638 | ACTION | 1059.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1061.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1062.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1063.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1066.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1066.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1066.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1066.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1067.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1069.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1071.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1072.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1073.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1074.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Delay | 20 | 100000 | ACTION | 1094.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 22 | 229166.6667 | ACTION | 1095.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1099.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1099.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1101.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1102.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1103.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1106.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1106.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1106.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1106.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1107.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1109.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1111.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1112.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1113.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1114.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1117.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1117.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1119.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1119.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1120.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1123.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1124.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1124.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1125.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1126.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1127.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1129.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1130.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1131.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1134.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1135.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1135.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1137.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1137.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1138.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1141.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1142.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1142.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1143.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1144.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1146.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1146.9736 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 87.1219 | 435609.644 | ACTION | 1146.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1147.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1148.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1148.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1151.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1152.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1153.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1154.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Queue | 3.0583 | 15291.2569 | ACTION | 1154.9417 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1158.185 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 1159.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 6.5614 | 68347.9638 | ACTION | 1159.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1161.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1162.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1163.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1166.1683 | MonopileInstallation
| WTIV | Delay | 71 | 739583.3333 | ACTION | 1237.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1237.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1237.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1238.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Delay | 84 | 420000 | ACTION | 1238.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1240.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1242.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1243.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1244.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1248.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1248.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1250.7113 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1250.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1251.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1252.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1255.028 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1255.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1255.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1256.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1258.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1258.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1260.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1261.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1262.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1266.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1266.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1268.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1268.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1269.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1270.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1272.8876 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 1281.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1282.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1283.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1283.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1284.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Delay | 14 | 70000 | ACTION | 1284.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1286.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1288.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1289.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1290.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1292.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Delay | 1 | 5000 | ACTION | 1293.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1294.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1294.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1296.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1296.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1297.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1300.7473 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1301.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1301.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1302.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1303.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1305.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1305.9736 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 146.1219 | 730609.644 | ACTION | 1305.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1306.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1307.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1307.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1310.8835 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1311.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1312.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1313.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1325.9417 | MonopileInstallation | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1333.9417 | MonopileInstallation | MonopileInstallation
| Feeder 0 | Queue | 23.0583 | 115291.2569 | ACTION | 1333.9417 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1337.185 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1338.8517 | MonopileInstallation | MonopileInstallation
| WTIV | Delay: Not enough vessels for monopiles | 26.5614 | 276681.2971 | ACTION | 1338.8517 | MonopileInstallation |  | Site
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1340.8517 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1341.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1342.1683 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1345.1683 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1345.8914 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1345.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1345.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1346.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 1350.8946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1352.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1353.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1354.3946 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1355.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Delay | 5 | 25000 | ACTION | 1358.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 1359.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1360.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1364.3946 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1364.7113 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1366.7113 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1367.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1368.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1370.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1371.028 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1374.028 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1374.751 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1374.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1375.7543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1377.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1378.9417 | MonopileInstallation | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1379.2543 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1380.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1381.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1385.2543 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1385.571 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1387.571 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1387.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1388.8876 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1391.8876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1392.6107 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1392.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1393.6139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1395.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1397.1139 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1398.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1399.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1403.1139 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1403.4306 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1405.4306 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1405.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1406.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1409.7473 | MonopileInstallation
| WTIV | Delay | 70 | 729166.6667 | ACTION | 1479.7473 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1480.4703 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1480.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1481.4736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1482.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1484.9736 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 146.1219 | 730609.644 | ACTION | 1484.9736 | MonopileInstallation |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1485.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1486.6403 | MonopileInstallation | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1486.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1489.8835 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 1492.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1496.9736 | MonopileInstallation | MonopileInstallation |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1497.2903 | MonopileInstallation | MonopileInstallation |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 1497.2903 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1501.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1505.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1509.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1513.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1517.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1518.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1520.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1521.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1525.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1529.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1533.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1537.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1541.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1543.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1544.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1546.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1550.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1554.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1558.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1562.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1566.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1567.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1569.2903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1570.7903 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1574.0335 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1576.0335 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1576.3502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1579.3502 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 1615.3502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1615.7302 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1621.7302 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1624.7302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1625.4902 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 38 | 633333.3333 | ACTION | 1663.4902 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1669.4902 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1672.4902 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1673.6302 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1679.6302 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1682.6302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1684.1502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1690.1502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1693.1502 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1694.1502 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1695.6502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1701.6502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1702.6502 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1703.6502 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1705.1502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1708.6502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1709.6502 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1711.1502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1714.6502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1715.6502 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1717.1502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1720.6502 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1720.9668 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1722.9668 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1723.2835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1726.2835 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1726.6635 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1732.6635 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1735.6635 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1736.4235 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1742.4235 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1745.4235 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1746.5635 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 39 | 650000 | ACTION | 1785.5635 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1791.5635 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1794.5635 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1796.0835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1802.0835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1805.0835 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1806.0835 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1807.5835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1813.5835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1814.5835 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1815.5835 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1817.0835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1820.5835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1821.5835 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1823.0835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1826.5835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1827.5835 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1829.0835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1832.5835 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1832.9002 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1834.9002 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1835.2168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1838.2168 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1838.5968 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1844.5968 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1847.5968 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1848.3568 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1854.3568 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1857.3568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1858.4968 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1864.4968 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1867.4968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1869.0168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1875.0168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1878.0168 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1879.0168 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1880.5168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1886.5168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1887.5168 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1888.5168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1890.0168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1893.5168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1894.5168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1896.0168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1899.5168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1900.5168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1902.0168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1905.5168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1905.8335 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1909.0767 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1913.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1917.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1921.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1925.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1929.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1930.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1932.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1933.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1937.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1941.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1945.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1949.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1953.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1955.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1956.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1958.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1962.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1966.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1970.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1974.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1978.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1979.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1981.0767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1982.5767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1985.82 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 1987.82 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1988.1367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1991.1367 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1991.5167 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 1993.5167 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1999.5167 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2002.5167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2003.2767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2009.2767 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2012.2767 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2013.4167 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2019.4167 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2022.4167 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2023.9367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2029.9367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2032.9367 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2033.9367 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2035.4367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2041.4367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2042.4367 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2043.4367 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2044.9367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2048.4367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2049.4367 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2050.9367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2054.4367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2055.4367 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2056.9367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2060.4367 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2060.7533 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2062.7533 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2063.07 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2066.07 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2066.45 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2072.45 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2075.45 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2076.21 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2082.21 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2085.21 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2086.35 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2092.35 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2095.35 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2096.87 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2102.87 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2105.87 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2106.87 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2108.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 2134.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2140.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2141.37 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2142.37 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2143.87 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2147.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2148.37 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2149.87 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2153.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2154.37 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2155.87 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2159.37 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2159.6867 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2161.6867 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2162.0033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2165.0033 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2165.3833 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2171.3833 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2174.3833 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2175.1433 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2181.1433 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2184.1433 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2185.2833 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2191.2833 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2194.2833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2195.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2201.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2204.8033 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2205.8033 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2207.3033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2213.3033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2214.3033 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2215.3033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2216.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2220.3033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2221.3033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2222.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2226.3033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2227.3033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2228.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 11 | 183333.3333 | ACTION | 2239.8033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2243.3033 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2243.62 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2246.8632 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2250.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2254.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2258.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2262.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2266.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2268.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2269.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2271.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2275.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2279.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2283.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2287.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2291.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2292.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 2334.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2336.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2337.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2341.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2345.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2349.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2353.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2357.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2359.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2360.8632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2362.3632 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2365.6065 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2367.6065 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2367.9231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2370.9231 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2371.3031 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 36 | 600000 | ACTION | 2407.3031 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2413.3031 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2416.3031 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2417.0631 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2423.0631 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2426.0631 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2427.2031 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2433.2031 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2436.2031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2437.7231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2443.7231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2446.7231 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2447.7231 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2449.2231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2455.2231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2456.2231 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2457.2231 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2458.7231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2462.2231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2463.2231 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2464.7231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2468.2231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2469.2231 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2470.7231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2474.2231 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2474.5398 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2476.5398 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2476.8565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2479.8565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2480.2365 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2486.2365 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2489.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2489.9965 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2495.9965 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2498.9965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2500.1365 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2506.1365 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2509.1365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2510.6565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2516.6565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2519.6565 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2520.6565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2522.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2528.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2529.1565 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2530.1565 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2534.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2535.6565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2539.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2540.1565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2541.6565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2545.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2546.1565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2547.6565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2551.1565 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2551.4731 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2553.4731 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2553.7898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2556.7898 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2557.1698 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2563.1698 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2566.1698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2566.9298 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2572.9298 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2575.9298 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2577.0698 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 25 | 416666.6667 | ACTION | 2602.0698 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2608.0698 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2611.0698 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2612.5898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2618.5898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2621.5898 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2622.5898 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2624.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2630.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2631.0898 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2632.0898 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2633.5898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2637.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2638.0898 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 2644.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2645.5898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2649.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2650.0898 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2651.5898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2655.0898 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2655.4065 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2658.6497 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2662.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2666.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2670.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2674.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2678.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2680.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2681.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2683.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 16 | 266666.6667 | ACTION | 2699.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2703.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2707.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2711.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2715.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2719.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2720.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2722.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2723.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2727.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2731.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2735.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2739.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2743.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2745.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2746.6497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2748.1497 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2751.393 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2753.393 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2753.7096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2756.7096 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2757.0896 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2763.0896 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2766.0896 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2766.8496 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2772.8496 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2775.8496 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 2789.8496 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2790.9896 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2796.9896 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2799.9896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2801.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2807.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2810.5096 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2811.5096 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2813.0096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2819.0096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2820.0096 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2821.0096 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2822.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2826.0096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2827.0096 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2828.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2832.0096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2833.0096 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2834.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 2839.5096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2843.0096 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2843.3263 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2845.3263 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2845.643 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2848.643 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2849.023 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2855.023 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2858.023 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2858.783 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2864.783 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2867.783 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2868.923 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2874.923 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2877.923 | TurbineInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 2904.923 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2906.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2912.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2915.443 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2916.443 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2917.943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2923.943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2924.943 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2925.943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2927.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2930.943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2931.943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2933.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2936.943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2937.943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2939.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 2940.443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2943.943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2944.2596 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 2946.2596 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2946.5763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2949.5763 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2949.9563 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2955.9563 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2958.9563 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2959.7163 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2965.7163 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2968.7163 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2969.8563 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2975.8563 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2978.8563 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2980.3763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2986.3763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2989.3763 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2990.3763 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2991.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 31 | 516666.6667 | ACTION | 3022.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3028.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3029.8763 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3030.8763 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3032.3763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3035.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3036.8763 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3038.3763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3041.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3042.8763 | TurbineInstallation
| WTIV | Delay | 38 | 633333.3333 | ACTION | 3080.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3082.3763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3085.8763 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3086.193 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3089.4362 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3093.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3097.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3101.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3105.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3109.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3110.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3112.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3113.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3117.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3121.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3125.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3129.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3133.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3135.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3136.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3138.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3142.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3146.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3150.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3154.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3158.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3159.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3161.4362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3162.9362 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3166.1794 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3168.1794 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3168.4961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3171.4961 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3171.8761 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3177.8761 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3180.8761 | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3203.8761 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3204.6361 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3210.6361 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3213.6361 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3214.7761 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3220.7761 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3223.7761 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3225.2961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3231.2961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3234.2961 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3235.2961 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3236.7961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3242.7961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3243.7961 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3244.7961 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3246.2961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3249.7961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3250.7961 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3252.2961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3255.7961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3256.7961 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3258.2961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3261.7961 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3262.1128 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3264.1128 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3264.4294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3267.4294 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3267.8094 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3273.8094 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3276.8094 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3277.5694 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3283.5694 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3286.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3287.7094 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3293.7094 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3296.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3298.2294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3304.2294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3307.2294 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3308.2294 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3309.7294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3315.7294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3316.7294 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3317.7294 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3319.2294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3322.7294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3323.7294 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3325.2294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3328.7294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3329.7294 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3331.2294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3334.7294 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3335.0461 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3337.0461 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3337.3628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3340.3628 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3340.7428 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3346.7428 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3349.7428 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3350.5028 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3356.5028 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3359.5028 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3360.6428 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3366.6428 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3369.6428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3371.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3377.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3380.1628 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3381.1628 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3382.6628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3388.6628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3389.6628 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3390.6628 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3392.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3395.6628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3396.6628 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3398.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3401.6628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3402.6628 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3404.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 64 | 1066666.6667 | ACTION | 3468.1628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3471.6628 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3471.9794 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 1 | 16666.6667 | ACTION | 3472.9794 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3473.9794 | TurbineInstallation
| WTIV | Transit | 1 | 16666.6667 | ACTION | 3474.9794 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3476.9794 | TurbineInstallation
| WTIV | Transit | 1 | 16666.6667 | ACTION | 3477.9794 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3487.9794 | TurbineInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 3488.2227 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3496.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3500.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3504.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3508.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3512.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3516.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3517.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3519.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3520.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3524.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3528.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3532.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3536.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3540.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3542.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3543.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3545.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3549.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3553.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3557.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3561.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3565.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3566.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3568.2227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3569.7227 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3572.9659 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3574.9659 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3575.2826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3578.2826 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3578.6626 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3584.6626 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3587.6626 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3588.4226 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3594.4226 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3597.4226 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3598.5626 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3604.5626 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3607.5626 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3609.0826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3615.0826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3618.0826 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3619.0826 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3620.5826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3626.5826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3627.5826 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3628.5826 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3630.0826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3633.5826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3634.5826 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3636.0826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3639.5826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3640.5826 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3642.0826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3645.5826 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3645.8993 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3647.8993 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3648.2159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3651.2159 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3656.2159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3656.5959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3658.5959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3664.5959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3667.5959 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3668.3559 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 31 | 516666.6667 | ACTION | 3699.3559 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3705.3559 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3708.3559 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3709.4959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3715.4959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3718.4959 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3726.4959 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3728.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3751.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3757.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3760.0159 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3761.0159 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3762.5159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3768.5159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3769.5159 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3770.5159 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3772.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3775.5159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3776.5159 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3778.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3781.5159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3782.5159 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3784.0159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3787.5159 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3787.8326 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 3789.8326 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3790.1493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3793.1493 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3793.5293 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 68 | 1133333.3333 | ACTION | 3861.5293 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3867.5293 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3870.5293 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3871.2893 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3877.2893 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3880.2893 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3881.4293 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3887.4293 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3890.4293 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3891.9493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3897.9493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3900.9493 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3901.9493 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3903.4493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3909.4493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3910.4493 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3911.4493 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3912.9493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3916.4493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3917.4493 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3918.9493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3922.4493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3923.4493 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3924.9493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3928.4493 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3928.7659 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3932.0092 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3936.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3940.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3944.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3948.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3952.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3953.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3955.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3956.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3960.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3964.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3968.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3972.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3976.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3978.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3979.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3981.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3985.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3989.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3993.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3997.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4001.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4002.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4004.0092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4005.5092 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4008.7524 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4010.7524 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4011.0691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4014.0691 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4014.4491 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4020.4491 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4023.4491 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4024.2091 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 9 | 150000 | ACTION | 4033.2091 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4039.2091 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4042.2091 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4043.3491 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4049.3491 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4052.3491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4053.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4059.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4062.8691 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4063.8691 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4070.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4072.3691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4078.3691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4079.3691 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4080.3691 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4081.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4085.3691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4086.3691 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4087.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4091.3691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4092.3691 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4093.8691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4097.3691 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4097.6857 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4099.6857 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4100.0024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4103.0024 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4103.3824 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4109.3824 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4112.3824 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4113.1424 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4119.1424 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4122.1424 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4123.2824 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4129.2824 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4132.2824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4133.8024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4139.8024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4142.8024 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4143.8024 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4145.3024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4151.3024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4152.3024 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4153.3024 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4154.8024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4158.3024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4159.3024 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4160.8024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4164.3024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4165.3024 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4166.8024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4170.3024 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4170.6191 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4172.6191 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4172.9357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4175.9357 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4176.3157 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4182.3157 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4185.3157 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4186.0757 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4192.0757 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4195.0757 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4196.2157 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4202.2157 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4205.2157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4206.7357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4212.7357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4215.7357 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4216.7357 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4218.2357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4224.2357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4225.2357 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4226.2357 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4227.7357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4231.2357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4232.2357 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4233.7357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4237.2357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4238.2357 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4239.7357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4243.2357 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4243.5524 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4246.7957 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4250.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4254.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4258.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4262.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4266.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4268.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4269.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4271.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4275.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4279.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4283.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4287.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4291.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4292.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4294.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4295.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4299.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4303.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4307.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4311.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4315.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4317.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4318.7957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4320.2957 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4323.5389 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4325.5389 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4325.8556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4328.8556 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4329.2356 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4335.2356 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4338.2356 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4338.9956 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4344.9956 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4347.9956 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4349.1356 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4355.1356 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4358.1356 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4359.6556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4365.6556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4368.6556 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4369.6556 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4371.1556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4377.1556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4378.1556 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4379.1556 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4380.6556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4384.1556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4385.1556 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4386.6556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4390.1556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4391.1556 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4392.6556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4396.1556 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4396.4722 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4398.4722 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4398.7889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4401.7889 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4402.1689 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4408.1689 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4411.1689 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4411.9289 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4417.9289 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4420.9289 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4422.0689 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4428.0689 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4431.0689 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4432.5889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4438.5889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4441.5889 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4442.5889 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4444.0889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4450.0889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4451.0889 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4452.0889 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4453.5889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4457.0889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4458.0889 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4459.5889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4463.0889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4464.0889 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4465.5889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4469.0889 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4469.4056 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4471.4056 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4471.7222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4474.7222 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4475.1022 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4481.1022 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4484.1022 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4484.8622 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4490.8622 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4493.8622 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4495.0022 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4501.0022 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4504.0022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4505.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4511.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4514.5222 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4515.5222 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4517.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4523.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4524.0222 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4525.0222 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4526.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 4539.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4543.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4544.0222 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4545.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4549.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4550.0222 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4552.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4553.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4555.5222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4559.0222 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4559.3389 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4562.5821 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4566.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4570.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4574.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4578.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4582.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4584.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4585.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4587.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4591.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4595.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4599.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4603.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4607.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4608.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4610.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4611.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4615.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4619.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4623.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4627.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4631.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4633.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4634.5821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4636.0821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4639.3254 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4641.3254 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4641.6421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4644.6421 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4658.6421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4659.0221 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4665.0221 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4668.0221 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4668.7821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4674.7821 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4677.7821 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4678.9221 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4685.9221 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4691.9221 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4694.9221 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4696.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4702.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4705.4421 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4706.4421 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4707.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4713.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4714.9421 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4715.9421 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 4726.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4728.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 4731.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4734.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4735.9421 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4737.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4740.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4741.9421 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4743.4421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4746.9421 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4747.2587 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4749.2587 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4749.5754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4752.5754 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4752.9554 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4758.9554 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4761.9554 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4762.7154 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 4804.7154 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4810.7154 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4813.7154 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4814.8554 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4820.8554 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4823.8554 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4825.3754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4831.3754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4834.3754 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4835.3754 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4836.8754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4842.8754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4843.8754 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4844.8754 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4846.3754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4849.8754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4850.8754 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4852.3754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4855.8754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4856.8754 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4858.3754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4861.8754 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4862.1921 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 4864.1921 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4864.5087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4867.5087 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4867.8887 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4873.8887 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4876.8887 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4877.6487 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4883.6487 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4886.6487 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4887.7887 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4893.7887 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4896.7887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4898.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4904.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4907.3087 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4908.3087 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4909.8087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4915.8087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4916.8087 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4917.8087 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4919.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4926.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4929.8087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4930.8087 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4932.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4936.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4939.8087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4940.8087 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4942.3087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4945.8087 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4946.1254 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4949.3686 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4953.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4957.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4961.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4965.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4969.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4970.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4972.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4973.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4977.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4981.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4985.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4989.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4993.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4995.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4996.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4998.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5002.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5006.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5010.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5014.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5018.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5019.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5021.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5023.3686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5024.8686 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5028.1119 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5030.1119 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5030.4285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5033.4285 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5033.8085 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5037.8085 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5043.8085 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5046.8085 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5047.5685 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5053.5685 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5056.5685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5057.7085 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5063.7085 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5066.7085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5068.2285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5074.2285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5077.2285 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5078.2285 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5079.7285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5085.7285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5086.7285 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5087.7285 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5089.2285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5092.7285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5093.7285 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5095.2285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5098.7285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5099.7285 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5101.2285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5104.7285 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5105.0452 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5107.0452 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5107.3619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5110.3619 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5110.7419 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5116.7419 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5119.7419 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5120.5019 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5126.5019 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5129.5019 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5130.6419 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5136.6419 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5139.6419 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5141.1619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5147.1619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5150.1619 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5151.1619 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5152.6619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5158.6619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5159.6619 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5160.6619 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5162.1619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5165.6619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5166.6619 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5168.1619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5171.6619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5172.6619 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5174.1619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5177.6619 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5177.9785 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5179.9785 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5180.2952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5183.2952 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5183.6752 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5189.6752 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5192.6752 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5193.4352 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5199.4352 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5202.4352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5203.5752 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5209.5752 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5212.5752 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5214.0952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5220.0952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5223.0952 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5224.0952 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5225.5952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5231.5952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5232.5952 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5233.5952 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5235.0952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5238.5952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5239.5952 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5241.0952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5244.5952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5245.5952 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5247.0952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5250.5952 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5250.9119 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5254.1551 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5258.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5262.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5266.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5270.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5274.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5275.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5277.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5278.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5282.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5286.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5290.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5294.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5298.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5300.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5301.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5303.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5307.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5311.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5315.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5319.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5323.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5324.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5326.1551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5327.6551 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5330.8984 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5332.8984 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5333.215 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5336.215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5336.595 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5342.595 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5345.595 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5350.595 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5351.355 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5357.355 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5360.355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5361.495 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5367.495 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5370.495 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5372.015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5378.015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5381.015 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5382.015 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5383.515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5389.515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5390.515 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5391.515 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5393.015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5396.515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5397.515 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5399.015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5402.515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5403.515 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5405.015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5408.515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5408.8317 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5410.8317 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5411.1484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5414.1484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5414.5284 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5420.5284 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5423.5284 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5424.2884 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5430.2884 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5433.2884 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5434.4284 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5440.4284 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5443.4284 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5444.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5446.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5452.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5455.9484 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5456.9484 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5458.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5464.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5465.4484 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5466.4484 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5471.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5472.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5476.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5477.4484 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5478.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5482.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5483.4484 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5484.9484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5488.4484 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5488.765 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5490.765 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5491.0817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5494.0817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5494.4617 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5500.4617 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5503.4617 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5504.2217 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5510.2217 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5513.2217 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5514.3617 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5520.3617 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5523.3617 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5524.8817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5530.8817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5533.8817 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5534.8817 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5536.3817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5542.3817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5543.3817 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5544.3817 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5545.8817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5549.3817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5550.3817 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5551.8817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5555.3817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5556.3817 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5557.8817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5561.3817 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5561.6984 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5564.9416 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5568.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5572.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5576.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5580.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5584.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5586.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5587.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5589.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5593.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5597.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5601.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5605.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5609.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5610.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5612.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5613.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5617.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5621.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5625.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5629.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5633.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5635.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5636.9416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5638.4416 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5641.6848 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5643.6848 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5644.0015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5647.0015 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5647.3815 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5653.3815 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5656.3815 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5657.1415 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5663.1415 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5666.1415 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5667.2815 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5673.2815 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5676.2815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5677.8015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5683.8015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5686.8015 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5687.8015 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5689.3015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5695.3015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5696.3015 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5697.3015 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5698.8015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5702.3015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5703.3015 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5704.8015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5708.3015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5709.3015 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5710.8015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5714.3015 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5714.6182 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5716.6182 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5716.9348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5719.9348 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5720.3148 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5726.3148 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5729.3148 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5730.0748 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5736.0748 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5739.0748 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5740.2148 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5746.2148 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5749.2148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5750.7348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5756.7348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5759.7348 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5760.7348 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5762.2348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5768.2348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5769.2348 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5770.2348 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5771.7348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5775.2348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5776.2348 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5777.7348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5781.2348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5782.2348 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5783.7348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5787.2348 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5787.5515 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5789.5515 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5789.8682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5792.8682 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5793.2482 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5799.2482 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5802.2482 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5803.0082 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5809.0082 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5812.0082 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5813.1482 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5819.1482 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5822.1482 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5823.6682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5829.6682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5832.6682 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5833.6682 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5835.1682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5841.1682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5842.1682 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5843.1682 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5844.6682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5848.1682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5849.1682 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5850.6682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5854.1682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5855.1682 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5856.6682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5860.1682 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5860.4848 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5863.7281 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5867.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5871.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5875.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5879.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5883.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5885.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5886.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5888.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5892.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5896.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5900.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5904.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5908.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5909.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5911.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5912.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5916.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5920.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5924.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5928.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5932.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5934.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5935.7281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5937.2281 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5940.4713 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 5942.4713 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5942.788 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5945.788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5946.168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5952.168 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5955.168 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5955.928 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5961.928 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5964.928 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5966.068 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5972.068 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5975.068 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5976.588 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5982.588 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5985.588 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5986.588 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5988.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 6001.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6007.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6008.088 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6009.088 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6010.588 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6014.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6015.088 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6016.588 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6020.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6021.088 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6022.588 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6026.088 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6026.4047 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6028.4047 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6028.7213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6031.7213 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6032.1013 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6038.1013 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6041.1013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6041.8613 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6047.8613 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6050.8613 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6052.0013 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6058.0013 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6061.0013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6062.5213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6068.5213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6071.5213 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6072.5213 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6074.0213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6080.0213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6081.0213 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6082.0213 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6083.5213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6087.0213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6088.0213 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6089.5213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6093.0213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6094.0213 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6095.5213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6099.0213 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6099.338 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6101.338 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6101.6547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6104.6547 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6105.0347 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6111.0347 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6114.0347 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6114.7947 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6120.7947 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6123.7947 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6124.9347 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6130.9347 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6133.9347 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6135.4547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6141.4547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6144.4547 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6145.4547 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6146.9547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6152.9547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6153.9547 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6154.9547 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6156.4547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6159.9547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6160.9547 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6162.4547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6165.9547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6166.9547 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6168.4547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6171.9547 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6172.2713 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6175.5146 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6179.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6183.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6187.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6191.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6195.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6197.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6198.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6200.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6204.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6208.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6212.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6216.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6220.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6221.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6223.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6224.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6228.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6232.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6236.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6240.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6244.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6246.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6247.5146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6249.0146 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6252.2578 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6254.2578 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6254.5745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6257.5745 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6257.9545 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6263.9545 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6266.9545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6267.7145 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6273.7145 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6276.7145 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6277.8545 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6283.8545 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6286.8545 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6288.3745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6294.3745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6297.3745 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6298.3745 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6299.8745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6305.8745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6306.8745 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6307.8745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6309.3745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6312.8745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6313.8745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6315.3745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6318.8745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6319.8745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6321.3745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6324.8745 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6325.1912 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6327.1912 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6327.5078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6330.5078 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6330.8878 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6336.8878 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6339.8878 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6340.6478 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6346.6478 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6349.6478 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6350.7878 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6356.7878 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6359.7878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6361.3078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6367.3078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6370.3078 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6371.3078 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6372.8078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6378.8078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6379.8078 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6380.8078 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6382.3078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6385.8078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6386.8078 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6388.3078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6391.8078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6392.8078 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6394.3078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6397.8078 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6398.1245 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6400.1245 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6400.4412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6403.4412 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6403.8212 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6409.8212 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6412.8212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6413.5812 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6419.5812 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6422.5812 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6423.7212 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6429.7212 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6432.7212 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6434.2412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6440.2412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6443.2412 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6444.2412 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6445.7412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6451.7412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6452.7412 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6453.7412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6455.2412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6458.7412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6459.7412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6461.2412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6464.7412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6465.7412 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6467.2412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6470.7412 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6471.0578 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6474.3011 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6478.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6482.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6486.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6490.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6494.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6495.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6497.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6498.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6502.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6506.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6510.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6514.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6518.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6520.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6521.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6523.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6527.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6531.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6535.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6539.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6543.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6544.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6546.3011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6547.8011 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6551.0443 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6553.0443 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6553.361 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6556.361 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6556.741 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6562.741 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6565.741 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6566.501 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6572.501 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6575.501 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6576.641 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6582.641 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6585.641 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6587.161 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6593.161 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6596.161 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6597.161 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6598.661 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6604.661 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6605.661 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6606.661 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6608.161 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6611.661 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6612.661 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6614.161 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6617.661 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6618.661 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6620.161 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6623.661 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6623.9776 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6625.9776 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6626.2943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6629.2943 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6629.6743 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6635.6743 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6638.6743 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6639.4343 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6645.4343 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6648.4343 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6649.5743 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6655.5743 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6658.5743 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6660.0943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6666.0943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6669.0943 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6670.0943 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6671.5943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6677.5943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6678.5943 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6679.5943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6681.0943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6684.5943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6685.5943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6687.0943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6690.5943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6691.5943 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6693.0943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6696.5943 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6696.911 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6698.911 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6699.2276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6702.2276 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6702.6076 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6708.6076 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6711.6076 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6712.3676 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6718.3676 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6721.3676 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6722.5076 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6728.5076 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6731.5076 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6733.0276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6739.0276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6742.0276 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6743.0276 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6744.5276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6750.5276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6751.5276 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6752.5276 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6754.0276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6757.5276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6758.5276 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6760.0276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6763.5276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6764.5276 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6766.0276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6769.5276 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6769.8443 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6773.0876 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6777.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6781.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6785.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6789.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6793.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6794.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6796.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6797.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6801.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6805.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6809.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6813.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6817.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6819.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6820.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6822.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6826.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6830.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6834.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6838.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6842.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6843.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6845.0876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6846.5876 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6849.8308 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6851.8308 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6852.1475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6855.1475 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6855.5275 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6861.5275 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6864.5275 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6865.2875 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6871.2875 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6874.2875 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6875.4275 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6881.4275 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6884.4275 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6885.9475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6891.9475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6894.9475 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6895.9475 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6897.4475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6903.4475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6904.4475 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6905.4475 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6906.9475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6910.4475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6911.4475 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6912.9475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6916.4475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6917.4475 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6918.9475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6922.4475 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6922.7641 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6924.7641 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6925.0808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6928.0808 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6928.4608 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6934.4608 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6937.4608 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6938.2208 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6944.2208 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6947.2208 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6948.3608 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6954.3608 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6957.3608 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6958.8808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6964.8808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6967.8808 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6968.8808 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6970.3808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6976.3808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6977.3808 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6978.3808 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6979.8808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6983.3808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6984.3808 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6985.8808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6989.3808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6990.3808 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6991.8808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6995.3808 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6995.6975 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 6997.6975 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6998.0141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7001.0141 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7001.3941 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7007.3941 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7010.3941 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7011.1541 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7017.1541 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7020.1541 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7021.2941 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7027.2941 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7030.2941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7031.8141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7037.8141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7040.8141 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7041.8141 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7043.3141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7049.3141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7050.3141 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7051.3141 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7052.8141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7056.3141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7057.3141 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7058.8141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7062.3141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7063.3141 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7064.8141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7068.3141 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7068.6308 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7071.874 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7075.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7079.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7083.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7087.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7091.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7093.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7094.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7096.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7100.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7104.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7108.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7112.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7116.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7117.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7119.374 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7120.874 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7124.1173 | TurbineInstallation
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7126.1173 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7126.4339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7129.4339 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7129.8139 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7135.8139 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7138.8139 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7139.5739 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7145.5739 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7148.5739 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7149.7139 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7155.7139 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7158.7139 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7160.2339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7166.2339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7169.2339 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7170.2339 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7171.7339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7177.7339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7178.7339 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7179.7339 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7181.2339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7184.7339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7185.7339 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7187.2339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7190.7339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7191.7339 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7193.2339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7196.7339 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7197.0506 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Position Onsite | 2 | 33333.3333 | ACTION | 7199.0506 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7199.3673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7202.3673 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7202.7473 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7208.7473 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7211.7473 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7212.5073 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7218.5073 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7221.5073 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7222.6473 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7228.6473 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7231.6473 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7233.1673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7239.1673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7242.1673 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7243.1673 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7244.6673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7250.6673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7251.6673 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7252.6673 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7254.1673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7257.6673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7258.6673 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7260.1673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7263.6673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7264.6673 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7266.1673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7269.6673 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7269.9839 | TurbineInstallation | TurbineInstallation |  | 22.5 | 150