## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 23.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 25.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 25.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 26.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 29.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 30.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 30.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 31.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 32.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 34.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 35.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 36.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 40.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 41.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 44.3461 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 56.3461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 64.3461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3 | 31250 | ACTION | 67.3461 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 68.3461 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 68.5894 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 70.5894 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 70.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 71.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 74.906 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 77.906 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 79.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 80.6291 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 80.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 81.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 83.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 85.1324 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 88.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 89.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 90.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 94.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 94.449 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 97.6923 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 109.6923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 117.6923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 120.9355 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 122.9355 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 123.2522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 124.2522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 127.2522 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 127.9752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 127.9785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 128.9785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 130.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 132.4785 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 133.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 134.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 138.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 138.7952 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 142.0384 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 154.0384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 162.0384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 165.2816 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 167.2816 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 179.2816 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 179.5983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 180.5983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 181.5983 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 184.5983 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 185.3214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 185.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 186.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 187.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 189.8246 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 190.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 191.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 195.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 196.1413 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 199.3845 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 211.3845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 219.3845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 222.6278 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 224.6278 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 224.9445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 225.9445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 228.9445 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 229.6675 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 229.6708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 230.6708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 246.6708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 248.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 250.1708 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 251.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 252.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 256.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 256.4874 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 259.7307 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 271.7307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 279.7307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 282.9739 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 284.9739 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 285.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 286.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 289.2906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 290.0137 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 290.0169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 291.0169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 292.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 294.5169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 295.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 296.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 300.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 300.8336 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 304.0768 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 316.0768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 324.0768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 327.3201 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 329.3201 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 329.6367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 330.6367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 333.6367 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 334.3598 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 334.363 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 335.363 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 336.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 338.863 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 339.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 340.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 344.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 345.1797 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 348.4229 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 360.4229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 368.4229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 371.6662 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 373.6662 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 373.9829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 374.9829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 377.9829 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 378.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 378.7092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 379.7092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 381.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 383.2092 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 384.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 385.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 389.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 389.5258 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 392.7691 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 404.7691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 412.7691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 416.0123 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 418.0123 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 418.329 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 419.329 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 422.329 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 423.0521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 423.0553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 424.0553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 425.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 427.5553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 428.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 429.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 433.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 433.872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 437.1152 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 449.1152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 457.1152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 460.3585 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 462.3585 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 462.6751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 463.6751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 466.6751 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 467.3982 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 467.4014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 468.4014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 469.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 471.9014 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 472.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 473.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 477.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 478.2181 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 481.4614 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 493.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 501.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 504.7046 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 506.7046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 507.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 508.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 511.0213 | MonopileInstallation
| WTIV | Delay | 80 | 833333.3333 | ACTION | 591.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 591.7443 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 591.7476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 592.7476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 594.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 596.2476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 597.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 598.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 602.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 602.5642 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 605.8075 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 617.8075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 625.8075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 629.0507 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 631.0507 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 631.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 632.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 635.3674 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 636.0905 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 636.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 637.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 638.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 640.5937 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 641.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 642.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 646.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 646.9104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 650.1536 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 662.1536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 670.1536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 673.3969 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 675.3969 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 675.7135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 676.7135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 679.7135 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 680.4366 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 680.4398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 681.4398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 682.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 684.9398 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 685.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 686.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 690.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 691.2565 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 694.4998 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 706.4998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 714.4998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 717.743 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 719.743 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 720.0597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 721.0597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 724.0597 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 724.7827 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 724.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 725.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 727.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 729.286 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 730.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 731.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 735.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 735.6027 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 738.8459 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 750.8459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 758.8459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 762.0891 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 764.0891 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 764.4058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 765.4058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 768.4058 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 769.1289 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 769.1321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 770.1321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 771.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 773.6321 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 774.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 775.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 779.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 779.9488 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 783.192 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 795.192 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 803.192 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 806.4353 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 808.4353 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 808.7519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 809.7519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 812.7519 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 813.475 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 813.4783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 814.4783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 815.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 817.9783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 818.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 819.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 823.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 824.2949 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 827.5382 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 839.5382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 847.5382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 850.7814 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 852.7814 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 853.0981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 854.0981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 857.0981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 857.8211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 857.8244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 858.8244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 860.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 862.3244 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 863.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 864.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 868.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 868.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 871.8843 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 883.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 913.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 921.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 925.1275 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 927.1275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 927.4442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 928.4442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 931.4442 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 932.1673 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 932.1705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 933.1705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 934.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 936.6705 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 937.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 938.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 942.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 942.9872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 946.2304 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 958.2304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 966.2304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 969.4737 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 971.4737 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 971.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 972.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 975.7903 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 976.5134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 976.5167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 977.5167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 979.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 981.0167 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 982.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 983.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 987.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 987.3333 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 990.5766 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1002.5766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1010.5766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1013.8198 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1015.8198 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1016.1365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1017.1365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1018.1365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 1043.1365 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1046.1365 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1046.8595 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1046.8628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1047.8628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1049.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1051.3628 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1052.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1053.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1057.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1057.6795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1060.9227 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1072.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1080.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1081.9227 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1085.166 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1088.166 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1090.166 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1090.4826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1091.4826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1094.4826 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1095.4826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1096.2057 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1096.2089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1097.2089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1098.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1100.7089 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1101.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1102.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1106.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1107.0256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1110.2688 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1122.2688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1130.2688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1133.5121 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1135.5121 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1135.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1136.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1139.8288 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1140.5518 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1140.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1141.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1143.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1145.0551 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1146.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1147.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1151.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1151.3717 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1154.615 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1166.615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 66 | 687500 | ACTION | 1232.615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1240.615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1243.8582 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1245.8582 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1246.1749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1247.1749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1250.1749 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1250.898 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1250.9012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1251.9012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1253.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1255.4012 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1256.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1257.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1261.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1261.7179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1264.9611 | MonopileInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 1283.9611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1295.9611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1303.9611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1307.2044 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1309.2044 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1309.521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1310.521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1313.521 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1314.2441 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1314.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1315.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1316.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1318.7473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1319.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1320.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1324.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1325.064 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1328.3072 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1340.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1348.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1351.5505 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1353.5505 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1353.8672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1354.8672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1357.8672 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 1359.8672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1360.5902 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1360.5935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1361.5935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1363.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1365.0935 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1366.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1367.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1371.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1371.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1374.6534 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1386.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1394.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1397.8966 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1399.8966 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1400.2133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1401.2133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1404.2133 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1404.9364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1404.9396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1405.9396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1407.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1409.4396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1410.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 69 | 718750 | ACTION | 1479.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1480.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1484.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1484.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1487.9995 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1499.9995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1507.9995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1511.2428 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1513.2428 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1513.5594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1514.5594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1517.5594 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1518.2825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1518.2857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1519.2857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1520.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1522.7857 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1523.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1524.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1528.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1529.1024 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1532.3457 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1544.3457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1552.3457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1555.5889 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1557.5889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1557.9056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1558.9056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1561.9056 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1562.6286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1562.6319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1563.6319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1565.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1567.1319 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1568.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1569.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1573.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1573.4485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1576.6918 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1588.6918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 28 | 291666.6667 | ACTION | 1616.6918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1624.6918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1627.935 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1629.935 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1630.2517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1631.2517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1634.2517 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 1664.2517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1664.9748 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1664.978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1665.978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1667.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1669.478 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1670.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1671.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1675.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1675.7947 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1679.0379 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1691.0379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1699.0379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1702.2812 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1704.2812 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1704.5978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1705.5978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1708.5978 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1709.3209 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1709.3242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1710.3242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1711.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1713.8242 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1714.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1715.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1719.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1720.1408 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1723.3841 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1735.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1743.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1746.6273 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1748.6273 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1748.944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1749.944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1752.944 | MonopileInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 1786.944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1787.667 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1787.6703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1788.6703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1790.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1792.1703 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1793.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1794.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1798.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1798.487 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1801.7302 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1813.7302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1821.7302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1824.9734 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1826.9734 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1827.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1828.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1831.2901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1832.0132 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1832.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1833.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1834.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1836.5164 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1837.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1838.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1842.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1842.8331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1846.0763 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1858.0763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1866.0763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1869.3196 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1871.3196 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1871.6362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1872.6362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1875.6362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1876.3593 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1876.3626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1877.3626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1878.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1880.8626 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1881.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1882.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1886.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1887.1792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1890.4225 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1902.4225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1910.4225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1913.6657 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1915.6657 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1915.9824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1916.9824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1919.9824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1920.7054 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1920.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1921.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1923.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1925.2087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1926.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1927.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1931.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1931.5254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1934.7686 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1946.7686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1954.7686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1958.0118 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1960.0118 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1960.3285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1961.3285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1964.3285 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1965.0516 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1965.0548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1966.0548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1967.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1969.5548 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1970.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1971.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1975.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1975.8715 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 1979.1147 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1991.1147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1999.1147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2002.358 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2004.358 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2004.6746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2005.6746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2008.6746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2009.3977 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2009.401 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2010.401 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2011.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2013.901 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2014.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2015.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2019.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2020.2176 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2023.4609 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2035.4609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2043.4609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2046.7041 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2048.7041 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2049.0208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2050.0208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2053.0208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2053.7438 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2053.7471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2054.7471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2056.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2058.2471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2059.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2060.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2064.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2064.5638 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2067.807 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2079.807 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2087.807 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2091.0503 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2093.0503 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2093.3669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2094.3669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2097.3669 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2098.09 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2098.0932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2099.0932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2100.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2102.5932 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2103.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2104.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2108.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2108.9099 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2112.1531 | MonopileInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 2133.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2145.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2153.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2156.3964 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2158.3964 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2158.7131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2159.7131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2162.7131 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2163.4361 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2163.4394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2164.4394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2165.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2167.9394 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2168.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2169.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2173.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2174.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2177.4993 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2189.4993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2197.4993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2200.7425 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2202.7425 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2203.0592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2204.0592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2207.0592 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2207.7823 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2207.7855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2208.7855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2210.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2212.2855 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2213.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2214.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2218.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2218.6022 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2221.8454 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2233.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2241.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2245.0887 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2247.0887 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2247.4053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2248.4053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2251.4053 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2252.1284 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2252.1316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2253.1316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2254.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2256.6316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2257.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2258.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2262.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2262.9483 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2266.1915 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2278.1915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2286.1915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2289.4348 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2291.4348 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2291.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2292.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 2335.7515 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2338.7515 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2339.4745 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2339.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2340.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2341.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2343.9778 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2344.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2345.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2349.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2350.2944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2353.5377 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2365.5377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2373.5377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2376.7809 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2378.7809 | MonopileInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 2382.7809 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2383.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2385.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2386.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2396.0976 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2399.0976 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 2408.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2408.8207 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2408.8239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2409.8239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2411.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2413.3239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2414.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2415.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2419.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2419.6406 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2422.8838 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2434.8838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2442.8838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2446.1271 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2448.1271 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2448.4437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2449.4437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2452.4437 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2453.1668 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2453.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2454.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2455.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2457.67 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2458.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2459.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2463.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2463.9867 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2467.23 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2479.23 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2487.23 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2490.4732 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2492.4732 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2492.7899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2493.7899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2496.7899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2497.5129 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2497.5162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2498.5162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2500.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2502.0162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2503.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2504.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2508.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2508.3328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2511.5761 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2523.5761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2531.5761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2534.8193 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2536.8193 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2537.136 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2538.136 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2541.136 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2541.8591 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2541.8623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2542.8623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2544.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2546.3623 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2547.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2548.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2552.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2552.679 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2555.9222 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2567.9222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2575.9222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2579.1655 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2581.1655 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2581.4821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2582.4821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2585.4821 | MonopileInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 2602.4821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2603.2052 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2603.2085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2604.2085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2605.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2607.7085 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2608.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2609.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2613.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2614.0251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2617.2684 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2629.2684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2637.2684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2640.5116 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2642.5116 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2642.8283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2643.8283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2646.8283 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2647.5513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2647.5546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2648.5546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2650.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2652.0546 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2653.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2654.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2658.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2658.3713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2661.6145 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2673.6145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2681.6145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2684.8577 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 2699.8577 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2701.8577 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2702.1744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2703.1744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2706.1744 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2706.8975 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2706.9007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2707.9007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2709.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2711.4007 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2712.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 2713.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2714.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2718.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2718.7174 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2721.9606 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2733.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2741.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2745.2039 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2747.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2747.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2748.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2751.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2752.2436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2752.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2753.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2754.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2756.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2757.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2758.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2762.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2763.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 2763.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2767.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2771.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 2775.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2776.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2778.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2779.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2783.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2787.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 2791.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2793.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2794.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2796.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2799.3068 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2801.3068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2801.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2804.6234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 2805.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 2811.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2814.3734 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 2815.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 2821.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 2824.8734 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2825.8734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2827.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 2833.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2834.3734 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2835.3734 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 2839.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2840.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2844.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2845.3734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2846.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2850.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2851.3734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2852.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2856.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2856.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2858.6901 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2859.0068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2862.0068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 2862.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 2868.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2871.7568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 2873.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 31 | 322916.6667 | ACTION | 2904.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 2910.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 2913.2568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2914.2568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2915.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 2921.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2922.7568 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2923.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2925.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2928.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2929.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2931.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2934.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 2935.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2937.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 2940.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 2943.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2944.0734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2947.3167 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2951.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2955.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 2959.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2960.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2962.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2963.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2967.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 2971.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 2975.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2977.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2978.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 2980.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2983.5599 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2985.5599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2985.8766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2988.8766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 2989.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 2995.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 2998.6266 | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 3022.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3024.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3030.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3033.1266 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3034.1266 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3035.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3041.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3042.6266 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3043.6266 | TurbineInstallation
| WTIV | Delay | 37 | 385416.6667 | ACTION | 3080.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3082.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3085.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3086.6266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3088.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3091.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3092.6266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3094.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3097.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3097.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3099.9433 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3100.2599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3103.2599 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3104.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3110.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3113.0099 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3114.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3120.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3123.5099 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3124.5099 | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 3136.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3138.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3144.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3145.0099 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3146.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3147.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3151.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3152.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3153.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3157.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3158.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3159.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3163.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3163.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3166.5698 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3170.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3174.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3178.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3180.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3181.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3183.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3187.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3191.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3195.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3196.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3198.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3199.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3202.8131 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3204.8131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3205.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3208.1297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3208.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3214.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3217.8797 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3219.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 3223.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3229.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3232.3797 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3233.3797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3234.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3240.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3241.8797 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3242.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3244.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3247.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3248.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3250.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3253.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3254.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3256.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3259.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3260.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3262.1964 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3262.5131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3265.5131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3266.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3272.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3275.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3276.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3282.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3285.7631 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3286.7631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3288.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3294.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3295.2631 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3296.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3297.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3301.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3302.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3303.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3307.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3308.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3309.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3313.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3313.5797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3316.823 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3320.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3324.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3328.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3330.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3331.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3333.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3337.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3341.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3345.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3346.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3348.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3349.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3353.0662 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3355.0662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3355.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3358.3829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3359.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3365.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3368.1329 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3369.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3375.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3378.6329 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3379.6329 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3381.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3387.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3388.1329 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3389.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3390.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3394.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3395.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3396.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3400.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3401.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3402.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 65 | 677083.3333 | ACTION | 3467.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3471.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3471.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 3495.4496 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3497.4496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3497.7662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3500.7662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3501.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3507.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3510.5162 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3512.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3518.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3521.0162 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3522.0162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3523.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3529.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3530.5162 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3531.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3533.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3536.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3537.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3539.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3542.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3543.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3545.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3548.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3548.8329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3552.0761 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3556.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3560.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3564.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3565.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3567.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3568.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3572.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3576.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3580.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3582.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3583.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3585.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3588.3194 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3590.3194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3590.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3593.636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3594.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3600.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3603.386 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3604.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3610.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3613.886 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3614.886 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3616.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3622.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3623.386 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3624.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3625.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3629.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3630.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3631.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3635.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3636.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3637.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3641.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3641.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3643.7027 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3644.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3647.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3647.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 3658.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3664.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3667.7694 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3669.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 3699.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3705.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3708.2694 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3709.2694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3710.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3716.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3717.7694 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3718.7694 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3726.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3728.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 22 | 229166.6667 | ACTION | 3750.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3753.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3754.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3756.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3759.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3760.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3762.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3765.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3766.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3769.3293 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3773.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3777.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3781.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3782.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3784.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3785.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3789.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3793.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3797.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3799.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3800.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3802.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3803.3293 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3804.3293 | TurbineInstallation
| WTIV | Transit | 2.2432 | 23367.1171 | ACTION | 3806.5725 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3808.5725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3808.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3811.8892 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3819.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3820.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 41 | 427083.3333 | ACTION | 3861.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3867.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3870.6392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3872.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3878.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3881.1392 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3882.1392 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3883.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3889.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3890.6392 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3891.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3893.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3896.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3897.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3899.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3902.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3903.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3905.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3908.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3908.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3910.9559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3911.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3914.2725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 3915.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3921.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 3924.0225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 3925.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 3931.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 3934.5225 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3935.5225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3937.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 3943.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3944.0225 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3945.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3946.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3950.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3951.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3952.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3956.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 3957.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3958.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 3962.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3962.3392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3965.5824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3969.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3973.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3977.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3979.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3980.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3982.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3986.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 3990.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 3994.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3995.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3997.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 3998.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4001.8257 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4003.8257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4004.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4007.1424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4007.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4013.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4016.8924 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4018.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4024.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4027.3924 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4028.3924 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4032.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4033.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4039.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4040.8924 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4041.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4043.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4046.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4047.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4049.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4052.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4053.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4055.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4058.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4059.209 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4061.209 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4061.5257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4064.5257 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 4070.5257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4071.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4077.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4080.2757 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4081.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4086.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4092.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4095.7757 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4096.7757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4098.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4104.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4105.2757 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4106.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4107.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4111.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4112.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4113.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4117.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4118.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4119.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4123.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4123.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4126.8356 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4130.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4134.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4138.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4140.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4141.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4143.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4147.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4151.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4155.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4156.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4158.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4159.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4163.0788 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4165.0788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4165.3955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4168.3955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4169.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4175.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4178.1455 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4179.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4185.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4188.6455 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4189.6455 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4191.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4197.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4198.1455 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4199.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4200.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4204.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4205.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4206.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4210.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4211.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4212.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4216.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4216.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4218.4622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4218.7788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4221.7788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4222.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4228.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4231.5288 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4233.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4239.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4242.0288 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4243.0288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4244.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4250.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4251.5288 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4252.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4254.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4257.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4258.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4260.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4263.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4264.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4266.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4269.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4269.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4273.0887 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4277.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4281.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4285.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4286.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4288.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4289.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4293.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4297.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4301.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4303.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4304.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4306.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4309.332 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4311.332 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4311.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4314.6487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4315.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4321.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4324.3987 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4325.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4331.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4334.8987 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4335.8987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4337.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4343.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4344.3987 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4345.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4346.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4350.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4351.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4352.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4356.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4357.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4358.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4362.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4362.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4364.7153 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4365.032 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4368.032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4368.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4374.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4377.782 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4379.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4385.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4388.282 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4389.282 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4390.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4396.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4397.782 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4398.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4400.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4403.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4404.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4406.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4409.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4410.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4412.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4415.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4416.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4419.3419 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4423.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4427.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4431.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4432.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4434.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4435.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4439.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4443.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4447.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4449.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4450.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4452.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4455.5851 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4457.5851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4457.9018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4460.9018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4461.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4467.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4470.6518 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4472.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4478.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4481.1518 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4482.1518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4483.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4489.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4490.6518 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4491.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4493.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4496.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4497.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4499.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4502.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4503.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4505.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4508.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4508.9685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4510.9685 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4511.2851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4514.2851 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4515.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4521.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4524.0351 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4525.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 4539.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4545.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4548.5351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4549.5351 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4551.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4553.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 4556.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4562.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4563.0351 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4564.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4565.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4569.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4570.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4571.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4575.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4576.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4577.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4581.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4581.3518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4584.5951 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4588.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4592.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4596.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4598.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4599.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4601.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4605.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4609.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4613.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4614.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4616.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4617.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4620.8383 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4622.8383 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4623.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4626.155 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4626.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4658.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4664.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4667.905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4669.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4675.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4678.405 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4679.405 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4680.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4685.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4691.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4692.905 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4693.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4695.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4698.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4699.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4701.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4704.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4705.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4707.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4710.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4711.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4713.2216 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4713.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4716.5383 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 4726.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4727.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4731.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4737.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4740.2883 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4741.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4747.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4750.7883 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4751.7883 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4753.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4759.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4760.2883 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4761.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4762.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 4804.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4808.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4809.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4810.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4814.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4815.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4816.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4820.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4820.605 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4823.8482 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4827.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4831.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4835.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4837.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4838.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4840.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4844.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4848.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4852.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4853.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4855.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4856.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4860.0915 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4862.0915 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4862.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4865.4081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4866.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4872.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4875.1581 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4876.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4882.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4885.6581 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4886.6581 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4888.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4894.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4895.1581 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4896.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4897.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4901.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4902.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4903.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4907.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4908.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4909.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4913.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4913.4748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4915.4748 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4915.7915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4918.7915 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 4919.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4926.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4932.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 4935.5415 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4936.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 4938.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 4944.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 4947.0415 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4948.0415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4949.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 4955.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4956.5415 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4957.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4959.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4962.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4963.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4965.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4968.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 4969.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4971.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 4974.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4974.8581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 4978.1014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4982.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4986.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 4990.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4991.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4993.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 4994.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 4998.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5002.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5006.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5008.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5009.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5011.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5014.3446 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5016.3446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5016.6613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5019.6613 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 5023.6613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5024.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5030.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5033.4113 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5034.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 5037.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5043.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5046.9113 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5047.9113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5049.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5055.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5056.4113 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5057.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5058.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5062.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5063.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5064.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5068.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5069.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5070.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5074.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5074.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5076.7279 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5077.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5080.0446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5080.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5086.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5089.7946 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5091.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5097.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5100.2946 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5101.2946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5102.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5108.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5109.7946 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5110.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5112.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5115.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5116.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5118.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5121.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5122.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5124.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5127.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5128.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5131.3545 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5135.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5139.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5143.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5144.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5146.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5147.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5151.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5155.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5159.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5161.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5162.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5164.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5167.5978 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5169.5978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5169.9144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5172.9144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5173.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5179.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5182.6644 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5184.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5190.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5193.1644 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5194.1644 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5195.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5201.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5202.6644 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5203.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5205.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5208.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5209.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5211.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5214.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5215.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5217.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5220.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5220.9811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5222.9811 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5223.2978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5226.2978 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5227.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5233.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5236.0478 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5237.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5243.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5246.5478 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5247.5478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5249.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5255.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5256.0478 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5257.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5258.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5262.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5263.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5264.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5268.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5269.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5270.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5274.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5274.3644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5277.6077 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5281.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5285.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5289.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5291.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5292.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5294.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5298.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5302.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5306.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5307.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5309.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5310.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5313.8509 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5315.8509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5316.1676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5319.1676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5319.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5325.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5328.9176 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5330.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5336.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5339.4176 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5340.4176 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5341.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 5350.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5356.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5357.9176 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5358.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5360.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5363.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5364.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5366.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5369.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5370.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5372.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5375.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5376.2342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5378.2342 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5378.5509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5381.5509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5382.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5388.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5391.3009 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5392.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5398.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5401.8009 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5402.8009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5404.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5410.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5411.3009 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5412.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5413.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5417.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5418.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5419.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5423.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5424.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5425.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5429.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5429.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5432.8608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5436.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5440.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5444.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5446.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5447.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5449.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5453.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5457.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5461.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5462.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5464.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5465.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 5467.8608 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 5469.8608 | TurbineInstallation
| WTIV | Transit | 1.2432 | 12950.4505 | ACTION | 5471.1041 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5473.1041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5473.4207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5476.4207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5477.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5483.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5486.1707 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5487.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5493.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5496.6707 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5497.6707 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5499.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5505.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5506.1707 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5507.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5508.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5512.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5513.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5514.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5518.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5519.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5520.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5524.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5524.4874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5526.4874 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5526.8041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5529.8041 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5530.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5536.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5539.5541 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5541.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5547.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5550.0541 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5551.0541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5552.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5558.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5559.5541 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5560.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5562.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5565.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5566.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5568.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5571.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5572.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5574.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5577.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5577.8707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5581.114 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5585.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5589.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5593.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5594.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5596.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5597.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5601.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5605.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5609.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5611.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5612.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5614.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5617.3572 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5619.3572 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5619.6739 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5622.6739 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5623.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5629.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5632.4239 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5633.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5639.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5642.9239 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5643.9239 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5645.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5651.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5652.4239 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5653.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5654.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5658.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5659.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5660.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5664.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5665.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5666.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5670.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5670.7406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5672.7406 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5673.0572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5676.0572 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5676.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5682.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5685.8072 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5687.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5693.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5696.3072 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5697.3072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5698.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5704.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5705.8072 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5706.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5708.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5711.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5712.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5714.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5717.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5718.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5720.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5723.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5724.1239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5727.3671 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5731.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5735.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5739.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5740.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5742.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5743.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5747.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5751.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5755.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5757.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5758.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5760.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5763.6104 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5765.6104 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5765.927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5768.927 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5769.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5775.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5778.677 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5780.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5786.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5789.177 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5790.177 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5791.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5797.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5798.677 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5799.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5801.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5804.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5805.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5807.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5810.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5811.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5813.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5816.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5816.9937 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5818.9937 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5819.3104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5822.3104 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5823.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5829.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5832.0604 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5833.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5839.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5842.5604 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5843.5604 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5845.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5851.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5852.0604 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5853.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5854.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5858.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5859.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5860.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5864.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5865.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5866.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5870.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5870.377 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5873.6203 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5877.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5881.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5885.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5887.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5888.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5890.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5894.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 5898.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 5902.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5903.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5905.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 5906.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5909.8635 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5911.8635 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5912.1802 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5915.1802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5915.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5921.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5924.9302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5926.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5932.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5935.4302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5936.4302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5937.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 5943.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5944.9302 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5945.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5947.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5950.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5951.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5953.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5956.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 5957.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5959.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 5962.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5963.2469 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5965.2469 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5965.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5968.5635 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 5969.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5975.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 5978.3135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 5979.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 5985.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 5988.8135 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5989.8135 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 6000.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6002.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6008.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6009.3135 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6010.3135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6011.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6015.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6016.3135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6017.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6021.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6022.3135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6023.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6027.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6027.6302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6030.8734 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6034.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6038.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6042.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6044.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6045.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6047.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6051.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6055.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6059.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6060.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6062.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6063.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6067.1167 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6069.1167 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6069.4333 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6072.4333 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6073.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6079.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6082.1833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6083.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6089.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6092.6833 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6093.6833 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6095.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6101.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6102.1833 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6103.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6104.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6108.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6109.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6110.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6114.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6115.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6116.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6120.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6120.5 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6122.5 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6122.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6125.8167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6126.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6132.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6135.5667 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6137.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 6144.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6150.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6153.0667 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6154.0667 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6155.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6161.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6162.5667 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6163.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6165.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6168.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6169.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6171.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6174.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6175.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6177.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6180.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6180.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6184.1266 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6188.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6192.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6196.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6197.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6199.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6200.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6204.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6208.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6212.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6214.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6215.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6217.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6220.3698 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6222.3698 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6222.6865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6225.6865 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6226.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6232.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6235.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6236.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6242.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6245.9365 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6246.9365 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6248.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6254.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6255.4365 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6256.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6257.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6261.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6262.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6263.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6267.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6268.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6269.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6273.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6273.7532 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6275.7532 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6276.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6279.0698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6279.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6285.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6288.8198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6290.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6296.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6299.3198 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6300.3198 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6301.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6307.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6308.8198 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6309.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6311.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6314.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6315.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6317.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6320.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6321.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6323.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6326.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6327.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6330.3797 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6334.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6338.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6342.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6343.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6345.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6346.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6350.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6354.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6358.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6360.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6361.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6363.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6366.623 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6368.623 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6368.9397 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6371.9397 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6372.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6378.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6381.6897 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6383.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6389.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6392.1897 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6393.1897 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6394.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6400.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6401.6897 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6402.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6404.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6407.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6408.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6410.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6413.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6414.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6416.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6419.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6420.0063 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6422.0063 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6422.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6425.323 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6426.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6432.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6435.073 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6436.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6442.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6445.573 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6446.573 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6448.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6454.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6455.073 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6456.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6457.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6461.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6462.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6463.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6467.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6468.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6469.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6473.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6473.3897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6476.6329 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6480.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6484.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6488.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6490.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6491.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6493.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6497.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6501.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6505.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6506.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6508.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6509.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6512.8761 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6514.8761 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6515.1928 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6518.1928 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6518.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6524.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6527.9428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6529.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6535.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6538.4428 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6539.4428 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6540.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6546.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6547.9428 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6548.9428 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6550.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6552.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6555.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6556.9428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6558.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6561.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6562.9428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6564.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6567.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6568.2595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6570.2595 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6570.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6573.5761 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6574.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6580.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6583.3261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6584.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6590.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6593.8261 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6594.8261 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6596.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6602.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6603.3261 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6604.3261 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6605.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6606.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6610.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6611.3261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6612.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6616.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6617.3261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6618.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6622.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6622.6428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6625.886 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6629.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6633.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6637.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6639.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6640.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6642.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6646.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6650.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6654.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6655.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6657.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6658.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6662.1293 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6664.1293 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6664.446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6667.446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6668.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6674.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6677.196 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6678.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6684.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6687.696 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6688.696 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6690.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6696.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6697.196 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6698.196 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6699.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6703.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6704.196 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6705.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6709.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6710.196 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6711.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6715.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6715.5126 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6717.5126 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6717.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6720.8293 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6721.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6727.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6730.5793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6732.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6738.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6741.0793 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6742.0793 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6743.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6749.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6750.5793 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6751.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6753.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6756.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6757.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6759.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6762.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6763.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6765.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6768.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6768.896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6772.1392 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6776.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6780.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6784.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6785.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6787.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6788.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6792.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6796.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6800.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6802.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6803.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6805.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6808.3824 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6810.3824 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6810.6991 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6813.6991 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6814.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6820.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6823.4491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6824.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6830.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6833.9491 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6834.9491 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6836.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6842.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6843.4491 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6844.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6845.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6849.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6850.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6851.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6855.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6856.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6857.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6861.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6861.7658 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6863.7658 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6864.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6867.0824 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6867.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6873.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6876.8324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6878.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6884.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6887.3324 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6888.3324 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6889.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6895.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6896.8324 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6897.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6899.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6902.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6903.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6905.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6908.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6909.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6911.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6914.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6915.1491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation