## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 83.2432 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 85.2432 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 86.9099 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 83.6667 | 871527.7778 | ACTION | 86.9099 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 91.9099 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 92.2266 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 93.2266 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 96.2266 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 96.9496 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 96.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 97.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 101.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 103.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 105.4529 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 106.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 107.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 111.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 111.7696 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 116.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 117.0862 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 118.0862 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 121.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 121.8093 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 121.8125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 122.8125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 124.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 126.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 127.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 128.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 147.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 151.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 151.6292 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 156.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 156.9459 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 157.9459 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 160.9459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 161.6689 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 161.6722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 162.6722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 163.2432 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 164.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 165.2432 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 166.1722 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 166.9099 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 167.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 168.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 172.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 172.4889 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 177.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 177.8055 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 178.8055 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 181.8055 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 183.8055 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 184.5286 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 187.5286 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 187.5318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 188.5318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 190.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 192.0318 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 105.1219 | 525609.644 | ACTION | 192.0318 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 193.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 196.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 197.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Delay | 18 | 90000 | ACTION | 210.0318 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 211.6985 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 214.9417 | MonopileInstallation
| Feeder 1 | Queue | 48.0318 | 240159.1936 | ACTION | 214.9417 | MonopileInstallation |  |  | Site
| WTIV | Delay | 23 | 239583.3333 | ACTION | 220.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 224.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 224.3485 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 226.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 229.3485 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 229.6652 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 230.6652 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 233.6652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 234.3882 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 234.3915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 234.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 235.3915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 236.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 238.8915 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 239.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 240.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 244.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 245.2082 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 246.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 250.2082 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 250.5248 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 251.5248 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 254.5248 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 254.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 255.2479 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 255.2511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 256.2511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 257.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 259.7511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 260.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 261.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 265.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 266.0678 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 266.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 271.0678 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 271.3845 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 272.3845 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 274.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 275.3845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 276.1075 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 276.1108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 277.1108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 278.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 280.6108 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 281.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 282.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 286.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 286.9275 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 286.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 291.9275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 292.2441 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 293.2441 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 294.9417 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 296.2441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 296.9672 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 296.9704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 297.9704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 298.185 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 299.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 300.185 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 301.4704 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 86.5287 | 432643.4278 | ACTION | 301.4704 | MonopileInstallation |  |  | Site
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 301.8517 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 302.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 303.1371 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 303.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 306.3803 | MonopileInstallation
| Feeder 0 | Queue | 4.5287 | 22643.4278 | ACTION | 306.3803 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 307.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 307.7871 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 312.7871 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 313.1038 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 314.1038 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 317.1038 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 317.8268 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 317.8301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 318.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 318.8301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 320.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 322.3301 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 323.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 324.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 326.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 328.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 328.6467 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 333.6467 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 333.9634 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 334.9634 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 337.9634 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 338.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 338.6865 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 342.6865 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 342.6897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 343.6897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 345.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 346.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 347.1897 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 348.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 349.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 352.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 356.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 356.5064 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 358.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 361.5064 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 361.8231 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 362.8231 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 365.8231 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 366.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 366.5461 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 366.5494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 367.5494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 369.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 371.0494 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 372.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 373.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 377.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 377.366 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 378.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 382.366 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 382.6827 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 383.6827 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 386.3803 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 386.6827 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 387.4058 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 387.409 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 388.409 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 389.6236 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 389.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 391.6236 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 391.909 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 85.5287 | 427643.4278 | ACTION | 391.909 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 392.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 393.2903 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 393.5757 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 393.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 396.8189 | MonopileInstallation
| Feeder 1 | Queue | 3.5287 | 17643.4278 | ACTION | 396.8189 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 397.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 398.2257 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 403.2257 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 403.5424 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 404.5424 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 407.5424 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 408.2654 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 408.2687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 408.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 409.2687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 410.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 412.7687 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 413.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 414.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 416.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 418.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 419.0853 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 424.0853 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 424.402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 425.402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 428.402 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 428.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 429.1251 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 429.1283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 430.1283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 436.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 9 | 93750 | ACTION | 439.1283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 440.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 442.6283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 443.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 444.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 448.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 448.945 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 453.945 | MonopileInstallation
| Feeder 0 | Delay | 22 | 110000 | ACTION | 458.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 458.945 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 459.2617 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 460.2617 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 463.2617 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 463.9847 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 463.988 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 464.988 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 466.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 468.488 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 469.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 470.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 470.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 474.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 474.8046 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 478.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 479.8046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 480.1213 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 481.1213 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 484.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 484.8444 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 484.8476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 485.8476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 487.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 489.3476 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 92.5287 | 462643.4278 | ACTION | 489.3476 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 490.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 490.8189 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 491.0143 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 491.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 494.2575 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 495.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 495.6643 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 498.8189 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Queue | 4.5614 | 22807.0226 | ACTION | 498.8189 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 502.0622 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 504.0622 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 505.7288 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 10.0646 | 104839.1425 | ACTION | 505.7288 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 510.7288 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 510.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 511.0455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 512.0455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 515.0455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 515.7686 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 515.7718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 516.7718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 518.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 518.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 520.2718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 521.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 522.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 526.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 526.5885 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 530.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 531.5885 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 531.9052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 532.9052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 535.9052 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 536.6282 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 536.6315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 537.6315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 538.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 539.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 541.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 542.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 543.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 547.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 547.4481 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 550.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 552.4481 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 552.7648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 553.7648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 556.7648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 557.4879 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 557.4911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 558.4911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 558.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 559.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 561.9911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 562.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 563.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 567.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 568.3078 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 570.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 573.3078 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 573.6245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 574.6245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 577.6245 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 578.3475 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 578.3508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 578.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 579.3508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 580.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 582.0622 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 582.8508 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 77.1219 | 385609.644 | ACTION | 582.8508 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 583.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 584.0622 | MonopileInstallation
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 584.5174 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 584.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 585.7288 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 587.7607 | MonopileInstallation
| Feeder 1 | Queue | 2.0318 | 10159.1936 | ACTION | 587.7607 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 588.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 589.1674 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 594.1674 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 594.4841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 595.4841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 598.4841 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 599.2072 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 599.2104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 599.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 600.2104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 601.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 603.7104 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 604.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 605.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 607.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 609.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 610.0271 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 615.0271 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 615.3438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 616.3438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 619.3438 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 619.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 620.0668 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 620.0701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 621.0701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 622.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 624.5701 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 625.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 626.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 627.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 630.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 630.8867 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 635.8867 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 636.2034 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 637.2034 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 639.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 640.2034 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 640.9265 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 640.9297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 641.9297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 643.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 645.4297 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 646.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 647.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 647.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 651.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 651.7464 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 656.7464 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 657.0631 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 658.0631 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 659.7607 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 661.0631 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 661.7861 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 661.7894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 662.7894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 664.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 666.2894 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 78.5287 | 392643.4278 | ACTION | 666.2894 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 667.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 667.7607 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 667.956 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 668.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 671.0039 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 671.1993 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 672.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 672.606 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 673.0039 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 674.6706 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 2.0646 | 21505.8092 | ACTION | 674.6706 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 679.6706 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 679.9873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 680.9873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 683.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 683.9873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 684.7103 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 684.7136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 685.7136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 687.2136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 689.2136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 690.2136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 691.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 691.2136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 695.2136 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 695.5302 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 700.5302 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 700.8469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 701.8469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 703.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 704.8469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 705.57 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 705.5732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 706.5732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 708.0732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 710.0732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 711.0732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 711.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 712.0732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 716.0732 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 716.3899 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 721.3899 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 721.7066 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 722.7066 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 723.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 725.7066 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 726.4296 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 726.4329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 727.4329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 728.9329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 730.9329 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 731.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 731.9329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 732.9329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 736.9329 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 737.2495 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 742.2495 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 742.5662 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 743.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 743.5662 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 746.5662 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 747.2893 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 747.2925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 748.2925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 749.7925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 751.1993 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 751.7925 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 77.1219 | 385609.644 | ACTION | 751.7925 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 752.7925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 753.4592 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 753.7925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 754.4425 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 756.4425 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 756.7024 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 757.7925 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 758.1092 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 758.1092 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 763.1092 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 763.4259 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 764.4259 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 767.4259 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 768.1489 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 768.1522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 768.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 769.1522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 770.6522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 772.6522 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 773.6522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 774.6522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 776.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 778.6522 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 778.9688 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 783.9688 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 784.2855 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 785.2855 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 788.2855 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 788.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 789.0086 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 789.0118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 790.0118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 791.5118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 793.5118 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 794.5118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 795.5118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 796.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 799.5118 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 799.8285 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 804.8285 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 805.1452 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 806.1452 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 808.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 809.1452 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 809.8682 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 809.8715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 810.8715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 812.3715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 814.3715 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 815.3715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 816.3715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 816.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 820.3715 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 820.6881 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 825.6881 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 826.0048 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 827.0048 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 828.7024 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 830.0048 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 830.7279 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 830.7311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 831.7311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 833.2311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 835.2311 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 77.1219 | 385609.644 | ACTION | 835.2311 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 836.2311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 836.7024 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 836.8978 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 837.2311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 839.9457 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 840.141 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 841.2311 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 841.5478 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 841.9457 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 843.6123 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 2.0646 | 21505.8092 | ACTION | 843.6123 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 848.6123 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 848.929 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 849.929 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 852.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 852.929 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 853.6521 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 853.6553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 854.6553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 856.1553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 858.1553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 859.1553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 860.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 860.1553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 862.1553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 866.1553 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 866.472 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 871.472 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 871.7887 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 872.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 872.7887 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 875.7887 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 876.5117 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 876.515 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 877.515 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 879.015 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 880.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 881.015 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 882.015 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Delay | 5 | 25000 | ACTION | 885.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 887.015 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 888.015 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 892.015 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 892.3316 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 897.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 897.3316 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 897.6483 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 898.6483 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 901.6483 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 902.3714 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 902.3746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 903.3746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 904.8746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 905.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 906.8746 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 907.8746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 908.8746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 912.8746 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 913.1913 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 917.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 918.1913 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 918.508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 919.508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 922.508 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 923.231 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 923.2343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 924.2343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 925.141 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 925.7343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 927.7343 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 84.1219 | 420609.644 | ACTION | 927.7343 | MonopileInstallation |  |  | Site
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 928.3843 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 928.7343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 929.4009 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 929.7343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 930.3843 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 932.0509 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 932.6442 | MonopileInstallation
| Feeder 1 | Queue | 0.59324 | 2966.2162 | ACTION | 932.6442 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 933.7343 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 934.0509 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 939.0509 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 939.3676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 940.3676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 943.3676 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 944.0907 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 944.0939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 944.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 945.0939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 946.5939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 948.5939 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 949.5939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 950.5939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 952.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 954.5939 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 954.9106 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 959.9106 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 960.2273 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 961.2273 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 964.2273 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 964.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 964.9503 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 964.9536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 965.9536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 967.4536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 969.4536 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 970.4536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 971.4536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 972.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 975.4536 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 975.7702 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 980.7702 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 981.0869 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 982.0869 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 984.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 985.0869 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 985.81 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 985.8132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 986.8132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 988.3132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 990.3132 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 991.3132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 992.3132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 992.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 996.3132 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 996.6299 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1001.6299 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1001.9466 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1002.9466 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1004.6442 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1005.9466 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1006.6696 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1006.6729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1007.6729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1009.1729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1011.1729 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 78.5287 | 392643.4278 | ACTION | 1011.1729 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1012.1729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1012.6442 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1012.8395 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1013.1729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1015.8874 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1016.0828 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1017.1729 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1017.4895 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 1017.8874 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 1019.5541 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 2.0646 | 21505.8092 | ACTION | 1019.5541 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1024.5541 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1024.8708 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1025.8708 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1028.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1028.8708 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1029.5938 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1029.5971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1030.5971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1032.0971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1034.0971 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1035.0971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1036.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1036.0971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1040.0971 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1040.4137 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1045.4137 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1045.7304 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1046.7304 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1048.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1049.7304 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1050.4535 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1050.4567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1051.4567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1052.9567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1054.9567 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1055.9567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1056.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1056.9567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1060.9567 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1061.2734 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1066.2734 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1066.5901 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1067.5901 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1068.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1070.5901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1071.3131 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1071.3164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1072.3164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1073.8164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1075.8164 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1076.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1076.8164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1077.8164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1081.8164 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1082.133 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1087.133 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1087.4497 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1088.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1088.4497 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1091.4497 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1092.1728 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1092.176 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1093.176 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1094.676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1096.0828 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1096.676 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 77.1219 | 385609.644 | ACTION | 1096.676 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1097.676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1098.3427 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1098.676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1099.326 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1101.326 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1101.5859 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1102.676 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1102.9927 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1102.9927 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 1.1369e-12 | 1.1842e-08 | ACTION | 1102.9927 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1107.9927 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1108.3094 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1109.3094 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1112.3094 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1113.0324 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1113.0357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1113.5859 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1114.0357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1115.5357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1117.5357 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1118.5357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1119.5357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1121.5859 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1123.5357 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1123.8523 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1128.8523 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1129.169 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1130.169 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1133.169 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1133.5859 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1133.8921 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1133.8953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1134.8953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1136.3953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1138.3953 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1139.3953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1140.3953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1141.5859 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1144.3953 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1144.712 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1149.712 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1150.0287 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1151.0287 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1154.0287 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1154.7517 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1154.755 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1155.755 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1157.255 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1159.255 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1160.255 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1161.255 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1165.255 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1165.5716 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1170.5716 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1170.8883 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1171.8883 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1174.8883 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1175.6114 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1175.6146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1176.6146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1178.1146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1180.1146 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 77.1219 | 385609.644 | ACTION | 1180.1146 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1181.1146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1181.7813 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1182.1146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1185.0245 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1186.1146 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 1186.4313 | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1186.4313 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1190.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1194.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1198.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1202.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1206.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1207.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1209.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1210.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1214.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1218.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1222.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1226.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1230.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1232.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1233.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1235.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1239.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1243.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1247.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1251.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1255.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1256.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1258.4313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1259.9313 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1263.1745 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1268.1745 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1268.4912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1271.4912 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1271.8712 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1277.8712 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1280.8712 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1281.6312 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1287.6312 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1290.6312 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1291.7712 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1297.7712 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1300.7712 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1302.2912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1308.2912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1311.2912 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1312.2912 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1313.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 1316.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1322.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1323.7912 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1324.7912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1326.2912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1329.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1330.7912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1332.2912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1335.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1336.7912 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1338.2912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1341.7912 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1342.1079 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1347.1079 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1347.4245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1350.4245 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1350.8045 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1356.8045 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1359.8045 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1360.5645 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1366.5645 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1369.5645 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1370.7045 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1376.7045 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1379.7045 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1381.2245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1387.2245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1390.2245 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1391.2245 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1392.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1398.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1399.7245 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1400.7245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1402.2245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1405.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1406.7245 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 1415.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1417.2245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1420.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1421.7245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1423.2245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1426.7245 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1427.0412 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1432.0412 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1432.3579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1435.3579 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1435.7379 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1441.7379 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1444.7379 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1445.4979 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1451.4979 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1454.4979 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1455.6379 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1461.6379 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1464.6379 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1466.1579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1472.1579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1475.1579 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1476.1579 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1477.6579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1483.6579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1484.6579 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1485.6579 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1487.1579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1490.6579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1491.6579 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1493.1579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1496.6579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1497.6579 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1499.1579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1502.6579 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1502.9745 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1506.2178 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1510.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1514.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1518.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1522.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1526.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1527.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1529.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1530.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1534.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1538.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1542.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1546.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1550.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1552.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1553.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1555.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1559.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1563.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1567.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1571.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1575.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1576.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1578.2178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1579.7178 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1582.961 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1587.961 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1588.2777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1591.2777 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1591.6577 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1597.6577 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1600.6577 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1601.4177 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1607.4177 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1610.4177 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1611.5577 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1617.5577 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1620.5577 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1622.0777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1628.0777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1631.0777 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1632.0777 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1633.5777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1639.5777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1640.5777 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1641.5777 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1643.0777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1646.5777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1647.5777 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1649.0777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1652.5777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1653.5777 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1655.0777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1658.5777 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1658.8943 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1663.8943 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1664.211 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1667.211 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1667.591 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1673.591 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1676.591 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1677.351 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1683.351 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1686.351 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1687.491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1693.491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1696.491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1698.011 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1704.011 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1707.011 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1708.011 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1709.511 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1715.511 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1716.511 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1717.511 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1719.011 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1722.511 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1723.511 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1725.011 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1728.511 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1729.511 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1731.011 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1734.511 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1734.8277 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1739.8277 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1740.1443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1743.1443 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1743.5243 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1749.5243 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1752.5243 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1753.2843 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1759.2843 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1762.2843 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1763.4243 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1769.4243 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1772.4243 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1773.9443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1779.9443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1782.9443 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1783.9443 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1785.4443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1791.4443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1792.4443 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1793.4443 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1794.9443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1798.4443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1799.4443 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1800.9443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1804.4443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1805.4443 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1806.9443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1810.4443 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1810.761 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1814.0043 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1818.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1822.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1826.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1830.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1834.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1835.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1837.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1838.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1842.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1846.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1850.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1854.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1858.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1860.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1861.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1863.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1867.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1871.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1875.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1879.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1883.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1884.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1886.0043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1887.5043 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1890.7475 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1895.7475 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1896.0642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1899.0642 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1899.4442 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1905.4442 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1908.4442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1909.2042 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1915.2042 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1918.2042 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1919.3442 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1925.3442 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1928.3442 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1929.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1935.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1938.8642 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1939.8642 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1941.3642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1947.3642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1948.3642 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1949.3642 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1950.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1954.3642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1955.3642 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1956.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1960.3642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1961.3642 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1962.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 1965.8642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1969.3642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1969.6808 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1974.6808 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1974.9975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1977.9975 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1978.3775 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1984.3775 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1987.3775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1988.1375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1994.1375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1997.1375 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1998.2775 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2004.2775 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2007.2775 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2008.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2014.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2017.7975 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2018.7975 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2020.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2022.2975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2028.2975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2029.2975 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2030.2975 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2031.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2035.2975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2036.2975 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2037.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2041.2975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2042.2975 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2043.7975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2047.2975 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2047.6142 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2052.6142 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2052.9308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2055.9308 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2056.3108 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2062.3108 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2065.3108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2066.0708 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2072.0708 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2075.0708 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2076.2108 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2082.2108 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2085.2108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2086.7308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2092.7308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2095.7308 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2096.7308 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2098.2308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2104.2308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2105.2308 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2106.2308 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2107.7308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2111.2308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2112.2308 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2113.7308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2117.2308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2118.2308 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2119.7308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2123.2308 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2123.5475 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2126.7907 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2130.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2134.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2138.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2142.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2146.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2148.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2149.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2151.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2155.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2159.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2163.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2167.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2171.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2172.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2174.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2175.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2179.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2183.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2187.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2191.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2195.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2197.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2198.7907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2200.2907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2203.534 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2208.534 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2208.8507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2211.8507 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2212.2307 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2218.2307 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2221.2307 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2221.9907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2227.9907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2230.9907 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2232.1307 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2238.1307 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2241.1307 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2242.6507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2248.6507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2251.6507 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2252.6507 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2254.1507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2260.1507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2261.1507 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2262.1507 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2263.6507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2267.1507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2268.1507 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2269.6507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2273.1507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2274.1507 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2275.6507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2279.1507 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2279.4673 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2284.4673 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2284.784 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2287.784 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2288.164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2294.164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2297.164 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2297.924 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2303.924 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2306.924 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2308.064 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2314.064 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2317.064 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2318.584 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2324.584 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2327.584 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2328.584 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2330.084 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2336.084 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2337.084 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2338.084 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2339.584 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2343.084 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2344.084 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2345.584 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2349.084 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2350.084 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2351.584 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2355.084 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2355.4007 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2360.4007 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2360.7173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2363.7173 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2364.0973 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2370.0973 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2373.0973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2373.8573 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2379.8573 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2382.8573 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2383.9973 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2389.9973 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2392.9973 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2394.5173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2400.5173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2403.5173 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2404.5173 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2406.0173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2412.0173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2413.0173 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2414.0173 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2415.5173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2419.0173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2420.0173 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2421.5173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2425.0173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2426.0173 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2427.5173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2431.0173 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2431.334 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2434.5772 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2438.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2442.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2446.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2450.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2454.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2456.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2457.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2459.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2463.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2467.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2471.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2475.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2479.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2480.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2482.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2483.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2487.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2491.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2495.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2499.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2503.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2505.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2506.5772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2508.0772 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2511.3205 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2516.3205 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2516.6371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2519.6371 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2520.0171 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2526.0171 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2529.0171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2529.7771 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2535.7771 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2538.7771 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2539.9171 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2545.9171 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2548.9171 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2550.4371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2556.4371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2559.4371 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2560.4371 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2561.9371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2567.9371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2568.9371 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2569.9371 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2571.4371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2574.9371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2575.9371 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2577.4371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2580.9371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2581.9371 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2583.4371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2586.9371 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2587.2538 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2592.2538 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2592.5705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2595.5705 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2595.9505 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2601.9505 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2604.9505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2605.7105 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2611.7105 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2614.7105 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2615.8505 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2621.8505 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2624.8505 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2626.3705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2632.3705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2635.3705 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2636.3705 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2637.8705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2643.8705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2644.8705 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2645.8705 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2647.3705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2650.8705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2651.8705 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2653.3705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2656.8705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2657.8705 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2659.3705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2662.8705 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2663.1871 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2668.1871 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2668.5038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2671.5038 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2671.8838 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2677.8838 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2680.8838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2681.6438 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2687.6438 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2690.6438 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2691.7838 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2697.7838 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2700.7838 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2702.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2708.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2711.3038 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2712.3038 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2713.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2719.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2720.8038 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2721.8038 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2723.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2726.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2727.8038 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2729.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2732.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2733.8038 | TurbineInstallation
| WTIV | Delay | 35 | 583333.3333 | ACTION | 2768.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2770.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 2780.3038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2783.8038 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2784.1205 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2787.3637 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2791.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2795.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2799.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2803.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2807.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2808.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2810.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2811.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2815.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2819.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2823.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2827.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2831.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2833.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2834.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2836.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2840.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2844.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2848.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2852.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2856.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2857.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2859.3637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2860.8637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2864.107 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2869.107 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2869.4236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2872.4236 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2872.8036 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2878.8036 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2881.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2882.5636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2888.5636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2891.5636 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2892.7036 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2898.7036 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2901.7036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2903.2236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2909.2236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2912.2236 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2913.2236 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2914.7236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2920.7236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2921.7236 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2922.7236 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2924.2236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2927.7236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2928.7236 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2930.2236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2933.7236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2934.7236 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2936.2236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2939.7236 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2940.0403 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2945.0403 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2945.357 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2948.357 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2948.737 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2954.737 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2957.737 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2958.497 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2964.497 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2967.497 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2968.637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2974.637 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2977.637 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2979.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2985.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2988.157 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2989.157 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2990.657 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2996.657 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2997.657 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2998.657 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3000.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3003.657 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3004.657 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3006.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3009.657 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3010.657 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3012.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 21 | 350000 | ACTION | 3033.157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3036.657 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3036.9736 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3041.9736 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3042.2903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3045.2903 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3047.2903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3047.6703 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 3050.6703 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3056.6703 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3059.6703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3060.4303 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3066.4303 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3069.4303 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3070.5703 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3076.5703 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3079.5703 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3081.0903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3087.0903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3090.0903 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3091.0903 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3092.5903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3098.5903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3099.5903 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3100.5903 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3102.0903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3105.5903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3106.5903 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3108.0903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3111.5903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3112.5903 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3114.0903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3117.5903 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3117.907 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3121.1502 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3125.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3129.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3133.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3137.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3141.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3142.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3144.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3145.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3149.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3153.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3157.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3161.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3165.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3167.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3168.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3170.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3174.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3178.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3182.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3186.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3190.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3191.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3193.1502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3194.6502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3197.8934 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3202.8934 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3203.2101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3206.2101 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3206.5901 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3212.5901 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3215.5901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3216.3501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3222.3501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3225.3501 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3226.4901 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3232.4901 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3235.4901 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3237.0101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3243.0101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3246.0101 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3247.0101 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3248.5101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3254.5101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3255.5101 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3256.5101 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3258.0101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3261.5101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3262.5101 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3264.0101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3267.5101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3268.5101 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3270.0101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3273.5101 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3273.8268 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3278.8268 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3279.1434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3282.1434 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3282.5234 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3288.5234 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3291.5234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3292.2834 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3298.2834 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3301.2834 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3302.4234 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3308.4234 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3311.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3312.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3318.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3321.9434 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3322.9434 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3324.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3330.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3331.4434 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3332.4434 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3333.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3337.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3341.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3342.4434 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 3351.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3352.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3356.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3357.4434 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3358.9434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3362.4434 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3362.7601 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3367.7601 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3368.0768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3371.0768 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3371.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3377.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3380.4568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3381.2168 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3387.2168 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3390.2168 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3391.3568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3397.3568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3400.3568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3401.8768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3407.8768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3410.8768 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3411.8768 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3413.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3419.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3420.3768 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3421.3768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3422.8768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3426.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3427.3768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3428.8768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3432.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3433.3768 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3435.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3436.8768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3440.3768 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3440.6934 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3443.9367 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3447.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3451.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3455.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3459.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3463.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3465.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3466.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3468.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3472.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3476.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3480.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3484.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3488.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3489.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3491.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3492.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3496.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3500.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3504.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3508.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3512.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3514.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3515.9367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3517.4367 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3520.6799 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3525.6799 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3525.9966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3528.9966 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3529.3766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3539.3766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3545.3766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3548.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3549.1366 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3555.1366 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3558.1366 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3559.2766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3565.2766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3568.2766 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3569.7966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3575.7966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3578.7966 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3579.7966 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3581.2966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3587.2966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3588.2966 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3589.2966 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3590.7966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3594.2966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3595.2966 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3596.7966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3600.2966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3601.2966 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3602.7966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3606.2966 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3606.6133 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3611.6133 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3611.9299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3614.9299 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3615.3099 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 15 | 250000 | ACTION | 3630.3099 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3636.3099 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3639.3099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3640.0699 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3646.0699 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3649.0699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3650.2099 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3656.2099 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3659.2099 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3660.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 3702.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3708.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3711.7299 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3712.7299 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3714.2299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3720.2299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3721.2299 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3722.2299 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3723.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3727.2299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3728.2299 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3729.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3733.2299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3734.2299 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3735.7299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3739.2299 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3739.5466 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3744.5466 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3744.8633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3747.8633 | TurbineInstallation
| WTIV | Delay | 20 | 333333.3333 | ACTION | 3767.8633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3768.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3774.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3777.2433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3778.0033 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3784.0033 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3787.0033 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3788.1433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3794.1433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3797.1433 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3798.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3804.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3807.6633 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3808.6633 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3810.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3816.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3817.1633 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3818.1633 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3819.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3823.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3824.1633 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3825.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3833.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3837.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3838.1633 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3840.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3841.6633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3845.1633 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3845.4799 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3848.7232 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3852.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3856.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3860.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3864.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3868.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3870.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3871.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3873.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3877.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3881.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3885.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3889.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3893.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3894.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3896.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3897.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3901.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3905.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3909.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3913.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3917.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3919.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3920.7232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3922.2232 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3925.4664 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3930.4664 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3930.7831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3933.7831 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3934.1631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3940.1631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3943.1631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3943.9231 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3949.9231 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3952.9231 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3954.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3960.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3963.0631 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3964.5831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3970.5831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3973.5831 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3974.5831 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3976.0831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3982.0831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3983.0831 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3984.0831 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3985.5831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3989.0831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3990.0831 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3991.5831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3995.0831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3996.0831 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3997.5831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4001.0831 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4001.3998 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4006.3998 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4006.7164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4009.7164 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4010.0964 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 51 | 850000 | ACTION | 4061.0964 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4067.0964 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4070.0964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4070.8564 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4076.8564 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4079.8564 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4082.8564 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4083.9964 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4089.9964 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4092.9964 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4094.5164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4100.5164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4103.5164 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4104.5164 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4106.0164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4112.0164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4113.0164 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4114.0164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4115.5164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4119.0164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4120.0164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4121.5164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4125.0164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4126.0164 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4127.5164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4131.0164 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4131.3331 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4136.3331 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4136.6498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4139.6498 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4140.0298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4146.0298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4149.0298 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4149.7898 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4155.7898 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4158.7898 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4159.9298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4165.9298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4168.9298 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4170.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4176.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4179.4498 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4180.4498 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4181.9498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4187.9498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4188.9498 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4189.9498 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4191.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4194.9498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4195.9498 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4197.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4202.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4205.9498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4206.9498 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4208.4498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4211.9498 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4212.2664 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4215.5097 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4219.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4223.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4227.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4231.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4235.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4237.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4238.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4240.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4244.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4248.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4252.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4256.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4260.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4261.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4263.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4264.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4268.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4272.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4276.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4277.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4281.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4285.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4287.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4288.5097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4290.0097 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4293.2529 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4298.2529 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4298.5696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4301.5696 | TurbineInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 4327.5696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4327.9496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4333.9496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4336.9496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4337.7096 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4343.7096 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4346.7096 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4347.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4353.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4356.8496 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4358.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4364.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4367.3696 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4368.3696 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4371.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4372.8696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4378.8696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4379.8696 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4380.8696 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4382.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4385.8696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4386.8696 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4388.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 15 | 250000 | ACTION | 4403.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4406.8696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4407.8696 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4409.3696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4412.8696 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4413.1862 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4418.1862 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4418.5029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4421.5029 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4421.8829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4427.8829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4430.8829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4431.6429 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4437.6429 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4440.6429 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4441.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4447.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4450.7829 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4452.3029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4458.3029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4461.3029 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4462.3029 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4463.8029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4469.8029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4470.8029 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4471.8029 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4473.3029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4476.8029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4477.8029 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4479.3029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4482.8029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4483.8029 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4485.3029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4488.8029 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4489.1196 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 62 | 1033333.3333 | ACTION | 4551.1196 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4556.1196 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4556.4362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4559.4362 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4559.8162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4565.8162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4568.8162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4569.5762 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4575.5762 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4578.5762 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4579.7162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 4605.7162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4611.7162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4614.7162 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4698.7162 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4700.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 4703.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4709.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4712.2362 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4713.2362 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4714.7362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4720.7362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4721.7362 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4722.7362 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4724.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4727.7362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4728.7362 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4730.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4733.7362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4734.7362 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4736.2362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4739.7362 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4740.0529 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4743.2962 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4747.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4751.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4755.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4759.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4763.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4764.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4766.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4767.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4771.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4775.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4779.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4783.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4787.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4789.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4790.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4792.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4796.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4800.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4804.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4808.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4812.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4813.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4815.2962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4816.7962 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3 | 50000 | ACTION | 4819.7962 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4833.7962 | TurbineInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 4834.0394 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4839.0394 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4839.3561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4842.3561 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4842.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4848.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4851.7361 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4852.4961 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4858.4961 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4861.4961 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4862.6361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4868.6361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4871.6361 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4873.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4879.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4882.1561 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4883.1561 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4889.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4890.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 4896.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4902.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4903.6561 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4904.6561 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4906.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4909.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4910.6561 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4912.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4915.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4916.6561 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4918.1561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4921.6561 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4921.9727 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4926.9727 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4927.2894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4930.2894 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4930.6694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4936.6694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4939.6694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4940.4294 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4946.4294 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4949.4294 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4950.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4956.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4959.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4961.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4967.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4970.0894 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4971.0894 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 4983.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4984.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4991.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4997.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4998.5894 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4999.5894 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5001.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5004.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5005.5894 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5007.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5010.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5011.5894 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5013.0894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5016.5894 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5016.9061 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5021.9061 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5022.2227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5025.2227 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5025.6027 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5030.6027 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5036.6027 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5039.6027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5040.3627 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5046.3627 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5049.3627 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5050.5027 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5056.5027 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5059.5027 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5061.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5066.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5072.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5075.0227 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5076.0227 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5077.5227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5083.5227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5084.5227 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5085.5227 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5087.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5090.5227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5091.5227 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5093.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5096.5227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5097.5227 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5099.0227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5102.5227 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5102.8394 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5106.0826 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5110.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5114.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5118.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5122.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5126.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5127.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5129.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5130.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5134.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5138.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5142.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 5146.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 5150.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5152.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 5153.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 1256 | 20933333.3333 | ACTION | 6409.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6411.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6415.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6419.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6423.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6427.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6431.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6432.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6434.0826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6435.5826 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6438.8259 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6443.8259 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6444.1425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6447.1425 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6447.5225 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6453.5225 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6456.5225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6457.2825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6463.2825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6466.2825 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6467.4225 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6473.4225 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6476.4225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6477.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6483.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6486.9425 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6487.9425 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6489.4425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6495.4425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6496.4425 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6497.4425 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6498.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 6516.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6520.4425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6521.4425 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6522.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6526.4425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6527.4425 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6528.9425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6532.4425 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6532.7592 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6537.7592 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6538.0759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6541.0759 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6541.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6547.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6550.4559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6551.2159 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6557.2159 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6560.2159 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6561.3559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6567.3559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6570.3559 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6571.8759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6577.8759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6580.8759 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6581.8759 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6583.3759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6589.3759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6590.3759 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6591.3759 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6592.8759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6596.3759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6597.3759 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6598.8759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6602.3759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6603.3759 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6604.8759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6608.3759 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6608.6925 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6613.6925 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6614.0092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6617.0092 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6617.3892 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6623.3892 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6626.3892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6627.1492 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6633.1492 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6636.1492 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6637.2892 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6643.2892 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6646.2892 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6647.8092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6653.8092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6656.8092 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6657.8092 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6659.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 6665.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6671.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6672.3092 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6673.3092 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6674.8092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6678.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6679.3092 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6680.8092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6684.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6685.3092 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6686.8092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6690.3092 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6690.6259 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6693.8691 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6697.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6701.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6705.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6709.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6713.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6715.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6716.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6718.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6722.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6726.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6730.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6734.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6738.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6739.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6741.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6742.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 6745.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6749.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6753.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6757.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6761.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6765.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6767.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6768.8691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6770.3691 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6773.6124 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6778.6124 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6778.929 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6781.929 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6782.309 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6788.309 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6791.309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6792.069 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6798.069 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6801.069 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6802.209 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6808.209 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6811.209 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 6824.209 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6825.729 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6831.729 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6834.729 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6835.729 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6837.229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6843.229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6844.229 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6845.229 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6846.729 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6850.229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6851.229 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6852.729 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6856.229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6857.229 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6858.729 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6862.229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6862.5457 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6867.5457 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6867.8624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6870.8624 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6871.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6877.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6880.2424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6881.0024 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6887.0024 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6890.0024 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6891.1424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6897.1424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6900.1424 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6901.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6907.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6910.6624 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6911.6624 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6912.6624 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6915.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6917.1624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6923.1624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6924.1624 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6925.1624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6926.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6930.1624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6931.1624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6932.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 51 | 850000 | ACTION | 6983.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6987.1624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6988.1624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6989.6624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6993.1624 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6993.479 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6998.479 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6998.7957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7001.7957 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7002.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7008.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7011.1757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7011.9357 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7017.9357 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7020.9357 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7022.0757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7028.0757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7031.0757 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7032.5957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7038.5957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7041.5957 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7042.5957 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7044.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 49 | 816666.6667 | ACTION | 7093.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7099.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7100.0957 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7101.0957 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7102.5957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7106.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7107.0957 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7108.5957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7112.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7113.0957 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7114.5957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7118.0957 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7118.4124 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7121.6556 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7125.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7129.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7133.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7137.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7141.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7143.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7144.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7146.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7150.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7154.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7158.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7162.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7166.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7167.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7169.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7170.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7174.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7178.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7182.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7186.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7190.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7192.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7193.6556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7195.1556 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7198.3989 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7203.3989 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7203.7155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7206.7155 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7207.0955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7213.0955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 9 | 150000 | ACTION | 7222.0955 | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7225.0955 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7230.0955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7230.8555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7236.8555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7239.8555 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7240.9955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7246.9955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7249.9955 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7251.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7257.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7260.5155 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7261.5155 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7263.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7269.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7270.0155 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7271.0155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7272.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7276.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7277.0155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7278.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7282.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7283.0155 | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 7299.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7300.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 7306.5155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7310.0155 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7310.3322 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7315.3322 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7315.6489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7318.6489 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7319.0289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7325.0289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7328.0289 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7328.7889 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7334.7889 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7337.7889 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7338.7889 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7339.9289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 12 | 200000 | ACTION | 7351.9289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7357.9289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7360.9289 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7362.4489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7368.4489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7371.4489 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7372.4489 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7373.9489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7379.9489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7380.9489 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7381.9489 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7383.4489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7386.9489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7387.9489 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7389.4489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7392.9489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7393.9489 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7395.4489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7398.9489 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7399.2655 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7404.2655 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7404.5822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7407.5822 | TurbineInstallation
| WTIV | Delay | 58 | 966666.6667 | ACTION | 7465.5822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7465.9622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7471.9622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7474.9622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7475.7222 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7481.7222 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7484.7222 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7485.8622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7491.8622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7494.8622 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7496.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7502.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7505.3822 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7506.3822 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7507.8822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7513.8822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7514.8822 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7515.8822 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7517.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7520.8822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7521.8822 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7523.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 27 | 450000 | ACTION | 7550.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7553.8822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7554.8822 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7556.3822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7559.8822 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7560.1989 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7563.4421 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7567.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7571.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7575.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7579.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7583.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7584.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7586.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7587.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7591.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7595.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7599.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7603.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7607.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7609.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7610.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7612.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7616.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7620.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7624.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7628.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7632.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7633.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7635.4421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7636.9421 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7640.1853 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7645.1853 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7645.502 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7648.502 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7648.882 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7654.882 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7657.882 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7658.642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7664.642 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7667.642 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7668.782 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 7674.782 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7680.782 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7683.782 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7685.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7691.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7694.302 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7695.302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7696.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7702.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7703.802 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7704.802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7706.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7709.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7710.802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7712.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 7725.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7728.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7729.802 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7731.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7733.302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7736.802 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7737.1187 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7742.1187 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7742.4353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7745.4353 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7745.8153 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7751.8153 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7754.8153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7755.5753 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7761.5753 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7764.5753 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7765.7153 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7771.7153 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7774.7153 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7776.2353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7782.2353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7785.2353 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7786.2353 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7787.7353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7793.7353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7794.7353 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7795.7353 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7797.2353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7800.7353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7801.7353 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.2353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7806.7353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7807.7353 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7809.2353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7812.7353 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7813.052 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7818.052 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7818.3687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7821.3687 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7821.7487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7827.7487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7830.7487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7831.5087 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7837.5087 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7840.5087 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7841.6487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7847.6487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7850.6487 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7852.1687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7858.1687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7861.1687 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7862.1687 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7863.6687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7869.6687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7870.6687 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7871.6687 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7873.1687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7876.6687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7877.6687 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7879.1687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7882.6687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7883.6687 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7885.1687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7888.6687 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7888.9853 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7892.2286 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7896.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7900.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7904.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7908.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7912.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7913.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7915.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7916.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7920.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7924.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7928.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7932.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7936.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7938.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7939.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7941.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7945.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7949.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7953.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7957.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7961.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7962.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7964.2286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7965.7286 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7968.9718 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7973.9718 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7974.2885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7977.2885 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7977.6685 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7983.6685 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7986.6685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7987.4285 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7993.4285 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7996.4285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7997.5685 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8003.5685 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8006.5685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8008.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8014.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8017.0885 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8018.0885 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8019.5885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8025.5885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8026.5885 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8027.5885 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8029.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8032.5885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8033.5885 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8035.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8038.5885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8039.5885 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8041.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 11 | 183333.3333 | ACTION | 8052.0885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8055.5885 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8055.9052 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8060.9052 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8061.2218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8064.2218 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8064.6018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 8072.6018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8078.6018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8081.6018 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8083.6018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8084.3618 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8086.3618 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8092.3618 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8095.3618 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8096.5018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8102.5018 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8105.5018 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8107.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8113.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8116.0218 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8117.0218 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8118.5218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8124.5218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8125.5218 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8126.5218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8128.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 44 | 733333.3333 | ACTION | 8172.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8175.5218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8176.5218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8178.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8182.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8185.5218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8186.5218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8188.0218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8191.5218 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8191.8385 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8196.8385 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8197.1552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8200.1552 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8200.5352 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8206.5352 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8209.5352 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8210.2952 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8216.2952 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8219.2952 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8220.4352 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8226.4352 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8229.4352 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8230.9552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8236.9552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8239.9552 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8240.9552 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8242.4552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8248.4552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8249.4552 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8250.4552 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8251.9552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8255.4552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8256.4552 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8257.9552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8261.4552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8262.4552 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8263.9552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8267.4552 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8267.7718 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8271.0151 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8275.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8279.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8283.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8287.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8291.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8292.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8294.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8295.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8299.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 8317.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8321.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8325.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8329.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8333.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8335.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8339.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8340.5151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8342.0151 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8345.2583 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8350.2583 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8350.575 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8353.575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8353.955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8359.955 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8362.955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8363.715 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8369.715 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8372.715 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8373.855 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 8379.855 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8385.855 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8388.855 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8390.375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8396.375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8399.375 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8400.375 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8401.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8407.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8408.875 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8409.875 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8411.375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8414.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8415.875 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 8451.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8453.375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8456.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8457.875 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8459.375 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8462.875 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8463.1916 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8468.1916 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8468.5083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8471.5083 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8471.8883 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8477.8883 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8480.8883 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8481.6483 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8487.6483 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8490.6483 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8491.7883 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8497.7883 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8500.7883 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8502.3083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8508.3083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8511.3083 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8512.3083 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8513.8083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8519.8083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8520.8083 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8521.8083 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8523.3083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8526.8083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8527.8083 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8529.3083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8532.8083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8533.8083 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8535.3083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8538.8083 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8539.125 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150