## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Queue | 120 | 600000 | ACTION | 120 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 125.2432 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 126.9099 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 123.6667 | 1288194.4444 | ACTION | 126.9099 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 131.9099 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 132.2266 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 133.2266 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 136.2266 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 6 | 62500 | ACTION | 142.2266 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 142.9496 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 142.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 143.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 147.9529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 149.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 151.4529 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 152.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 153.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 157.4529 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 157.7696 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 162.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 163.0862 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 164.0862 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 167.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 167.8093 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 167.8125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 168.8125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 170.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 172 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 172.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 173.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 174.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 178.3125 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 178.6292 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 180 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 183.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 183.9459 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 184.9459 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 187.9459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 188.6689 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 188.6722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 189.6722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 192 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Delay | 19 | 95000 | ACTION | 211 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 25 | 260416.6667 | ACTION | 214.6722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 216.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 218.1722 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 219 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 219.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 220.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 221.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 225.1722 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 225.4889 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 230.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 230.8055 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 231 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 231.8055 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 234.8055 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 235.5286 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 235.5318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 236.5318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 238.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 239 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 240.0318 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 241.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 242.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 246.0318 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 246.3485 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 251 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 251.3485 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 251.6652 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 252.6652 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 255.6652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 256.3882 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 256.3915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 257.3915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 258.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 259 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 260.8915 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 261.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 262.2432 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 262.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 264.2432 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 265.9099 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 266.8915 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 267.2082 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 272.2082 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 272.5248 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 273.5248 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 276.5248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 277.2479 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 277.2511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 278.2511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 279.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 281.7511 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 154.8412 | 774206.1327 | ACTION | 281.7511 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 282.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 283.4178 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 283.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 286.661 | MonopileInstallation
| Feeder 1 | Queue | 20.7511 | 103755.6823 | ACTION | 286.661 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 287.7511 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 288.0678 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 293.0678 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 293.3845 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 294.3845 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 297.3845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 298.1075 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 298.1108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 298.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 299.1108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 300.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 302.6108 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 303.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 304.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 306.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 308.6108 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 308.9275 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 313.9275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 314.2441 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 315.2441 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 318.2441 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 318.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 318.9672 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 318.9704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 319.9704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 321.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 323.4704 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 324.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 325.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 326.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 329.4704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 329.7871 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 334.7871 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 335.1038 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 336.1038 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 338.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 339.1038 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 342.1038 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 342.8268 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 342.8301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 343.8301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 345.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 346.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 347.3301 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 348.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 349.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 352.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 356.3301 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 356.6467 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 358.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 361.6467 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 361.9634 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 362.9634 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 365.9634 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 366.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 366.6865 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 366.6897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 367.6897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 369.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 371.1897 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 372.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 373.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 377.1897 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 377.5064 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 378.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 382.5064 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 382.8231 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 383.8231 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 386.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 386.8231 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 387.5461 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 387.5494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 388.5494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 390.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 392.0494 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 393.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 394.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 398.0494 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 398.366 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 398.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 403.366 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 403.6827 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 404.6827 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 406.661 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 407.6827 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 408.4058 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 408.409 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 409.409 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 409.9043 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 410.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 411.9043 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 412.909 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 126.248 | 631239.9165 | ACTION | 412.909 | MonopileInstallation |  |  | Site
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 413.571 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 413.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 414.5757 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 414.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 417.8189 | MonopileInstallation
| Feeder 0 | Queue | 4.248 | 21239.9165 | ACTION | 417.8189 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 418.909 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 419.2257 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 424.2257 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 424.5424 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 425.5424 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 428.5424 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 429.2654 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 429.2687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 429.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 430.2687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 9 | 93750 | ACTION | 439.2687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 440.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 442.7687 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 443.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 444.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 448.7687 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 449.0853 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 453.0853 | MonopileInstallation
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 458.0853 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 458.402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Delay | 29 | 145000 | ACTION | 458.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 459.402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 462.402 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 463.1251 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 463.1283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 464.1283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 465.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 466.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 467.6283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 468.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 469.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 473.6283 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 473.945 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 478.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 478.945 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 479.2617 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 480.2617 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 483.2617 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 483.9847 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 483.988 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 484.988 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 486.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 486.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 488.488 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 489.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 490.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 494.488 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 494.8046 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 498.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 499.8046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 500.1213 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 501.1213 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 504.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 504.8444 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 504.8476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 505.8476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 506.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 507.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 509.3476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 510.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 511.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 515.3476 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 515.6643 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 518.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 520.6643 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 520.981 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 521.981 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 524.981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 525.704 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 525.7073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 526.7073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 526.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 528.2073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 530.2073 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 531.2073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 532.2073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 536.2073 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 536.5239 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 538.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 541.5239 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 541.8406 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 542.8406 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 545.8406 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 546.5637 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 546.5669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 546.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 547.5669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 549.0669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 551.0669 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 133.248 | 666239.9165 | ACTION | 551.0669 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 552.0669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 552.7336 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 553.0669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 555.9768 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 557.0669 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 557.3836 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 558.8189 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 566.8189 | MonopileInstallation | MonopileInstallation | 5
| Feeder 0 | Queue | 10.8421 | 54210.5339 | ACTION | 566.8189 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 570.0622 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 572.0622 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 573.7288 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 16.3453 | 170263.1244 | ACTION | 573.7288 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 578.7288 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 578.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 579.0455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 580.0455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 583.0455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 583.7686 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 583.7718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 584.7718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 586.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 586.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 588.2718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 589.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 590.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 594.2718 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 594.5885 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 598.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 599.5885 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 599.9052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 600.9052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 603.9052 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 604.6282 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 604.6315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 605.6315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 606.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 607.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 609.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 610.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 611.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 615.1315 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 615.4481 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 618.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 620.4481 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 620.7648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 621.7648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 624.7648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 625.4879 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 625.4911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 626.4911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 626.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 627.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 629.9911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 630.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 631.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 635.9911 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 636.3078 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 638.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 641.3078 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 641.6245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 642.6245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 645.6245 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 646.3475 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 646.3508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 646.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 647.3508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 648.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 650.8508 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 651.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 652.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 656.8508 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 657.1674 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 658.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 662.1674 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 662.4841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 663.4841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 666.4841 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 666.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 667.2072 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 667.2104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 668.2104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 669.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 671.7104 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 672.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 673.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 677.7104 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 678.0271 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 678.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 683.0271 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 683.3438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 684.3438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 686.8189 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 687.3438 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 688.0668 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 688.0701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 689.0701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 690.0622 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 690.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 692.0622 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 692.5701 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 118.8412 | 594206.1327 | ACTION | 692.5701 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 693.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 693.7288 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 694.2367 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 694.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 697.48 | MonopileInstallation
| Feeder 0 | Queue | 3.7511 | 18755.6823 | ACTION | 697.48 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 698.5701 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 698.8867 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 703.8867 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 704.2034 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 705.2034 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 708.2034 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 708.9265 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 708.9297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 709.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 709.9297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 711.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 713.4297 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 714.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 715.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 717.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 719.4297 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 719.7464 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 724.7464 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 725.0631 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 726.0631 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 729.0631 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 729.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 729.7861 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 729.7894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 730.7894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 732.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 734.2894 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 735.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 736.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 737.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 740.2894 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 740.606 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 745.606 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 745.9227 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 746.9227 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 749.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 749.9227 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 750.6458 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 750.649 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 751.649 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 753.149 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 755.149 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 756.149 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 757.149 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 757.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 9 | 93750 | ACTION | 766.149 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 769.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 770.149 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 770.4657 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 775.4657 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 775.7824 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 776.7824 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 777.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 779.7824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 780.5054 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 780.5087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 781.5087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 783.0087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 785.0087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 786.0087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 787.0087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 789.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 791.0087 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 791.3253 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 796.3253 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 796.642 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 797.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 797.642 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 800.642 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 801.3651 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 801.3683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 802.3683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 803.8683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 805.8683 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 806.8683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 807.8683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 809.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 811.8683 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 812.185 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 817.185 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 817.48 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 817.5017 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 818.5017 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 820.7232 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 821.5017 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 822.2247 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 822.228 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 822.7232 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 823.228 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 824.3899 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 824.728 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 826.728 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 129.248 | 646239.9165 | ACTION | 826.728 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 827.728 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 828.3946 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 828.728 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 831.6379 | MonopileInstallation
| Feeder 1 | Queue | 7.248 | 36239.9165 | ACTION | 831.6379 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 832.728 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 833.0446 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 838.0446 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 838.3613 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 839.3613 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 842.3613 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 843.0844 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 843.0876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 843.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 844.0876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 845.5876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 847.5876 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 848.5876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 849.5876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 851.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 853.5876 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 853.9043 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 858.9043 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 859.221 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 860.221 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 863.221 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 863.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 863.944 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 863.9473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 864.9473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 866.4473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 868.4473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 869.4473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 870.4473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 871.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 874.4473 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 874.7639 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 879.7639 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 880.0806 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 881.0806 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 883.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 885.0806 | MonopileInstallation
| Feeder 0 | Delay | 2 | 10000 | ACTION | 885.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 888.0806 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 888.8037 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 888.8069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 889.8069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 891.3069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 893.3069 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 893.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 894.3069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 895.3069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 899.3069 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 899.6236 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 904.6236 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 904.9402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 905.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 905.9402 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 908.9402 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 909.6633 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 909.6666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 910.6666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 912.1666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 913.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 914.1666 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 915.1666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 916.1666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 920.1666 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 920.4832 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 925.4832 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 925.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 925.7999 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 926.7999 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 929.7999 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 930.523 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 930.5262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 931.5262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 933.0262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 933.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 935.0262 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 936.0262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 937.0262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 941.0262 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 941.3429 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 945.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 946.3429 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 946.6595 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 947.6595 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 950.6595 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 951.3826 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 951.3859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 952.3859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 953.6379 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 953.8859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 955.8859 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 124.248 | 621239.9165 | ACTION | 955.8859 | MonopileInstallation |  |  | Site
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 956.8811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 956.8859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 957.5525 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 957.8859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 958.8811 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 960.5478 | MonopileInstallation | MonopileInstallation | 5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 960.7958 | MonopileInstallation
| Feeder 0 | Queue | 0.24798 | 1239.9165 | ACTION | 960.7958 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 961.8859 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 962.2025 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 967.2025 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 967.5192 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 968.5192 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 971.5192 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 972.2423 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 972.2455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 972.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 973.2455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 974.7455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 976.7455 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 977.7455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 978.7455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 980.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 982.7455 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 983.0622 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 988.0622 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 988.3788 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 989.3788 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 992.3788 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 992.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 993.1019 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 993.1052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 994.1052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 995.6052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 997.6052 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 998.6052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 999.6052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1000.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1003.6052 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1003.9218 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1008.9218 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1009.2385 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1010.2385 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1012.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1013.2385 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1013.9616 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1013.9648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1014.9648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1016.4648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1018.4648 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1019.4648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1020.4648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1020.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1024.4648 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1024.7815 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1029.7815 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1030.0981 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1031.0981 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1032.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1034.0981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1034.8212 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1034.8245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1035.8245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1037.3245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1039.3245 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1040.3245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1040.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1041.3245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1045.3245 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1045.6411 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1050.6411 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1050.9578 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1051.9578 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1052.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1054.9578 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1055.6809 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1055.6841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1056.6841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1058.1841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1060.1841 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1060.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1061.1841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1062.1841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1066.1841 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1066.5008 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1071.5008 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1071.8174 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1072.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1072.8174 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1075.8174 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1076.5405 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1076.5438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1077.5438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1079.0438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1080.7958 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1081.0438 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 120.248 | 601239.9165 | ACTION | 1081.0438 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1082.0438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1082.7104 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1083.0438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1084.039 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1085.9537 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1086.039 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1087.0438 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1087.3604 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1087.7057 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Delay: Not enough vessels for monopiles | 0.34526 | 3596.4577 | ACTION | 1087.7057 | MonopileInstallation |  |  | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1092.7057 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1093.0223 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1094.0223 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1097.0223 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1097.7454 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1097.7487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1097.9537 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1098.7487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1100.2487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1102.2487 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1103.2487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1104.2487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1105.9537 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1108.2487 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1108.5653 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1113.5653 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1113.882 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1114.882 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1117.882 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1117.9537 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1118.6051 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1118.6083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1119.6083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1121.1083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1123.1083 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1124.1083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1125.1083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1125.9537 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1129.1083 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1129.425 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1134.425 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1134.7416 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1135.7416 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1138.7416 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1139.4647 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1139.468 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1140.468 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1141.968 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1143.968 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1144.968 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1145.968 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1149.968 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1150.2846 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1155.2846 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1155.6013 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1156.6013 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1159.6013 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1160.3244 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1160.3276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1161.3276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1162.8276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1164.8276 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1165.8276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1166.8276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1170.8276 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1171.1443 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1176.1443 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1176.4609 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1177.4609 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1180.4609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1181.184 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1181.1873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1182.1873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1183.6873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1185.6873 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1186.6873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1187.6873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1191.6873 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1192.0039 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1197.0039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1197.3206 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1198.3206 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1201.3206 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1202.0437 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1202.0469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1203.0469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1204.5469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1206.5469 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 118.8412 | 594206.1327 | ACTION | 1206.5469 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1207.5469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1208.2136 | MonopileInstallation | MonopileInstallation | 5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1208.5469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1211.4568 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1212.5469 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1212.8636 | MonopileInstallation | MonopileInstallation | 5 |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 1212.8636 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1216.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1220.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1224.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1228.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1232.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1234.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1235.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1237.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1241.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1245.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1249.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1253.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1257.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1258.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1260.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1261.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1265.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1269.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1273.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1277.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1281.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1283.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1284.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1286.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1290.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1294.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1298.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1302.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1306.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1307.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1309.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1310.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1314.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1318.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1322.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1326.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1330.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1332.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1333.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1335.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1339.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1343.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1347.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1351.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1355.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1356.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1358.3636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1359.8636 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1363.1068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1368.1068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1368.4235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1371.4235 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1371.8035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1377.8035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1380.8035 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1381.5635 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1387.5635 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1390.5635 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1391.7035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1397.7035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1400.7035 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1402.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 1416.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1422.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1425.2235 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1426.2235 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1427.7235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1433.7235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1434.7235 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1435.7235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1437.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1440.7235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1441.7235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1443.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1446.7235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1447.7235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1449.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1452.7235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1453.0402 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1458.0402 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1458.3568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1461.3568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1461.7368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1467.7368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1470.7368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1471.4968 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1477.4968 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1480.4968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1481.6368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1487.6368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1490.6368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1492.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1498.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1501.1568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1502.1568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1503.6568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1509.6568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1510.6568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1511.6568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1513.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1516.6568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1517.6568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1519.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1522.6568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1523.6568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1525.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1528.6568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1528.9735 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1533.9735 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1534.2902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1537.2902 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1537.6702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1543.6702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1546.6702 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1547.4302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1553.4302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1556.4302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1557.5702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 1560.5702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1566.5702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1569.5702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1571.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1577.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1580.0902 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1581.0902 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1582.5902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1588.5902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1589.5902 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1590.5902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1592.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1595.5902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1596.5902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1598.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1601.5902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1602.5902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1604.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1607.5902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1607.9068 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1612.9068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1613.2235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1616.2235 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1616.6035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1622.6035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1625.6035 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1626.3635 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1632.3635 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1635.3635 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1636.5035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1642.5035 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1645.5035 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1647.0235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1653.0235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1656.0235 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1657.0235 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1658.5235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1664.5235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1665.5235 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1666.5235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1668.0235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1671.5235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1672.5235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1674.0235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1677.5235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1678.5235 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1680.0235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1683.5235 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1683.8402 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1688.8402 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1689.1568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1692.1568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1692.5368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1698.5368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1701.5368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1702.2968 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1708.2968 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1711.2968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1712.4368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1718.4368 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1721.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1722.9568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1728.9568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1731.9568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1732.9568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1734.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1740.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1741.4568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1742.4568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1743.9568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1747.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1748.4568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1749.9568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1753.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1754.4568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1755.9568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1759.4568 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1759.7735 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1764.7735 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1765.0902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1768.0902 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1768.4702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1774.4702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1777.4702 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1778.2302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1784.2302 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1787.2302 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1788.3702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1794.3702 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1797.3702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1798.8902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1804.8902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 1807.8902 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1808.8902 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 1810.3902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 1816.3902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 1817.3902 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1818.3902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1819.8902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1823.3902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1824.3902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1825.8902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1829.3902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 1830.3902 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 1831.8902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 1835.3902 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1835.7068 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1838.9501 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1842.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1846.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1850.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1854.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1858.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1860.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1861.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1863.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1867.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1871.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1875.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1879.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1883.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1884.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1886.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1887.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1891.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1895.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1899.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1903.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1907.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1909.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1910.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1912.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1916.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1920.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1924.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1928.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1932.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1933.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1935.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1936.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1940.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1944.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1948.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1952.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1956.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1958.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1959.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1961.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1965.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1969.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1973.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1977.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1981.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1982.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1984.4501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1985.9501 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1989.1933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1994.1933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1994.51 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1997.51 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1997.89 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2003.89 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2006.89 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2007.65 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2013.65 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2016.65 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2017.79 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2021.79 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2027.79 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2030.79 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2032.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2038.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2041.31 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2042.31 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2043.81 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2049.81 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2050.81 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2051.81 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2053.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2056.81 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2057.81 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2059.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2062.81 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2063.81 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2065.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2068.81 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2069.1266 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2074.1266 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2074.4433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2077.4433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2077.8233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2083.8233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2086.8233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2087.5833 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2093.5833 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2096.5833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2097.7233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2103.7233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2106.7233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2108.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2114.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2117.2433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2118.2433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2119.7433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2125.7433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2126.7433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2127.7433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2129.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2132.7433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2133.7433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2135.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2138.7433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2139.7433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2141.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2144.7433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2145.06 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2150.06 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2150.3766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2153.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2153.7566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2159.7566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2162.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2163.5166 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2169.5166 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2172.5166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2173.6566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2179.6566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2182.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2184.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2190.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2193.1766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2194.1766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2195.6766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2201.6766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2202.6766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2203.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2205.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2208.6766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2209.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2211.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2214.6766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2215.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2217.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2220.6766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2220.9933 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2225.9933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2226.31 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2229.31 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2229.69 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2235.69 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2238.69 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2239.45 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2245.45 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2248.45 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2249.59 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2255.59 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2258.59 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2260.11 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2266.11 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2269.11 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2270.11 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2271.61 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2277.61 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2278.61 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2279.61 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2281.11 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2284.61 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2285.61 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2287.11 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2290.61 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2291.61 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2293.11 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2296.61 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2296.9266 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2301.9266 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2302.2433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2305.2433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2305.6233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2311.6233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2314.6233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2315.3833 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2321.3833 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2324.3833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2325.5233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2331.5233 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2334.5233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2336.0433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2342.0433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2345.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2346.0433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2347.5433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2353.5433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2354.5433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2355.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2357.0433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2360.5433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2361.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2363.0433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2366.5433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2367.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2369.0433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2372.5433 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2372.86 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2377.86 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2378.1766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2381.1766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2381.5566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2387.5566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2390.5566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2391.3166 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2397.3166 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2400.3166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2401.4566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2407.4566 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2410.4566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2411.9766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2417.9766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2420.9766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2421.9766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2423.4766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2429.4766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2430.4766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2431.4766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2432.9766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2436.4766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2437.4766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2438.9766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2442.4766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2443.4766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2444.9766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2448.4766 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2448.7933 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2452.0365 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2456.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2460.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2464.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2468.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2472.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2473.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2475.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2476.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2480.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2484.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2488.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2492.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2496.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2498.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2499.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2501.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2505.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2509.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2513.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2517.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2521.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2522.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2524.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2525.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2529.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2533.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2537.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2541.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2545.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2547.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2548.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2550.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2554.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2558.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2562.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2566.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2570.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2571.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2573.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2574.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2578.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2582.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2586.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2590.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2594.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2596.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2597.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2599.0365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2602.2798 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2607.2798 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2607.5965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2610.5965 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2610.9765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2616.9765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2619.9765 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2620.7365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2626.7365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2629.7365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2630.8765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2636.8765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2639.8765 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2641.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2647.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2650.3965 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2651.3965 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2652.8965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2658.8965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2659.8965 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2660.8965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2662.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2665.8965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2666.8965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2668.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2671.8965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2672.8965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2674.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2677.8965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2678.2131 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2683.2131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2683.5298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2686.5298 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2686.9098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2692.9098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2695.9098 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2696.6698 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2702.6698 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2705.6698 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2706.8098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2712.8098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2715.8098 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2717.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2723.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2726.3298 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2727.3298 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2728.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2734.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2735.8298 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2736.8298 | TurbineInstallation
| WTIV | Delay | 33 | 550000 | ACTION | 2769.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2771.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 9 | 150000 | ACTION | 2780.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2783.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2784.8298 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2786.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2789.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2790.8298 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2792.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2795.8298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2796.1465 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2801.1465 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2801.4631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2804.4631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2804.8431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2810.8431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2813.8431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2814.6031 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2820.6031 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2823.6031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2824.7431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2830.7431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2833.7431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2835.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2841.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2844.2631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2845.2631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2846.7631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2852.7631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2853.7631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2854.7631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2856.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2859.7631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2860.7631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2862.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2865.7631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2866.7631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2868.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2871.7631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2872.0798 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2877.0798 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2877.3965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2880.3965 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2880.7765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2886.7765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2889.7765 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2890.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2896.5365 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2899.5365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2900.6765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2906.6765 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2909.6765 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2911.1965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2917.1965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2920.1965 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2921.1965 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2922.6965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2928.6965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2929.6965 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2930.6965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2932.1965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2935.6965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2936.6965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2938.1965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2941.6965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2942.6965 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2944.1965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2947.6965 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2948.0131 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2953.0131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2953.3298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2956.3298 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2956.7098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2962.7098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2965.7098 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2966.4698 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2972.4698 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2975.4698 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2976.6098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2982.6098 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2985.6098 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2987.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2993.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2996.1298 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2997.1298 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2998.6298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3004.6298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3005.6298 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3006.6298 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3008.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3011.6298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3012.6298 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3014.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 19 | 316666.6667 | ACTION | 3033.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3036.6298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3037.6298 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3039.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 12 | 200000 | ACTION | 3051.1298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3054.6298 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3054.9465 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3059.9465 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3060.2631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3063.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3063.6431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3069.6431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3072.6431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3073.4031 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3079.4031 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3082.4031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3083.5431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3089.5431 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3092.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3094.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3100.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3103.0631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3104.0631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3105.5631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3111.5631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3112.5631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3113.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3115.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3118.5631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3119.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3121.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3124.5631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3125.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3127.0631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3130.5631 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3130.8798 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3134.123 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3138.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3142.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3146.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3150.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3154.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3155.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3157.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3158.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3162.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3166.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3170.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3174.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3178.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3180.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3181.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3183.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3187.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3191.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3195.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3199.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3203.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3204.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3206.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3207.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3211.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3215.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3219.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3223.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3227.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3229.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3230.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3232.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3236.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3240.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3244.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3248.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3252.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3253.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3255.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3256.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3260.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3264.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3268.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3272.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3276.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3278.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3279.623 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3281.123 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3284.3663 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3289.3663 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3289.6829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3292.6829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3293.0629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3299.0629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3302.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3302.8229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3308.8229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3311.8229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3312.9629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3318.9629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3321.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3323.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3329.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3332.4829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3333.4829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3334.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 17 | 283333.3333 | ACTION | 3351.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3357.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3358.9829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3359.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3361.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3364.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3365.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3367.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3370.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3371.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3373.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3376.9829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3377.2996 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3382.2996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3382.6163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3385.6163 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3385.9963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3391.9963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3394.9963 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3395.7563 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3401.7563 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3404.7563 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3405.8963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3411.8963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3414.8963 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3416.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3422.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3425.4163 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3426.4163 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3427.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3434.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3440.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3441.9163 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3442.9163 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3444.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3447.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3448.9163 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3450.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3453.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3454.9163 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3456.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3459.9163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3460.2329 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3465.2329 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3465.5496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3468.5496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3468.9296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3474.9296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3477.9296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3478.6896 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3484.6896 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3487.6896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3488.8296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3494.8296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3497.8296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3499.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3505.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3508.3496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3509.3496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3510.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3516.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3517.8496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3518.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3520.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3523.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3524.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3526.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3529.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3530.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3532.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3539.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3542.8496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3543.1663 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3548.1663 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3548.4829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3551.4829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3551.8629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3557.8629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3560.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3561.6229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3567.6229 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3570.6229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3571.7629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3577.7629 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3580.7629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3582.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3588.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3591.2829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3592.2829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3593.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3599.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3600.7829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3601.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3603.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3606.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3607.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3609.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3611.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3614.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3615.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3617.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 3630.2829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3633.7829 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3634.0996 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3639.0996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3639.4163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3642.4163 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3642.7963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3648.7963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3651.7963 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3652.5563 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3658.5563 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3661.5563 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 3703.5563 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3704.6963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3710.6963 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3713.6963 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3715.2163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3721.2163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3724.2163 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3725.2163 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3726.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3732.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3733.7163 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3734.7163 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3736.2163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3739.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3740.7163 | TurbineInstallation
| WTIV | Delay | 28 | 466666.6667 | ACTION | 3768.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3770.2163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3773.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3774.7163 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3776.2163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3779.7163 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3780.0329 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3785.0329 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3785.3496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3788.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3788.7296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3794.7296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3797.7296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3798.4896 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3804.4896 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3807.4896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3808.6296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3814.6296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3817.6296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3819.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3825.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3828.1496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3829.1496 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3831.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3832.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3840.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3846.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3847.6496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3848.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3850.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3853.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3854.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3856.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3859.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3860.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3862.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3866.1496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3869.6496 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3869.9663 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3873.2095 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3877.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3881.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3885.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3889.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3893.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3894.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3896.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3897.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3901.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3905.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3909.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3913.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3917.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3919.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3920.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3922.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3926.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3930.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3934.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3938.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3942.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3943.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3945.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3946.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3950.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3954.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3958.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3962.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3966.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3968.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3969.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3971.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3975.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3979.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3983.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3987.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3991.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3992.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3994.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3995.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3999.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4003.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4007.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4011.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4015.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4017.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4019.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4020.7095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4022.2095 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4025.4528 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 4040.4528 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4045.4528 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4045.7694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4048.7694 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 4061.7694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4062.1494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4068.1494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4071.1494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4071.9094 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4077.9094 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4080.9094 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4082.9094 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4084.0494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4090.0494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4093.0494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4094.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4100.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4103.5694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4104.5694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4106.0694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4112.0694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4113.0694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4114.0694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4115.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4119.0694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4120.0694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4121.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4125.0694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4126.0694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4127.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4131.0694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4131.3861 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4136.3861 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4136.7028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4139.7028 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4140.0828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4146.0828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4149.0828 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4149.8428 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4155.8428 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4158.8428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4159.9828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4165.9828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4168.9828 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4170.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4176.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4179.5028 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4180.5028 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4182.0028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4188.0028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4189.0028 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4190.0028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4191.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4195.0028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4196.0028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4197.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 4203.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4207.0028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4208.0028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4209.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4213.0028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4213.3194 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4218.3194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4218.6361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4221.6361 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4222.0161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4228.0161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4231.0161 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4231.7761 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4237.7761 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4240.7761 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4241.9161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4247.9161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4250.9161 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4252.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4258.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4261.4361 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4262.4361 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4263.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4269.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4270.9361 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4271.9361 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4279.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4281.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4283.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4286.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4287.9361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4289.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4292.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4293.9361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4295.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4298.9361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4299.2528 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4304.2528 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4304.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4307.5694 | TurbineInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 4328.5694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4328.9494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4334.9494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4337.9494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4338.7094 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4344.7094 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4347.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4348.8494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4354.8494 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4357.8494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4359.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4365.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4368.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4369.3694 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4371.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4372.8694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4378.8694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4379.8694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4380.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4382.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4385.8694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4386.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4388.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 15 | 250000 | ACTION | 4403.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4406.8694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4407.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4409.3694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4412.8694 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4413.1861 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4418.1861 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4418.5028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4421.5028 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4421.8828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4427.8828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4430.8828 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4431.6428 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4437.6428 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4440.6428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4441.7828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4447.7828 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4450.7828 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4452.3028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4458.3028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4461.3028 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4462.3028 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4463.8028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4469.8028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4470.8028 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4471.8028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4473.3028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4476.8028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4477.8028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4479.3028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4482.8028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4483.8028 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4485.3028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4488.8028 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4489.1194 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 62 | 1033333.3333 | ACTION | 4551.1194 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4556.1194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4556.4361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4559.4361 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4559.8161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4565.8161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4568.8161 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4569.5761 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4575.5761 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4578.5761 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4579.7161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 27 | 450000 | ACTION | 4606.7161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4612.7161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4615.7161 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4699.7161 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4701.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4703.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4709.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4712.2361 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4713.2361 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4714.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4720.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4721.7361 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4722.7361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4724.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4727.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4728.7361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4730.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4733.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4734.7361 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4736.2361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4739.7361 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4740.0528 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4743.296 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4747.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4751.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4755.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4759.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4763.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4764.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4766.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4767.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4771.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4775.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4779.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4783.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4787.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4789.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4790.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4792.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4796.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4800.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4804.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4808.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4812.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4813.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4815.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4816.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4820.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4834.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4838.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4842.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4846.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4850.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4852.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4853.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4855.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4859.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4863.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4867.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4871.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4875.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4876.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4878.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4879.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4883.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4887.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4891.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4895.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4899.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4901.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4902.796 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4904.296 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4907.5393 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4912.5393 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4912.8559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4915.8559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4916.2359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4922.2359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4925.2359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4925.9959 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4931.9959 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4934.9959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4936.1359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4942.1359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4945.1359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4946.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4952.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4955.6559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4956.6559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4958.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4964.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4965.1559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4966.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4967.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4971.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4972.1559 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 4983.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4984.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4988.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4989.1559 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4992.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4993.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4997.1559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4997.4726 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5002.4726 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5002.7893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5005.7893 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5006.1693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5012.1693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5015.1693 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5015.9293 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5021.9293 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5024.9293 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 5030.9293 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5032.0693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5038.0693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5041.0693 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5042.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5048.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5051.5893 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5052.5893 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5054.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5060.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5061.0893 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5062.0893 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5066.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5067.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5071.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5072.0893 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5073.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5077.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5078.0893 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5079.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5083.0893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5083.4059 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5088.4059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5088.7226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5091.7226 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5092.1026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5098.1026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5101.1026 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5101.8626 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5107.8626 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5110.8626 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5112.0026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5118.0026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5121.0026 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5122.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5128.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5131.5226 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5132.5226 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5134.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5140.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5141.0226 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5142.0226 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5143.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5147.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5148.0226 | TurbineInstallation
| WTIV | Delay | 1262 | 21033333.3333 | ACTION | 6410.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6411.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6415.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6416.0226 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6417.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6421.0226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6421.3393 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6426.3393 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6426.6559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6429.6559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6430.0359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6432.0359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6438.0359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6441.0359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6441.7959 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6447.7959 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6450.7959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6451.9359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6457.9359 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6460.9359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6462.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6468.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6471.4559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6472.4559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6473.9559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6479.9559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6480.9559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6481.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6483.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6486.9559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6487.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6489.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6492.9559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6493.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6495.4559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6498.9559 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6499.2726 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6504.2726 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6504.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 6507.5893 | TurbineInstallation
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6510.5893 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6517.5893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6517.9693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6523.9693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6526.9693 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6527.7293 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6533.7293 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6536.7293 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6537.8693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6543.8693 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6546.8693 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6548.3893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6554.3893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6557.3893 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6558.3893 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6559.8893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6565.8893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6566.8893 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6567.8893 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6569.3893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6572.8893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6573.8893 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6575.3893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6578.8893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6579.8893 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6581.3893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6584.8893 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6585.2059 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6590.2059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6590.5226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6593.5226 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6593.9026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6599.9026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6602.9026 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6603.6626 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6609.6626 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6612.6626 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6613.8026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6619.8026 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6622.8026 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6624.3226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6630.3226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6633.3226 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6634.3226 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6635.8226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6641.8226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6642.8226 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6643.8226 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6645.3226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6648.8226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6649.8226 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6651.3226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6654.8226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6655.8226 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6657.3226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6660.8226 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6661.1393 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3 | 50000 | ACTION | 6664.1393 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6665.1393 | TurbineInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 6665.3825 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6669.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6673.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6677.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6681.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6685.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6686.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6688.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6689.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6693.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6697.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6701.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6705.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6709.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6711.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6712.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6714.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6718.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6722.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6726.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6730.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6734.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6735.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6737.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6738.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6742.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 6745.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6749.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6753.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6757.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6761.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6763.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6764.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6766.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6770.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6774.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6778.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6782.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6786.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6787.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6789.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6790.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6794.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6798.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6802.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6806.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6810.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6812.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6813.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6820.8825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6822.3825 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6825.6257 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6830.6257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6830.9424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6833.9424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6834.3224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6840.3224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6843.3224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6844.0824 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6850.0824 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6853.0824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6854.2224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6860.2224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6863.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6864.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6870.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6873.7424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6874.7424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6876.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6882.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6883.2424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6884.2424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6885.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6889.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6890.2424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6891.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6895.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6896.2424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6897.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6901.2424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6901.5591 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6906.5591 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6906.8757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6909.8757 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6913.8757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6914.2557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6916.2557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6922.2557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6925.2557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6926.0157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6932.0157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6935.0157 | TurbineInstallation
| WTIV | Delay | 41 | 683333.3333 | ACTION | 6976.0157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6977.1557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6984.1557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6990.1557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6993.1557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6994.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7000.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7003.6757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7004.6757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7006.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7012.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7013.1757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7014.1757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7015.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7019.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7020.1757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7021.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7025.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7026.1757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7027.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7031.1757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7031.4924 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7036.4924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7036.8091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7039.8091 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7040.1891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7046.1891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7049.1891 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7050.1891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7050.9491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 7092.9491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7098.9491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7101.9491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7103.0891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7109.0891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7112.0891 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7113.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7119.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7122.6091 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7123.6091 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7125.1091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7131.1091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7132.1091 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7133.1091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7134.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7138.1091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7139.1091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7140.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7144.1091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7145.1091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7146.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7150.1091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7150.4257 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7155.4257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7155.7424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7158.7424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7159.1224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7165.1224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7168.1224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7168.8824 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7174.8824 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7177.8824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7179.0224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7185.0224 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7188.0224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7189.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7195.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7198.5424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7199.5424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7201.0424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7207.0424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7208.0424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7209.0424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7210.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 20 | 333333.3333 | ACTION | 7230.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7234.0424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7235.0424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7236.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7240.0424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7241.0424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7242.5424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7246.0424 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7246.3591 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7251.3591 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7251.6757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7254.6757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7255.0557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7261.0557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7264.0557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7264.8157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7270.8157 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7273.8157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7274.9557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7280.9557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7283.9557 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 7298.9557 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7300.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7307.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7313.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7316.4757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7317.4757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7318.9757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7324.9757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7325.9757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7326.9757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7328.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7331.9757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7332.9757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7334.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 7352.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7355.9757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7356.9757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7358.4757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7361.9757 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7362.2924 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7367.2924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7367.6091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7370.6091 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7370.9891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7376.9891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7379.9891 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7380.7491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7386.7491 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7389.7491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7390.8891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7396.8891 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7399.8891 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7401.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 65 | 1083333.3333 | ACTION | 7466.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7472.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7475.4091 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7476.4091 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7477.9091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7483.9091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7484.9091 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7485.9091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7487.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7490.9091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7491.9091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7493.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7496.9091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7497.9091 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7499.4091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7502.9091 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7503.2257 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7506.469 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7510.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7514.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7518.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7522.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7526.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7527.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7529.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7530.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7534.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7538.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7542.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7546.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7550.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7552.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7553.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7555.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7559.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7563.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7567.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7571.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7575.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7576.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7578.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7579.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7583.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7587.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7591.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7595.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7599.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7601.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7602.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7604.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7608.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7612.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7616.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7620.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7624.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7625.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7627.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7628.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7632.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7636.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7640.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7644.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7648.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7650.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7651.969 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7653.469 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7656.7122 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7661.7122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7662.0289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7665.0289 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7665.4089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7671.4089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7674.4089 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7675.4089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7676.1689 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7682.1689 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7685.1689 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7686.3089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7692.3089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7695.3089 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7696.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7702.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7705.8289 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7706.8289 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7708.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7714.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7715.3289 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7716.3289 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 7725.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7726.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7730.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7731.3289 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7732.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7733.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7737.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7738.3289 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7739.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7743.3289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7743.6456 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7748.6456 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7748.9622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7751.9622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7752.3422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7758.3422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7761.3422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7762.1022 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7768.1022 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7771.1022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7772.2422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7778.2422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7781.2422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7782.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7788.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7791.7622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7792.7622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7794.2622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7800.2622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7801.2622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7802.2622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7807.2622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7808.2622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7809.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7813.2622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7814.2622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7815.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7819.2622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7819.5789 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7824.5789 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7824.8956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7827.8956 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7828.2756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7834.2756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7837.2756 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7838.0356 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7844.0356 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7847.0356 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7848.1756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7854.1756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7857.1756 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7858.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7864.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7867.6956 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7868.6956 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7870.1956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7876.1956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7877.1956 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7878.1956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7879.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7883.1956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7884.1956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7885.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7889.1956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7890.1956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7891.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7895.1956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7895.5122 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7900.5122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7900.8289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7903.8289 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7904.2089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7910.2089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7913.2089 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7913.9689 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7919.9689 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7922.9689 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7924.1089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7930.1089 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7933.1089 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7934.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7940.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7943.6289 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7944.6289 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7946.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7948.1289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7954.1289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7955.1289 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7956.1289 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7957.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7961.1289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7962.1289 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7963.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7967.1289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7968.1289 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7969.6289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7973.1289 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7973.4456 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7978.4456 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7978.7622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7981.7622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7982.1422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7988.1422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7991.1422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7991.9022 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7997.9022 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8000.9022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8002.0422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8008.0422 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8011.0422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8012.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8018.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8021.5622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8022.5622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8024.0622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8030.0622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8031.0622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8032.0622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8033.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8037.0622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8038.0622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8039.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 8052.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8056.0622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8057.0622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8058.5622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8062.0622 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8062.3789 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8067.3789 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8067.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8070.6956 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8071.6956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8072.0756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8073.0756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8079.0756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8082.0756 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8084.0756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8084.8356 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8086.8356 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8092.8356 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8095.8356 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8096.9756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8102.9756 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8105.9756 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8107.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8113.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8116.4956 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8117.4956 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8118.9956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8124.9956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8125.9956 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8126.9956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8128.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 44 | 733333.3333 | ACTION | 8172.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8175.9956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8176.9956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8178.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8182.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8185.9956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8186.9956 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8188.4956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8191.9956 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8192.3122 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8195.5555 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8199.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8203.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8207.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8211.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8215.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8217.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8218.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8220.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8224.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8228.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8232.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8236.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8240.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8241.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8243.0555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8244.5555 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8247.7987 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8252.7987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8253.1154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8256.1154 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8256.4954 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8262.4954 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8265.4954 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8266.2554 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8272.2554 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8275.2554 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8276.3954 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8282.3954 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8285.3954 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8286.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 31 | 516666.6667 | ACTION | 8317.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8323.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8326.9154 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8327.9154 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8329.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 8342.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8348.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8349.4154 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8350.4154 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8351.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8355.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8356.4154 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8357.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8361.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8362.4154 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8363.9154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8367.4154 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8367.732 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8372.732 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8373.0487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8376.0487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8376.4287 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8380.4287 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8386.4287 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8389.4287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8390.1887 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8396.1887 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8399.1887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8400.3287 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8406.3287 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8409.3287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8410.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8416.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8419.8487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8420.8487 | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 8452.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8454.3487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8460.3487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8461.3487 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8462.3487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8463.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8467.3487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8468.3487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8469.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8473.3487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8474.3487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8475.8487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8479.3487 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8479.6654 | TurbineInstallation | TurbineInstallation | 5 |  | 22.5 | 150