## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 83.2432 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 85.2432 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 86.9099 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay: Not enough vessels for monopiles | 83.6667 | 871527.7778 | ACTION | 86.9099 | MonopileInstallation |  |  | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 106.9099 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 107.2266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 108.2266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 111.2266 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 111.9496 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 111.9529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 112.9529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 114.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 116.4529 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 117.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 118.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 122.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 122.7696 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 142.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 143.0862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 144.0862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 147.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 147.8093 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 147.8125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 148.8125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 150.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 152.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 153.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 154.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 158.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 158.6292 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 163.2432 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 165.2432 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 166.9099 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 178.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 178.9459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 179.9459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 182.9459 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 183.9459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 184.6689 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 187.6689 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 187.6722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 188.6722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 190.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 192.1722 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 193.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 196.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 197.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 23 | 239583.3333 | ACTION | 220.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 224.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 224.4889 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 244.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 244.8055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 245.8055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 248.8055 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 249.5286 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 249.5318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 250.5318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 252.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 254.0318 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 167.1219 | 835609.644 | ACTION | 254.0318 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 255.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 255.6985 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 256.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 258.9417 | MonopileInstallation
| Feeder 1 | Queue | 92.0318 | 460159.1936 | ACTION | 258.9417 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 260.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 260.3485 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 270.9417 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 278.9417 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 280.3485 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 280.6652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 281.6652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 284.6652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 285.3882 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 285.3915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 286.3915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 287.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 289.8915 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 290.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 290.9417 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 291.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 295.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 296.2082 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 298.9417 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 310.9417 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 316.2082 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 316.5248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 317.5248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 318.9417 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 320.5248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 321.2479 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 321.2511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 322.2511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 323.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 325.7511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 326.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 327.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 330.9417 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 331.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 332.0678 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 338.9417 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 342.185 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 344.185 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 345.8517 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 352.0678 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 352.3845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 353.3845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 356.3845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 357.1075 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 357.1108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 358.1108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 359.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 361.6108 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 362.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 363.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 367.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 367.9275 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 387.9275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 388.2441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 389.2441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 392.2441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 392.9672 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 392.9704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 393.9704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 395.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 397.4704 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 397.4704 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 398.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 399.1371 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 399.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 402.3803 | MonopileInstallation
| Feeder 0 | Queue | 56.5287 | 282643.4278 | ACTION | 402.3803 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 403.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 403.7871 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 414.3803 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 422.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 423.7871 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 424.1038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 425.1038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 428.1038 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 428.8268 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 428.8301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 429.8301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 434.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay | 10 | 104166.6667 | ACTION | 439.8301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 441.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 443.3301 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 444.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 445.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 449.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 449.6467 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 453.6467 | MonopileInstallation
| Feeder 1 | Delay | 24 | 120000 | ACTION | 458.3803 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 466.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 473.6467 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 473.9634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 474.9634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 477.9634 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 478.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 478.6865 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 478.6897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 479.6897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 481.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 483.1897 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 484.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 485.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 486.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 489.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 489.5064 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 498.3803 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 506.3803 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 509.5064 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 509.6236 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 509.8231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 510.8231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 511.6236 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 513.2903 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 513.8231 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 514.5461 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 514.5494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 515.5494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 517.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 519.0494 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 520.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 521.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 525.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 525.366 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 545.366 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 545.6827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 546.6827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 549.6827 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 550.4058 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 550.409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 551.409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 552.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 554.909 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 152.5287 | 762643.4278 | ACTION | 554.909 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 555.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 556.5757 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 556.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 559.8189 | MonopileInstallation
| Feeder 1 | Queue | 46.5287 | 232643.4278 | ACTION | 559.8189 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 560.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 561.2257 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 571.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 579.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 581.2257 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 581.5424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 582.5424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 585.5424 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 586.2654 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 586.2687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 587.2687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 588.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 590.7687 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 591.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 591.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 592.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 596.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 597.0853 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 599.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 611.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 617.0853 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 617.402 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 618.402 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 619.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 621.402 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 622.1251 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 622.1283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 623.1283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 624.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 626.6283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 627.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 628.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 631.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 632.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 632.945 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 639.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 643.0622 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 645.0622 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 646.7288 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 652.945 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 653.2617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 654.2617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 657.2617 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 657.9847 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 657.988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 658.988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 660.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 662.488 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 663.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 664.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 668.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 668.8046 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 688.8046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 689.1213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 690.1213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 693.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 693.8444 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 693.8476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 694.8476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 696.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 698.3476 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 698.3476 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 699.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 700.0143 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 700.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 703.2575 | MonopileInstallation
| Feeder 0 | Queue | 56.5287 | 282643.4278 | ACTION | 703.2575 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 704.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 704.6643 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 715.2575 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 723.2575 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 724.6643 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 724.981 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 725.981 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 728.981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 729.704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 729.7073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 730.7073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 732.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 734.2073 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 735.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 735.2575 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 736.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 740.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 740.5239 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 743.2575 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 755.2575 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 760.5239 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 760.8406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 761.8406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 763.2575 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 764.8406 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 766.8406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 767.5637 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 767.5669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 768.5669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 770.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 772.0669 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 773.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 774.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 775.2575 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 778.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 778.3836 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 783.2575 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 786.5008 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 788.5008 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 790.1674 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 798.3836 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 798.7003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 799.7003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 802.7003 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 803.4233 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 803.4266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 804.4266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 805.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 807.9266 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 808.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 809.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 813.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 814.2432 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 834.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 834.5599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 835.5599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 838.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 839.283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 839.2862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 840.2862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 841.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 843.7862 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 140.5287 | 702643.4278 | ACTION | 843.7862 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 844.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 845.4529 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 845.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 848.6961 | MonopileInstallation
| Feeder 1 | Queue | 58.5287 | 292643.4278 | ACTION | 848.6961 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 849.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 850.1029 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 860.6961 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 868.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 870.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 870.4196 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 871.4196 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 874.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 875.1426 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 875.1459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 876.1459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 877.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 879.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 880.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 880.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 881.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Delay | 5 | 25000 | ACTION | 885.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay | 6 | 62500 | ACTION | 887.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 891.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 891.9625 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 893.6961 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 905.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 911.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 912.2792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 913.2792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 913.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 916.2792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 917.0023 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 917.0055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 918.0055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 919.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 921.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 922.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 923.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 925.6961 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 927.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 927.8222 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 933.6961 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 936.9394 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 938.9394 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 940.606 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 947.8222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 948.1389 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 949.1389 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 952.1389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 952.8619 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 952.8652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 953.8652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 955.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 957.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 958.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 959.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 963.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 963.6818 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 983.6818 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 983.9985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 984.9985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 987.9985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 988.7216 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 988.7248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 989.7248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 991.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 993.2248 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 144.5287 | 722643.4278 | ACTION | 993.2248 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 994.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 994.8915 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 995.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 998.1347 | MonopileInstallation
| Feeder 0 | Queue | 57.5287 | 287643.4278 | ACTION | 998.1347 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 999.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 999.5415 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1010.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1018.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1019.5415 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1019.8581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1020.8581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1023.8581 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1024.5812 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1024.5845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1025.5845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1027.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1029.0845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1030.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1030.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1031.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1035.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1035.4011 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1038.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1050.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1055.4011 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1055.7178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1056.7178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1058.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1059.7178 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1060.4409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1060.4441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1061.4441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1062.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1064.9441 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1065.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1066.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1070.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1070.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1071.2608 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1078.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1081.378 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1083.378 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1085.0446 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1091.2608 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1091.5774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1092.5774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1095.5774 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1096.3005 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1096.3038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1097.3038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1098.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1100.8038 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1101.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1102.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1106.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1107.1204 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1127.1204 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1127.4371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1128.4371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1131.4371 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1132.1602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1132.1634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1133.1634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1134.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1136.6634 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 1136.6634 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1137.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1138.3301 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1138.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1141.5733 | MonopileInstallation
| Feeder 1 | Queue | 56.5287 | 282643.4278 | ACTION | 1141.5733 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1142.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1142.9801 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1153.5733 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1161.5733 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1162.9801 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1163.2967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1164.2967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1167.2967 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1168.0198 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1168.0231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1169.0231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1170.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1172.5231 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1173.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1173.5733 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1174.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1178.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1178.8397 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1181.5733 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1193.5733 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1198.8397 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1199.1564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1200.1564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1201.5733 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1203.1564 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1203.8795 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1203.8827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1204.8827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1206.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1208.3827 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1209.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1210.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1213.5733 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1214.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1214.6994 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1221.5733 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1224.8166 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 1226.8166 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 1228.4832 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1234.6994 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1235.016 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1236.016 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1239.016 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1239.7391 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1239.7424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1240.7424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1242.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1244.2424 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1245.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1246.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1250.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1250.559 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1270.559 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1270.8757 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1271.8757 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1274.8757 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1275.5988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1275.602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1276.602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1278.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1280.102 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 1280.102 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1281.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1281.7687 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1282.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1285.0119 | MonopileInstallation
| Feeder 0 | Queue | 56.5287 | 282643.4278 | ACTION | 1285.0119 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1286.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1286.4187 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1297.0119 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1305.0119 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1306.4187 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1306.7353 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1307.7353 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1310.7353 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1311.4584 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1311.4617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1312.4617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1313.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1315.9617 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1316.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1317.0119 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1317.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1318.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1322.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1323.2783 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1325.0119 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1337.0119 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1343.2783 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1343.595 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1344.595 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1345.0119 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1347.595 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1348.3181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1348.3213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1349.3213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1350.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1352.8213 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1353.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1354.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1357.0119 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1358.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1359.138 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1365.0119 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1368.2552 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1370.2552 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1371.9218 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1379.138 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1379.4546 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1380.4546 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1383.4546 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1384.1777 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1384.181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1385.181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1386.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1388.681 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1389.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1390.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1394.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1394.9976 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1414.9976 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1415.3143 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1416.3143 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1419.3143 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1420.0374 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1420.0406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1421.0406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1422.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1424.5406 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 139.5287 | 697643.4278 | ACTION | 1424.5406 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1425.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1426.2073 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1426.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1429.4505 | MonopileInstallation
| Feeder 1 | Queue | 57.5287 | 287643.4278 | ACTION | 1429.4505 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1430.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1430.8573 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1441.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1449.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1450.8573 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1451.1739 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1452.1739 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1455.1739 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1455.897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1455.9003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1456.9003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1458.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1460.4003 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1461.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1461.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1462.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1466.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1466.7169 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1469.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1481.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1486.7169 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1487.0336 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1488.0336 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1489.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1491.0336 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1491.7567 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1491.7599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1492.7599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1494.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1496.2599 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1497.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1498.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1501.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1502.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1502.5766 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1509.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1512.6938 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 1514.6938 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 1516.3604 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1522.5766 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1522.8932 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1523.8932 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1526.8932 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1527.6163 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1527.6195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1528.6195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1530.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1532.1195 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1533.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1534.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1538.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1538.4362 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1558.4362 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1558.7529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1559.7529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1562.7529 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1563.4759 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1563.4792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1564.4792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1565.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1567.9792 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 1567.9792 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1568.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1569.6459 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1569.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1572.8891 | MonopileInstallation
| Feeder 0 | Queue | 56.5287 | 282643.4278 | ACTION | 1572.8891 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1573.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1574.2959 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1584.8891 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1592.8891 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1594.2959 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1594.6125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1595.6125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1598.6125 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1599.3356 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1599.3388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1600.3388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1601.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1603.8388 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1604.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1604.8891 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1605.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1609.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1610.1555 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1612.8891 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1624.8891 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1630.1555 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1630.4722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1631.4722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1632.8891 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1634.4722 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1635.1952 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1635.1985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1636.1985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1637.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1639.6985 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1640.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1641.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1644.8891 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1645.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1646.0152 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1652.8891 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1656.1324 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1658.1324 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1659.799 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1666.0152 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1666.3318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1667.3318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1670.3318 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1671.0549 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1671.0581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1672.0581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1673.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1675.5581 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1676.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1677.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1681.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1681.8748 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1701.8748 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1702.1915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1703.1915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1706.1915 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1706.9145 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1706.9178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1707.9178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1709.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1711.4178 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 1711.4178 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1712.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1713.0845 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1713.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1716.3277 | MonopileInstallation
| Feeder 1 | Queue | 56.5287 | 282643.4278 | ACTION | 1716.3277 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1717.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1717.7345 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1728.3277 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1736.3277 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1737.7345 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1738.0511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1739.0511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1742.0511 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1742.7742 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1742.7774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1743.7774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1745.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1747.2774 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1748.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1748.3277 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1749.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1753.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1753.5941 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1756.3277 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1773.5941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1773.9108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1774.9108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1777.9108 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1778.6338 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1778.6371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1779.6371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1781.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1783.1371 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1784.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1785.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1789.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1789.4538 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1809.4538 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1809.7704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1810.7704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1813.7704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1814.4935 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1814.4967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1815.4967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1816.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1818.9967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1819.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1820.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1824.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1825.3134 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1845.3134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1845.6301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1846.6301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1849.6301 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1850.3531 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1850.3564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1851.3564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1852.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1854.8564 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 138.5287 | 692643.4278 | ACTION | 1854.8564 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1855.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1856.5231 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1856.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1859.7663 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1860.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1861.1731 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 1861.1731 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1865.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1869.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1873.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1877.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1881.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1882.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1884.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1885.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1889.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1893.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1897.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1901.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1905.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1907.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1908.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1910.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1914.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1918.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1922.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1926.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1930.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1931.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1933.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1934.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1937.9163 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 1957.9163 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1958.233 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1961.233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 1961.613 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 1965.613 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1971.613 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1974.613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 1975.373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1981.373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1984.373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 1985.513 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 1991.513 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 1994.513 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 1996.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2002.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2005.033 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2006.033 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2007.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2013.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2014.533 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2015.533 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2017.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 2021.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2024.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2025.533 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2027.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2030.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2031.533 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2033.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2036.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2036.8496 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2056.8496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2057.1663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2060.1663 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2060.5463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2066.5463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2069.5463 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2070.3063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2076.3063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2079.3063 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2080.4463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2086.4463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2089.4463 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2090.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2096.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2099.9663 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2100.9663 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2102.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2108.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2109.4663 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2110.4663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2111.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2115.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2116.4663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2117.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2121.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2122.4663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2123.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2127.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2127.783 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2147.783 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2148.0996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2151.0996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2151.4796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2157.4796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2160.4796 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2161.2396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2167.2396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2170.2396 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2171.3796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2177.3796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2180.3796 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2181.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2187.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2190.8996 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2191.8996 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2193.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2199.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2200.3996 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2201.3996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2202.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2206.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2207.3996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2208.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2212.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2213.3996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2214.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2218.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2218.7163 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2221.9595 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2225.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2229.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2233.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2237.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2241.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2243.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2244.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2246.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2250.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2254.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2258.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2262.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2266.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2267.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2269.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2270.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2274.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2278.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2282.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2286.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2290.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2292.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2293.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2295.4595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2298.7028 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2318.7028 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2319.0195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2322.0195 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2322.3995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2328.3995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2331.3995 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2332.1595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2338.1595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2341.1595 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2342.2995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2348.2995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2351.2995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2352.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2358.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2361.8195 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2362.8195 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2364.3195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2370.3195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2371.3195 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2372.3195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2373.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2377.3195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2378.3195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2379.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2383.3195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2384.3195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2385.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2389.3195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2389.6361 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2409.6361 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2409.9528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2412.9528 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2413.3328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2419.3328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2422.3328 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2423.0928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2429.0928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2432.0928 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2433.2328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2439.2328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2442.2328 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2443.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2449.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2452.7528 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2453.7528 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2455.2528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2461.2528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2462.2528 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2463.2528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2464.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2468.2528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2469.2528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2470.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2474.2528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2475.2528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2476.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2480.2528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2480.5695 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2500.5695 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2500.8861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2503.8861 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2504.2661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2510.2661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2513.2661 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2514.0261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2520.0261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2523.0261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2524.1661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2530.1661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2533.1661 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2534.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2540.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2543.6861 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2544.6861 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2546.1861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2552.1861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2553.1861 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2554.1861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2555.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2559.1861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2560.1861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2561.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2565.1861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2566.1861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2567.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2571.1861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2571.5028 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2574.746 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2578.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2582.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2586.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2590.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2594.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2596.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2597.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2599.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2603.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2607.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2611.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2615.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2619.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2620.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2622.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2623.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2627.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2631.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2635.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2639.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2643.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2645.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2646.746 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2648.246 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2651.4893 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2671.4893 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2671.8059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2674.8059 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2675.1859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2681.1859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2684.1859 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2684.9459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2690.9459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2693.9459 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2695.0859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2701.0859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2704.0859 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2705.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2711.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2714.6059 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2715.6059 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2717.1059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2723.1059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2724.1059 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2725.1059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2726.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2730.1059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2731.1059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2732.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 47 | 783333.3333 | ACTION | 2779.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2783.1059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2784.1059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2785.6059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2789.1059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2789.4226 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2809.4226 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2809.7393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2812.7393 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2813.1193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2819.1193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2822.1193 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2822.8793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2828.8793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2831.8793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2833.0193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2839.0193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2842.0193 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2843.5393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2849.5393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2852.5393 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2853.5393 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2855.0393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2861.0393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2862.0393 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2863.0393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2864.5393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2868.0393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2869.0393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2870.5393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2874.0393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2875.0393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2876.5393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2880.0393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2880.3559 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2900.3559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2900.6726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2903.6726 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2904.0526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2910.0526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2913.0526 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2913.8126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2919.8126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2922.8126 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2923.9526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2929.9526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2932.9526 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2934.4726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2940.4726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2943.4726 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2944.4726 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2945.9726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2951.9726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2952.9726 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2953.9726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2955.4726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2958.9726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2959.9726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2961.4726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2964.9726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2965.9726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2967.4726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2970.9726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2971.2893 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2974.5325 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2978.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2982.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2986.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2990.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2994.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2996.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2997.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2999.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3003.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3007.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3011.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 22 | 366666.6667 | ACTION | 3033.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3037.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3041.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3042.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3044.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3046.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3047.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3051.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3055.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3059.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3063.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3067.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3069.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3070.5325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3072.0325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3075.2758 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3095.2758 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3095.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3098.5924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3098.9724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3104.9724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3107.9724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3108.7324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3114.7324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3117.7324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3118.8724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3124.8724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3127.8724 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3129.3924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3135.3924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3138.3924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3139.3924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3140.8924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3146.8924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3147.8924 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3148.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3150.3924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3153.8924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3154.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3156.3924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3159.8924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3160.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3162.3924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3165.8924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3166.2091 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3186.2091 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3186.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3189.5258 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3189.9058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3195.9058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3198.9058 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3199.6658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3205.6658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3208.6658 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3209.8058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3215.8058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3218.8058 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3220.3258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3226.3258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3229.3258 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3230.3258 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3231.8258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3237.8258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3238.8258 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3239.8258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3241.3258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3244.8258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3245.8258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3247.3258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3250.8258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3251.8258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3253.3258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3256.8258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3257.1424 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3277.1424 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3277.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3280.4591 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3280.8391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3286.8391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3289.8391 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3290.5991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3296.5991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3299.5991 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3300.7391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3306.7391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3309.7391 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3311.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3317.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3320.2591 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3321.2591 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3322.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3328.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3329.7591 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3330.7591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3332.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3337.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3340.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3341.7591 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3351.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3353.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3356.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3357.7591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3359.2591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3362.7591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3363.0758 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3366.319 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3370.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3374.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3378.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3382.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3386.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3387.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3389.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3390.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3394.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3398.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3402.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3406.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3410.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3412.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3413.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3415.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3419.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3423.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3427.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3431.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3435.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3436.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3438.319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3439.819 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3443.0622 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3463.0622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3463.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3466.3789 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3466.7589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3472.7589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3475.7589 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3476.5189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3482.5189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3485.5189 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3486.6589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3492.6589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3495.6589 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3497.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3503.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3506.1789 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3507.1789 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3508.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3514.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3515.6789 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3516.6789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3518.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3521.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3522.6789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3524.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3527.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3528.6789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3530.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3538.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3541.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3541.9956 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3561.9956 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3562.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3565.3122 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3565.6922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3571.6922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3574.6922 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3575.4522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3581.4522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3584.4522 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3585.5922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3591.5922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3594.5922 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3596.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3602.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3605.1122 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3606.1122 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3607.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 3610.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3616.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3617.6122 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3618.6122 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 3626.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3628.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3630.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3633.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3634.6122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3636.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3639.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3640.6122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3642.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3645.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3645.9289 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3665.9289 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3666.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3669.2456 | TurbineInstallation
| WTIV | Delay | 33 | 550000 | ACTION | 3702.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3702.6256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3708.6256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3711.6256 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3712.3856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3718.3856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3721.3856 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3722.5256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3728.5256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3731.5256 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3733.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3739.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3742.0456 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3743.0456 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3768.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3769.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3775.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3776.5456 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3777.5456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3779.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3782.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3783.5456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3785.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3788.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3789.5456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3791.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3794.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3794.8622 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3798.1055 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3802.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3806.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3810.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3814.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3818.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3819.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3821.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3822.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3826.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3833.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3837.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3841.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3845.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3849.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3851.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3852.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3854.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3858.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3862.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3866.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3870.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3874.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3875.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3877.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3878.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3881.8487 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3901.8487 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3902.1654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3905.1654 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3905.5454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3911.5454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3914.5454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3915.3054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3921.3054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3924.3054 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3925.4454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3931.4454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3934.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3935.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3941.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3944.9654 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3945.9654 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3947.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3953.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3954.4654 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3955.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3956.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3960.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3961.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3962.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3966.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3967.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3968.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3972.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3972.7821 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3992.7821 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3993.0987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3996.0987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3996.4787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4002.4787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4005.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4006.2387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 54 | 900000 | ACTION | 4060.2387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4066.2387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4069.2387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4070.3787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4076.3787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4079.3787 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4082.3787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4083.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4089.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4092.8987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4093.8987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4095.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4101.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4102.3987 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4103.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4104.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4108.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4109.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4110.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4114.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4115.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4116.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4120.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4120.7154 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4140.7154 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4141.0321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4144.0321 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4144.4121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4150.4121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4153.4121 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4154.1721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4160.1721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4163.1721 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4164.3121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4170.3121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4173.3121 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4174.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4180.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4183.8321 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4184.8321 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4186.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4192.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4193.3321 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4194.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4195.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4202.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4206.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4207.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4208.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4212.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4213.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4214.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4218.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4218.6487 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4221.892 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4225.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4229.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4233.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4237.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4241.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4243.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4244.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4246.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4250.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4254.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4258.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4262.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4266.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4267.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4269.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4270.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4274.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 4277.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4281.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4285.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4289.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4293.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4295.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4296.892 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4298.392 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4301.6352 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4321.6352 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4321.9519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4324.9519 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4327.9519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4328.3319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4334.3319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4337.3319 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4338.0919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4344.0919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4347.0919 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4348.2319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4354.2319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4357.2319 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4358.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4364.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4367.7519 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4368.7519 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4370.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4372.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4378.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4379.2519 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4380.2519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4381.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4385.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4386.2519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4387.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 15 | 250000 | ACTION | 4402.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4406.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4407.2519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4408.7519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4412.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4412.5686 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4432.5686 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4432.8852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4435.8852 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4436.2652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4442.2652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4445.2652 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4446.0252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4452.0252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4455.0252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4456.1652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4462.1652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4465.1652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4466.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4472.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4475.6852 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4476.6852 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4478.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4484.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4485.1852 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4486.1852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4487.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 63 | 1050000 | ACTION | 4550.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4554.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4555.1852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4556.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4560.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4561.1852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4562.6852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4566.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4566.5019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4586.5019 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4586.8186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4589.8186 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4603.8186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4604.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4605.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4611.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4614.1986 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4698.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4698.9586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4702.9586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4708.9586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4711.9586 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4713.0986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4719.0986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4722.0986 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4723.6186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4729.6186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4732.6186 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4733.6186 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4735.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4741.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4742.1186 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4743.1186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4744.6186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4748.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4749.1186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4750.6186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4754.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4755.1186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4756.6186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4760.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4760.4352 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4763.6785 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4767.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4771.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4775.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4779.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4783.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4785.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4786.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4788.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4792.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4796.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4800.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4804.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4808.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4809.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4811.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4812.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4816.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4833.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4837.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4841.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4845.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4849.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4851.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4852.6785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4854.1785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4857.4217 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4877.4217 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4877.7384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4880.7384 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4881.1184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4889.1184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4895.1184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4898.1184 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4898.8784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4904.8784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4907.8784 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4909.0184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4915.0184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4918.0184 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4919.5384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4925.5384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4928.5384 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4929.5384 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4931.0384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4937.0384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4938.0384 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4939.0384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4940.5384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4944.0384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4945.0384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4946.5384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4950.0384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4951.0384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4952.5384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4956.0384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4956.355 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4976.355 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4976.6717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4979.6717 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4982.6717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4983.0517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4989.0517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4992.0517 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4992.8117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4998.8117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5001.8117 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5002.9517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5008.9517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5011.9517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5013.4717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5019.4717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5022.4717 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5023.4717 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5024.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 5030.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5036.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5037.9717 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5038.9717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5040.4717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5043.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5044.9717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5046.4717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5049.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5050.9717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5052.4717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5055.9717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5056.2884 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 5076.2884 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5076.605 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5079.605 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5079.985 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5085.985 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5088.985 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5089.745 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5095.745 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5098.745 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5099.885 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5105.885 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5108.885 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5110.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5116.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5119.405 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5120.405 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5121.905 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5127.905 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5128.905 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5129.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5131.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5134.905 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5135.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5137.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5140.905 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5141.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5143.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1266 | 21100000 | ACTION | 6409.405 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6412.905 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6413.2217 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6416.4649 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6420.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6424.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6428.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6432.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6436.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6437.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6439.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6440.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6444.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6448.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6452.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6456.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6460.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6462.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6463.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6465.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6469.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6473.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6477.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6481.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6485.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6486.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6488.4649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6489.9649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6493.2082 | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 6512.2082 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6532.2082 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6532.5249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6535.5249 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6535.9049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6541.9049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6544.9049 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6545.6649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6551.6649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6554.6649 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6555.8049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6561.8049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6564.8049 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6566.3249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6572.3249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6575.3249 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6576.3249 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6577.8249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6583.8249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6584.8249 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6585.8249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6587.3249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6590.8249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6591.8249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6593.3249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6596.8249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6597.8249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6599.3249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6602.8249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6603.1415 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6623.1415 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6623.4582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6626.4582 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6626.8382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6632.8382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6635.8382 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6636.5982 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6642.5982 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6645.5982 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6646.7382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6652.7382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6655.7382 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6657.2582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6663.2582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.2582 | TurbineInstallation
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6667.2582 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6668.2582 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6669.7582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6675.7582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6676.7582 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6677.7582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6679.2582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6682.7582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6683.7582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6685.2582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6688.7582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6689.7582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6691.2582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6694.7582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6695.0749 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6715.0749 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6715.3915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6718.3915 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6718.7715 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6724.7715 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6727.7715 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6728.5315 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6734.5315 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6737.5315 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6738.6715 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 19 | 316666.6667 | ACTION | 6757.6715 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6763.6715 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6766.6715 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6768.1915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6774.1915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6777.1915 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6778.1915 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6779.6915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6785.6915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6786.6915 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6787.6915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6789.1915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6792.6915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6793.6915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6795.1915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6798.6915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6799.6915 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6801.1915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6804.6915 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6805.0082 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6808.2514 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6812.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6820.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6824.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6828.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6832.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6836.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6837.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6839.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6840.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6844.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6848.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6852.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6856.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6860.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6862.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6863.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6865.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6869.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6873.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6877.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6881.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6885.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6886.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6888.2514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6889.7514 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6892.9947 | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 6911.9947 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6931.9947 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6932.3113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6935.3113 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6941.3113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6941.6913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 6983.6913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6989.6913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6992.6913 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6993.4513 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6999.4513 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7002.4513 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7003.5913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7009.5913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7012.5913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7014.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7020.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7023.1113 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7024.1113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7025.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7031.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7032.6113 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7033.6113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7035.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7038.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7039.6113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7041.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7044.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7045.6113 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7049.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7051.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 7093.1113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7096.6113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7096.928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7116.928 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7117.2447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7120.2447 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7120.6247 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7126.6247 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7129.6247 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7130.3847 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7136.3847 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7139.3847 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7140.5247 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7146.5247 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7149.5247 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7151.0447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7157.0447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7160.0447 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7161.0447 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7162.5447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7168.5447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7169.5447 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7170.5447 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7172.0447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7175.5447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7176.5447 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7178.0447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7181.5447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7182.5447 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7184.0447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7187.5447 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7187.8613 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7207.8613 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7208.178 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7211.178 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7211.558 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 7229.558 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7235.558 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7238.558 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7239.318 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7245.318 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7248.318 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7249.458 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7255.458 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7258.458 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7259.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7265.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7268.978 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7269.978 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7271.478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7277.478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7278.478 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7279.478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7280.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7306.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7310.478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7311.478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7312.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7316.478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7317.478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7318.978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7322.478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7322.7947 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7326.0379 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7330.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7334.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7338.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7342.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7346.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7347.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7349.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7350.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7354.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7358.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7362.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7366.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7370.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7372.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7373.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7375.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7379.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7383.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7387.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7391.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7395.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7396.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7398.0379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7399.5379 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7402.7812 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7422.7812 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7423.0978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7426.0978 | TurbineInstallation
| WTIV | Delay | 40 | 666666.6667 | ACTION | 7466.0978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7466.4778 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7472.4778 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7475.4778 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7476.2378 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7482.2378 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7485.2378 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7486.3778 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7492.3778 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7495.3778 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7496.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7502.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7505.8978 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7506.8978 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7508.3978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7514.3978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7515.3978 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7516.3978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7517.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7521.3978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7522.3978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7523.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7549.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7553.3978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7554.3978 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7555.8978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7559.3978 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7559.7145 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7579.7145 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7580.0312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7583.0312 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7583.4112 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7589.4112 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7592.4112 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7593.1712 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7599.1712 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7602.1712 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7604.1712 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7605.3112 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7611.3112 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7614.3112 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7615.8312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7621.8312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7624.8312 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7625.8312 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7627.3312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7633.3312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7634.3312 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7635.3312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7636.8312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7640.3312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7641.3312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7642.8312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7646.3312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7647.3312 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7648.8312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7652.3312 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7652.6478 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7672.6478 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7672.9645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7675.9645 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7676.3445 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7682.3445 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7685.3445 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7686.1045 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7692.1045 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7695.1045 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7696.2445 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7702.2445 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7705.2445 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7706.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7712.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7715.7645 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7716.7645 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 7724.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7726.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7731.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7737.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7738.2645 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7739.2645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7740.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7744.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7745.2645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7746.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7750.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7751.2645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7752.7645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7756.2645 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7756.5812 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7759.8244 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7763.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7767.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7771.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7775.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7779.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7781.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7782.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7784.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7788.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7792.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7796.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7800.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7804.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7805.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7807.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7808.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7812.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7816.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7820.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7824.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7828.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7830.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7831.8244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7833.3244 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7836.5677 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7856.5677 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7856.8843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7859.8843 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7860.2643 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7866.2643 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7869.2643 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7870.0243 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7876.0243 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7879.0243 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7880.1643 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7886.1643 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7889.1643 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7890.6843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7896.6843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7899.6843 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7900.6843 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7902.1843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7908.1843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7909.1843 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7910.1843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7911.6843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7915.1843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7916.1843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7917.6843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7921.1843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7922.1843 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7923.6843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7927.1843 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7927.501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7947.501 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7947.8177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7950.8177 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7951.1977 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7957.1977 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7960.1977 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7960.9577 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7966.9577 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7969.9577 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7971.0977 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7977.0977 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7980.0977 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7981.6177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7987.6177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7990.6177 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7991.6177 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7993.1177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7999.1177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8000.1177 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8001.1177 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8002.6177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8006.1177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8007.1177 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8008.6177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8012.1177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8013.1177 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8014.6177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8018.1177 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8018.4343 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8038.4343 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8038.751 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8041.751 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8042.751 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8043.131 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 9 | 150000 | ACTION | 8052.131 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8058.131 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8061.131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8061.891 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 11 | 183333.3333 | ACTION | 8072.891 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8078.891 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8081.891 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8085.891 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8087.031 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8093.031 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8096.031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8097.551 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8103.551 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8106.551 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8107.551 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8109.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8115.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8116.051 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8117.051 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8118.551 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8122.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8123.051 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8124.551 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8128.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8129.051 | TurbineInstallation
| WTIV | Delay | 43 | 716666.6667 | ACTION | 8172.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8173.551 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8177.051 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8177.3677 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8180.6109 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8184.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8188.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8192.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8196.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8200.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8202.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8203.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8205.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8209.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8213.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8217.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8221.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8225.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8226.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8228.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8229.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8233.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8237.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8241.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8245.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8249.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8251.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8252.6109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8254.1109 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8257.3541 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8277.3541 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8277.6708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8280.6708 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8281.0508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8287.0508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8290.0508 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 8315.0508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8315.8108 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8317.8108 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8323.8108 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8326.8108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8327.9508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 8341.9508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8347.9508 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8350.9508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8352.4708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8358.4708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8361.4708 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8362.4708 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8363.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8369.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8370.9708 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8371.9708 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8373.4708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8376.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8377.9708 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8379.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8381.4708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8384.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8385.9708 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8387.4708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8390.9708 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8391.2875 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8411.2875 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8411.6041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8414.6041 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8414.9841 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 37 | 616666.6667 | ACTION | 8451.9841 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8457.9841 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8460.9841 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8461.7441 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8467.7441 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8470.7441 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8471.8841 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8477.8841 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8480.8841 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8482.4041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8488.4041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8491.4041 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8492.4041 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8493.9041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8499.9041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8500.9041 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8501.9041 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8503.4041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8506.9041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8507.9041 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8509.4041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8512.9041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8513.9041 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8515.4041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8518.9041 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8519.2208 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8539.2208 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8539.5375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8542.5375 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8543.5375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8543.9175 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8549.9175 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8552.9175 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8553.6775 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8559.6775 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8562.6775 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8563.8175 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8569.8175 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8572.8175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8574.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8580.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8583.3375 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8584.3375 | TurbineInstallation
| WTIV | Delay | 18 | 300000 | ACTION | 8602.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8603.8375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8609.8375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8610.8375 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8611.8375 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8613.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8616.8375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8617.8375 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8619.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8622.8375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8623.8375 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8625.3375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8628.8375 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8629.1541 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8632.3974 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8636.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8640.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8644.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8648.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8652.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8653.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8655.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8656.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8660.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8664.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 8667.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8671.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8675.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8679.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8681.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8682.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8684.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8688.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8692.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8714.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8718.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 8721.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8725.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8729.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8730.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8732.3974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8733.8974 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8737.1406 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8757.1406 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8757.4573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8760.4573 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8760.8373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8766.8373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8769.8373 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8770.5973 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8776.5973 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8779.5973 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8780.7373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8786.7373 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8789.7373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8791.2573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8797.2573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8800.2573 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8801.2573 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8802.7573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8808.7573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8809.7573 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8810.7573 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8812.2573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8815.7573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8816.7573 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8818.2573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8821.7573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8822.7573 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8824.2573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8827.7573 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8828.074 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8848.074 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8848.3906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8851.3906 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8851.7706 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8857.7706 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8860.7706 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8861.5306 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8867.5306 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8870.5306 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8871.6706 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8877.6706 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8880.6706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8882.1906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8888.1906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8891.1906 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8892.1906 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8893.6906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8899.6906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8900.6906 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8901.6906 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8903.1906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8906.6906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8907.6906 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8909.1906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8912.6906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8913.6906 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8915.1906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8918.6906 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8919.0073 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8939.0073 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8939.324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8942.324 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8942.704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8948.704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8951.704 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8952.464 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8958.464 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8961.464 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8962.604 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8968.604 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8971.604 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8973.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 8999.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9005.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9008.124 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9009.124 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9010.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 11 | 183333.3333 | ACTION | 9021.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9027.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9028.624 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9029.624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9031.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9034.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9035.624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9037.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9040.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9041.624 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9043.124 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9046.624 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9046.9406 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9050.1839 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9054.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9058.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9062.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9066.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9070.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9071.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9073.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9074.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9078.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9082.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9086.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9090.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9094.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9096.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9097.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9099.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9103.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9107.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9111.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9115.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9119.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9120.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9122.1839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9123.6839 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9126.9271 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9146.9271 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9147.2438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9150.2438 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9150.6238 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9156.6238 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9159.6238 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9160.3838 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9164.3838 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9170.3838 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9173.3838 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9174.5238 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 9192.5238 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9198.5238 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9201.5238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9203.0438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9209.0438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9212.0438 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9213.0438 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9214.5438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9220.5438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9221.5438 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9222.5438 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9224.0438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9227.5438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9228.5438 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9230.0438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9233.5438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9234.5438 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9236.0438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9239.5438 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9239.8604 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9259.8604 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9260.1771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9263.1771 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9263.5571 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9269.5571 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9272.5571 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9273.3171 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9279.3171 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9282.3171 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9283.4571 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9289.4571 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9292.4571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9293.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9299.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9302.9771 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9303.9771 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9305.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9311.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9312.4771 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9313.4771 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 9319.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9320.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 9328.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9332.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9333.4771 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9334.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9338.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9339.4771 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9340.9771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9344.4771 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9344.7938 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9364.7938 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9365.1104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9368.1104 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9368.4904 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9374.4904 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9377.4904 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9378.2504 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9384.2504 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9387.2504 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9388.3904 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9394.3904 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9397.3904 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9398.9104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9404.9104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9407.9104 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9408.9104 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9410.4104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9416.4104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9417.4104 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9418.4104 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9419.9104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9423.4104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9424.4104 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9425.9104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9429.4104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9430.4104 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9431.9104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9435.4104 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9435.7271 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9438.9704 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9442.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9446.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9450.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9454.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9458.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9460.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9461.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9463.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9467.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9471.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9475.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9479.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9483.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9484.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9486.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9487.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9491.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9495.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9499.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9503.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9507.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9509.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9510.9704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9512.4704 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9515.7136 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 9525.7136 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9545.7136 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9546.0303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9549.0303 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9550.0303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9550.4103 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 9553.4103 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9559.4103 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9562.4103 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9563.1703 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9569.1703 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9572.1703 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9573.3103 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9579.3103 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9582.3103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9583.8303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9589.8303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9592.8303 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9593.8303 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9595.3303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9601.3303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9602.3303 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9603.3303 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9604.8303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9608.3303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9609.3303 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9610.8303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9614.3303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9615.3303 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9616.8303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9620.3303 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9620.6469 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9640.6469 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9640.9636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9643.9636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9644.3436 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9650.3436 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9653.3436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9654.1036 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9660.1036 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9663.1036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9664.2436 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9670.2436 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9673.2436 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9674.2436 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9675.7636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9681.7636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9684.7636 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9685.7636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9687.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9693.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9694.2636 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9695.2636 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9697.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9698.7636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9702.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9703.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9704.7636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9708.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9709.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9710.7636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9714.2636 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9714.5803 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9734.5803 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9734.8969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9737.8969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9738.2769 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9744.2769 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9747.2769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9748.0369 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9754.0369 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9757.0369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9758.1769 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9764.1769 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9767.1769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9768.6969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9774.6969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9777.6969 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9778.6969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9780.1969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9786.1969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9787.1969 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9788.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9789.6969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9793.1969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9794.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9795.6969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9799.1969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9800.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9801.6969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9805.1969 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9805.5136 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9808.7568 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9812.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9816.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9820.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9824.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9828.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9830.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9831.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9833.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9837.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9841.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9845.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9849.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9853.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9854.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9856.2568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9857.7568 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9861.0001 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9881.0001 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9881.3167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9884.3167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9884.6967 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9890.6967 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9893.6967 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9894.4567 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9900.4567 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9903.4567 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9904.5967 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 9909.5967 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9915.5967 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9918.5967 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9920.1167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9926.1167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9929.1167 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9930.1167 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9931.6167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9937.6167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9938.6167 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9939.6167 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9941.1167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9944.6167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9945.6167 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9947.1167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9950.6167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9951.6167 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9953.1167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9956.6167 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9956.9334 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9976.9334 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9977.2501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9980.2501 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9980.6301 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9986.6301 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9989.6301 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9990.3901 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9996.3901 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9999.3901 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10000.5301 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10006.5301 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10009.5301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10011.0501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10017.0501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10020.0501 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10021.0501 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10022.5501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10028.5501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10029.5501 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10030.5501 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10032.0501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10035.5501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10036.5501 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10038.0501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10041.5501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10042.5501 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10044.0501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10047.5501 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10047.8667 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150