## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Queue | 120 | 600000 | ACTION | 120 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 125.2432 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 126.9099 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay: Not enough vessels for monopiles | 123.6667 | 1288194.4444 | ACTION | 126.9099 | MonopileInstallation |  |  | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 146.9099 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 147.2266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 148.2266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 151.2266 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 151.9496 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 151.9529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 152.9529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 154.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 156.4529 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 157.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 158.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 162.4529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 162.7696 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 172 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 180 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 182.7696 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 183.0862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 184.0862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 187.0862 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 187.8093 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 187.8125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 188.8125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 190.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 192 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 192.3125 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 193.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 196.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 197.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Delay | 19 | 95000 | ACTION | 211 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 219 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay | 23 | 239583.3333 | ACTION | 220.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 224.3125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 224.6292 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 231 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 239 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 244.6292 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 244.9459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 245.9459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 248.9459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 249.6689 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 249.6722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 250.6722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 251 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 252.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 254.1722 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 255.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 256.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 259 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 260.1722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 260.4889 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 262.2432 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 264.2432 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 265.9099 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 280.4889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 280.8055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 281.8055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 284.8055 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 285.5286 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 285.5318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 286.5318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 288.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 290.0318 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 291.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 292.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 296.0318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 296.3485 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 316.3485 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 316.6652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 317.6652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 320.6652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 321.3882 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 321.3915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 322.3915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 323.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 325.8915 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 326.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 327.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 331.8915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 332.2082 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 352.2082 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 352.5248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 353.5248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 356.5248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 357.2479 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 357.2511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 358.2511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 359.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 361.7511 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 234.8412 | 1174206.1327 | ACTION | 361.7511 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 362.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 363.4178 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 363.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 366.661 | MonopileInstallation
| Feeder 1 | Queue | 100.7511 | 503755.6823 | ACTION | 366.661 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 367.7511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 368.0678 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 378.661 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 386.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 388.0678 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 388.3845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 389.3845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 392.3845 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 393.1075 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 393.1108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 394.1108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 395.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 397.6108 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 398.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 398.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 399.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 403.6108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 403.9275 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 406.661 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 418.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 423.9275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 424.2441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 425.2441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 426.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 428.2441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 428.9672 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 428.9704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 429.9704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 439.9704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 441.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 443.4704 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 444.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 445.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 449.4704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 449.7871 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 453.7871 | MonopileInstallation
| Feeder 0 | Delay | 32 | 160000 | ACTION | 458.661 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 470.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 473.7871 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 474.1038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 475.1038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 478.1038 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 478.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 478.8268 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 478.8301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 479.8301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 481.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 483.3301 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 484.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 485.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 489.3301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 489.6467 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 490.661 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 498.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 509.6467 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 509.9634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 510.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 510.9634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 513.9634 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 514.6865 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 514.6897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 515.6897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 517.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 518.661 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 519.1897 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 520.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 521.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 521.9043 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 523.9043 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 525.1897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 525.5064 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 525.571 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 545.5064 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 545.8231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 546.8231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 549.8231 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 550.5461 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 550.5494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 551.5494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 553.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 555.0494 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 556.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 557.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 561.0494 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 561.366 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 581.366 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 581.6827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 582.6827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 585.6827 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 586.4058 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 586.409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 587.409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 588.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 590.909 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 224.248 | 1121239.9165 | ACTION | 590.909 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 591.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 592.5757 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 592.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 595.8189 | MonopileInstallation
| Feeder 0 | Queue | 70.248 | 351239.9165 | ACTION | 595.8189 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 596.909 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 597.2257 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 607.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 615.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 617.2257 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 617.5424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 618.5424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 621.5424 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 622.2654 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 622.2687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 623.2687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 624.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 626.7687 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 627.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 627.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 628.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 632.7687 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 633.0853 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 635.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 647.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 653.0853 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 653.402 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 654.402 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 655.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 657.402 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 658.1251 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 658.1283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 659.1283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 660.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 662.6283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 663.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 664.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 667.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 668.6283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 668.945 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 675.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 687.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 688.945 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 689.2617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 690.2617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 693.2617 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 693.9847 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 693.988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 694.988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 695.8189 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 696.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 698.488 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 699.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 700.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 704.488 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 704.8046 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 707.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 715.8189 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 719.0622 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 721.0622 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 722.7288 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 724.8046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 725.1213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 726.1213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 729.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 729.8444 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 729.8476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 730.8476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 732.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 734.3476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 735.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 736.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 740.3476 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 740.6643 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 760.6643 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 760.981 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 761.981 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 764.981 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 766.981 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 767.704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 767.7073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 768.7073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 770.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 772.2073 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 773.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 774.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 778.2073 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 778.5239 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 798.5239 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 798.8406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 799.8406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 802.8406 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 803.5637 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 803.5669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 804.5669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 806.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 808.0669 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 212.248 | 1061239.9165 | ACTION | 808.0669 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 809.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 809.7336 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 810.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 812.9768 | MonopileInstallation
| Feeder 1 | Queue | 90.248 | 451239.9165 | ACTION | 812.9768 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 814.0669 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 814.3836 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 824.9768 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 832.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 834.3836 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 834.7003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 835.7003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 838.7003 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 839.4233 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 839.4266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 840.4266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 841.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 843.9266 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 844.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 844.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 845.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 849.9266 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 850.2432 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 852.9768 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 864.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 870.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 870.5599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 871.5599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 872.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 874.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 875.283 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 875.2862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 876.2862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 877.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 879.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 880.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 881.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Delay | 13 | 65000 | ACTION | 885.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Delay | 6 | 62500 | ACTION | 887.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 891.7862 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 892.1029 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 897.9768 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 905.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 912.1029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 912.4196 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 913.4196 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 916.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 917.1426 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 917.1459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 917.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 918.1459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 919.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 921.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 922.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 923.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 925.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 927.6459 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 927.9625 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 937.9768 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 945.9768 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 947.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 948.2792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 949.2201 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 949.2792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 951.2201 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 952.2792 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 952.8867 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 953.0023 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 953.0055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 954.0055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 955.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 957.5055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 958.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 959.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 963.5055 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 963.8222 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 983.8222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 984.1389 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 985.1389 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 988.1389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 988.8619 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 988.8652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 989.8652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 991.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 993.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 994.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 995.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 999.3652 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 999.6818 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1019.6818 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1019.9985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1020.9985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1023.9985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1024.7216 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1024.7248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1025.7248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1027.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1029.2248 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 216.248 | 1081239.9165 | ACTION | 1029.2248 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1030.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1030.8915 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1031.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1034.1347 | MonopileInstallation
| Feeder 0 | Queue | 81.248 | 406239.9165 | ACTION | 1034.1347 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1035.2248 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1035.5415 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1046.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1054.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1055.5415 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1055.8581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1056.8581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1059.8581 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1060.5812 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1060.5845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1061.5845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1063.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1065.0845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1066.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1066.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1067.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1071.0845 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1071.4011 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1074.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1086.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1091.4011 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1091.7178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1092.7178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1094.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1095.7178 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1096.4409 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1096.4441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1097.4441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1098.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1100.9441 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1101.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1102.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1106.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1106.9441 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1107.2608 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1114.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1126.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1127.2608 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1127.5774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1128.5774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1131.5774 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1132.3005 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1132.3038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1133.3038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1134.1347 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1134.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1136.8038 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1137.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1138.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1142.8038 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1143.1204 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1146.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1154.1347 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1157.378 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1159.378 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1161.0446 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1163.1204 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1163.4371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1164.4371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1167.4371 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1168.1602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1168.1634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1169.1634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1170.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1172.6634 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1173.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1174.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1178.6634 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1178.9801 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1198.9801 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1199.2967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1200.2967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1203.2967 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1204.0198 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1204.0231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1205.0231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1206.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1208.5231 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1209.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1210.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1214.5231 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1214.8397 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1234.8397 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1235.1564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1236.1564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1239.1564 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1239.8795 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1239.8827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1240.8827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1242.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1244.3827 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 210.248 | 1051239.9165 | ACTION | 1244.3827 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1245.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1246.0494 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1246.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1249.2926 | MonopileInstallation
| Feeder 1 | Queue | 88.248 | 441239.9165 | ACTION | 1249.2926 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1250.3827 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1250.6994 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1261.2926 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1269.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1270.6994 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1271.016 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1272.016 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1275.016 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1275.7391 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1275.7424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1276.7424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1278.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1280.2424 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1281.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1281.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1282.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1286.2424 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1286.559 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1289.2926 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1301.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1306.559 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1306.8757 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1307.8757 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1309.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1310.8757 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1311.5988 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1311.602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1312.602 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1314.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1316.102 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1317.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1318.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1321.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1322.102 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1322.4187 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1329.2926 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1341.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1342.4187 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1342.7353 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1343.7353 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1346.7353 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1347.4584 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1347.4617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1348.4617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1349.2926 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1349.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1351.9617 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1352.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1353.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1357.9617 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1358.2783 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1361.2926 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1369.2926 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1372.5359 | MonopileInstallation
| Feeder 0 | Position Onsite | 2 | 10000 | ACTION | 1374.5359 | MonopileInstallation
| Feeder 0 | Jackup | 1.6667 | 8333.3333 | ACTION | 1376.2025 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1378.2783 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1378.595 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1379.595 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1382.595 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1383.3181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1383.3213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1384.3213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1385.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1387.8213 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1388.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1389.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1393.8213 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1394.138 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1414.138 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1414.4546 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1415.4546 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1418.4546 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1419.1777 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1419.181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1420.181 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1421.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1423.681 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1424.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1425.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1429.681 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1429.9976 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1449.9976 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1450.3143 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1451.3143 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1454.3143 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1455.0374 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1455.0406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1456.0406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1457.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1459.5406 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 210.248 | 1051239.9165 | ACTION | 1459.5406 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1460.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1461.2073 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1461.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1464.4505 | MonopileInstallation
| Feeder 0 | Queue | 88.248 | 441239.9165 | ACTION | 1464.4505 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1465.5406 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1465.8573 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1476.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1484.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1485.8573 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1486.1739 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1487.1739 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1490.1739 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1490.897 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1490.9003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1491.9003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1493.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1495.4003 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1496.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1496.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1497.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1501.4003 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1501.7169 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1504.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1516.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1521.7169 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1522.0336 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1523.0336 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1524.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1526.0336 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1526.7567 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1526.7599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1527.7599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1529.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1531.2599 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1532.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1533.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1536.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1537.2599 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1537.5766 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1544.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1556.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1557.5766 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1557.8932 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1558.8932 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1561.8932 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1562.6163 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1562.6195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1563.6195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1564.4505 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1565.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1567.1195 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1568.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1569.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1573.1195 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1573.4362 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1576.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1584.4505 | MonopileInstallation | MonopileInstallation | 20
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1587.6938 | MonopileInstallation
| Feeder 1 | Position Onsite | 2 | 10000 | ACTION | 1589.6938 | MonopileInstallation
| Feeder 1 | Jackup | 1.6667 | 8333.3333 | ACTION | 1591.3604 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1593.4362 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1593.7529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1594.7529 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1597.7529 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1598.4759 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1598.4792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1599.4792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1600.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1602.9792 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1603.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1604.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1608.9792 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1609.2959 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1629.2959 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1629.6125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1630.6125 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1633.6125 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1634.3356 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1634.3388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1635.3388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1636.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1638.8388 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1639.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1640.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1644.8388 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1645.1555 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1665.1555 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1665.4722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1666.4722 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1669.4722 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1670.1952 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1670.1985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1671.1985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1672.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1674.6985 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 210.248 | 1051239.9165 | ACTION | 1674.6985 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1675.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1676.3652 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1676.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1679.6084 | MonopileInstallation
| Feeder 1 | Queue | 88.248 | 441239.9165 | ACTION | 1679.6084 | MonopileInstallation |  |  | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1680.6985 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1681.0152 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1691.6084 | MonopileInstallation | MonopileInstallation | 20
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1699.6084 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1701.0152 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1701.3318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1702.3318 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1705.3318 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1706.0549 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1706.0581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1707.0581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1708.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1710.5581 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1711.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1711.6084 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1712.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1716.5581 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1716.8748 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1719.6084 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1736.8748 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1737.1915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1738.1915 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1741.1915 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1741.9145 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1741.9178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1742.9178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1744.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1746.4178 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1747.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1748.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1752.4178 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1752.7345 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1772.7345 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1773.0511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1774.0511 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1777.0511 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1777.7742 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1777.7774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1778.7774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1780.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1782.2774 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1783.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1784.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1788.2774 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1788.5941 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1808.5941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1808.9108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1809.9108 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1812.9108 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1813.6338 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1813.6371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1814.6371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1816.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1818.1371 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1819.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1820.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1824.1371 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1824.4538 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1844.4538 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1844.7704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1845.7704 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1848.7704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1849.4935 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1849.4967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1850.4967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1851.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1853.9967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1854.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1855.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1859.9967 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1860.3134 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Position Onsite | 20 | 208333.3333 | ACTION | 1880.3134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1880.6301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1881.6301 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1884.6301 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1885.3531 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1885.3564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1886.3564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1887.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1889.8564 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 210.248 | 1051239.9165 | ACTION | 1889.8564 | MonopileInstallation |  |  | Site
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1890.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Jackdown | 1.6667 | 8333.3333 | ACTION | 1891.5231 | MonopileInstallation | MonopileInstallation | 20
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1891.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1894.7663 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1895.8564 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1896.1731 | MonopileInstallation | MonopileInstallation | 20 |  | 22.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 1896.1731 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1900.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1904.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1908.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1912.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1916.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1917.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1919.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1920.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1924.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1928.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1932.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1936.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1940.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1942.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1943.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1945.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1949.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1953.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1957.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1961.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1965.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1966.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1968.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1969.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1973.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1977.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1981.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1985.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 1989.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1991.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1992.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 1994.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 1998.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2002.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2006.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2010.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2014.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2015.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2017.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2018.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2022.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2026.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2030.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2034.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2038.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2040.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2041.6731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2043.1731 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2046.4163 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2066.4163 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2066.733 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2069.733 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2070.113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2076.113 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2079.113 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2079.873 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2085.873 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2088.873 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2090.013 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2096.013 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2099.013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2100.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2106.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2109.533 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2110.533 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2112.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2118.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2119.033 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2120.033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2121.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2125.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2126.033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2127.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2131.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2132.033 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2133.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2137.033 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2137.3496 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2157.3496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2157.6663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2160.6663 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2161.0463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2167.0463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2170.0463 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2170.8063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2176.8063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2179.8063 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2180.9463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2186.9463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2189.9463 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2191.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2197.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2200.4663 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2201.4663 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2202.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2208.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2209.9663 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2210.9663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2212.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2215.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2216.9663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2218.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2221.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2222.9663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2224.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2227.9663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2228.283 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2248.283 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2248.5996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2251.5996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2251.9796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2257.9796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2260.9796 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2261.7396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2267.7396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2270.7396 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2271.8796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2277.8796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2280.8796 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2282.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2288.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2291.3996 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2292.3996 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2293.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2299.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2300.8996 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2301.8996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2303.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2306.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2307.8996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2309.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2312.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2313.8996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2315.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2318.8996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2319.2163 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2339.2163 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2339.533 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2342.533 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2342.913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2348.913 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2351.913 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2352.673 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2358.673 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2361.673 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2362.813 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2368.813 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2371.813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2373.333 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2379.333 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2382.333 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2383.333 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2384.833 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2390.833 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2391.833 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2392.833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2394.333 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2397.833 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2398.833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2400.333 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2403.833 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2404.833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2406.333 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2409.833 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2410.1496 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2430.1496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2430.4663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2433.4663 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2433.8463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2439.8463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2442.8463 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2443.6063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2449.6063 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2452.6063 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2453.7463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2459.7463 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2462.7463 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2464.2663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2470.2663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2473.2663 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2474.2663 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2475.7663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2481.7663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2482.7663 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2483.7663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2485.2663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2488.7663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2489.7663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2491.2663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2494.7663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2495.7663 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2497.2663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2500.7663 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2501.083 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2521.083 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2521.3996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2524.3996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2524.7796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2530.7796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2533.7796 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2534.5396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2540.5396 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2543.5396 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2544.6796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2550.6796 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2553.6796 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2555.1996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2561.1996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2564.1996 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2565.1996 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2566.6996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2572.6996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2573.6996 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2574.6996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2576.1996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2579.6996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2580.6996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2582.1996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2585.6996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2586.6996 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2588.1996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2591.6996 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2592.0163 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2595.2595 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2599.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2603.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2607.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2611.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2615.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2616.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2618.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2619.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2623.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2627.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2631.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2635.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2639.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2641.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2642.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2644.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2648.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2652.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2656.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2660.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2664.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2665.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2667.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2668.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2672.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2676.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2680.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2684.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2688.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2690.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2691.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2693.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2697.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2701.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2705.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2709.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2713.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2714.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2716.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2717.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2721.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2725.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2729.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2733.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 2737.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 2738.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2740.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2741.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 2743.2595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 2749.2595 | TurbineInstallation
| WTIV | Transit | 3 | 50000 | ACTION | 2752.2595 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 2764.2595 | TurbineInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 2764.5028 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2784.5028 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2784.8195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2787.8195 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2788.1995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2794.1995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2797.1995 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2797.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2803.9595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2806.9595 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2808.0995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2814.0995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2817.0995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2818.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2824.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2827.6195 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2828.6195 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2830.1195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2836.1195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2837.1195 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2838.1195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2839.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2843.1195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2844.1195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2845.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2849.1195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2850.1195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2851.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2855.1195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2855.4361 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2875.4361 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2875.7528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2878.7528 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2879.1328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2885.1328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2888.1328 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2888.8928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2894.8928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2897.8928 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2899.0328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2905.0328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2908.0328 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 2909.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2915.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 2918.5528 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2919.5528 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 2921.0528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 2927.0528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 2928.0528 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2929.0528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2930.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2934.0528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2935.0528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2936.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2940.0528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 2941.0528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 2942.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 2946.0528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2946.3695 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 2966.3695 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2966.6861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2969.6861 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 2970.0661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2976.0661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2979.0661 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 2979.8261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2985.8261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2988.8261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 2989.9661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 2995.9661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 2998.9661 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3000.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3006.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3009.4861 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3010.4861 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3011.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 21 | 350000 | ACTION | 3032.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3038.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3039.9861 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3040.9861 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3050.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3052.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3055.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3056.9861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3058.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3061.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3062.9861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3064.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3067.9861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3068.3028 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3088.3028 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3088.6195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3091.6195 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3091.9995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3097.9995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3100.9995 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3101.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3107.7595 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3110.7595 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3111.8995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3117.8995 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3120.8995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3122.4195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3128.4195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3131.4195 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3132.4195 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3133.9195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3139.9195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3140.9195 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3141.9195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3143.4195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3146.9195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3147.9195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3149.4195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3152.9195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3153.9195 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3155.4195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3158.9195 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3159.2361 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3179.2361 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3179.5528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3182.5528 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3182.9328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3188.9328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3191.9328 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3192.6928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3198.6928 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3201.6928 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3202.8328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3208.8328 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3211.8328 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3213.3528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3219.3528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3222.3528 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3223.3528 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3224.8528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3230.8528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3231.8528 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3232.8528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3234.3528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3237.8528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3238.8528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3240.3528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3243.8528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3244.8528 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3246.3528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3249.8528 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3250.1695 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3270.1695 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3270.4861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3273.4861 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3273.8661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3279.8661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3282.8661 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3283.6261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3289.6261 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3292.6261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3293.7661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3299.7661 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3302.7661 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3304.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3310.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3313.2861 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3314.2861 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3315.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3321.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3322.7861 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3323.7861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3325.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3328.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3329.7861 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3331.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 3337.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3340.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3341.7861 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3351.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3353.2861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3356.7861 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3357.1028 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3360.346 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3364.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3368.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3372.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3376.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3380.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3381.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3383.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3384.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3388.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3392.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3396.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3400.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3404.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3406.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3407.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3409.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3413.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3417.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3421.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3425.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3429.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3430.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3432.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3433.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3437.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3441.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3445.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3449.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3453.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3455.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3456.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3458.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3462.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3466.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3470.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3474.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3478.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3479.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3481.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3482.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3486.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3490.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3494.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3498.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3502.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3504.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3505.846 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3507.346 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3510.5893 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3530.5893 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3530.9059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3533.9059 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3538.9059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3539.2859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3545.2859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3548.2859 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3549.0459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3555.0459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3558.0459 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3559.1859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3565.1859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3568.1859 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3569.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3575.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3578.7059 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3579.7059 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3581.2059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3587.2059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3588.2059 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3589.2059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3590.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3594.2059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3595.2059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3596.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3600.2059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3601.2059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3602.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3606.2059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3606.5226 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3626.5226 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3626.8393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3629.8393 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3630.2193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3636.2193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3639.2193 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3639.9793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3645.9793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3648.9793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3650.1193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3656.1193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3659.1193 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3660.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 42 | 700000 | ACTION | 3702.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3708.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3711.6393 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3712.6393 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3714.1393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3720.1393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3721.1393 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3722.1393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3723.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3727.1393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3728.1393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3729.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3733.1393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3734.1393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3735.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3739.1393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3739.4559 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 21 | 350000 | ACTION | 3760.4559 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3780.4559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3780.7726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3783.7726 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3784.1526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3790.1526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3793.1526 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3793.9126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3799.9126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3802.9126 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3804.0526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3810.0526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3813.0526 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3814.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3820.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3823.5726 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3824.5726 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3826.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 14 | 233333.3333 | ACTION | 3840.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3846.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3847.0726 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3848.0726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3849.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3853.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3854.0726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3855.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3859.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3860.0726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3861.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3865.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3869.0726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3869.3893 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3889.3893 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3889.7059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3892.7059 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3893.0859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3899.0859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3902.0859 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3902.8459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3908.8459 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3911.8459 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3912.9859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3918.9859 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3921.9859 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3923.5059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3929.5059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3932.5059 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3933.5059 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3935.0059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3941.0059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3942.0059 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3943.0059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3944.5059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3948.0059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3949.0059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3950.5059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3954.0059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3955.0059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3956.5059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3960.0059 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3960.3226 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 3980.3226 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3980.6393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3983.6393 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3984.0193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3990.0193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3993.0193 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3993.7793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3999.7793 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4002.7793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4003.9193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 57 | 950000 | ACTION | 4060.9193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4066.9193 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4069.9193 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4071.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4077.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4080.4393 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4081.4393 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4082.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4083.9393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4089.9393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4090.9393 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4091.9393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4093.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4096.9393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4097.9393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4099.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4102.9393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4103.9393 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4105.4393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4108.9393 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4109.2559 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4129.2559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4129.5726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4132.5726 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4132.9526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4138.9526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4141.9526 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4142.7126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4148.7126 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4151.7126 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4152.8526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4158.8526 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4161.8526 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4163.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4169.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4172.3726 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4173.3726 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4174.8726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4180.8726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4181.8726 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4182.8726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4184.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4187.8726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4188.8726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4190.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4193.8726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4194.8726 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4196.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 4202.3726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4205.8726 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4206.1893 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4209.4325 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4213.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4217.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4221.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4225.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4229.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4230.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4232.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4233.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4237.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4241.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4245.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4249.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4253.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4255.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4256.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4258.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4262.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4266.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4270.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4274.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 4277.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4281.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4282.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4284.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4285.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4289.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4293.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4297.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4301.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4305.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4307.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4308.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4310.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4314.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4318.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4322.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4326.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4330.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4331.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4333.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4334.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4338.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4342.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4346.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4350.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4354.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4356.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4357.9325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4359.4325 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4362.6758 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4382.6758 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4382.9924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4385.9924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4386.3724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 16 | 266666.6667 | ACTION | 4402.3724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4408.3724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4411.3724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4412.1324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4418.1324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4421.1324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4422.2724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4428.2724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4431.2724 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4432.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4438.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4441.7924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4442.7924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4444.2924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4450.2924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4451.2924 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4452.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4453.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4457.2924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4458.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4459.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4463.2924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4464.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4465.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4469.2924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4469.6091 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4489.6091 | TurbineInstallation
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.6091 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4550.9258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4553.9258 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4554.3058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4560.3058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4563.3058 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4564.0658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4570.0658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4573.0658 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4574.2058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4580.2058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4583.2058 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4586.2058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4587.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 18 | 300000 | ACTION | 4605.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4611.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4614.7258 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4615.7258 | TurbineInstallation
| WTIV | Delay | 83 | 1383333.3333 | ACTION | 4698.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4700.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4702.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4708.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4709.2258 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4710.2258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4711.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4715.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4716.2258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4717.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4721.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4722.2258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4723.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4727.2258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4727.5424 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4747.5424 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4747.8591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4750.8591 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4751.2391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4757.2391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4760.2391 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4760.9991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4766.9991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4769.9991 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4771.1391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4777.1391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4780.1391 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4781.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4787.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4790.6591 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4791.6591 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4793.1591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4799.1591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4800.1591 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4801.1591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4802.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4834.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4838.1591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4839.1591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4840.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4844.1591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4845.1591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4846.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4850.1591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4850.4758 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4870.4758 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4870.7924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4873.7924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4874.1724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4880.1724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4883.1724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4883.9324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4888.9324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4894.9324 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4897.9324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4899.0724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4905.0724 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4908.0724 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4909.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4915.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4918.5924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4919.5924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4921.0924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4927.0924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4928.0924 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4929.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4930.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4934.0924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4935.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4936.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4940.0924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4941.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4942.5924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4946.0924 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4946.4091 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 4966.4091 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4966.7258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4969.7258 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4970.1058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 13 | 216666.6667 | ACTION | 4983.1058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4989.1058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4992.1058 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4992.8658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4998.8658 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5001.8658 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5003.0058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5009.0058 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5012.0058 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5013.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5019.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5022.5258 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5023.5258 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5025.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 5031.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5037.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5038.0258 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5039.0258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5040.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5044.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5045.0258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5046.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5050.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5051.0258 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5052.5258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5056.0258 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5056.3424 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 5076.3424 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5076.6591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5079.6591 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5080.0391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5086.0391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5089.0391 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5089.7991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5095.7991 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5098.7991 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5099.9391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5105.9391 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5108.9391 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5110.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5116.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5119.4591 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5120.4591 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5121.9591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5127.9591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5128.9591 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5129.9591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5131.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5134.9591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5135.9591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5137.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5140.9591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5141.9591 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5143.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1266 | 21100000 | ACTION | 6409.4591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6412.9591 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6413.2758 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6416.519 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6420.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6424.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6428.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6432.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6436.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6438.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6439.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6441.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6445.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6449.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6453.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6457.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6461.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6462.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6464.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6465.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6469.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6473.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6477.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6481.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6485.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6487.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6488.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6490.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6494.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6498.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6502.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6506.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6513.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6517.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6518.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6520.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6521.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6525.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6529.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6533.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6537.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6541.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6543.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6544.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6546.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6550.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6554.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6558.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6562.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6566.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6567.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6569.019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6570.519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6573.7622 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6593.7622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6594.0789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6597.0789 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6597.4589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6603.4589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6606.4589 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6607.2189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6613.2189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6616.2189 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6617.3589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6623.3589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6626.3589 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6627.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6633.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6636.8789 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6637.8789 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6639.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6645.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6646.3789 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6647.3789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6648.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6652.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6653.3789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6654.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6658.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6659.3789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6660.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6664.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6668.3789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6668.6956 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6688.6956 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6689.0122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6692.0122 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6692.3922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6698.3922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6701.3922 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6702.1522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6708.1522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6711.1522 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6712.2922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6718.2922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6721.2922 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6722.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6728.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6731.8122 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6732.8122 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6734.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6740.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6741.3122 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6742.3122 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6757.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6758.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6762.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6763.3122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6764.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6768.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6769.3122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6770.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6774.3122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6774.6289 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6794.6289 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6794.9456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6797.9456 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6798.3256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6804.3256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6807.3256 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6808.0856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 16 | 266666.6667 | ACTION | 6824.0856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6830.0856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6833.0856 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6834.2256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6840.2256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6843.2256 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6844.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6850.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6853.7456 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6854.7456 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6856.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6862.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6863.2456 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6864.2456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6865.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6869.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6870.2456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6871.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6875.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6876.2456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6877.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6881.2456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6881.5622 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 6901.5622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6901.8789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6904.8789 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6905.2589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 6915.2589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6921.2589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6924.2589 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6925.0189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6931.0189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6934.0189 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 6976.0189 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6977.1589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6984.1589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6990.1589 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6993.1589 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6994.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7000.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7003.6789 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7004.6789 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7006.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7012.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7013.1789 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7014.1789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7015.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7019.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7020.1789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7021.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7025.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7026.1789 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7027.6789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7031.1789 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7031.4956 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7051.4956 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7051.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7054.8122 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7055.8122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7056.1922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 36 | 600000 | ACTION | 7092.1922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7098.1922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7101.1922 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7101.9522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7107.9522 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7110.9522 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7112.0922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7118.0922 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7121.0922 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7122.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7128.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7131.6122 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7132.6122 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7134.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7140.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7141.1122 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7142.1122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7143.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7147.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7148.1122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7149.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7153.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7154.1122 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7155.6122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7159.1122 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7159.4289 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7179.4289 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7179.7456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7182.7456 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7183.1256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7189.1256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7192.1256 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7192.8856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7198.8856 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7201.8856 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7203.0256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7209.0256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7212.0256 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7222.0256 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7223.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 6 | 100000 | ACTION | 7229.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7235.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7238.5456 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7239.5456 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7241.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7247.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7248.0456 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7249.0456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7250.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7254.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7255.0456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7256.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7260.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7261.0456 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7262.5456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7266.0456 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7266.3622 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7269.6055 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7273.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7277.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7281.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7285.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7295.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7299.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7301.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7302.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7304.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7308.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7312.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7316.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7320.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7324.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7325.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7327.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7328.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7332.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7336.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7340.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7344.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7348.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7350.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7351.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7353.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7357.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7361.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7365.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7369.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7373.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7374.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7376.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7377.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7381.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7385.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7389.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7393.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7397.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7399.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7400.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7402.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7406.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7410.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7414.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7418.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7422.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7423.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7425.1055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7426.6055 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7429.8487 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 7465.8487 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7485.8487 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7486.1654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7489.1654 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7489.5454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7495.5454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7498.5454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7499.3054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7505.3054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7508.3054 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7509.4454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7515.4454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7518.4454 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7519.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 30 | 500000 | ACTION | 7549.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7555.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7558.9654 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7559.9654 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7561.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7567.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7568.4654 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7569.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7570.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7574.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7575.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7576.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 3 | 50000 | ACTION | 7579.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7583.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7584.4654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7585.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7589.4654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7589.7821 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7609.7821 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7610.0987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7613.0987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7613.4787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7619.4787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7622.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7623.2387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7629.2387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7632.2387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7633.3787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7639.3787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7642.3787 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7643.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7649.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7652.8987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7653.8987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7655.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7661.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7662.3987 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7663.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7664.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7668.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7669.3987 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7674.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7675.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7679.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7680.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7681.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7685.3987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7685.7154 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7705.7154 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7706.0321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7709.0321 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7709.4121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 22 | 366666.6667 | ACTION | 7731.4121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7737.4121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7740.4121 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7741.1721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7747.1721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7750.1721 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7751.3121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7757.3121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7760.3121 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7761.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7767.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7770.8321 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7771.8321 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7773.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7779.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7780.3321 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7781.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7782.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7786.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7787.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7788.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7792.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7793.3321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7794.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7798.3321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7798.6487 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7818.6487 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7818.9654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7821.9654 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7822.3454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7828.3454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7831.3454 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7832.1054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7838.1054 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7841.1054 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7842.2454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7848.2454 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7851.2454 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7852.7654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7858.7654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7861.7654 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7862.7654 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7864.2654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7870.2654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7871.2654 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7872.2654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7873.7654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7877.2654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7878.2654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7879.7654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7883.2654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7884.2654 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7885.7654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7889.2654 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7889.5821 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 7909.5821 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7909.8987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7912.8987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7913.2787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7919.2787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7922.2787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7923.0387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7929.0387 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7932.0387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7933.1787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7939.1787 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7942.1787 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7943.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7945.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7951.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7954.6987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7955.6987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7957.1987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7963.1987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7964.1987 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7965.1987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7966.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7970.1987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7971.1987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7972.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7976.1987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7977.1987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7978.6987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7982.1987 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7982.5154 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8002.5154 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8002.8321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8005.8321 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8006.2121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8012.2121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8015.2121 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8015.9721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8021.9721 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8024.9721 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8026.1121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8032.1121 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8035.1121 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8036.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 15 | 250000 | ACTION | 8051.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8057.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8060.6321 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8061.6321 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8063.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8073.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8079.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8080.1321 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8081.1321 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8086.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8087.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8091.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8092.1321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8093.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8094.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8098.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8099.1321 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8100.6321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8104.1321 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8104.4487 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8107.692 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8111.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8115.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8119.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8123.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8127.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8129.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8130.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8132.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8134.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 37 | 616666.6667 | ACTION | 8171.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8175.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8179.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8183.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8187.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8191.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8192.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8194.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8195.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8199.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8203.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8207.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8211.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8215.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8217.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8218.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8220.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8224.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8228.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8232.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8236.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8240.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8241.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8243.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8244.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8248.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8252.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8256.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8260.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8264.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8266.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8267.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8269.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8273.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8277.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8281.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8285.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8289.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8290.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8292.192 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8293.692 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8296.9352 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 8338.9352 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8358.9352 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8359.2519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8362.2519 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8362.6319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8368.6319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8371.6319 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8372.3919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8378.3919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8381.3919 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8382.5319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8388.5319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8391.5319 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8393.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8399.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8402.0519 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8403.0519 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8404.5519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8410.5519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8411.5519 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8412.5519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8414.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 38 | 633333.3333 | ACTION | 8452.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8455.5519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8456.5519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8458.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8461.5519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8462.5519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8464.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8467.5519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8467.8686 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8487.8686 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8488.1852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8491.1852 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8491.5652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8497.5652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8500.5652 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8501.3252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8507.3252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8510.3252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8511.4652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8517.4652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8520.4652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8521.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8527.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8530.9852 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8531.9852 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8533.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8539.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8540.4852 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8541.4852 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8543.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8544.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8548.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8549.4852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8550.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8554.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8555.4852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8556.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8560.4852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8560.8019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8580.8019 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8581.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8584.1186 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 8592.1186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8592.4986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8602.4986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8608.4986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8611.4986 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8612.2586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8618.2586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8621.2586 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8622.3986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8628.3986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8631.3986 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8632.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8638.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8641.9186 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8642.9186 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8644.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 77 | 1283333.3333 | ACTION | 8721.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8727.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8728.4186 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8729.4186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8730.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8734.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8735.4186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8736.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8740.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8741.4186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8742.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8746.4186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8746.7352 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8766.7352 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8767.0519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8770.0519 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8770.4319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8776.4319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8779.4319 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8780.1919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8786.1919 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8789.1919 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8790.3319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8796.3319 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8799.3319 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8800.8519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8806.8519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8809.8519 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8810.8519 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8812.3519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8818.3519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8819.3519 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8820.3519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8821.8519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8825.3519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8826.3519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8827.8519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8831.3519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8832.3519 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8833.8519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8837.3519 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8837.6686 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8857.6686 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8857.9852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8860.9852 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8861.3652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8867.3652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8870.3652 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8871.1252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8877.1252 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8880.1252 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8881.2652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8887.2652 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8890.2652 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8891.7852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8897.7852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8900.7852 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8901.7852 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8903.2852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8909.2852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8910.2852 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8911.2852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8912.7852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8916.2852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8917.2852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8918.7852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8922.2852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8923.2852 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8924.7852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8928.2852 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8928.6019 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 8948.6019 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8948.9186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8951.9186 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8952.2986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8958.2986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8961.2986 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8962.0586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8968.0586 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8971.0586 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8972.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 26 | 433333.3333 | ACTION | 8998.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9004.1986 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9007.1986 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9008.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9014.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9017.7186 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9018.7186 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 9021.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9023.2186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9029.2186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9030.2186 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9031.2186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9032.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9036.2186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9037.2186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9038.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9042.2186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9043.2186 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9044.7186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9048.2186 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9048.5352 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9051.7785 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9055.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9059.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9063.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9067.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9071.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9073.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9074.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9076.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9080.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9084.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9088.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9092.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9096.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9097.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9099.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9100.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9104.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9108.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9112.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9116.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9120.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9122.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9123.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9125.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9129.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9133.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9137.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9141.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9145.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9146.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9148.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9149.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9153.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9157.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9161.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9165.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9169.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9171.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9172.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9174.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9178.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9182.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9186.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9190.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9194.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9195.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9197.2785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9198.7785 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9202.0217 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9222.0217 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9222.3384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9225.3384 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9225.7184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9231.7184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9234.7184 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9235.4784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9241.4784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9244.4784 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9245.6184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9251.6184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9254.6184 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9256.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9262.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9265.1384 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9266.1384 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9267.6384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9273.6384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9274.6384 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9275.6384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9277.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9280.6384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9281.6384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9283.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9286.6384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9287.6384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9289.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9292.6384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9292.955 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9312.955 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9313.2717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9316.2717 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 9319.2717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9319.6517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 9 | 150000 | ACTION | 9328.6517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9334.6517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9337.6517 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9338.4117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9344.4117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9347.4117 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9348.5517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9354.5517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9357.5517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9359.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9365.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9368.0717 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9369.0717 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9370.5717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9376.5717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9377.5717 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9378.5717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9380.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9383.5717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9384.5717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9386.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9389.5717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9390.5717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9392.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9395.5717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9395.8884 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9415.8884 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9416.205 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9419.205 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9419.585 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9425.585 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9428.585 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9429.345 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9435.345 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9438.345 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9439.485 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9445.485 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9448.485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9450.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9456.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9459.005 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9460.005 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9462.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9463.505 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9469.505 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9470.505 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9471.505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9473.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9476.505 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9477.505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9479.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9482.505 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9483.505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9485.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9488.505 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9488.8217 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9508.8217 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9509.1384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9512.1384 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9512.5184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9518.5184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9521.5184 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 9530.5184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9531.2784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9532.2784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9538.2784 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9541.2784 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9542.4184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 11 | 183333.3333 | ACTION | 9553.4184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9559.4184 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9562.4184 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9563.9384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9569.9384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9572.9384 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9573.9384 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9575.4384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9581.4384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9582.4384 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9583.4384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9584.9384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9588.4384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9589.4384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9590.9384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9594.4384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9595.4384 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9596.9384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9600.4384 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9600.755 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9620.755 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9621.0717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9624.0717 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9624.4517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9630.4517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9633.4517 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9634.2117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9640.2117 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9643.2117 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9644.3517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9650.3517 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9653.3517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9654.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9660.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9663.8717 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9664.8717 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9666.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 8 | 133333.3333 | ACTION | 9674.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9680.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9681.3717 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9682.3717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9683.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9687.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9688.3717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9689.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9693.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9694.3717 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9695.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9697.8717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9701.3717 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9701.6884 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9721.6884 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9722.005 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9725.005 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9725.385 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9731.385 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9734.385 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9735.145 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9741.145 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9744.145 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9745.285 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9751.285 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9754.285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9755.805 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9761.805 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9764.805 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9765.805 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9767.305 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9773.305 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9774.305 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9775.305 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9776.805 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9780.305 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9781.305 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9782.805 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9786.305 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9787.305 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9788.805 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9792.305 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9792.6217 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9795.8649 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9799.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9803.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9807.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9811.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9815.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9817.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9818.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9820.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9824.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9828.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9832.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9836.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9840.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9841.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9843.3649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9844.8649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9848.1082 | TurbineInstallation
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9868.1082 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9868.4249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9871.4249 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9871.8049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9877.8049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9880.8049 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9881.5649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9887.5649 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9890.5649 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9891.7049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9897.7049 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9900.7049 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9902.2249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9908.2249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9911.2249 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9912.2249 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9913.7249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9919.7249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9920.7249 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9921.7249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9923.2249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9926.7249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9927.7249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9929.2249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9932.7249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9933.7249 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9935.2249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9938.7249 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9939.0415 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Position Onsite | 20 | 333333.3333 | ACTION | 9959.0415 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9959.3582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9962.3582 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9962.7382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9968.7382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9971.7382 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9972.4982 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9978.4982 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9981.4982 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9982.6382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9988.6382 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9991.6382 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9993.1582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9999.1582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10002.1582 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10003.1582 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10004.6582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10010.6582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10011.6582 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10012.6582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10014.1582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10017.6582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10018.6582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10020.1582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10023.6582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10024.6582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10026.1582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10029.6582 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10029.9749 | TurbineInstallation | TurbineInstallation | 20 |  | 22.5 | 150