## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 23.2432 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 33.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 38.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 39.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 49.6599 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 51.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 52.383 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 52.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 53.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 54.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 64.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 65.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 74.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 75.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 79.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 85.0029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 88.2461 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 100.2461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 108.2461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 111.4894 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 121.4894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 126.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 127.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 137.906 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 142.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 143.6291 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 143.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 144.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 147.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 148.8324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 158.8324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 159.8324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 160.8324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 164.8324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 170.249 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 173.4923 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 185.4923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 193.4923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 196.7355 | MonopileInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 203.7355 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 213.7355 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 219.1522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 220.1522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 230.1522 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 230.8752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 230.8785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 231.8785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 233.0785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 243.0785 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 244.0785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 245.0785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 249.0785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 254.4952 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 257.7384 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 269.7384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 277.7384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 280.9816 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 290.9816 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 296.3983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 297.3983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 307.3983 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 308.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 308.1246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 309.1246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 310.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 320.3246 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 321.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 322.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 326.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 331.7413 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 334.9845 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 346.9845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 354.9845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 358.2278 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 368.2278 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 373.6445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 374.6445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 384.6445 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 385.3675 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 385.3708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 386.3708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 387.5708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 397.5708 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 398.5708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 399.5708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 403.5708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 408.9874 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 412.2307 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 424.2307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 432.2307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 435.4739 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 439.4739 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 449.4739 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 453.4739 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 458.8906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 459.8906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 469.8906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 470.6137 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 470.6169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 471.6169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 472.8169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 482.8169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 483.8169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 484.8169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 488.8169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 494.2336 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 497.4768 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 509.4768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 517.4768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 520.7201 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 530.7201 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 536.1367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 537.1367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 547.1367 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 547.8598 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 547.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 548.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 550.063 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 560.063 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 561.063 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 562.063 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 566.063 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 571.4797 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 574.7229 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 586.7229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 594.7229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 597.9662 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 607.9662 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 613.3829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 614.3829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 624.3829 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 625.1059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 625.1092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 626.1092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 627.3092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 637.3092 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 638.3092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 639.3092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 643.3092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 648.7258 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 651.9691 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 663.9691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 671.9691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 675.2123 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 685.2123 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 690.629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 691.629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 701.629 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 702.3521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 702.3553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 703.3553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 704.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 714.5553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 715.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 716.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 720.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 725.972 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 729.2152 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 741.2152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 749.2152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 752.4585 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 762.4585 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 767.8751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 768.8751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 778.8751 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 779.5982 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 779.6014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 780.6014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 781.8014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 791.8014 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 792.8014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 793.8014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 797.8014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 803.2181 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 806.4614 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 818.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 826.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 829.7046 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 839.7046 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 845.1213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 846.1213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 856.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 856.8443 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 856.8476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 857.8476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 859.0476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 869.0476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 870.0476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 871.0476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 875.0476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 880.4642 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3 | 50000 | ACTION | 883.4642 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 885.4642 | MonopileInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 885.7075 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 897.7075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 905.7075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 908.9507 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 918.9507 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 924.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 925.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 935.3674 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 936.0905 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 936.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 937.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 938.2937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 948.2937 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 949.2937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 950.2937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 954.2937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 959.7104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 962.9536 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 974.9536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 982.9536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 986.1969 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 996.1969 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1001.6135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1002.6135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1012.6135 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1013.3366 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1013.3398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1014.3398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1015.5398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1025.5398 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1026.5398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1027.5398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1031.5398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1036.9565 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1040.1998 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1052.1998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1060.1998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1063.443 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1073.443 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1078.8597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1079.8597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1089.8597 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1090.5827 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1090.586 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1091.586 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1092.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1102.786 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1103.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1104.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1108.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1114.2027 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1117.4459 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1129.4459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1137.4459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1140.6891 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1150.6891 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1156.1058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1157.1058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1167.1058 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1167.8289 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1167.8321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1168.8321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1170.0321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1180.0321 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1181.0321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1182.0321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1186.0321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1191.4488 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1194.692 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1206.692 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1214.692 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1217.9353 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1227.9353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1233.3519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1234.3519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1244.3519 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1245.075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1245.0783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1246.0783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1247.2783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1257.2783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1258.2783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1259.2783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1263.2783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1268.6949 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1271.9382 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1283.9382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1291.9382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1295.1814 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1305.1814 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1310.5981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1311.5981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1321.5981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1322.3211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1322.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1323.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1324.5244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1334.5244 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1335.5244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1336.5244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1340.5244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1345.9411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1349.1843 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1361.1843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1369.1843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1372.4275 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1382.4275 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1387.8442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1388.8442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1398.8442 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1399.5673 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1399.5705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1400.5705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1401.7705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1411.7705 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1412.7705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 1416.7705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1417.7705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1421.7705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1427.1872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1430.4304 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1442.4304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1450.4304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1453.6737 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1463.6737 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1469.0903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1470.0903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1480.0903 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1480.8134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1480.8167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1481.8167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1483.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1493.0167 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1494.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1495.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1499.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1504.4333 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1507.6766 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1519.6766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1527.6766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1530.9198 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1540.9198 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1546.3365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1547.3365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1557.3365 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1558.0595 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 1560.0595 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1560.0628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1561.0628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1562.2628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1572.2628 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1573.2628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1574.2628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1578.2628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1583.6795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1586.9227 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1598.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1606.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1610.166 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1620.166 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1625.5826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1626.5826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1636.5826 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1637.3057 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1637.3089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1638.3089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1639.5089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1649.5089 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1650.5089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1651.5089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1655.5089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1660.9256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1664.1688 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1676.1688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1684.1688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1687.4121 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1697.4121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1702.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1703.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1713.8288 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1714.5518 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1714.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1715.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1716.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1726.7551 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1727.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1728.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1732.7551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1738.1717 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1741.415 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1753.415 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1761.415 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1764.6582 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1774.6582 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1780.0749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1781.0749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1791.0749 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1791.798 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1791.8012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1792.8012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1794.0012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1804.0012 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1805.0012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1806.0012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1810.0012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1815.4179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1818.6611 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1830.6611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1838.6611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1841.9044 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1851.9044 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1857.321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1858.321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1868.321 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1869.0441 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1869.0473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1870.0473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1871.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1881.2473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1882.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1883.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1887.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1892.664 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1895.9072 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1907.9072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1915.9072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1919.1505 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1929.1505 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1934.5672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1935.5672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1945.5672 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1946.2902 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1946.2935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1947.2935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1948.4935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1958.4935 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1959.4935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1960.4935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1964.4935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1969.9101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1973.1534 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1985.1534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1993.1534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1996.3966 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2006.3966 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2011.8133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2012.8133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2022.8133 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2023.5364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2023.5396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2024.5396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2025.7396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2035.7396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2036.7396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2037.7396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2041.7396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2047.1563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2050.3995 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2062.3995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2070.3995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2073.6428 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2083.6428 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2089.0594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2090.0594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2100.0594 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2100.7825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2100.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2101.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2102.9857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2112.9857 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2113.9857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2114.9857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2118.9857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2124.4024 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2127.6457 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2139.6457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2147.6457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2150.8889 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2160.8889 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2166.3056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2167.3056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2177.3056 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2178.0286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2178.0319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2179.0319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2180.2319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2190.2319 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2191.2319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2192.2319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2196.2319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2201.6485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2204.8918 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2216.8918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2224.8918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2228.135 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2238.135 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2243.5517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2244.5517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2254.5517 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2255.2748 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2255.278 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2256.278 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2257.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2267.478 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2268.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2269.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2273.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2278.8947 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2282.1379 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2294.1379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2302.1379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2305.3812 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2315.3812 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2320.7978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2321.7978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2331.7978 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2332.5209 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2332.5242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2333.5242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2334.7242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2344.7242 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2345.7242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2346.7242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2350.7242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2356.1408 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2359.3841 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2371.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2379.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2382.6273 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2392.6273 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2398.044 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2399.044 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2409.044 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2409.767 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2409.7703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2410.7703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2411.9703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2421.9703 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2422.9703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2423.9703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2427.9703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2433.387 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2436.6302 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2448.6302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2456.6302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2459.8734 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2469.8734 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2475.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2476.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2486.2901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2487.0132 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2487.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2488.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2489.2164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2499.2164 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2500.2164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2501.2164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2505.2164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2510.6331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2513.8763 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2525.8763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2533.8763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2537.1196 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2547.1196 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2552.5362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2553.5362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2563.5362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2564.2593 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2564.2626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2565.2626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2566.4626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2576.4626 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2577.4626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2578.4626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2582.4626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2587.8792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2591.1225 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2603.1225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2611.1225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2614.3657 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2624.3657 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2629.7824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2630.7824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2640.7824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2641.5054 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2641.5087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2642.5087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2643.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2653.7087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2654.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2655.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2659.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2665.1254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2668.3686 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2680.3686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2688.3686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2691.6118 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2701.6118 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2707.0285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2708.0285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2718.0285 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2718.7516 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2718.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2719.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2720.9548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2730.9548 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2731.9548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2732.9548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 48 | 800000 | ACTION | 2780.9548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2784.9548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2790.3715 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2793.6147 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2805.6147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2813.6147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2816.858 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2826.858 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2832.2746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2833.2746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2843.2746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2843.9977 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2844.001 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2845.001 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2846.201 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2856.201 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2857.201 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2858.201 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2862.201 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2867.6176 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2870.8609 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2882.8609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2890.8609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2894.1041 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2904.1041 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2909.5208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2910.5208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2920.5208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2921.2438 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2921.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2922.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2923.4471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2933.4471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2934.4471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2935.4471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2939.4471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2944.8638 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2948.107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2960.107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2968.107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2971.3503 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2981.3503 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2986.7669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2987.7669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2997.7669 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2998.49 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2998.4932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2999.4932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3000.6932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3010.6932 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3011.6932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3012.6932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 350000 | ACTION | 3033.6932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3037.6932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3043.1099 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 2 | 33333.3333 | ACTION | 3045.1099 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3046.1099 | MonopileInstallation
| WTIV | Transit | 1.2432 | 20720.7207 | ACTION | 3047.3531 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3059.3531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3067.3531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3070.5964 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3080.5964 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3086.0131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3087.0131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3097.0131 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3097.7361 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3097.7394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3098.7394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3099.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3109.9394 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3110.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3111.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3115.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3121.356 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3124.5993 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3136.5993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3144.5993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3147.8425 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3157.8425 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3163.2592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3164.2592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3174.2592 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3174.9823 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3174.9855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3175.9855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3177.1855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3187.1855 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3188.1855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3189.1855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3193.1855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3198.6022 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3201.8454 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3213.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3221.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3225.0887 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3235.0887 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3240.5053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3241.5053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3251.5053 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3252.2284 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3252.2316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3253.2316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3254.4316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3264.4316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3265.4316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3266.4316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3270.4316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3275.8483 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3279.0915 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3291.0915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3299.0915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3302.3348 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3312.3348 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3317.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3318.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3328.7515 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3329.4745 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3329.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3330.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3331.6778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3341.6778 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3342.6778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3352.6778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3353.6778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3357.6778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3363.0944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3366.3377 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3378.3377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3386.3377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3389.5809 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3399.5809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3404.9976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3405.9976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3415.9976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3416.7207 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3416.7239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3417.7239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3418.9239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3428.9239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3429.9239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3430.9239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3435.9239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3439.9239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3445.3406 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3448.5838 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3460.5838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3468.5838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3471.8271 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3481.8271 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3487.2437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3488.2437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3498.2437 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3498.9668 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3498.97 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3499.97 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3501.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3511.17 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3512.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3513.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3517.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3522.5867 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3525.83 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3537.83 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3545.83 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3549.0732 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3559.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3564.4899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3565.4899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3575.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3576.2129 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3576.2162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3577.2162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3578.4162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3588.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3589.4162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3590.4162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3594.4162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3599.8328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3603.0761 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3615.0761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3623.0761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3626.3193 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3636.3193 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3641.736 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3642.736 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3652.736 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3653.4591 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3653.4623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3654.4623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3655.6623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3665.6623 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3666.6623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 37 | 616666.6667 | ACTION | 3703.6623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3704.6623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3708.6623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3714.079 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3717.3222 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3729.3222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3737.3222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3740.5655 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3750.5655 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3755.9821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3756.9821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3761.9821 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3771.9821 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3772.7052 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3772.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3773.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3774.9085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3784.9085 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3785.9085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3786.9085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3790.9085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3796.3251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3799.5684 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3811.5684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3819.5684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3822.8116 | MonopileInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 3834.8116 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3844.8116 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3850.2283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3851.2283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3861.2283 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3861.9513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3861.9546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3862.9546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3864.1546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3874.1546 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3875.1546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3876.1546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3880.1546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3885.5713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3888.8145 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3900.8145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3908.8145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3912.0577 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3922.0577 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3927.4744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3928.4744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3938.4744 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3939.1975 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3939.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3940.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3941.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3951.4007 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3952.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3953.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3957.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3962.8174 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3966.0606 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3978.0606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3986.0606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3989.3039 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3999.3039 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4004.7205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 4005.7205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 4015.7205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 4016.4436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 4016.4469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4017.4469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 733333.3333 | ACTION | 4061.4469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 4062.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 4072.6469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4073.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 4074.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 4078.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4084.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 4084.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4086.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4088.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4090.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4092.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4094.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4094.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4095.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4096.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4098.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4100.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4102.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4104.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4106.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4107.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4107.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4108.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4110.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4112.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4114.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4116.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4118.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4119.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4120.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4120.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4124.0568 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4134.0568 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4139.4734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4140.4734 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4140.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4142.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4143.8534 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4144.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4146.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4147.6134 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4148.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4150.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4151.7534 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4153.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4155.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4156.2734 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4157.2734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4158.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4160.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4161.7734 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4162.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4163.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4165.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4165.7734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4167.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4168.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4169.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4170.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4172.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4177.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4187.6901 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4193.1068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4194.1068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4194.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4196.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4197.4868 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4202.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4203.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4205.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4206.2468 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4207.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4209.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4210.3868 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4211.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4213.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4214.9068 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4215.9068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4217.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4219.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4220.4068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4220.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4222.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4223.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4224.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4225.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4227.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4227.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4229.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4230.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4236.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4246.3234 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4251.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4252.7401 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4253.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4255.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4256.1201 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4256.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4258.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4259.8801 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4261.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4263.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4264.0201 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4265.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4267.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4268.5401 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4269.5401 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4279.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4281.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4283.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4285.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4286.0401 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4286.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4288.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4289.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4290.0401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4291.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4293.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4293.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4295.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4296.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4301.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4305.2 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4307.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4309.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4311.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4313.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4315.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4315.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4316.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4317.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4319.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4321.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4323.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4325.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4327.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4328.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4328.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4329.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4331.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4333.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4335.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4337.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4339.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4340.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4341.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4341.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4345.1933 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4355.1933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4360.6099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4361.6099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4361.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4363.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4364.9899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4365.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4370.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4372.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4373.7499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4374.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4376.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4377.8899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4379.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4381.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4382.4099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4383.4099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4384.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4386.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4387.9099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4388.4099 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4402.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4403.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4405.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4405.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4407.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4408.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4409.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4410.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4412.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4417.8266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4427.8266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4433.2433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4434.2433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4434.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4436.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4437.6233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4438.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4440.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4441.3833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4442.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4444.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4445.5233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4447.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4449.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4450.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4451.0433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4452.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4454.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4455.5433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4456.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4457.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4459.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4459.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4461.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4462.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4463.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4464.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4466.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4471.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4481.4599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4486.8766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4487.8766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4488.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 62 | 1033333.3333 | ACTION | 4550.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4552.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4553.2566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4554.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4556.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4557.0166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4558.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4560.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4561.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4562.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4564.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4565.6766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4566.6766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4568.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4570.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4571.1766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4571.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4573.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4574.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4575.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4576.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4578.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4578.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4580.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4581.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4587.0933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4590.3365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4592.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4594.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4596.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4597.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4599.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4602.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4604.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4605.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4605.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4606.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4608.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4610.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4612.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4614.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4616.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4618.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4619.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4620.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4620.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4622.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4624.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4626.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4628.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4630.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4631.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4632.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4633.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4636.3297 | TurbineInstallation
| WTIV | Delay | 66 | 1100000 | ACTION | 4702.3297 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4712.3297 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4717.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4718.7464 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4719.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4721.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4722.1264 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4722.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4724.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4725.8864 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4727.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4729.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4730.0264 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4731.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4733.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4734.5464 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4735.5464 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4737.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4739.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4740.0464 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4740.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4742.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4743.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4744.0464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4745.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4747.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4747.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4749.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4750.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4755.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4765.9631 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4771.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4772.3797 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4772.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4774.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4775.7597 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4776.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4778.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4779.5197 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4780.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4782.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4783.6597 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4785.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4787.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4788.1797 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4789.1797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4790.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4792.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4793.6797 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4794.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4795.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4797.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4797.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4799.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4800.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4801.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4802.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4834.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4836.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4841.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4851.5964 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4857.0131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4858.0131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4858.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4860.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4861.3931 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4862.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4864.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4865.1531 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4866.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4868.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4869.2931 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4870.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4872.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4873.8131 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4874.8131 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4876.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4878.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4879.3131 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4879.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4881.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4882.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4883.3131 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4888.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4889.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4891.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4891.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4893.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4894.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4900.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4903.473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4905.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4907.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4909.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4911.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4913.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4914.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4914.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4915.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4917.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4919.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4921.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4923.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4925.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4926.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4927.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4927.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4929.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4931.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4933.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4935.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4937.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4938.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4939.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4940.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4943.4662 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4953.4662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4958.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4959.8829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4960.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4962.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4963.2629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4964.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4966.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4967.0229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4968.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4970.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4971.1629 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 4982.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4983.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4985.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4986.6829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4987.6829 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4991.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4993.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4995.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4996.1829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4996.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4998.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4999.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5000.1829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5001.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5003.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5003.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5005.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5006.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5012.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 5022.0996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5027.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5028.5162 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5030.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5030.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5032.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5033.8962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5034.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5036.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5037.6562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5038.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5040.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5041.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5043.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5045.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5046.3162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5047.3162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5048.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5050.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5051.8162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5052.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5053.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5055.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5055.8162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5057.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5058.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5059.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5060.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5062.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5067.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 5077.7329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5083.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5084.1496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5084.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5086.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5087.5296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5088.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5090.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5091.2896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5092.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5094.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5095.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5096.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5098.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5099.9496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5100.9496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5102.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5104.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5105.4496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5105.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5107.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5108.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5109.4496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5110.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5112.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5112.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5114.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5115.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5121.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5124.6095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5126.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5128.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5130.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5132.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5134.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5135.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5136.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5136.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5138.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5140.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5142.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5144.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5146.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5147.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5148.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5149.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5151.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5153.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1256 | 20933333.3333 | ACTION | 6409.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6411.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6413.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6415.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6415.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6416.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6417.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6420.6027 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6430.6027 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6436.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6437.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6437.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6439.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6440.3994 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6441.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6443.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6444.1594 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6445.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6447.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6448.2994 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6449.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6451.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6452.8194 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6453.8194 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6455.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6457.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6458.3194 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6458.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6460.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6461.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6462.3194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6463.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6465.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6465.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6467.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6468.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6474.236 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6484.236 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6489.6527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6490.6527 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6491.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6493.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6494.0327 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6494.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6496.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6497.7927 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6498.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6500.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6501.9327 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6516.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6518.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6520.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6521.4527 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6522.4527 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6523.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6525.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6526.9527 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6527.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6528.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6530.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6530.9527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6532.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6533.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6534.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6535.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6537.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6542.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6552.8694 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6558.286 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6559.286 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6559.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6561.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6562.666 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6563.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6565.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6566.426 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6567.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6569.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6570.566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6572.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6574.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6575.086 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6576.086 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6577.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6579.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6580.586 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6581.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6582.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6584.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6584.586 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6586.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6587.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6588.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6589.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6591.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6596.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6599.746 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6601.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6603.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6605.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6607.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6609.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6610.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6611.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6611.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6613.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6615.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6617.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6619.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6621.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6622.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6623.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6624.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6626.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6628.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6630.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6632.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6634.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6634.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6635.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6636.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6639.7392 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6649.7392 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6655.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6656.1559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6656.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6658.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6659.5359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6660.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6662.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6663.2959 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6665.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6667.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6668.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6669.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6671.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6672.9559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6673.9559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6675.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6677.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6678.4559 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6678.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6680.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6681.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6682.4559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6683.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6685.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6685.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6687.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6688.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6694.3725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6704.3725 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6709.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6710.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6711.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6713.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6714.1692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6714.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6716.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6717.9292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6719.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6721.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6722.0692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6723.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6725.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6726.5892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6727.5892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6729.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6731.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6732.0892 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6732.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6734.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6735.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6736.0892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6737.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6739.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6739.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6741.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 6757.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6758.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6764.0059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6774.0059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6779.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6780.4225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6780.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6782.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6783.8025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6784.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6786.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6787.5625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6788.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6790.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6791.7025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6793.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6795.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6796.2225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6797.2225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6798.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6800.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6801.7225 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6802.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6803.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6805.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6805.7225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6807.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6808.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6809.2225 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6823.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6824.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6826.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6831.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6834.8824 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6836.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6838.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6840.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6842.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6844.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6845.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6846.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6847.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6849.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6851.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6853.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6855.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6857.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6857.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6858.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6859.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6861.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6863.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6865.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6867.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6869.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6870.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6870.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6871.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6874.8757 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6884.8757 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6890.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6891.2924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6891.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6893.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6894.6724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6895.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6897.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6898.4324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6899.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6901.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6902.5724 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6904.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6906.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6907.0924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6908.0924 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 6915.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6916.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6918.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6919.5924 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6920.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6921.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6923.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6923.5924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6925.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6926.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6927.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6928.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6930.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6935.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6945.509 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6950.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6951.9257 | TurbineInstallation
| WTIV | Delay | 24 | 400000 | ACTION | 6975.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6976.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6978.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6979.3057 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6980.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 6983.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6985.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6986.0657 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6987.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6989.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6990.2057 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6991.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6993.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6994.7257 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6995.7257 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6997.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6999.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7000.2257 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7000.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7002.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7003.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7004.2257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7005.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7007.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7007.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7009.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7010.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7016.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7026.1424 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7031.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7032.559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7032.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7034.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7035.939 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7036.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7038.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7039.699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7040.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7042.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7043.839 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7045.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7049.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7051.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7052.359 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7053.359 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7055.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7056.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 36 | 600000 | ACTION | 7092.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7094.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7095.859 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7096.359 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7097.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7099.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7099.859 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7101.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7102.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7103.359 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7104.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7106.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7111.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7115.0189 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7117.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7119.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7121.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7123.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7125.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7125.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7126.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7127.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7129.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7131.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7133.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7135.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7137.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7138.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7138.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7139.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7141.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7143.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7145.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7147.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7149.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7150.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7151.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7151.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7155.0122 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7165.0122 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7170.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7171.4288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7171.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7173.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7174.8088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7175.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7177.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7178.5688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7179.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7181.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7182.7088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7184.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7186.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7187.2288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7188.2288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7189.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7191.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7192.7288 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7193.2288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7194.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7196.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7196.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7198.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7199.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7200.2288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7201.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7203.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7208.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 216666.6667 | ACTION | 7221.6455 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7231.6455 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7237.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7238.0622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7238.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7240.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7241.4422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7242.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7244.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7245.2022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7246.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7248.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7249.3422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7250.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7252.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7253.8622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7254.8622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7256.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7258.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7259.3622 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7259.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7261.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7262.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7263.3622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7264.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7266.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7266.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7268.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7269.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7275.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7285.2788 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7295.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7300.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7301.6955 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7306.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7307.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7309.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7310.0755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7310.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7312.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7313.8355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7314.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7316.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7317.9755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7319.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7321.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7322.4955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7323.4955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7324.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7326.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7327.9955 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7328.4955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7329.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7331.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7331.9955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7333.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7334.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7335.4955 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7338.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7339.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 7348.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7350.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7355.9122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7359.1554 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7361.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7363.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7365.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7367.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7369.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7369.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7370.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7371.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7373.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7375.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7377.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7379.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7381.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7382.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7382.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7383.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7385.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7387.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7389.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7391.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7393.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7394.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7395.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7395.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7399.1487 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7409.1487 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7414.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7415.5653 | TurbineInstallation
| WTIV | Delay | 50 | 833333.3333 | ACTION | 7465.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7465.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7467.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7468.9453 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7469.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7471.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7472.7053 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7473.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7475.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7476.8453 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7478.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7480.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7481.3653 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7482.3653 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7483.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7485.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7486.8653 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7487.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7488.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7490.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7490.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7492.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7493.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7494.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7495.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7497.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7502.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7512.782 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7518.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7519.1987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7519.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7521.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7522.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7523.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7549.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7551.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7552.3387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7553.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7555.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7556.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7557.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7559.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7560.9987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7561.9987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7563.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7565.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7566.4987 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7566.9987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7568.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7569.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7570.4987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7571.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7573.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7573.9987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7575.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7576.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7582.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7592.4153 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7597.832 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7598.832 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7599.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7601.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7602.212 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7603.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7603.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7605.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7606.972 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7608.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7610.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7611.112 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7612.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7614.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7615.632 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7616.632 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7618.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7620.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7621.132 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7621.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7623.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7624.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7625.132 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7626.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7628.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7628.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7630.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7631.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7637.0487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7640.2919 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7642.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7644.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7646.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7648.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7650.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7651.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7651.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7652.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7654.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7656.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7658.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7660.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7662.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7663.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7664.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7664.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7666.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7668.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7670.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7672.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7674.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7675.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7676.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7677.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7680.2851 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7690.2851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7695.7018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7696.7018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7697.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7699.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7700.0818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7700.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7702.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7703.8418 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7704.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7706.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7707.9818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7709.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7711.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7712.5018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7713.5018 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7714.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7716.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 7725.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7727.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7728.0018 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7728.5018 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7731.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7733.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7734.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7735.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7736.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7738.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7738.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7740.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7741.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7746.9185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7756.9185 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7762.3351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7763.3351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7763.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7765.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7766.7151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7767.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7769.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7770.4751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7771.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7773.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7774.6151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7776.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7778.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7779.1351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7780.1351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7781.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7783.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7784.6351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7785.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7786.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7788.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7788.6351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7790.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7791.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7792.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7793.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7795.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7800.5518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7810.5518 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7815.9685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7816.9685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7817.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7819.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7820.3485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7821.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7823.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7824.1085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7825.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7827.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7828.2485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7829.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7831.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7832.7685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7833.7685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7835.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7837.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7838.2685 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7838.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7840.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7841.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7842.2685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7843.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7845.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7845.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7847.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7848.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7854.1851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7857.4284 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7859.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7861.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7863.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7865.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7867.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7868.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7868.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7869.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7871.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7873.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7875.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7877.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7879.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7880.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7881.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7881.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7883.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7885.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7887.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7889.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7891.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7892.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7893.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7894.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7897.4216 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7907.4216 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7912.8383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7913.8383 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7914.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7916.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7917.2183 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7917.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7919.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7920.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7922.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7924.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7925.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7926.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7928.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7929.6383 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7930.6383 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7932.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7934.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7935.1383 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7935.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7937.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7938.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7939.1383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7940.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7942.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7942.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7944.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7945.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7946.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7952.055 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7962.055 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7967.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7968.4716 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7968.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7970.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7971.8516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7972.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7974.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7975.6116 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7976.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7978.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7979.7516 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7981.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7983.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7984.2716 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7985.2716 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7986.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7988.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7989.7716 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7990.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7991.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7993.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7993.7716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7995.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7996.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7997.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7998.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8000.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8005.6883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8015.6883 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8021.105 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8022.105 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8022.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8024.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8025.485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8026.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8028.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8029.245 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8030.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8032.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8033.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8034.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8036.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8037.905 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8038.905 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8040.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 8051.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8053.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8054.405 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8054.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8056.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8057.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8058.405 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8059.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8061.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8061.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8063.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8064.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8070.3216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8073.5649 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8075.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8077.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8079.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8081.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8083.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8084.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8085.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8085.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8087.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8089.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8091.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8093.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8095.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8096.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8097.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8098.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8100.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8102.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8104.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8106.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8108.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8108.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8109.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8110.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8113.5581 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8123.5581 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8128.9748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8129.9748 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 8171.9748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8172.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8174.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8175.3548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8176.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8178.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8179.1148 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8181.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8182.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8184.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8185.2548 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8186.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8188.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8189.7748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8190.7748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8192.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8194.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8195.2748 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8195.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8197.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8198.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8199.2748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8200.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8202.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8202.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8204.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8205.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8211.1915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8221.1915 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8226.6081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8227.6081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8227.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8229.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8230.9881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8231.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8233.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8234.7481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8235.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8237.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8238.8881 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8240.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8242.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8243.4081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8244.4081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8245.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8247.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8248.9081 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8249.4081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8250.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8252.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8252.9081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8254.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8255.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8256.4081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8257.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8259.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8264.8248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8274.8248 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8280.2415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8281.2415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8281.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8283.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8284.6215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8285.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8287.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8288.3815 | TurbineInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 8314.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8315.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8317.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8319.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8320.5215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8322.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8324.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8325.0415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8326.0415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8327.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8329.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8330.5415 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8331.0415 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 8342.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8343.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8345.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8345.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8347.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8348.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8349.0415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8350.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8352.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8357.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8360.7014 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8362.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8364.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8366.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8368.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8370.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8371.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8372.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8372.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8374.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8376.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8378.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8380.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8382.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8383.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8384.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8385.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8387.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8389.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8391.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8393.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8395.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8395.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8396.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8397.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8400.6946 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8410.6946 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8416.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8417.1113 | TurbineInstallation
| WTIV | Delay | 34 | 566666.6667 | ACTION | 8451.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8451.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8453.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8454.4913 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8455.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8457.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8458.2513 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8459.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8461.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8462.3913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8463.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8465.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8466.9113 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8467.9113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8469.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8471.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8472.4113 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8472.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8474.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8475.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8476.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8477.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8479.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8479.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8481.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8482.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8488.3279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8498.3279 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8503.7446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8504.7446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8505.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8507.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8508.1246 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8508.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8510.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8511.8846 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8513.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8515.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8516.0246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8517.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8519.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8520.5446 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8521.5446 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8523.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8525.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8526.0446 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8526.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8528.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8529.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8530.0446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8531.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8533.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8533.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8535.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8536.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8541.9613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8551.9613 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8557.3779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8558.3779 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8558.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8560.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8561.7579 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8562.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8564.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8565.5179 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8566.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8568.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8569.6579 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8571.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8573.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8574.1779 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8575.1779 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8576.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8578.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8579.6779 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8580.1779 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8602.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8603.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8605.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8605.6779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8607.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8608.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8609.1779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8610.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8612.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8617.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8620.8378 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8622.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8624.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8626.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8628.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8630.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8631.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8632.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8633.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8635.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8637.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8639.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8641.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8643.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8643.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8644.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8645.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8647.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8649.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8651.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8653.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8655.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8656.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8656.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8657.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8660.8311 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 8667.8311 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8677.8311 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8683.2478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8684.2478 | TurbineInstallation
| WTIV | Delay | 33 | 550000 | ACTION | 8717.2478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8717.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8719.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8720.6278 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8721.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8722.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8724.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8725.3878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8726.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8728.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8729.5278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8731.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8733.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8734.0478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8735.0478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8736.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8738.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8739.5478 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8740.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8741.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8743.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8743.5478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8745.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8746.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8747.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8748.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8750.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8755.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8765.4644 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8770.8811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8771.8811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8772.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8774.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8775.2611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8776.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8778.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8779.0211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8780.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8782.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8783.1611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8784.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8786.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8787.6811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8788.6811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8790.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8792.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8793.1811 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8793.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8795.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8796.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8797.1811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8798.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8800.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8800.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8802.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8803.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8809.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8819.0978 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8824.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8825.5144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8825.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8827.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8828.8944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8829.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8831.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8832.6544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8833.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8835.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8836.7944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8838.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8840.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8841.3144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8842.3144 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 8845.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8846.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8848.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8849.8144 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8850.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8851.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8853.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8853.8144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8855.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8856.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8857.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8858.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8860.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8865.7311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8868.9743 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8870.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8872.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8874.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8876.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8878.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8879.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8880.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8881.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8883.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8885.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8887.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8889.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8891.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8891.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8892.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8893.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8895.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8897.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8899.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8901.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8903.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8904.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8904.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8905.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8908.9676 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8918.9676 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8924.3842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8925.3842 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8925.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8927.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8928.7642 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8929.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8931.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8932.5242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8933.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8935.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8936.6642 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8938.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8940.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8941.1842 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8942.1842 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8943.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8945.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8946.6842 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8947.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8948.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8950.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8950.6842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8952.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8953.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8954.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8955.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8957.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8962.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8972.6009 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8978.0176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8979.0176 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8979.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8980.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8982.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8983.3976 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8984.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8985.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 216666.6667 | ACTION | 8998.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9000.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9001.1576 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9002.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9004.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9005.2976 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9006.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9008.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9009.8176 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9010.8176 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9012.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9014.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9015.3176 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9015.8176 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 9021.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9023.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9024.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9025.3176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9026.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9028.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9028.8176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9030.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9031.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9037.2342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9047.2342 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9052.6509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9053.6509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9054.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9056.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9057.0309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9057.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9059.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9060.7909 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9061.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9063.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9064.9309 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9066.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9068.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9069.4509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9070.4509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9071.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9073.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9074.9509 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9075.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9076.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9078.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9078.9509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9080.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9081.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9082.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9083.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9085.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9090.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9094.1108 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9096.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9098.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9100.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9102.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9104.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9104.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9105.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9106.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9108.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9110.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9112.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9114.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9116.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9117.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9117.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9118.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9120.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9122.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9124.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9126.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9128.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9129.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9130.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9130.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9134.1041 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9144.1041 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9149.5207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9150.5207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9150.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9152.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9153.9007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9154.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9156.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9157.6607 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9158.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9160.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9161.8007 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 9164.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9166.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9168.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9169.3207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9170.3207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9171.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9173.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9174.8207 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9175.3207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9176.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9180.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9182.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9182.8207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9184.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9185.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9186.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9187.3207 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 9192.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9193.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9195.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9200.7374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9210.7374 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9216.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9217.1541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9217.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9219.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9220.5341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9221.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9223.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9224.2941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9225.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9227.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9228.4341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9229.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9231.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9232.9541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9233.9541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9235.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9237.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9238.4541 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9238.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9240.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9241.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9242.4541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9243.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9245.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9245.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9247.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9248.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9254.3707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9264.3707 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9269.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9270.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9271.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9273.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9274.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9274.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9276.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9277.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9279.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9281.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9282.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9283.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9285.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9286.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9287.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9289.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9291.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9292.0874 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9292.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9294.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9295.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9296.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9297.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9299.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9299.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9301.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9302.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9308.0041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9311.2473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9313.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9315.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9317.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9319.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9321.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9321.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9322.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9323.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9325.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9327.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9329.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9331.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9333.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9334.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9334.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9335.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9338.9906 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9348.9906 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9354.4072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9355.4072 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9355.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9357.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9358.7872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9359.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9361.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9362.5472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9363.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9365.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9366.6872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9368.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9370.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9371.2072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9372.2072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9373.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9375.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9376.7072 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9377.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9378.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9380.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9380.7072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9382.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9383.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9384.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9385.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9387.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9392.6239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9402.6239 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9408.0406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9409.0406 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9409.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9411.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9412.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9413.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9415.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9416.1806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9417.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9419.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9420.3206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9421.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9423.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9424.8406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9425.8406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9427.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9429.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9430.3406 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9430.8406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9432.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9433.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9434.3406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9435.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9437.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9437.8406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9439.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9440.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9446.2572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5