## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 23.2432 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 33.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 38.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 39.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 49.6599 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 51.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 52.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 52.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 53.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 54.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 64.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 65.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 74.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 75.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 79.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 85.0029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 88.2461 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 100.2461 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 108.2461 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 111.4894 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 121.4894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 126.906 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 127.906 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 137.906 | MonopileInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 142.906 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 143.6291 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 143.6324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 144.6324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 147.6324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 148.8324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 158.8324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 159.8324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 160.8324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 164.8324 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 170.249 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 173.4923 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 185.4923 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 193.4923 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 196.7355 | MonopileInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 203.7355 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 213.7355 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 219.1522 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 220.1522 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 230.1522 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 230.8752 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 230.8785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 231.8785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 233.0785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 243.0785 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 244.0785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 245.0785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 249.0785 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 254.4952 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 257.7384 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 269.7384 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 277.7384 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 280.9816 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 290.9816 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 296.3983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 297.3983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 307.3983 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 308.1214 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 308.1246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 309.1246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 310.3246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 320.3246 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 321.3246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 322.3246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 326.3246 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 331.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 334.9845 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 346.9845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 354.9845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 358.2278 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 368.2278 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 373.6445 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 374.6445 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 384.6445 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 385.3675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 385.3708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 386.3708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 387.5708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 397.5708 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 398.5708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 399.5708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 403.5708 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 408.9874 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 412.2307 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 424.2307 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 432.2307 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 435.4739 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 439.4739 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 449.4739 | MonopileInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 453.4739 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 458.8906 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 459.8906 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 469.8906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 470.6137 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 470.6169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 471.6169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 472.8169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 482.8169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 483.8169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 484.8169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 488.8169 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 494.2336 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 497.4768 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 509.4768 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 517.4768 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 520.7201 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 530.7201 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 536.1367 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 537.1367 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 547.1367 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 547.8598 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 547.863 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 548.863 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 550.063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 560.063 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 561.063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 562.063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 566.063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 571.4797 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 574.7229 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 586.7229 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 594.7229 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 597.9662 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 607.9662 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 613.3829 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 614.3829 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 624.3829 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 625.1059 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 625.1092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 626.1092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 627.3092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 637.3092 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 638.3092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 639.3092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 643.3092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 648.7258 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 651.9691 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 663.9691 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 671.9691 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 675.2123 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 685.2123 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 690.629 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 691.629 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 701.629 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 702.3521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 702.3553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 703.3553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 704.5553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 714.5553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 715.5553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 716.5553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 720.5553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 725.972 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 729.2152 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 741.2152 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 749.2152 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 752.4585 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 762.4585 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 767.8751 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 768.8751 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 778.8751 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 779.5982 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 779.6014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 780.6014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 781.8014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 791.8014 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 792.8014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 793.8014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 797.8014 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 803.2181 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 806.4614 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 818.4614 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 826.4614 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 829.7046 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 839.7046 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 845.1213 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 846.1213 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 856.1213 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 856.8443 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 856.8476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 857.8476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 859.0476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 869.0476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 870.0476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 871.0476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 875.0476 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 880.4642 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3 | 50000 | ACTION | 883.4642 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 885.4642 | MonopileInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 885.7075 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 897.7075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 905.7075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 908.9507 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 918.9507 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 924.3674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 925.3674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 935.3674 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 936.0905 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 936.0937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 937.0937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 938.2937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 948.2937 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 949.2937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 950.2937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 954.2937 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 959.7104 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 962.9536 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 974.9536 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 982.9536 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 986.1969 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 996.1969 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1001.6135 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1002.6135 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1012.6135 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1013.3366 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1013.3398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1014.3398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1015.5398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1025.5398 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1026.5398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1027.5398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1031.5398 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1036.9565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1040.1998 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1052.1998 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1060.1998 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1063.443 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1073.443 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1078.8597 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1079.8597 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1089.8597 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1090.5827 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1090.586 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1091.586 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1092.786 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1102.786 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1103.786 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1104.786 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1108.786 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1114.2027 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1117.4459 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1129.4459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1137.4459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1140.6891 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1150.6891 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1156.1058 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1157.1058 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1167.1058 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1167.8289 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1167.8321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1168.8321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1170.0321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1180.0321 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1181.0321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1182.0321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1186.0321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1191.4488 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1194.692 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1206.692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1214.692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1217.9353 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1227.9353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1233.3519 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1234.3519 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1244.3519 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1245.075 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1245.0783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1246.0783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1247.2783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1257.2783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1258.2783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1259.2783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1263.2783 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1268.6949 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1271.9382 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1283.9382 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1291.9382 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1295.1814 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1305.1814 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1310.5981 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1311.5981 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1321.5981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1322.3211 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1322.3244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1323.3244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1324.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1334.5244 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1335.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1336.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1340.5244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1345.9411 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1349.1843 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1361.1843 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1369.1843 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1372.4275 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1382.4275 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1387.8442 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1388.8442 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1398.8442 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1399.5673 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1399.5705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1400.5705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1401.7705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1411.7705 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1412.7705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 1416.7705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1417.7705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1421.7705 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1427.1872 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1430.4304 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1442.4304 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1450.4304 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1453.6737 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1463.6737 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1469.0903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1470.0903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1480.0903 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1480.8134 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1480.8167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1481.8167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1483.0167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1493.0167 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1494.0167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1495.0167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1499.0167 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1504.4333 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1507.6766 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1519.6766 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1527.6766 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1530.9198 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1540.9198 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1546.3365 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1547.3365 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1557.3365 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1558.0595 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 1560.0595 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1560.0628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1561.0628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1562.2628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1572.2628 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1573.2628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1574.2628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1578.2628 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1583.6795 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1586.9227 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1598.9227 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1606.9227 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1610.166 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1620.166 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1625.5826 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1626.5826 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1636.5826 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1637.3057 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1637.3089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1638.3089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1639.5089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1649.5089 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1650.5089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1651.5089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1655.5089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1660.9256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1664.1688 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1676.1688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1684.1688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1687.4121 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1697.4121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1702.8288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1703.8288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1713.8288 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1714.5518 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1714.5551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1715.5551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1716.7551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1726.7551 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1727.7551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1728.7551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1732.7551 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1738.1717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1741.415 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1753.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1761.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1764.6582 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1774.6582 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1780.0749 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1781.0749 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1791.0749 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1791.798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1791.8012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1792.8012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1794.0012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1804.0012 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1805.0012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1806.0012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1810.0012 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1815.4179 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1818.6611 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1830.6611 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1838.6611 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1841.9044 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1851.9044 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1857.321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1858.321 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1868.321 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1869.0441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1869.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1870.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1871.2473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1881.2473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1882.2473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1883.2473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1887.2473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1892.664 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1895.9072 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1907.9072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1915.9072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1919.1505 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 1929.1505 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1934.5672 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1935.5672 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1945.5672 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1946.2902 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1946.2935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1947.2935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1948.4935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1958.4935 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1959.4935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1960.4935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1964.4935 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1969.9101 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1973.1534 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1985.1534 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1993.1534 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1996.3966 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2006.3966 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2011.8133 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2012.8133 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2022.8133 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2023.5364 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2023.5396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2024.5396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2025.7396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2035.7396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2036.7396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2037.7396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2041.7396 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2047.1563 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2050.3995 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2062.3995 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2070.3995 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2073.6428 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2083.6428 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2089.0594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2090.0594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2100.0594 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2100.7825 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2100.7857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2101.7857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2102.9857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2112.9857 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2113.9857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2114.9857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2118.9857 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2124.4024 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2127.6457 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2139.6457 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2147.6457 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2150.8889 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2160.8889 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2166.3056 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2167.3056 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2177.3056 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2178.0286 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2178.0319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2179.0319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2180.2319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2190.2319 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2191.2319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2192.2319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2196.2319 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2201.6485 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2204.8918 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2216.8918 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2224.8918 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2228.135 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2238.135 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2243.5517 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2244.5517 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2254.5517 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2255.2748 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2255.278 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2256.278 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2257.478 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2267.478 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2268.478 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2269.478 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2273.478 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2278.8947 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2282.1379 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2294.1379 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2302.1379 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2305.3812 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2315.3812 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2320.7978 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2321.7978 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2331.7978 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2332.5209 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2332.5242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2333.5242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2334.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2344.7242 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2345.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2346.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2350.7242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2356.1408 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2359.3841 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2371.3841 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2379.3841 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2382.6273 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2392.6273 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2398.044 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2399.044 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2409.044 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2409.767 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2409.7703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2410.7703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2411.9703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2421.9703 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2422.9703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2423.9703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2427.9703 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2433.387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2436.6302 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2448.6302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2456.6302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2459.8734 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2469.8734 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2475.2901 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2476.2901 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2486.2901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2487.0132 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2487.0164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2488.0164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2489.2164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2499.2164 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2500.2164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2501.2164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2505.2164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2510.6331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2513.8763 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2525.8763 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2533.8763 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2537.1196 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2547.1196 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2552.5362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2553.5362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2563.5362 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2564.2593 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2564.2626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2565.2626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2566.4626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2576.4626 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2577.4626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2578.4626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2582.4626 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2587.8792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2591.1225 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2603.1225 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2611.1225 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2614.3657 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2624.3657 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2629.7824 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2630.7824 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2640.7824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2641.5054 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2641.5087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2642.5087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2643.7087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2653.7087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2654.7087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2655.7087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2659.7087 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2665.1254 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2668.3686 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2680.3686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2688.3686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2691.6118 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2701.6118 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2707.0285 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2708.0285 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2718.0285 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2718.7516 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2718.7548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2719.7548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2720.9548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2730.9548 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2731.9548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2732.9548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 48 | 800000 | ACTION | 2780.9548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2784.9548 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2790.3715 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2793.6147 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2805.6147 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2813.6147 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2816.858 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2826.858 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2832.2746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2833.2746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2843.2746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2843.9977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2844.001 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2845.001 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2846.201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2856.201 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2857.201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2858.201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2862.201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2867.6176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2870.8609 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2882.8609 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2890.8609 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2894.1041 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2904.1041 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2909.5208 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2910.5208 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2920.5208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2921.2438 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2921.2471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2922.2471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2923.4471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2933.4471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2934.4471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2935.4471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2939.4471 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2944.8638 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2948.107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2960.107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2968.107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2971.3503 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 2981.3503 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2986.7669 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2987.7669 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2997.7669 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2998.49 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2998.4932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2999.4932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3000.6932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3010.6932 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3011.6932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3012.6932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 350000 | ACTION | 3033.6932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3037.6932 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3043.1099 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 2 | 33333.3333 | ACTION | 3045.1099 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3046.1099 | MonopileInstallation
| WTIV | Transit | 1.2432 | 20720.7207 | ACTION | 3047.3531 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3059.3531 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3067.3531 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3070.5964 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3080.5964 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3086.0131 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3087.0131 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3097.0131 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3097.7361 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3097.7394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3098.7394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3099.9394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3109.9394 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3110.9394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3111.9394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3115.9394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3121.356 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3124.5993 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3136.5993 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3144.5993 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3147.8425 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3157.8425 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3163.2592 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3164.2592 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3174.2592 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3174.9823 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3174.9855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3175.9855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3177.1855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3187.1855 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3188.1855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3189.1855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3193.1855 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3198.6022 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3201.8454 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3213.8454 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3221.8454 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3225.0887 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3235.0887 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3240.5053 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3241.5053 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3251.5053 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3252.2284 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3252.2316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3253.2316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3254.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3264.4316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3265.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3266.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3270.4316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3275.8483 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3279.0915 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3291.0915 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3299.0915 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3302.3348 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3312.3348 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3317.7515 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3318.7515 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3328.7515 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3329.4745 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3329.4778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3330.4778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3331.6778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3341.6778 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3342.6778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3352.6778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3353.6778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3357.6778 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3363.0944 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3366.3377 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3378.3377 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3386.3377 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3389.5809 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3399.5809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3404.9976 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3405.9976 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3415.9976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3416.7207 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3416.7239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3417.7239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3418.9239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3428.9239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3429.9239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3430.9239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3435.9239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3439.9239 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3445.3406 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3448.5838 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3460.5838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3468.5838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3471.8271 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3481.8271 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3487.2437 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3488.2437 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3498.2437 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3498.9668 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3498.97 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3499.97 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3501.17 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3511.17 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3512.17 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3513.17 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3517.17 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3522.5867 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3525.83 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3537.83 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3545.83 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3549.0732 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3559.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3564.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3565.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3575.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3576.2129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3576.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3577.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3578.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3588.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3589.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3590.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3594.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3599.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3603.0761 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3615.0761 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3623.0761 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3626.3193 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3636.3193 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3641.736 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3642.736 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3652.736 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3653.4591 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3653.4623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3654.4623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3655.6623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3665.6623 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3666.6623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 37 | 616666.6667 | ACTION | 3703.6623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3704.6623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3708.6623 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3714.079 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3717.3222 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3729.3222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3737.3222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3740.5655 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3750.5655 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3755.9821 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3756.9821 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 3761.9821 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3771.9821 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3772.7052 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3772.7085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3773.7085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3774.9085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3784.9085 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3785.9085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3786.9085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3790.9085 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3796.3251 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3799.5684 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3811.5684 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3819.5684 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3822.8116 | MonopileInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 3834.8116 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3844.8116 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3850.2283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3851.2283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3861.2283 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3861.9513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3861.9546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3862.9546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3864.1546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3874.1546 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3875.1546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3876.1546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3880.1546 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3885.5713 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3888.8145 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3900.8145 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3908.8145 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3912.0577 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3922.0577 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3927.4744 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3928.4744 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3938.4744 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3939.1975 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3939.2007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3940.2007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3941.4007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3951.4007 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3952.4007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3953.4007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3957.4007 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3962.8174 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3966.0606 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3978.0606 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3986.0606 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3989.3039 | MonopileInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 3999.3039 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4004.7205 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 4005.7205 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 4015.7205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 4016.4436 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 4016.4469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4017.4469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 733333.3333 | ACTION | 4061.4469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 4062.6469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 4072.6469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4073.6469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 4074.6469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 4078.6469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4084.0635 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 4084.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4086.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4088.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4090.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4092.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4094.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4094.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4095.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4096.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4098.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4100.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4102.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4104.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4106.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4107.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4107.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4108.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4110.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4112.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4114.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4116.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4118.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4119.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4120.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4120.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4122.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4124.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4126.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4128.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4130.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4131.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4132.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4133.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4135.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4137.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4139.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4141.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4143.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4143.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4144.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4145.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4147.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4149.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4151.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4153.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4155.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4156.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4156.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4157.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4160.8068 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4170.8068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4176.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4177.2234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4177.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4179.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4180.6034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4181.3634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4183.3634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4184.3634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4185.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4187.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4188.5034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4190.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4192.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4193.0234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4194.0234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4195.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4197.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4198.5234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4199.0234 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4203.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4204.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4206.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4206.5234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4208.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4209.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4210.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4211.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4213.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4218.4401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4228.4401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4233.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4234.8568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4235.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4237.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4238.2368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4238.9968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4240.9968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4241.9968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4243.1368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4245.1368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4246.1368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4247.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4249.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4250.6568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4251.6568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4253.1568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4255.1568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4256.1568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4256.6568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4258.1568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4259.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4260.1568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4261.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4263.1568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4263.6568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4265.1568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4266.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4272.0734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4277.0734 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4287.0734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4292.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4293.4901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4293.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4295.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4296.8701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4297.6301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4299.6301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4300.6301 | TurbineInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 4327.6301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4328.7701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4330.7701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4331.7701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4333.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4335.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4336.2901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4337.2901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4338.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4340.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4341.7901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4342.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4343.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4345.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4345.7901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4347.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4348.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4349.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4350.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4352.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4357.7068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4367.7068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4373.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4374.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4374.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4376.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4377.5034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4378.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4380.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4381.2634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4382.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4384.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4385.4034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4386.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4388.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4389.9234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4390.9234 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 4402.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4404.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4406.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4407.4234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4407.9234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4409.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4410.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4411.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4412.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4414.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4414.9234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4416.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4417.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4423.3401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4433.3401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4438.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4439.7568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4440.1368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4442.1368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4443.1368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4443.8968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4445.8968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4446.8968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4448.0368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4450.0368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4451.0368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4452.5568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4454.5568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4455.5568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4456.5568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4458.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4460.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4461.0568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4461.5568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4463.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4464.5568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4465.0568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4466.5568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4468.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4468.5568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4470.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4471.5568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4476.9734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4486.9734 | TurbineInstallation
| WTIV | Delay | 64 | 1066666.6667 | ACTION | 4550.9734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4556.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4557.3901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4557.7701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4559.7701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4560.7701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4561.5301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4563.5301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4564.5301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4565.6701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4567.6701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4568.6701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4570.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4572.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4573.1901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4574.1901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4575.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4577.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4578.6901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4579.1901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4580.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4582.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4582.6901 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4586.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4588.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4605.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4606.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4607.1901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4608.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4610.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 4616.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4621.6068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4624.85 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4626.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4628.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4630.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4632.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4634.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4635.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4636.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4637.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4639.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4642.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4644.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4646.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4648.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4651.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4653.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4653.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4654.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4655.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 4678.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4680.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 300000 | ACTION | 4698.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4700.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4702.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4704.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4706.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4708.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4709.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4709.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4710.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4712.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4714.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4716.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4718.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4720.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4721.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4722.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4722.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4724.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4726.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4728.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4730.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4732.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4733.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4734.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4735.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4737.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4739.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4741.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4743.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4745.1 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4745.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4746.6 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4747.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4750.5933 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4760.5933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4766.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4767.0099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4767.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4769.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4770.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4771.1499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4773.1499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4774.1499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4775.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4777.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4778.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4779.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4781.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4782.8099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4783.8099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4785.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4787.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4788.3099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4788.8099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4790.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4791.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4792.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4793.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4795.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4795.8099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4797.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4798.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4804.2266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4814.2266 | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 4833.2266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4838.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4839.6433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4840.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4842.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4843.0233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4843.7833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4845.7833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4846.7833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4847.9233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4849.9233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4850.9233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4852.4433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4854.4433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4855.4433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4856.4433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4857.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4859.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4860.9433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4861.4433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4862.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4864.4433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4864.9433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4866.4433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4867.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4868.4433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4869.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4871.4433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4876.8599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4886.8599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4892.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4893.2766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4893.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4895.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4896.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4897.4166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4899.4166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4900.4166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4901.5566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4903.5566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4904.5566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4906.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4908.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4909.0766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4910.0766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4911.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4913.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4914.5766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4915.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4916.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4918.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4918.5766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4920.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4921.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4922.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4923.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4925.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4930.4933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 4940.4933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4945.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4946.9099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4947.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4949.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4950.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4951.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4953.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4954.0499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4955.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4957.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4958.1899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4959.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4961.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4962.7099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4963.7099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4965.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4967.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4968.2099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4968.7099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4970.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 200000 | ACTION | 4982.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4983.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4984.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4985.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4987.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4987.7099 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4991.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4993.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4994.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5000.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 5010.1266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5015.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5016.5433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5016.9233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5018.9233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5019.9233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5020.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5022.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5023.6833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5024.8233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 5030.8233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5032.8233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5033.8233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5035.3433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5037.3433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5038.3433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5039.3433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5040.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5042.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5043.8433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5044.3433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5045.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5047.3433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5047.8433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5049.3433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5050.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5051.3433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5052.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5054.3433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5059.7599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 5069.7599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5075.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5076.1766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5076.5566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5078.5566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5079.5566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5080.3166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5082.3166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5083.3166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5084.4566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5086.4566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5087.4566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5088.9766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5090.9766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5091.9766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5092.9766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5094.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5096.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5097.4766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5097.9766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5099.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5100.9766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5101.4766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5102.9766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5104.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5104.9766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5106.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5107.9766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5113.3933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5116.6365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5118.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5120.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5122.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5124.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5126.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5127.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5128.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5128.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5130.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5132.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5134.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5136.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5138.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5139.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5140.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5141.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5143.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5145.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5147.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5149.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5151.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5151.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5152.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5153.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1256 | 20933333.3333 | ACTION | 6409.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6411.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6413.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6415.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6417.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6419.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6420.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6420.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6421.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6423.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6425.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6427.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6429.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6431.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6432.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6433.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6433.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6435.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6437.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6439.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6441.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6443.8865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6444.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6445.3865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6446.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6449.3797 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6459.3797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6464.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6465.7964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6466.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6468.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6469.1764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6469.9364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6471.9364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6472.9364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6474.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6476.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6477.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6478.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6480.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6481.5964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6482.5964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6484.0964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6486.0964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6487.0964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6487.5964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6489.0964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6490.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6491.0964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6492.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6494.0964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6494.5964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6496.0964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6497.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6503.0131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 6513.0131 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6523.0131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6528.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6529.4297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6529.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6531.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6532.8097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6533.5697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6535.5697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6536.5697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6537.7097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6539.7097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6540.7097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6542.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6544.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6545.2297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6546.2297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6547.7297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6549.7297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6550.7297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6551.2297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6552.7297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6554.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6554.7297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6556.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6557.7297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6558.2297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6559.7297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6561.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6566.6464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6576.6464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6582.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6583.0631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6583.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6585.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6586.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6587.2031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6589.2031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6590.2031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6591.3431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6593.3431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6594.3431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6595.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6597.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6598.8631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6599.8631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6601.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6603.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6604.3631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6604.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6606.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6607.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6608.3631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6609.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6611.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6611.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6613.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6614.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6620.2797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6630.2797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6635.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6636.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6637.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6639.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6640.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6640.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6642.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6643.8364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6644.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6646.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6647.9764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6649.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6651.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6652.4964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6653.4964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6654.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6656.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6657.9964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6658.4964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6659.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6661.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6661.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6663.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6665.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6666.4964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6667.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6669.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6674.9131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6684.9131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6690.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6691.3297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6691.7097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6693.7097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6694.7097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6695.4697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6697.4697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6698.4697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6699.6097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6701.6097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6702.6097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6704.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6706.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6707.1297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6708.1297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6709.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6711.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6712.6297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6713.1297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6714.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6716.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6716.6297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6718.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6719.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6720.1297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6721.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6723.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6728.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6738.5464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6743.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6744.9631 | TurbineInstallation
| WTIV | Delay | 13 | 216666.6667 | ACTION | 6757.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6758.3431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6760.3431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6761.3431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6762.1031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6764.1031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6765.1031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6766.2431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6768.2431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6769.2431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6770.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6772.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6773.7631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6774.7631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6776.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6778.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6779.2631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6779.7631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6781.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6782.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6783.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6784.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6786.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6786.7631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6788.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6789.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6795.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6798.423 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6800.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6802.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6804.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6806.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6808.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6809.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6809.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6810.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6812.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6820.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6822.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6824.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6826.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6828.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6829.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6830.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6830.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6832.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6834.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6836.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6838.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6840.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6841.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6842.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6843.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6845.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6847.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6849.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6851.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6853.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6853.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6854.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6855.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6857.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6859.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6861.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6863.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6865.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6866.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6866.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6867.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6869.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6871.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6873.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6875.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6877.673 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6878.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6879.173 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6879.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6883.1662 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 6893.1662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6898.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6899.5829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6899.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6901.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6902.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6903.7229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6905.7229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6906.7229 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 6915.7229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6916.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6918.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6919.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6921.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6923.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6924.3829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6925.3829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6926.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6928.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6929.8829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6930.3829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6931.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6933.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6933.8829 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 6975.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6977.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 6983.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6984.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6985.3829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6986.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6988.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6993.7996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7003.7996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7009.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7010.2162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7010.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7012.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7013.5962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7014.3562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7016.3562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7017.3562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7018.4962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7020.4962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7021.4962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7023.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7025.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7026.0162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7027.0162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7028.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7030.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7031.5162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7032.0162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7033.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7035.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7035.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7037.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7038.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7039.0162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7040.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7042.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7047.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7057.4329 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7059.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7064.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7065.8496 | TurbineInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 7092.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7093.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7095.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7096.2296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7096.9896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7098.9896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7099.9896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7101.1296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7103.1296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7104.1296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7105.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7107.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7108.6496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7109.6496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7111.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7113.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7114.1496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7114.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7116.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7117.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7118.1496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7119.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7121.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7121.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7123.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7124.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7130.0662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7140.0662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7145.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7146.4829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7146.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7148.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7149.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7150.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7152.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7153.6229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7154.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7156.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7157.7629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7159.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7161.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7162.2829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7163.2829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7164.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7166.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7167.7829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7168.2829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7169.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7171.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7171.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7173.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7174.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7175.2829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7176.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7178.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7183.6996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7193.6996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7199.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7200.1162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7200.4962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7202.4962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7203.4962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7204.2562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7206.2562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7207.2562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7208.3962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7210.3962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7211.3962 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7221.3962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7222.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7229.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7231.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7232.9162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7233.9162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7235.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7237.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7238.4162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7238.9162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7240.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7241.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7242.4162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7243.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7245.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7245.9162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7247.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7248.9162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7254.3329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7264.3329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7269.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7270.7496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7271.1296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7273.1296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7274.1296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7274.8896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7276.8896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7277.8896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7279.0296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7281.0296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7282.0296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7283.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 15 | 250000 | ACTION | 7298.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7300.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7301.5496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7302.5496 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7306.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7308.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7310.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7311.0496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7311.5496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7313.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7314.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7315.0496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7316.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7318.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7318.5496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7320.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7321.5496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7326.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7330.2095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7332.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7334.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7336.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7338.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7340.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7340.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7341.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7342.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7344.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7346.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7348.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7350.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7352.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7353.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7353.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7354.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7356.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7358.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7360.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7362.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7364.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7365.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7366.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7366.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7368.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7370.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7372.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7374.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7376.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7377.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7378.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7379.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7381.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7383.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7385.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7387.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7389.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7389.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7390.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7391.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7393.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7395.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7397.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7399.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7401.4595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7402.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7402.9595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7403.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7406.9527 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7416.9527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7422.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7423.3694 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 7465.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7465.7494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7467.7494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7468.7494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7469.5094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7471.5094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7472.5094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7473.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7475.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7476.6494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7478.1694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7480.1694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7481.1694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7482.1694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7483.6694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7485.6694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7486.6694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7487.1694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7488.6694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7490.1694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7490.6694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7492.1694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7493.6694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7494.1694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7495.6694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7497.1694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7502.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7512.586 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7518.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7519.0027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7519.3827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7521.3827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7522.3827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7523.1427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7549.1427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7551.1427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7552.1427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7553.2827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7555.2827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7556.2827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7557.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7559.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7560.8027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7561.8027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7563.3027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7565.3027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7566.3027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7566.8027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7568.3027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7569.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7570.3027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7571.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7573.3027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7573.8027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7575.3027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7576.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7582.2194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7592.2194 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7597.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7598.636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7599.016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7601.016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7602.016 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7602.776 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7603.776 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7605.776 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7606.776 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7607.916 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7609.916 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7610.916 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7612.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7614.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7615.436 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7616.436 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7617.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7619.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7620.936 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7621.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7622.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7624.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7624.936 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7626.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7627.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7628.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7629.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7631.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7636.8527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7646.8527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7652.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7653.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7653.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7655.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7656.6494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7657.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7659.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7660.4094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7661.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7663.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7664.5494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7666.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7668.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7669.0694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7670.0694 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7674.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7675.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7677.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7678.5694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7679.0694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7680.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7682.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7682.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7684.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7685.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7686.0694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7687.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7689.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7694.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7704.486 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7709.9027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7710.9027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7711.2827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7713.2827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7714.2827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7715.0427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7717.0427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7718.0427 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7725.0427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7726.1827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7728.1827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7729.1827 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7731.1827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7732.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7734.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7735.7027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7736.7027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7738.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7740.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7741.2027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7741.7027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7743.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7744.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7745.2027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7746.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7748.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7748.7027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7750.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7751.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7757.1194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7767.1194 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7772.536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7773.536 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7773.916 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7775.916 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7776.916 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7777.676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7779.676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7780.676 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7781.816 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7783.816 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7784.816 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7786.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7788.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7789.336 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7790.336 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7791.836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7793.836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7794.836 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7795.336 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7796.836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7798.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7798.836 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7800.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7801.836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7802.336 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7805.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7810.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7813.996 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7815.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7817.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7819.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7821.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7823.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7824.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7825.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7826.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7828.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7830.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7832.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7834.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7836.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7836.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7837.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7838.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7840.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7842.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7844.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7846.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7848.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7849.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7849.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7850.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7852.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7854.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7856.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7858.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7860.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7861.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7862.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7862.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7864.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7866.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7868.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7870.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7872.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7873.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7874.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7875.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7877.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7879.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7881.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7883.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7885.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7885.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7886.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7887.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7890.7392 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7900.7392 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7906.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7907.1559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7907.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7909.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7910.5359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7911.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7913.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7914.2959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7915.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7917.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7918.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7919.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7921.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7922.9559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7923.9559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7925.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7927.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7928.4559 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7928.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7930.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7931.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7932.4559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7933.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7935.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7935.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7937.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7938.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7944.3725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 7954.3725 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7959.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7960.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7961.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7963.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7964.1692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7964.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7966.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7967.9292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7969.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7971.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7972.0692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7973.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7975.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7976.5892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7977.5892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7979.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7981.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7982.0892 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7982.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7984.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7985.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7986.0892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7987.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7989.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7989.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7991.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7992.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7998.0059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8008.0059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8013.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8014.4225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8014.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8016.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8017.8025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8018.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8020.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8021.5625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8022.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8024.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8025.7025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8027.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8029.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8030.2225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8031.2225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8032.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8034.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8035.7225 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8036.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8037.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8039.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8039.7225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8041.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8051.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8052.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8053.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8054.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8056.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8061.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8071.6392 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8077.0559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8078.0559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8078.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8080.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8081.4359 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8083.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8084.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8085.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8087.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8088.1959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8089.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8091.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8092.3359 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8094.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8095.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8097.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8098.8559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8099.8559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8101.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8103.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8104.3559 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8104.8559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8106.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8107.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8108.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8109.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8111.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8111.8559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8113.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8114.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8120.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8130.2725 | TurbineInstallation
| WTIV | Delay | 41 | 683333.3333 | ACTION | 8171.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8176.6892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8177.6892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8178.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8180.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8181.0692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8181.8292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8183.8292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8184.8292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8185.9692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8187.9692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8188.9692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8190.4892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8192.4892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8193.4892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8194.4892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8195.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8197.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8198.9892 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8199.4892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8200.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8202.4892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8202.9892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8204.4892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8205.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8206.4892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8207.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8209.4892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8214.9059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8224.9059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8230.3225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8231.3225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8231.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8233.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8234.7025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8235.4625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8237.4625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8238.4625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8239.6025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8241.6025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8242.6025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8244.1225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8246.1225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8247.1225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8248.1225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8249.6225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8251.6225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8252.6225 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8253.1225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8254.6225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8256.1225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8256.6225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8258.1225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8259.6225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8260.1225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8261.6225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8263.1225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8268.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8271.7824 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8273.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8275.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8277.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8279.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8281.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8282.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8283.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8284.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8286.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8288.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8290.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8292.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8294.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8294.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8295.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8296.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8298.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8300.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8302.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8304.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8314.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8316.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8317.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8319.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8320.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8320.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8321.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8323.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8325.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8327.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8329.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8331.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8332.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8333.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8333.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8335.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 8338.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8340.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8342.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8344.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8346.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8347.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8348.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8349.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8351.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8353.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8355.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8357.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8359.0324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8359.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8360.5324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8361.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8364.5257 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8374.5257 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8379.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8380.9424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8381.3224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8383.3224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8384.3224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8385.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8387.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8388.0824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8389.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8391.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8392.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8393.7424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8395.7424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8396.7424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8397.7424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8399.2424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8401.2424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8402.2424 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8402.7424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8404.2424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8405.7424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8406.2424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8407.7424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8409.2424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8409.7424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8411.2424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8412.7424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8418.159 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 30 | 500000 | ACTION | 8448.159 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8458.159 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8463.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8464.5757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8464.9557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8466.9557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8467.9557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8468.7157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8470.7157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8471.7157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8472.8557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8474.8557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8475.8557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8477.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8479.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8480.3757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8481.3757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8482.8757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8484.8757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8485.8757 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8486.3757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8487.8757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8489.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8489.8757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8491.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8492.8757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8493.3757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8494.8757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8496.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8501.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8511.7924 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8517.209 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8518.209 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8518.589 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8520.589 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8521.589 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8522.349 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8524.349 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8525.349 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8526.489 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8528.489 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8529.489 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8531.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8533.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8534.009 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8535.009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8536.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8538.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8539.509 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8540.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8541.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8543.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8545.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8545.509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8547.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8548.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8549.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8550.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8552.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8557.4257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8567.4257 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8572.8424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8573.8424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8574.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8576.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8577.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8577.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8579.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8580.9824 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8602.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8604.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8606.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8607.1224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8608.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8610.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8611.6424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8612.6424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8614.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8616.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8617.1424 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8617.6424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8619.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8620.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8621.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8622.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8624.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8624.6424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8626.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8627.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8633.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8643.059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8648.4757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8649.4757 | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 8672.4757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8672.8557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8674.8557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8675.8557 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8679.8557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8680.6157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 37 | 616666.6667 | ACTION | 8717.6157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8719.6157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8720.6157 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8721.6157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8722.7557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8724.7557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8725.7557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8727.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8729.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8730.2757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8731.2757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8732.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8734.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8735.7757 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8736.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8737.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8739.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8739.7757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8741.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8742.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8743.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8744.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8746.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8751.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8761.6924 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8767.109 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8768.109 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8768.489 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8770.489 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8771.489 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8772.249 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8774.249 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8775.249 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8776.389 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8778.389 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8779.389 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8780.909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8782.909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8783.909 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8784.909 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8786.409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8788.409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8789.409 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8789.909 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8791.409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8792.909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8793.409 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8794.909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8796.409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8796.909 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8798.409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8799.909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8805.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8808.5689 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8810.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8812.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8814.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8816.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8818.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8819.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8820.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8820.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8822.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8824.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8826.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8828.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8830.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8831.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8832.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8833.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8835.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8837.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8839.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8841.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8843.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8843.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8844.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8845.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8847.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8849.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8851.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8853.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8855.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8856.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8856.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8857.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8859.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8861.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8863.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8865.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8867.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8868.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8869.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8869.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8871.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8873.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8875.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8877.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8879.8189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8880.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8881.3189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8882.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8885.3122 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8895.3122 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8900.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8901.7288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8902.1088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8904.1088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8905.1088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8905.8688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8907.8688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8908.8688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8910.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8912.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8913.0088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8914.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8916.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8917.5288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8918.5288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8920.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8922.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8923.0288 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8923.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8925.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8926.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8927.0288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8928.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8930.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8930.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8932.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8933.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8938.9455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 8948.9455 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8954.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8955.3622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8955.7422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8957.7422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8958.7422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8959.5022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8961.5022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8962.5022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8963.6422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8965.6422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8966.6422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8968.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8970.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8971.1622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8972.1622 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8974.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8975.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8977.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8978.6622 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8979.1622 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8980.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8981.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8983.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8983.6622 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 8998.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9000.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9001.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9002.1622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9003.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9005.1622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9010.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9020.5788 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9025.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9026.9955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9027.3755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9029.3755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9030.3755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9031.1355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9033.1355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9034.1355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9035.2755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9037.2755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9038.2755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9039.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9041.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9042.7955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9043.7955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9045.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9047.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9048.2955 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9048.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9050.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9051.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9052.2955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9053.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9055.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9055.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9057.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9058.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9064.2122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9074.2122 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9079.6288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9080.6288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9081.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9083.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9084.0088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9084.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9086.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9087.7688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9088.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9090.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9091.9088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9093.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9095.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9096.4288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9097.4288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9098.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9100.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9101.9288 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9102.4288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9103.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9105.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9105.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9107.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9108.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9109.4288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9110.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9112.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9114.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9119.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9129.8455 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9135.2622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9136.2622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9136.6422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9138.6422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9139.6422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9140.4022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9142.4022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9143.4022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9144.5422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9146.5422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9147.5422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9149.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9151.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9152.0622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9153.0622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9154.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9156.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9157.5622 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9158.0622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9159.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9161.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9161.5622 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 9164.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9166.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9167.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9168.0622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9169.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9171.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9176.4788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9186.4788 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9191.8955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9192.8955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9193.2755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9195.2755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9196.2755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9197.0355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9199.0355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9200.0355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9201.1755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9203.1755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9204.1755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9205.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9207.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9208.6955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9209.6955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9211.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9213.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9214.1955 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9214.6955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9216.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9217.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9218.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9219.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9221.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9221.6955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9223.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9224.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9230.1122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9233.3554 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9235.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9237.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9239.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9241.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9243.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9244.1054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9244.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9245.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9247.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9249.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9251.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9253.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9255.6054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9256.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9257.1054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9257.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9261.0987 | TurbineInstallation
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9271.0987 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9276.5153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9277.5153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9277.8953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9279.8953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9280.8953 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9281.6553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9283.6553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9284.6553 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9285.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9287.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9288.7953 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9290.3153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9292.3153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9293.3153 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9294.3153 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9295.8153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9297.8153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9298.8153 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9299.3153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9300.8153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9302.3153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9302.8153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9304.3153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9305.8153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9306.3153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9307.8153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9309.3153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9314.732 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 10 | 166666.6667 | ACTION | 9324.732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9330.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9331.1487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9331.5287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9333.5287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9334.5287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9335.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9337.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9338.2887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9339.4287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9341.4287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9342.4287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9343.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9345.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9346.9487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9347.9487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9349.4487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9351.4487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9352.4487 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9352.9487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9354.4487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9355.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9356.4487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9357.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9359.4487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9359.9487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9361.4487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9362.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9368.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 10 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5