## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 64 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 76 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 84 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 87.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 92.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 97.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 98.6599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 108.6599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 109.383 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 109.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 110.3862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 111.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 121.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 122.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 123.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 127.5862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 133.0029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 138.0029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 143.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 144.4196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 154.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 155.1426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 155.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 156.1459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 157.3459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 167.3459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 168.3459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 169.3459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 173.3459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 178.7625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 183.7625 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 189.7625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 195.1792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 196.1792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 197.1792 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 207.1792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 207.9023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 207.9055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 208.9055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 210.1055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 220.1055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 221.1055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 222.1055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 226.1055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 231.5222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 236.5222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 241.9389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 242.9389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 252.9389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 253.6619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 253.6652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 254.6652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 255.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 265.8652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 266.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 267.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 271.8652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 277.2818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 280.5251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 292.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 300.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 312.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 320.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 332.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 340.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 352.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 360.5251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 363.7683 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 368.7683 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 374.185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 375.185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 385.185 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 385.9081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 385.9113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 386.9113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 388.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 398.1113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 399.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 400.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 404.1113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 409.528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 414.528 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 419.9446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 420.9446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 430.9446 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 431.6677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 431.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 432.671 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 433.871 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 443.871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 444.871 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 445.871 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 449.871 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 455.2876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 460.2876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 465.7043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 466.7043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 476.7043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 477.4274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 477.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 478.4306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 479.6306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 489.6306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 490.6306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 491.6306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 495.6306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 501.0473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 506.0473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 511.4639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 512.4639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 522.4639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 523.187 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 523.1903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 524.1903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 525.3903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 535.3903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 536.3903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 537.3903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 541.3903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 546.8069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 550.0502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 562.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 570.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 582.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 590.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 602.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 610.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 622.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 630.0502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 633.2934 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 638.2934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 643.7101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 644.7101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 654.7101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 655.4331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 655.4364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 656.4364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 657.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 667.6364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 668.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 669.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 673.6364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 679.0531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 684.0531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 689.4697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 690.4697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 700.4697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 701.1928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 701.196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 702.196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 703.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 713.396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 714.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 715.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 719.396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 724.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 729.8127 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 735.2294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 736.2294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 746.2294 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 746.9524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 746.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 747.9557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 749.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 759.1557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 760.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 761.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 762.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 763.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 767.1557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 772.5724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 777.5724 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 782.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 783.989 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 793.989 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 794.7121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 794.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 795.7153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 796.9153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 806.9153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 807.9153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 808.9153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 812.9153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 818.332 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 821.5752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 833.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 841.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 853.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 861.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 873.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 881.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 893.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 901.5752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 904.8185 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 909.8185 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 915.2352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 916.2352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 926.2352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 926.9582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 926.9615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 927.9615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 929.1615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 939.1615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 940.1615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 941.1615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 945.1615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 950.5781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 955.5781 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 960.9948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 961.9948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 971.9948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 972.7179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 972.7211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 973.7211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 974.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 984.9211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 985.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 986.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 990.9211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 996.3378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1001.3378 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1006.7545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1007.7545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1017.7545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1018.4775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1018.4808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1019.4808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1020.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1030.6808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1031.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1032.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1036.6808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1042.0974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1047.0974 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1052.5141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1053.5141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1063.5141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1064.2372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1064.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1065.2404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1066.4404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1076.4404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1077.4404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1078.4404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1082.4404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1087.8571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1091.1003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1103.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1111.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1123.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1131.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1143.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1151.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1163.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1171.1003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1174.3436 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1179.3436 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1184.7602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1185.7602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1195.7602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1196.4833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1196.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1197.4866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1198.6866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1208.6866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1209.6866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1210.6866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1214.6866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1220.1032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1225.1032 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1230.5199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1231.5199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1241.5199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1242.243 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1242.2462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1243.2462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1244.4462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1254.4462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1255.4462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1256.4462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1260.4462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1265.8629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1270.8629 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1276.2795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1277.2795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1287.2795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1288.0026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1288.0059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1289.0059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1290.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1300.2059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1301.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1302.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1306.2059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1311.6225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1316.6225 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1322.0392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1323.0392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1333.0392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1333.7622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1333.7655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1334.7655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1335.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1345.9655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1346.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1347.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1351.9655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1357.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1360.6254 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1372.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1380.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1392.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1400.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1412.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1420.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1432.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1440.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1443.8687 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1448.8687 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1454.2853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1455.2853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1465.2853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1466.0084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1466.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1467.0116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1468.2116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1478.2116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1479.2116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1480.2116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1484.2116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1489.6283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1494.6283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1500.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1501.045 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1511.045 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1511.768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1511.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1512.7713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1513.9713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1523.9713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1524.9713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1525.9713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1529.9713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1535.388 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1540.388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1545.8046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1546.8046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1556.8046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1557.5277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1557.5309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1558.5309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1559.7309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1569.7309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1570.7309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1571.7309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1575.7309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1581.1476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1586.1476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1591.5643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1592.5643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1602.5643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1603.2873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1603.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1604.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1605.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1615.4906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1616.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1617.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1621.4906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1626.9072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1630.1505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1642.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1650.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1662.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1670.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1682.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1690.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1702.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1710.1505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1713.3937 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1718.3937 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1723.8104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1724.8104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1734.8104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1735.5335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1735.5367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1736.5367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1737.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1747.7367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1748.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1749.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1753.7367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1759.1534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1764.1534 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1769.5701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1770.5701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1780.5701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1781.2931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1781.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1782.2964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1783.4964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1793.4964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1794.4964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1795.4964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1799.4964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1804.913 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1809.913 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1815.3297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1816.3297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1826.3297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1827.0528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1827.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1828.056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1829.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1839.256 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1840.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1841.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1845.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1850.6727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1855.6727 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1861.0893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1862.0893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1872.0893 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1872.8124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1872.8157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1873.8157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1875.0157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1885.0157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1886.0157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1887.0157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1891.0157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1896.4323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1899.6756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1911.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1919.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1931.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1939.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1951.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1959.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1971.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1979.6756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1982.9188 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1987.9188 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1993.3355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1994.3355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2004.3355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2005.0585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2005.0618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2006.0618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2007.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2017.2618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2018.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2019.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2023.2618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2028.6785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2033.6785 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2039.0951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2040.0951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2050.0951 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2050.8182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2050.8214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2051.8214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2053.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2063.0214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2064.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2065.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2069.0214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2074.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2079.4381 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2084.8548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2085.8548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2095.8548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2096.5778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2096.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2097.5811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2098.7811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2108.7811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2109.7811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2110.7811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2114.7811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2120.1978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2125.1978 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2130.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2131.6144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2141.6144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2142.3375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2142.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2143.3407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2144.5407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2154.5407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2155.5407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2156.5407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2160.5407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2165.9574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2169.2007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2181.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2189.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2201.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2209.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2221.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2229.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2241.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2249.2007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2252.4439 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2257.4439 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2262.8606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2263.8606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2273.8606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2274.5836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2274.5869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2275.5869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2276.7869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2286.7869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2287.7869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2288.7869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2292.7869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2298.2035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2303.2035 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2308.6202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2309.6202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2319.6202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2320.3433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2320.3465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2321.3465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2322.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2332.5465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2333.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2334.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2338.5465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2343.9632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2348.9632 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2354.3799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2355.3799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2365.3799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2366.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2366.1062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2367.1062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2368.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2378.3062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2379.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2380.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2384.3062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2389.7228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2394.7228 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2400.1395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2401.1395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2411.1395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2411.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2411.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2412.8658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2414.0658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2424.0658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2425.0658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2426.0658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2430.0658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2435.4825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2438.7257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2450.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2458.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2470.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2478.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2490.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2498.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2510.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2518.7257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2521.969 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2526.969 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2532.3856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2533.3856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2543.3856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2544.1087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2544.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2545.112 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2546.312 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2556.312 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2557.312 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2558.312 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2562.312 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2567.7286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2572.7286 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2578.1453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2579.1453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2589.1453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2589.8684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2589.8716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2590.8716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2592.0716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2602.0716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2603.0716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2604.0716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2608.0716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2613.4883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2618.4883 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2623.9049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2624.9049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2634.9049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2635.628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2635.6313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2636.6313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2637.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2647.8313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2648.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2649.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2653.8313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2659.2479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2664.2479 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2669.6646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2670.6646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2680.6646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2681.3877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2681.3909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2682.3909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2683.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2693.5909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2694.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2695.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2699.5909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2705.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2708.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2720.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2728.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2740.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 30 | 500000 | ACTION | 2770.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2778.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2790.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2798.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2810.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2818.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2821.4941 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2826.4941 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2831.9107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2832.9107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2842.9107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2843.6338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2843.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2844.637 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2845.837 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2855.837 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2856.837 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2857.837 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2861.837 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2867.2537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2872.2537 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2877.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2878.6704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2888.6704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2889.3934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2889.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2890.3967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2891.5967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2901.5967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2902.5967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2903.5967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2907.5967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2913.0134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2918.0134 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2923.43 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2924.43 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2934.43 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2935.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2935.1563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2936.1563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2937.3563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2947.3563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2948.3563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2949.3563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2953.3563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2958.773 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2963.773 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2969.1897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2970.1897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2980.1897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2980.9127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2980.916 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2981.916 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2983.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2993.116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2994.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2995.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2999.116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3004.5327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3007.7759 | MonopileInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3032.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3044.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3052.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3064.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3072.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3084.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3092.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3104.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3112.7759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3116.0191 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3121.0191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3126.4358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3127.4358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3137.4358 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3138.1589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3138.1621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3139.1621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3140.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3150.3621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3151.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3152.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3156.3621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3161.7788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3166.7788 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3172.1955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3173.1955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3183.1955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3183.9185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3183.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3184.9218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3186.1218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3196.1218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3197.1218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3198.1218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3202.1218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3207.5384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3212.5384 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3217.9551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3218.9551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3228.9551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3229.6782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3229.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3230.6814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3231.8814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3241.8814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3242.8814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3243.8814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3247.8814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3253.2981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3258.2981 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3263.7148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3264.7148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3274.7148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3275.4378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3275.4411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3276.4411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3277.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3287.6411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3288.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3289.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3293.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3299.0577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3302.301 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3314.301 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3322.301 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3334.301 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3342.301 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3345.5442 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3350.5442 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3355.9609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3356.9609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3366.9609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3367.684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3367.6872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3368.6872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3369.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3379.8872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3380.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3381.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3385.8872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3391.3039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3396.3039 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3401.7205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3402.7205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3412.7205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3413.4436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3413.4469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3414.4469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3415.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3425.6469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3426.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3427.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3431.6469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3437.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 3437.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3439.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3441.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3443.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3445.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3447.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3447.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3448.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3449.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3451.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3453.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3455.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3457.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3459.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3460.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3460.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3461.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3463.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3465.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3467.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3469.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3471.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3472.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3473.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3473.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3477.0568 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3482.0568 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3487.4734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3488.4734 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3488.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3490.8534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3491.8534 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3492.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3494.6134 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3495.6134 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3496.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3498.7534 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3499.7534 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3501.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3503.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3504.2734 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3505.2734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3506.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3508.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3509.7734 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3510.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3511.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3513.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3513.7734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3515.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3516.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3517.2734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3518.7734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3520.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3525.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3530.6901 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3536.1068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3537.1068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3537.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3539.4868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3540.4868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3541.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3543.2468 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3544.2468 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3545.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3547.3868 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3548.3868 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3549.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3551.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3552.9068 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3553.9068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3555.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3557.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3558.4068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3558.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3560.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3561.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3562.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3563.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3565.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3565.9068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3567.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3568.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3574.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3579.3234 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3584.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3585.7401 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3586.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3588.1201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3589.1201 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3589.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3591.8801 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3592.8801 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3594.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3596.0201 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3597.0201 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3598.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3600.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3601.5401 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3602.5401 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3604.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3606.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3607.0401 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3607.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3609.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3610.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3611.0401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3612.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 3618.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3620.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3620.5401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3622.0401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3623.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3628.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3632.2 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3634.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3636.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3638.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3640.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3642.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3642.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3643.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3644.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3646.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3648.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3650.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3652.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3654.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3655.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3655.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3656.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3658.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3660.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3662.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3664.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3666.7 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3667.45 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3668.2 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3668.95 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3672.1933 | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 3701.1933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3706.1933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3711.6099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3712.6099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3712.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3714.9899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3715.9899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3716.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3718.7499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3719.7499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3720.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3722.8899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3723.8899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3725.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3727.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3728.4099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3729.4099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3730.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3732.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3733.9099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3734.4099 | TurbineInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 3764.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3765.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3767.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3767.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3769.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3770.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3771.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3772.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3774.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3779.8266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3784.8266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3790.2433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3791.2433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3791.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3793.6233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3794.6233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3795.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3797.3833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3798.3833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3799.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3801.5233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3802.5233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3804.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3806.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3807.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3808.0433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3809.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3811.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3812.5433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3813.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3814.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3816.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3816.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3818.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3819.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3820.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3821.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3823.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3828.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3833.4599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3838.8766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3839.8766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3840.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3842.2566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3843.2566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3844.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3846.0166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3847.0166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3848.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3850.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3851.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3852.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3854.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3855.6766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3856.6766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3858.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3860.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3861.1766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3861.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3863.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3864.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3865.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3866.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3868.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3868.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3870.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3871.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3877.0933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3880.3365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3882.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3884.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3886.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3888.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3890.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3891.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3891.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3892.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3894.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3896.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3898.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3900.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3902.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3903.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3904.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3904.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3906.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3908.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3910.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3912.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3914.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3915.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3916.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3917.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3920.3297 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3925.3297 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3930.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3931.7464 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3932.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3934.1264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3935.1264 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3935.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3937.8864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3938.8864 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3940.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3942.0264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3943.0264 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3944.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3946.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3947.5464 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3948.5464 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3950.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3952.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3953.0464 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3953.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3955.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3956.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3957.0464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3958.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3960.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3960.5464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3962.0464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3963.5464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3968.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3973.9631 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3979.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3980.3797 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3980.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3982.7597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3983.7597 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3984.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3986.5197 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3987.5197 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3988.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3990.6597 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3991.6597 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3993.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3995.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3996.1797 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3997.1797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3998.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4000.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4001.6797 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4002.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4003.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4007.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4009.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4009.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4011.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 42 | 700000 | ACTION | 4053.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4054.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4055.1797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4056.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4058.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4063.5964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4068.5964 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4074.0131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4075.0131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4075.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4077.3931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4078.3931 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4079.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4081.1531 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4082.1531 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4083.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4085.2931 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4086.2931 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4087.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4089.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4090.8131 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4091.8131 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4093.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4095.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4096.3131 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4096.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4098.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4099.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4100.3131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4101.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4103.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4103.8131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4105.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4106.8131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4112.2297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4115.473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4117.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4119.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4121.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4123.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4125.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4126.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4126.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4127.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4129.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4131.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4133.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4135.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4137.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4138.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4139.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4139.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4141.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4143.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4145.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4147.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4149.973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4150.723 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4151.473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4152.223 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4155.4662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4160.4662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4165.8829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4166.8829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4167.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4169.2629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4170.2629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4171.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4173.0229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4174.0229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4175.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4177.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4178.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4179.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4181.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4182.6829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4183.6829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4185.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4187.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4188.1829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4188.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4190.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4191.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4192.1829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4193.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4195.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4195.6829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4197.1829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4198.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4204.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4209.0996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4214.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4215.5162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4215.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4217.8962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4218.8962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4219.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4221.6562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4222.6562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4223.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4225.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4226.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4228.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4230.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4231.3162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4232.3162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4233.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4235.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4236.8162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4237.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4238.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4240.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4240.8162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4242.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4243.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4244.3162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4245.8162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4247.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4252.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4257.7329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4263.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4264.1496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4264.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4266.5296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4267.5296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4268.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4276.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4278.2896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4279.2896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4280.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4282.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4283.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4284.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4286.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4287.9496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4288.9496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4290.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4292.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4293.4496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4293.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4295.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 4304.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4305.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4306.4496 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 4318.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4319.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4321.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4321.9496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4323.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4324.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4330.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4333.6095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4335.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4337.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4339.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4341.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4343.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4344.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4345.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4345.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4347.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4349.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4351.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4353.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4355.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4356.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4357.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4358.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4360.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4362.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4364.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4366.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4368.1095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4368.8595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4369.6095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4370.3595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4373.6027 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4378.6027 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4384.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4385.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4385.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4387.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4388.3994 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4393.3994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4394.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4396.1594 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4397.1594 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4398.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4400.2994 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4401.2994 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4402.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4404.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4405.8194 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4406.8194 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4408.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4410.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4411.3194 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4411.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4413.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4414.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4415.3194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4416.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4418.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4418.8194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4420.3194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4421.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4427.236 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4432.236 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4437.6527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4438.6527 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4439.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4441.0327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4442.0327 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4442.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4444.7927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4445.7927 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4446.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4448.9327 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4449.9327 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4451.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4453.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4454.4527 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4455.4527 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4456.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4458.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4459.9527 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4460.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4461.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4463.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4463.9527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4465.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4466.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4467.4527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4468.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4470.4527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4475.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4480.8694 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4486.286 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4487.286 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4487.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4489.666 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4490.666 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4491.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4493.426 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4494.426 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4495.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4497.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4498.566 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4505.566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4507.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4509.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4510.086 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4511.086 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4512.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4514.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4515.586 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4516.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4517.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4519.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 4542.086 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4542.586 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4544.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4545.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4546.086 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4547.586 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4549.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4554.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4557.746 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4559.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4561.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4563.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4565.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4567.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4568.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4569.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4569.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4571.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4573.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4575.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4577.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4579.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4580.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4581.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4582.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4584.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4586.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4588.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4592.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4594.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4596.246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4596.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4597.746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4598.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4601.7392 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4606.7392 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4612.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4613.1559 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 4624.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4624.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4626.5359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4627.5359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4628.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 67 | 1116666.6667 | ACTION | 4695.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4697.2959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4698.2959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4699.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4701.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4702.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4703.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4705.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4706.9559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4707.9559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4709.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4711.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4712.4559 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4712.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4714.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4715.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4716.4559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4717.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4719.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4719.9559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4721.4559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4722.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4728.3725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4733.3725 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4738.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4739.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4740.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4742.1692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4743.1692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4743.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4745.9292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4746.9292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4748.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4750.0692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4751.0692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4752.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4754.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4755.5892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4756.5892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4758.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4760.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4761.0892 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4761.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4763.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4764.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4765.0892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4766.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4768.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4768.5892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4770.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4771.5892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4777.0059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4782.0059 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4787.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4788.4225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4788.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4790.8025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4791.8025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4792.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4794.5625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4795.5625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4796.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4798.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4799.7025 | TurbineInstallation
| WTIV | Delay | 29 | 483333.3333 | ACTION | 4828.7025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4830.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4832.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4833.2225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4834.2225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4835.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4837.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4838.7225 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4839.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4840.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4842.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4842.7225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4844.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4845.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4846.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4847.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4849.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4854.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4857.8824 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4859.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4861.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4863.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4865.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4867.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4868.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4869.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4870.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4872.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4874.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4876.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4878.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4880.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4880.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4881.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4882.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4884.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4886.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4888.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4890.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4892.3824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4893.1324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4893.8824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4894.6324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4897.8757 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4902.8757 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4908.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4909.2924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4909.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4911.6724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4912.6724 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4913.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4915.4324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4916.4324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4917.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4919.5724 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4920.5724 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4922.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4924.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4925.0924 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4926.0924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4927.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4929.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4930.5924 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4931.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4932.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4934.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4934.5924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4936.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4937.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4938.0924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4939.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4941.0924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4946.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4951.509 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4956.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4957.9257 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4958.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4960.3057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4961.3057 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4962.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4964.0657 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4965.0657 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4966.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4968.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4969.2057 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4977.2057 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4978.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4980.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4981.7257 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4982.7257 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4984.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4988.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4990.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4991.2257 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4991.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4993.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4994.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4995.2257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4996.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4998.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4998.7257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5000.2257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5001.7257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5007.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5012.1424 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5017.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5018.559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5018.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5020.939 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5021.939 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5022.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5026.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5028.699 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5029.699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5030.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5032.839 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5033.839 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5035.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5037.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5038.359 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5039.359 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5040.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5042.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5043.859 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5044.359 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5045.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5047.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5047.859 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5049.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5050.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5051.359 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5052.859 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5054.359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5059.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5063.0189 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5065.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5067.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5069.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5071.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5073.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5073.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5074.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5075.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5077.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5079.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5081.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5083.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5085.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5086.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5086.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5087.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5089.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5091.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5093.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5095.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5097.5189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5098.2689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5099.0189 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5099.7689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5103.0122 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5108.0122 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5113.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5114.4288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5114.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5116.8088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5117.8088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5118.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5120.5688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5121.5688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5122.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5124.7088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5125.7088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5127.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5129.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5130.2288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5131.2288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5132.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5134.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5135.7288 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5136.2288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5137.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5139.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5139.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5141.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5142.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5143.2288 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 5160.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5161.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5163.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5168.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5173.6455 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5179.0622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5180.0622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5180.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5182.4422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5183.4422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5184.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5186.2022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5187.2022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5188.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5190.3422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5191.3422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5192.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5194.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5195.8622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5196.8622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5198.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5200.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5201.3622 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5201.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5203.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5204.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5205.3622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5206.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5208.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5208.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5210.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5211.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5217.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5222.2788 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5227.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5228.6955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5229.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5231.0755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5232.0755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5232.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5234.8355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5235.8355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5236.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5238.9755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5239.9755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5241.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5243.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5244.4955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5245.4955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5246.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5248.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5249.9955 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5250.4955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5251.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5253.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5253.9955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5255.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5256.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5257.4955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5258.9955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5260.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5265.9122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5269.1554 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 5278.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5280.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5282.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5284.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5286.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5288.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5288.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5289.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5290.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5292.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5294.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5296.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5298.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5300.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5301.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5301.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5302.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5304.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5306.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5308.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5310.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5312.6554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5313.4054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5314.1554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5314.9054 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5318.1487 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5323.1487 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5328.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5329.5653 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5329.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5331.9453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5332.9453 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5333.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5335.7053 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5336.7053 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5337.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5339.8453 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5340.8453 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5342.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5344.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5345.3653 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5346.3653 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5347.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5349.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5350.8653 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5351.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5352.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5354.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5354.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5356.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5357.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5358.3653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5359.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5361.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5366.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5371.782 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5377.1987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5378.1987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5378.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5380.5787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5381.5787 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5382.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5384.3387 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5385.3387 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5386.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5388.4787 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5389.4787 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5390.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5392.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5393.9987 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5394.9987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5396.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5398.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5399.4987 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5399.9987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5401.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5402.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5403.4987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5404.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5406.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5406.9987 | TurbineInstallation
| WTIV | Delay | 75 | 1250000 | ACTION | 5481.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5483.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5484.9987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5490.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5495.4153 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5500.832 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5501.832 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5502.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5504.212 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5505.212 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5505.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5507.972 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5508.972 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5510.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5512.112 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5513.112 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5514.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5516.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5517.632 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5518.632 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5520.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5522.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5523.132 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5523.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5525.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5526.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5527.132 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5528.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5530.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5530.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5532.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5533.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5539.0487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5542.2919 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5544.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5546.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5548.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5550.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5552.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5553.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5553.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5554.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5556.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5558.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5560.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5562.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5564.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5565.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5566.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5566.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5568.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5570.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5572.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5574.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5576.7919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5577.5419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5578.2919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5579.0419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5582.2851 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5587.2851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5592.7018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5593.7018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5594.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5596.0818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5597.0818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5597.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5599.8418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5600.8418 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5601.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5603.9818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5604.9818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5606.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5608.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5609.5018 | TurbineInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 5628.5018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5629.5018 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 5636.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5638.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5640.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5641.0018 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5641.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5643.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5644.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5645.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5646.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5648.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5648.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5650.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5651.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5656.9185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5661.9185 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5667.3351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5668.3351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5668.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5670.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5671.7151 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 5680.7151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5681.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 5687.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5689.4751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5690.4751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5691.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5693.6151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5694.6151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5696.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5698.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5699.1351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5700.1351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5701.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5703.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5704.6351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5705.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5706.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5708.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5708.6351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5710.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5711.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5712.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5713.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5715.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5720.5518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5725.5518 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5730.9685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5731.9685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5732.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5734.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5735.3485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5736.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5738.1085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5739.1085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5740.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5742.2485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5743.2485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5744.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5746.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5747.7685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5748.7685 | TurbineInstallation
| WTIV | Delay | 57 | 950000 | ACTION | 5805.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5807.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5809.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5810.2685 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5810.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5812.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5813.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5814.2685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5815.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5817.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5817.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5819.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5820.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5826.1851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5829.4284 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5831.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5833.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5835.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5837.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5839.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5840.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5840.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5841.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5843.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5845.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5847.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5849.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5851.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5852.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5853.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5853.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5855.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5857.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5859.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5861.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5863.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5864.6784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5865.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5866.1784 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5869.4216 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5874.4216 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5879.8383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5880.8383 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5881.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5883.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5884.2183 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5884.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5886.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5887.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5889.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5891.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5892.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5893.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5895.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5896.6383 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5897.6383 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5899.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5901.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5902.1383 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5902.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5904.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5905.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5906.1383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5907.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5909.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5909.6383 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5911.1383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5912.6383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5918.055 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5923.055 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5928.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5929.4716 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5929.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5931.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5933.8516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5934.8516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5935.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5937.6116 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5938.6116 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5939.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5941.7516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5942.7516 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5944.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5946.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5947.2716 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5948.2716 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5949.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5951.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5952.7716 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5953.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5954.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5956.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5956.7716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5958.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5959.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5960.2716 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5961.7716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5963.2716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5968.6883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5973.6883 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5979.105 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5980.105 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5980.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5982.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5983.485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5984.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5986.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5987.245 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5988.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5990.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5991.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5992.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5994.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5995.905 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5996.905 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5998.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6000.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6001.405 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6001.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6003.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6004.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6005.405 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6006.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6008.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6008.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6010.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6011.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6017.3216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6020.5649 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6022.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6024.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6026.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6028.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6030.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6031.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6032.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6032.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6034.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6036.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6038.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6040.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6042.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6043.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6044.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6045.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6047.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6049.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6051.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6053.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6055.0649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6055.8149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6056.5649 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6057.3149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6060.5581 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6065.5581 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6070.9748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6071.9748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6072.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6074.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6075.3548 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6076.3548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6077.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6081.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6083.1148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6084.1148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6085.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6087.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6088.2548 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6094.2548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6095.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6097.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6098.7748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6099.7748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6101.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6103.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6104.2748 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6104.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6106.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6107.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6108.2748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6109.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6111.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6111.7748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6113.2748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6114.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6120.1915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6125.1915 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6130.6081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6131.6081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6131.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6133.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6134.9881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6135.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6137.7481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6138.7481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6139.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6141.8881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6142.8881 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6144.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 26 | 433333.3333 | ACTION | 6170.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6172.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6173.4081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6174.4081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6175.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6177.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6178.9081 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6179.4081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6180.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6182.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6182.9081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6184.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6185.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6186.4081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6187.9081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6189.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6194.8248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6199.8248 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6205.2415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6206.2415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6206.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6208.6215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6209.6215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6210.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6212.3815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6213.3815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6214.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6216.5215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6217.5215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6219.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6221.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6222.0415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6223.0415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6224.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6226.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6227.5415 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6228.0415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6229.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6231.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6231.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6233.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6234.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6235.0415 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6239.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6240.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6242.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6247.4581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6250.7014 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6252.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6254.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6256.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6258.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6260.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6261.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6262.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6262.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6264.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6266.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6268.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6270.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6272.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6273.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6274.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6275.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6277.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6279.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6281.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6283.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6285.2014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6285.9514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6286.7014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6287.4514 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6290.6946 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6295.6946 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6301.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6302.1113 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 6313.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6313.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6315.4913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6316.4913 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6317.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6319.2513 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6320.2513 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6321.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6323.3913 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6324.3913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6325.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6327.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6328.9113 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6329.9113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6331.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6333.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6334.4113 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6334.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6336.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6337.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6338.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6339.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6341.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6341.9113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6343.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6344.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6350.3279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6355.3279 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6360.7446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6361.7446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6362.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6364.1246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6365.1246 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6365.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6367.8846 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6368.8846 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6370.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6372.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6373.0246 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6379.0246 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6380.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6382.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6384.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6385.5446 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6386.5446 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6388.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6390.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6391.0446 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6391.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6393.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6394.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6395.0446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6396.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6398.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6398.5446 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6400.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6401.5446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6406.9613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6411.9613 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6417.3779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6418.3779 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6418.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6420.7579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6421.7579 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6422.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6424.5179 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6425.5179 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6426.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6428.6579 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6429.6579 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6431.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6433.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6434.1779 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6435.1779 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6436.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6438.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6439.6779 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6440.1779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6441.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6443.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6443.6779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6445.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6446.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6447.1779 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6448.6779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6450.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6455.5946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6458.8378 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6460.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6462.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6464.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6466.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6468.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6469.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6470.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6471.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6473.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6475.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6477.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6479.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6481.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6481.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6482.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6483.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6485.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6487.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6489.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6491.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6493.3378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6494.0878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6494.8378 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6495.5878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6498.8311 | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 6514.8311 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6519.8311 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6525.2478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6526.2478 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6526.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6528.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6529.6278 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6530.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6532.3878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6533.3878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6534.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6536.5278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6537.5278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6539.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6541.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6542.0478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6543.0478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6544.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6546.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6547.5478 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6548.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6549.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6551.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6551.5478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6553.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6554.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6555.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6556.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6558.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6563.4644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6568.4644 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6573.8811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6574.8811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6575.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6577.2611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6578.2611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6579.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6581.0211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6582.0211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6583.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6585.1611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6586.1611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6587.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6589.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6590.6811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6591.6811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6593.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6595.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6596.1811 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6596.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6598.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6599.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6600.1811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6601.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6603.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6603.6811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6605.1811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6606.6811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6612.0978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6617.0978 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6622.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6623.5144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6623.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6625.8944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6626.8944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6627.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6629.6544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6630.6544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6631.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6633.7944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6634.7944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6636.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6638.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6639.3144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6640.3144 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6641.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6643.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6644.8144 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6645.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6646.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6648.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6648.8144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6650.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6651.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6652.3144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6653.8144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6655.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 6661.3144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6666.7311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6669.9743 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6671.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6673.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6675.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6677.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6679.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6680.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6681.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6682.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6684.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6686.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6688.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6690.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6692.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6692.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6693.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6694.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6696.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6698.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6700.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6702.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6704.4743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6705.2243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6705.9743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6706.7243 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6709.9676 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6714.9676 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6720.3842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6721.3842 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6721.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6723.7642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6724.7642 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6725.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6727.5242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6728.5242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6729.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6731.6642 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6732.6642 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6734.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6736.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6737.1842 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6738.1842 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6753.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6754.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6756.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6757.6842 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6758.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6759.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6761.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6761.6842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6763.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6764.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6765.1842 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6766.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6768.1842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6773.6009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6778.6009 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6784.0176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6785.0176 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6785.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6787.3976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6788.3976 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6789.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6791.1576 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6792.1576 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6793.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6795.2976 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6796.2976 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6797.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6799.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6800.8176 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6801.8176 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6803.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6805.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6806.3176 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6806.8176 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6820.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6822.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6823.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6824.3176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6825.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6827.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6827.8176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6829.3176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6830.8176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6836.2342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6841.2342 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6846.6509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6847.6509 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6848.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6850.0309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6851.0309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6851.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6853.7909 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6854.7909 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6855.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6857.9309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6858.9309 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6860.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6862.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6863.4509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6864.4509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6865.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6867.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6868.9509 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6869.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6870.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6872.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6872.9509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6874.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6875.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6876.4509 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6877.9509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6879.4509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6884.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6888.1108 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6890.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6892.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6894.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6896.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6898.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6898.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6899.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6900.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6902.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6904.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6906.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6908.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6910.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6911.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6911.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6912.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6914.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6916.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6918.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6920.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6922.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6923.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6924.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6924.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6928.1041 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6933.1041 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6938.5207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6939.5207 | TurbineInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 6969.5207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6969.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6971.9007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6972.9007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6973.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6975.6607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6976.6607 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6977.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6979.8007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6980.8007 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6982.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6984.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6985.3207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6986.3207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6987.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6989.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6990.8207 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6991.3207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6992.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6994.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6994.8207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6996.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6997.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6998.3207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6999.8207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7001.3207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7006.7374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7011.7374 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7017.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7018.1541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7018.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7020.5341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7021.5341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7022.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7024.2941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7025.2941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7026.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7028.4341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7029.4341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7030.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7032.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7033.9541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7034.9541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7036.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7038.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7039.4541 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7039.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7041.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 43 | 716666.6667 | ACTION | 7084.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7085.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7086.4541 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7087.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7088.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7090.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7090.9541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7092.4541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7093.9541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7099.3707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7104.3707 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7109.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7110.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7111.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7113.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7114.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7114.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7116.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7117.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7119.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7121.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7122.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7123.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7125.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7126.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7127.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7129.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7131.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7132.0874 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7132.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7134.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7135.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7136.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7137.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7139.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7139.5874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7141.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7142.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7148.0041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7151.2473 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7153.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7155.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7157.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7159.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7161.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7161.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7162.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7163.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7165.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7167.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7169.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7171.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7173.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7174.2473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7174.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7175.7473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7178.9906 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7183.9906 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7189.4072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7190.4072 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7190.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7192.7872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7193.7872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7194.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7196.5472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7197.5472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7198.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7200.6872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7201.6872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7203.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7205.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7206.2072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7207.2072 | TurbineInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 7228.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7229.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7231.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7232.7072 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7233.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7234.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7236.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7236.7072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7238.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7239.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7240.2072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7241.7072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7243.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7248.6239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7253.6239 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7259.0406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7260.0406 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7260.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7262.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7263.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7264.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7266.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7267.1806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7268.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7270.3206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7271.3206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7272.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7274.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7275.8406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7276.8406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7278.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7280.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7281.3406 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7281.8406 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 7291.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7293.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7295.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7296.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7297.3406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7298.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7300.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7300.8406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7302.3406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7303.8406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7309.2572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5