## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 64 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 76 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 84 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 96 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 104 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 116 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 124 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 127.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 132.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 137.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 138.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 148.6599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 149.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 149.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 150.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 151.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 161.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 162.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 163.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 167.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 173.0029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 178.0029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 183.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 184.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 216666.6667 | ACTION | 197.4196 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 207.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 208.1426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 208.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 209.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 210.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 220.3459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 221.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 222.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 226.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 231.7625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 236.7625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 242.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 243.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 253.1792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 253.9023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 253.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 254.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 256.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 266.1055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 267.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 268.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 272.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 277.5222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 282.5222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 287.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 288.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 298.9389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 299.6619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 299.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 300.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 301.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 311.8652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 312.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 313.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 317.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 323.2818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 328.2818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 333.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 334.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 344.6985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 345.4216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 345.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 346.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 347.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 357.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 358.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 359.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 363.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 369.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 374.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 379.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 380.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 390.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 391.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 391.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 392.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 393.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 403.3845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 404.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 405.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 409.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 414.8011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 418.0444 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 430.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 438.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 450.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 458.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 470.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 478.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 490.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 498.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 510.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 518.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 530.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 538.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 541.2876 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 546.2876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 551.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 552.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 562.7043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 563.4274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 563.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 564.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 565.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 575.6306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 576.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 577.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 581.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 587.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 592.0473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 597.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 598.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 608.4639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 609.187 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 609.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 610.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 611.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 621.3903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 622.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 623.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 627.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 632.8069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 637.8069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 643.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 644.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 654.2236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 654.9467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 654.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 655.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 657.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 667.1499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 668.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 669.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 673.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 678.5666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 683.5666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 688.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 689.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 699.9832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 700.7063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 700.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 701.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 702.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 712.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 713.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 714.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 718.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 724.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 729.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 734.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 735.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 745.7429 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 746.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 746.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 747.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 748.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 758.6692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 759.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 761.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 762.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 763.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 767.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 773.0859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 778.0859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 783.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 784.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 794.5025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 795.2256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 795.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 796.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 797.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 807.4288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 808.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 809.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 813.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 818.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 822.0888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 834.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 842.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 854.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 862.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 874.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 882.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 894.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 902.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 914.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 922.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 934.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 942.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 945.332 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 950.332 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 955.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 956.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 966.7487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 967.4717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 967.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 968.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 969.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 979.675 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 980.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 981.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 985.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 991.0917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 996.0917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1001.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1002.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1012.5083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1013.2314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1013.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1014.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1015.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1025.4346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1026.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1027.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1031.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1036.8513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1041.8513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1047.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1048.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1058.268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1058.991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1058.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1059.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1061.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1071.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1072.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1073.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1077.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1082.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1087.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1093.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1094.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1104.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1104.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1104.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1105.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1106.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1116.9539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1117.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1118.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1122.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1128.3706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1133.3706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1138.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1139.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1149.7873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1150.5103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1150.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1151.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1152.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1162.7136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1163.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1164.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1168.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1174.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1179.1302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1184.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1185.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1195.5469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1196.27 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1196.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1197.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1198.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1208.4732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1209.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1210.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1214.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1219.8899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1223.1331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1235.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1243.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1255.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1263.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1275.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1283.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1295.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1303.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1315.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1323.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1335.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1343.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1346.3764 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1351.3764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1356.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1357.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1367.793 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1368.5161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1368.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1369.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1370.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1380.7194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1381.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1382.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1386.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1392.136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1397.136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1402.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1403.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1413.5527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1414.2758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1414.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1415.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1416.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1426.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1427.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1428.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1432.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1437.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1442.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1448.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1449.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1459.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1460.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1460.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1461.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1462.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1472.2387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1473.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1474.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1478.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1483.6553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1488.6553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1494.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1495.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1505.072 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1505.7951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1505.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1506.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1507.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1517.9983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1518.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1519.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1523.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1529.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1534.415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1539.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1540.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1550.8316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1551.5547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1551.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1552.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1553.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1563.758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1564.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1565.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1569.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1575.1746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1580.1746 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1585.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1586.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1596.5913 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1597.3144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1597.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1598.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1599.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1609.5176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1610.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1611.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1615.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1620.9343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1624.1775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1636.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1644.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1656.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1664.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1676.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1684.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1696.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1704.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1716.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1724.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1736.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1744.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1747.4208 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1752.4208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1757.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1758.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1768.8374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1769.5605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1769.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1770.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1771.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1781.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1782.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1783.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1787.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1793.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1798.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1803.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1804.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1814.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1815.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1815.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1816.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1817.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1827.5234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1828.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1829.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1833.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1838.9401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1843.9401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1849.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1850.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1860.3567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1861.0798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1861.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1862.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1863.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1873.283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1874.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1875.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1879.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1884.6997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1889.6997 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1895.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1896.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1906.1164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1906.8394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1906.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1907.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1909.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1919.0427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1920.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1921.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1925.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1930.4594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1935.4594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1940.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1941.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1951.876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1952.5991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1952.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1953.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1954.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1964.8023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1965.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1966.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1970.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1976.219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1981.219 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1986.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1987.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1997.6357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1998.3587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1998.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1999.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2000.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2010.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2011.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2012.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2016.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2021.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2025.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2037.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2045.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2057.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2065.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2077.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2085.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2097.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2105.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2117.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2125.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2137.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2145.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2148.4651 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2153.4651 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2158.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2159.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2169.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2170.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2170.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2171.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2172.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2182.8081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2183.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2184.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2188.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2194.2248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2199.2248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2204.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2205.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2215.6415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2216.3645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2216.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2217.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2218.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2228.5678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2229.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2230.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2234.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2239.9844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2244.9844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2250.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2251.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2261.4011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2262.1242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2262.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2263.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2264.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2274.3274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2275.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2276.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2280.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2285.7441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2290.7441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2296.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2297.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2307.1608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2307.8838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2307.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2308.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2310.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2320.0871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2321.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2322.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2326.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2331.5037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2336.5037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2341.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2342.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2352.9204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2353.6435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2353.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2354.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2355.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2365.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2366.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2367.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2371.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2377.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2382.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2387.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2388.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2398.6801 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2399.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2399.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2400.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2401.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2411.6064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2412.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2413.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2417.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2423.023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2426.2663 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2438.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2446.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2458.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2466.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2478.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2486.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2498.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2506.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2518.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2526.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2538.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2546.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2549.5095 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2554.5095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2559.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2560.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2570.9262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2571.6493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2571.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2572.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2573.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2583.8525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2584.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2585.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2589.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2595.2692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2600.2692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2605.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2606.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2616.6858 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2617.4089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2617.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2618.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2619.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2629.6122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2630.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2631.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2635.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2641.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2646.0288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2651.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2652.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2662.4455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2663.1686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2663.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2664.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2665.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2675.3718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2676.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2677.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2681.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2686.7885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2691.7885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2697.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2698.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2708.2051 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2708.9282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2708.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2709.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2711.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2721.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2722.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2723.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2727.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2732.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2737.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2742.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2743.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 27 | 450000 | ACTION | 2770.9648 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2780.9648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2781.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2781.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2782.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2783.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2793.8911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2794.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2795.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2799.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2805.3078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2810.3078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2815.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2816.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2826.7244 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2827.4475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2827.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2828.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2829.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2839.6507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2840.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2841.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2845.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2851.0674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2854.3107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2866.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2874.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2886.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2894.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2906.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2914.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2926.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2934.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2946.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2954.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2966.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2974.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2977.5539 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2982.5539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2987.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2988.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2998.9706 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2999.6936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2999.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3000.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3001.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3011.8969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3012.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 21 | 350000 | ACTION | 3033.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3034.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3041.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3045.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3051.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3056.3136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3061.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3062.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3072.7302 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3073.4533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3073.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3074.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3075.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3085.6565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3086.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3087.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3091.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3097.0732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3102.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3107.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3108.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3118.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3119.2129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3119.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3120.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3121.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3131.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3132.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3133.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3137.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3142.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3147.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3153.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3154.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3164.2495 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3164.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3164.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3165.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3167.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3177.1758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3178.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3179.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3183.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3188.5925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3193.5925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3199.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3200.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3210.0092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3210.7322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3210.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3211.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3212.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3222.9355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3223.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3224.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3228.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3234.3521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3239.3521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3244.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3245.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3255.7688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3256.4919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3256.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3257.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3258.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3268.6951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3269.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3270.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3274.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3280.1118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3283.355 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3295.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3303.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3315.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3323.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3326.5983 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3331.5983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3337.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3338.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3348.0149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3348.738 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3348.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3349.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3350.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3360.9413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3361.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3362.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3366.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3372.3579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3377.3579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3382.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3383.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3393.7746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3394.4977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3394.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3395.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3396.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3406.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3407.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3408.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3412.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3418.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 3418.1176 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3420.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3422.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3424.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3426.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3428.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3428.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3429.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3430.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3432.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3434.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3436.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3438.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3440.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3441.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3441.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3442.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3444.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3446.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3448.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3450.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3452.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3453.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3454.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3454.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3456.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3458.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3460.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3462.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3464.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3465.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3466.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3467.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3469.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3471.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3473.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3475.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3477.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3477.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3478.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3479.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3481.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3483.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3485.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3487.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3489.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3490.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3490.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3491.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3494.8608 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3499.8608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3505.2775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3506.2775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3506.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3508.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3509.6575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3510.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3512.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3513.4175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3514.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3516.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3517.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3519.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3521.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3522.0775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3523.0775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3524.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3526.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3527.5775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3528.0775 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 3535.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3536.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3537.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3539.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3539.5775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3541.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3542.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3543.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3544.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3546.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3551.4942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3556.4942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3561.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3562.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3563.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3565.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3566.2908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3567.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3569.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3570.0508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3571.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3573.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3574.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3575.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3577.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3578.7108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3579.7108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3581.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3583.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3584.2108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3584.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3586.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3587.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3588.2108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3589.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3591.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3591.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3593.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3594.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3600.1275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3605.1275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3610.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3611.5442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3611.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3613.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3614.9242 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3618.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3619.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3621.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3622.6842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3623.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3625.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3626.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3628.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3630.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3631.3442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3632.3442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3633.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3635.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3636.8442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3637.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3638.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3640.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3640.8442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3642.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3643.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3644.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3645.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3647.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3652.7608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3657.7608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3663.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3664.1775 | TurbineInstallation
| WTIV | Delay | 37 | 616666.6667 | ACTION | 3701.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3701.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3703.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3704.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3705.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3707.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3708.3175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3709.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3711.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3712.4575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3713.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3715.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3716.9775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3717.9775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3719.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3721.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3722.4775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3722.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3724.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3725.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3726.4775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3727.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3729.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3729.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3731.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3732.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3738.3942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3743.3942 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 3760.3942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3765.8108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3766.8108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3767.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3769.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3770.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3770.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3772.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3773.9508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3775.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3777.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3778.0908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3779.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3781.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3782.6108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3783.6108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3785.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3787.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3788.1108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3788.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3790.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3791.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3792.1108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3793.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3795.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3795.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3797.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3798.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3804.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3809.0275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3814.4442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3815.4442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3815.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3817.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3818.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3819.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3821.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3822.5842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3823.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 3829.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3831.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3832.7242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3834.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3836.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3837.2442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3838.2442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3839.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3841.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3842.7442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3843.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3844.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3846.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3846.7442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3848.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3849.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3850.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3851.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3853.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3858.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3861.9041 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3863.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3865.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3867.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3869.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3871.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3872.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3873.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3874.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3876.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3878.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3880.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3882.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3884.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3884.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3885.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3886.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3888.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3890.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3892.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3894.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3896.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3897.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3897.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3898.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3900.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3902.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3904.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3906.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3908.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3909.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3910.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3910.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3912.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3914.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3916.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3918.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3920.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3921.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3922.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3923.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3925.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3927.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3929.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3931.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3933.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3933.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3934.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3935.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3938.6473 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3943.6473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3949.064 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3950.064 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3950.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3952.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3953.444 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3954.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3956.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3957.204 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3958.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3960.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3961.344 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3962.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3964.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3965.864 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3966.864 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3968.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3970.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3971.364 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3971.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3973.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3974.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3975.364 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3976.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3978.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3978.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3980.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3981.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3987.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3992.2806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3997.6973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3998.6973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3999.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4001.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4002.0773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4002.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4004.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4005.8373 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4007.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4008.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4010.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4011.9773 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 4053.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4055.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4057.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4058.4973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4059.4973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4060.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4062.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4063.9973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4064.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4065.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4067.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4067.9973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4069.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4070.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4071.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4072.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4074.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4079.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4084.914 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4090.3306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4091.3306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4091.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4093.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4094.7106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4095.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4097.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4098.4706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4099.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4101.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4102.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4104.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4106.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4107.1306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4108.1306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4109.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4111.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4112.6306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4113.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4114.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4116.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4116.6306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4118.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4119.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4120.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4121.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4123.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4128.5473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4133.5473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4138.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4139.964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4140.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4142.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4143.344 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4144.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4146.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4147.104 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4148.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4150.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4151.244 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4152.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4154.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4155.764 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4156.764 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4158.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4160.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4161.264 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4161.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4163.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4164.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4165.264 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4166.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4168.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4168.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4170.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4171.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4177.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4182.1806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4187.5973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4188.5973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4188.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4190.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4191.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4192.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4194.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4195.7373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4196.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4198.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4199.8773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4201.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4203.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4204.3973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4205.3973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4206.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4208.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4209.8973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4210.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4211.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4213.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4213.8973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4215.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4216.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4217.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4218.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4220.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4225.814 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4230.814 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4236.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4237.2306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4237.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4239.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4240.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4241.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4243.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4244.3706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4245.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4247.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4248.5106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4250.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4252.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4253.0306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4254.0306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4255.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4257.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4258.5306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4259.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4260.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4262.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4262.5306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4264.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4265.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4266.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4267.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 4276.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4278.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4283.4473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4286.6906 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4288.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4290.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4292.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4294.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4296.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4297.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4298.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4298.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4300.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4302.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4304.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4306.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4308.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4309.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4310.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4311.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4313.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4315.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4317.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4319.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4321.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4321.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4322.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4323.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4325.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4327.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4329.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4331.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4333.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4334.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4334.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4335.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4337.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4339.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4341.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4343.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4345.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4346.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4347.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4347.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4349.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4351.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4353.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4355.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4357.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4358.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4359.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4360.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4363.4338 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4368.4338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4373.8505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4374.8505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4375.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4377.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4378.2305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4378.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4380.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4381.9905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4383.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4385.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4386.1305 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 4393.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4394.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4396.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4397.6505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4398.6505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4400.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4402.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4403.1505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4403.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4405.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4406.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4407.1505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4408.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4410.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4410.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4412.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4413.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4419.0671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4424.0671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4429.4838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4430.4838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4430.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4432.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4433.8638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4434.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4436.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4437.6238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4438.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4440.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4441.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4443.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4445.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4446.2838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4447.2838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4448.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4450.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4451.7838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4452.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4453.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4455.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4455.7838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4457.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4458.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4459.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4460.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4462.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4467.7005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4472.7005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4478.1171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4479.1171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4479.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4481.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4482.4971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4483.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4485.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4486.2571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4487.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4489.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4490.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4491.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4493.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4494.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4495.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4497.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4505.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4507.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4508.4171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4508.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4510.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4511.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4512.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4513.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4515.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4515.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4517.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4518.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 24 | 400000 | ACTION | 4542.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4548.3338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4553.3338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4558.7505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4559.7505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4560.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4562.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4563.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4563.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4565.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4566.8905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4568.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4570.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4571.0305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4572.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4574.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4575.5505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4576.5505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4578.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4580.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4581.0505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4581.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4583.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4584.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4585.0505 | TurbineInstallation
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4593.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4594.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4596.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4596.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4598.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4599.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4604.9671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4609.9671 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4615.9671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4621.3838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4622.3838 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4624.3838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4624.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4626.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4627.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4628.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 67 | 1116666.6667 | ACTION | 4695.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4697.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4698.5238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4699.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4701.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4702.6638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4704.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4706.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4707.1838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4708.1838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4709.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4711.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4712.6838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4713.1838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4714.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4716.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4716.6838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4718.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4719.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4720.1838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4721.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4723.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4728.6005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4733.6005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4739.0171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4740.0171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4740.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4742.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4743.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4744.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4746.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4747.1571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4748.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4750.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4751.2971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4752.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4754.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4755.8171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4756.8171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4758.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4760.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4761.3171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4761.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4763.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4764.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4765.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4766.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4768.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4768.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4770.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4771.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4777.2338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4780.477 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4782.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4784.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4786.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4788.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4790.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4791.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4791.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4792.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4794.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4796.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4798.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4800.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4802.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4803.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4804.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4804.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4806.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4808.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4810.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4812.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 4828.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4830.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4831.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4832.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4833.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4835.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4837.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4839.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4841.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4843.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4843.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4844.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4845.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4847.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4849.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4851.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4853.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4855.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4856.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4856.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4857.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4859.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4861.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4863.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4865.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4867.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4868.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4869.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4869.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4873.2203 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4878.2203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4883.6369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4884.6369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4885.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4887.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4888.0169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4888.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4890.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4891.7769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4892.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4894.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4895.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4897.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4899.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4900.4369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4901.4369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4902.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4904.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4905.9369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4906.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4907.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4909.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4909.9369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4911.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4912.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4913.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4914.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4916.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4921.8536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4926.8536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4932.2703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4933.2703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4933.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4935.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4936.6503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4937.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4939.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4940.4103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4941.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4943.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4944.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4946.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4948.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4949.0703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4950.0703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4951.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4953.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4954.5703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4955.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4956.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4958.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4958.5703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4960.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4961.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4962.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4963.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4965.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4970.4869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4975.4869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4980.9036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4981.9036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4982.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4984.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4985.2836 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4988.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4989.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4991.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4992.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4993.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4995.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4996.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4997.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4999.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5000.7036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5001.7036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5003.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5005.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5006.2036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5006.7036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5008.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5009.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5010.2036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5011.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5013.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5013.7036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5015.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5016.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5022.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5027.1203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5032.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5033.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5033.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5035.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5036.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5037.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5039.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5040.6769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5041.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5043.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5044.8169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5046.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5048.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5049.3369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5050.3369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5051.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5053.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5054.8369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5055.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5056.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5058.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5058.8369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5060.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5061.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5062.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5063.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5065.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5070.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5075.7536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5081.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5082.1703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5082.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5084.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5085.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5086.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5088.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5089.3103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5090.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5092.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5093.4503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5094.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5096.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5097.9703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5098.9703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5100.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5102.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5103.4703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5103.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5105.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5106.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5107.4703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5108.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5110.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5110.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5112.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5113.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5119.3869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5124.3869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5129.8036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5130.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5131.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5133.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5134.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5134.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5136.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5137.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5139.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5141.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5142.0836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5143.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 5160.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5162.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5163.6036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5164.6036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5166.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5168.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5169.1036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5169.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5171.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5172.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5173.1036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5174.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5176.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5176.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5178.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5179.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5185.0203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5188.2635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5190.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5192.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5194.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5196.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5198.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5199.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5199.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5200.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5202.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5204.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5206.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5208.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5210.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5211.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5212.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5212.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5214.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5216.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5218.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5220.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5222.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5223.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5224.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5225.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5227.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5229.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5231.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5233.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5235.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5235.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5236.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5237.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5239.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5241.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5243.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5245.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5247.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5248.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5248.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5249.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5251.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5253.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5255.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5257.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5259.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5260.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5261.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5261.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5265.0068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5270.0068 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 5279.0068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5284.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5285.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5285.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5287.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5288.8034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5289.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5291.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5292.5634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5293.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5295.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5296.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5298.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5300.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5301.2234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5302.2234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5303.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5305.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5306.7234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5307.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5308.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5310.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5310.7234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5312.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5313.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5314.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5315.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5317.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5322.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5327.6401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5333.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5334.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5334.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5336.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5337.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5338.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5340.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5341.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5342.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5344.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5345.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5346.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5348.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5349.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5350.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5352.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5354.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5355.3568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5355.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5357.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5358.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5359.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5360.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5362.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5362.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5364.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5365.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5371.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5376.2734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5381.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5382.6901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5383.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5385.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5386.0701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5386.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5388.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5389.8301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5390.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5392.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5393.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5395.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5397.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5398.4901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5399.4901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5400.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5402.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5403.9901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5404.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5405.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5407.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5407.9901 | TurbineInstallation
| WTIV | Delay | 74 | 1233333.3333 | ACTION | 5481.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5483.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5484.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5485.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5486.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5488.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5493.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5498.9068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5504.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5505.3234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5505.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5507.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5508.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5509.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5511.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5512.4634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5513.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5515.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5516.6034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5518.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5520.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5521.1234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5522.1234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5523.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5525.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5526.6234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5527.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5528.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5530.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5530.6234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5532.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5533.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5534.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5535.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5537.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5542.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5547.5401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5552.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5553.9568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5554.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5556.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5557.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5558.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5560.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5561.0968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5562.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5564.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5565.2368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5566.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5568.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5569.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5570.7568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5572.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5574.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5575.2568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5575.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5577.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5578.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5579.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5580.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5582.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5582.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5584.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5585.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5591.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5596.1734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5601.5901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5602.5901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5602.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5604.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5605.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5606.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5608.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5609.7301 | TurbineInstallation
| WTIV | Delay | 27 | 450000 | ACTION | 5636.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5637.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5639.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5640.8701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5642.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5644.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5645.3901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5646.3901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5647.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5649.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5650.8901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5651.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5652.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5654.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5654.8901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5656.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5657.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5658.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5659.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5661.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5666.8068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5670.05 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5672.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5674.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5676.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5678.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5680.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5680.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5681.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5682.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5684.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5686.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5688.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5690.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5692.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5693.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5693.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5694.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5696.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5698.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5700.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5702.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5704.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5705.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5706.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5706.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5708.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5710.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5712.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5714.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5716.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5717.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5718.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5719.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5721.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5723.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5725.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5727.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5729.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5729.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5730.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5731.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5733.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5735.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5737.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5739.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5741.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5742.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5742.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5743.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5746.7933 | TurbineInstallation
| WTIV | Delay | 57 | 950000 | ACTION | 5803.7933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5808.7933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5814.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5815.2099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5815.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5817.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5818.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5819.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5821.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5822.3499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5823.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5825.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5826.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5828.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5830.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5831.0099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5832.0099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5833.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5835.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5836.5099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5837.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5838.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5840.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5840.5099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5842.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5843.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5844.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5845.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5847.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5852.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5857.4266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5862.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5863.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5864.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5866.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5867.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5867.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5869.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5870.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5872.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5874.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5875.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5876.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5878.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5879.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5880.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5882.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5884.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5885.1433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5885.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5887.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5888.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5889.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5890.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5892.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5892.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5894.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5895.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5901.0599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5906.0599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5911.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5912.4766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5912.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5914.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5915.8566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5916.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5918.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5919.6166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5920.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5922.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5923.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5925.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5927.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5928.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5929.2766 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5931.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5932.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5934.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5935.7766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5936.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5937.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5939.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5939.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5941.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5942.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5943.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5944.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5946.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5951.6933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5956.6933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5962.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5963.1099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5963.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5965.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5966.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5967.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5969.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5970.2499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5971.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5973.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5974.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5975.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5977.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5978.9099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5979.9099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5981.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5983.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5984.4099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5984.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5986.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5987.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5988.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5989.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5991.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5991.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5993.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5994.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6000.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6005.3266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6010.7433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6011.7433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6012.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6014.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6015.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6015.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6017.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6018.8833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6020.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6022.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6023.0233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6024.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6026.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6027.5433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6028.5433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6030.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6032.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6033.0433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6033.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6035.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6036.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6037.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6038.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6040.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6040.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6042.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6043.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6048.9599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6053.9599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6059.3766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6060.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6060.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6062.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6063.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6064.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6066.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6067.5166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6068.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6070.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6071.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6073.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6081.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6083.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6084.1766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6085.1766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6086.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6094.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6096.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6097.6766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6098.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6099.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6101.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6101.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6103.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6104.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6105.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6106.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6108.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6113.5933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6116.8365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6118.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6120.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6122.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6124.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6126.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6127.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6128.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6129.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6131.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6133.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6135.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6137.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6139.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6139.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6140.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6141.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6143.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6145.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 6168.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6170.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6172.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6174.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6175.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6175.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6176.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6178.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6180.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6182.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6184.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6186.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6187.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6188.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6188.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6190.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6192.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6194.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6196.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6198.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6199.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6200.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6201.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6203.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6205.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6207.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6209.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6211.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6211.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6212.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6213.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6216.5797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6221.5797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6226.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6227.9964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6228.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6230.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6231.3764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6232.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6234.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6235.1364 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6238.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6239.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6241.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6242.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6243.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6245.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6246.7964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6247.7964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6249.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6251.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6252.2964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6252.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6254.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6255.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6256.2964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6257.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6259.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6259.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6261.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6262.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6268.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6273.2131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6278.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6279.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6280.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6282.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6283.0097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6283.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6285.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6286.7697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6287.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6289.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6290.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6292.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6294.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6295.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6296.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6297.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6299.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6300.9297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6301.4297 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 6313.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6314.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6316.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6316.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6318.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6319.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6320.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6321.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6323.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6328.8464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6333.8464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6339.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6340.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6340.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6342.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6343.6431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6344.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6346.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6347.4031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6348.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6350.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6351.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6353.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6355.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6356.0631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6357.0631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6358.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6360.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6361.5631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6362.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6363.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6365.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6365.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6367.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6368.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6369.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6370.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 6378.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6380.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6385.4797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6390.4797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6395.8964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6396.8964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6397.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6399.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6400.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6401.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6403.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6404.0364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6405.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6407.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6408.1764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6409.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6411.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6412.6964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6413.6964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6415.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6417.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6418.1964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6418.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6420.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6421.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6422.1964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6423.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6425.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6425.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6427.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6428.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6434.1131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6439.1131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6444.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6445.5297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6445.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6447.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6448.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6449.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6451.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6452.6697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6453.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6455.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6456.8097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6458.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6460.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6461.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6462.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6463.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6465.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6466.8297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6467.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6468.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6470.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6470.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6472.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6473.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6474.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6475.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6477.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6482.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6487.7464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6493.1631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6494.1631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6494.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6496.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6498.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6499.5431 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6514.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6515.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6517.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6518.3031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6519.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6521.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6522.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6523.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6525.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6526.9631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6527.9631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6529.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6531.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6532.4631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6532.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6534.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6535.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6536.4631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6537.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6539.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6539.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6541.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6542.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6548.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6551.623 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6553.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6555.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6557.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6559.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6561.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6562.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6563.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6563.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6565.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6567.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6569.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6571.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6573.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6574.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6575.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6576.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6578.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6580.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6582.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6584.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6586.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6586.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6587.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6588.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6590.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6592.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6594.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6596.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6598.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6599.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6599.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6600.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6602.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6604.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6606.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6608.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6610.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6611.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6612.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6612.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6614.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6616.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6618.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6620.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6622.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6623.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6624.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6625.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6628.3662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6633.3662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6638.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6639.7829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6640.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6642.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6643.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6643.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6645.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6646.9229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6648.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6650.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6651.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6652.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6654.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6655.5829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6656.5829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6658.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 6663.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6665.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6666.0829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6666.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6668.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6669.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6670.0829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6671.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6673.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6673.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6675.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6676.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6681.9996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6686.9996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6692.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6693.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6693.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6695.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6696.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6697.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6699.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6700.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6701.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6703.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6704.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6706.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6708.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6709.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6710.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6711.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6713.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6714.7162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6715.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6716.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6718.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6718.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6720.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6721.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6722.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6723.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6725.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6730.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6735.6329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6741.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6742.0496 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 6754.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6754.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6756.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6757.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6758.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6760.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6761.1896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6762.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6764.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6765.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6766.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6768.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6769.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6770.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6772.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6774.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6775.3496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6775.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6777.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6778.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6779.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6780.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6782.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6782.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6784.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6785.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6791.2662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6796.2662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6801.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6802.6829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6803.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6805.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6806.0629 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6821.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6821.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6823.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6824.8229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6825.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6827.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6828.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6830.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6832.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6833.4829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6834.4829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6835.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6837.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6838.9829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6839.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6840.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6842.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6842.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6844.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6845.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6846.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6847.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6849.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6854.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6859.8996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6865.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6866.3162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6866.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6868.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6869.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6870.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6872.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6873.4562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6874.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6876.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6877.5962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6879.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6881.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6882.1162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6883.1162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6884.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6886.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6887.6162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6888.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6889.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6891.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6891.6162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6893.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6894.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6895.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6896.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6898.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6903.5329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6908.5329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6913.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6914.9496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6915.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6917.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6918.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6919.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6921.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6922.0896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6923.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6925.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6926.2296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6927.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6929.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6930.7496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6931.7496 | TurbineInstallation
| WTIV | Delay | 38 | 633333.3333 | ACTION | 6969.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6971.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6973.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6974.2496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6974.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6976.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6977.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6978.2496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6979.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6981.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6981.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6983.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6984.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6990.1662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6993.4095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6995.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6997.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6999.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7001.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7003.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7004.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7004.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7005.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7007.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7009.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7011.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7013.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7015.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7016.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7017.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7017.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7021.1527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7026.1527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7031.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7032.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7032.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7034.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7035.9494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7036.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7038.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7039.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7040.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 733333.3333 | ACTION | 7084.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7086.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7087.8494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7089.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7091.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7092.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7093.3694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7094.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7096.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7097.8694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7098.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7099.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7101.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7101.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7103.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7104.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7105.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7106.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7108.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7113.786 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7118.786 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7124.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7125.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7125.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7127.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7128.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7129.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7131.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7132.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7133.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7135.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7136.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7138.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7140.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7141.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7142.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7143.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7145.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7146.5027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7147.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7148.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7150.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7150.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7152.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7153.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7154.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7155.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7157.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7162.4194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5