## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 92 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 100 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 112 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 120 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 163.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 168.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 173.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 174.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 184.6599 | MonopileInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 187.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 188.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 188.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 189.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 25 | 416666.6667 | ACTION | 214.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 215.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 225.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 226.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 227.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 231.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 237.0029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 242.0029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 247.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 248.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 258.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 259.1426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 259.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 260.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 261.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 271.3459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 272.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 273.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 277.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 282.7625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 287.7625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 293.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 294.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 304.1792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 304.9023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 304.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 305.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 307.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 317.1055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 318.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 319.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 323.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 328.5222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 333.5222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 338.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 339.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 349.9389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 350.6619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 350.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 351.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 352.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 353.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 363.8652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 364.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 365.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 369.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 375.2818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 380.2818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 385.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 386.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 396.6985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 397.4216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 397.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 398.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 399.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 409.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 410.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 411.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 415.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 421.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 426.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 431.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 432.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 439.4582 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 449.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 450.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 450.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 451.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 453.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 454.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 464.3845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 465.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 466.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 470.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 475.8011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 519.0444 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 531.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 539.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 551.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 559.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 571.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 579.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 591.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 599.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 611.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 619.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 631.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 639.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 682.2876 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 687.2876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 692.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 693.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 703.7043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 704.4274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 704.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 705.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 706.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 716.6306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 717.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 718.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 722.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 728.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 733.0473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 738.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 739.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 749.4639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 750.187 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 750.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 751.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 752.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 762.3903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 763.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 766.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 767.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 771.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 776.8069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 781.8069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 787.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 788.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 798.2236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 798.9467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 798.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 799.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 801.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 811.1499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 812.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 813.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 817.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 822.5666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 827.5666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 832.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 833.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 843.9832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 844.7063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 844.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 845.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 846.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 856.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 857.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 858.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 862.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 866.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 872.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 877.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 882.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 883.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 885.7429 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 895.7429 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 896.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 896.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 897.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 898.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 908.6692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 909.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 910.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 914.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 920.0859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 925.0859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 930.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 931.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 941.5025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 942.2256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 942.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 943.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 944.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 954.4288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 955.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 956.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 960.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 965.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 1009.0888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1021.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1029.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1041.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1049.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1061.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1069.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1081.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1089.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1101.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1109.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1121.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1129.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 1172.332 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1177.332 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1182.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1183.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1193.7487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1194.4717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1194.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1195.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1196.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1206.675 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1207.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1208.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1212.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1218.0917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1223.0917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1228.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1229.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1239.5083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1240.2314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1240.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1241.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1242.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1252.4346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1253.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1254.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1258.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1263.8513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1268.8513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1274.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1275.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1285.268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1285.991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1285.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1286.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1288.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1298.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1299.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1300.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1304.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1309.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1314.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1320.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1321.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1331.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1331.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1331.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1332.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1333.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1343.9539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1344.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1345.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1349.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1355.3706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1360.3706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1365.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1366.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1376.7873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1377.5103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1377.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1378.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1379.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1389.7136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1390.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1391.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1395.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1401.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1406.1302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1411.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1412.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1422.5469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1423.27 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1423.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1424.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1425.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1435.4732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1436.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1437.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1441.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1446.8899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 1490.1331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1502.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1510.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1522.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1530.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1542.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1550.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1562.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1570.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1582.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1590.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1602.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1610.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 1653.3764 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1658.3764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1663.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1664.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1674.793 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1675.5161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1675.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1676.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1677.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1687.7194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1688.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1689.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1693.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1699.136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1704.136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1709.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1710.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1720.5527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1721.2758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1721.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1722.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1723.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1733.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1734.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1735.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1739.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1744.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1749.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1755.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1756.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1766.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1767.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1767.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1768.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1769.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1779.2387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1780.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1781.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1785.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1790.6553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1795.6553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1801.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1802.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1812.072 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1812.7951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1812.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1813.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1814.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1824.9983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1825.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1826.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1830.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1836.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1841.415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1846.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1847.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1857.8316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1858.5547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1858.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1859.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1860.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1870.758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1871.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1872.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1876.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1882.1746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1887.1746 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1892.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1893.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1903.5913 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1904.3144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1904.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1905.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1906.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1916.5176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1917.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1918.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1922.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1927.9343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 1971.1775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1983.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1991.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2003.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2011.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2023.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2031.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2043.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2051.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2063.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2071.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2083.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2091.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 2134.4208 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2139.4208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2144.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2145.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2155.8374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2156.5605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2156.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2157.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2158.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2168.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2169.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2170.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2174.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2180.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2185.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2190.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2191.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2201.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2202.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2202.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2203.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2204.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2214.5234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2215.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2216.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2220.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2225.9401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2230.9401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2236.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2237.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2247.3567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2248.0798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2248.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2249.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2250.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2260.283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2261.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2262.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2266.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2271.6997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2276.6997 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2282.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2283.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2293.1164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2293.8394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2293.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2294.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2296.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2306.0427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2307.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2308.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2312.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2317.4594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2322.4594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2327.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2328.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2338.876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2339.5991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2339.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2340.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2341.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2351.8023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2352.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2353.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2357.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2363.219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2368.219 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2373.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2374.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2384.6357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2385.3587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2385.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2386.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2387.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2397.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2398.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2399.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2403.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2408.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 2452.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2464.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2472.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2484.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2492.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2504.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2512.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2524.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2532.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2544.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2552.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2564.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2572.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 2615.4651 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2620.4651 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2625.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2626.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2636.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2637.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2637.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2638.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2639.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2649.8081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2650.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2651.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2655.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2661.2248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2666.2248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2671.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2672.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2682.6415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2683.3645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2683.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2684.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2685.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2695.5678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2696.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2697.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2701.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2706.9844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2711.9844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2717.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2718.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2728.4011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2729.1242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2729.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2730.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2731.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 34 | 566666.6667 | ACTION | 2765.3274 | MonopileInstallation
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2775.3274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2776.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 2777.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2778.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2780.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2784.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2789.7441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2794.7441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2800.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2801.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2811.1608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2811.8838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2811.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2812.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2814.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2824.0871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2825.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2826.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2830.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2835.5037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2840.5037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2845.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2846.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2856.9204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2857.6435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2857.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2858.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2859.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2869.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2870.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2871.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2875.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2881.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2886.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2891.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2892.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2902.6801 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2903.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2903.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2904.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2905.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2915.6064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2916.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2917.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2921.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2927.023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 2970.2663 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2982.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2990.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3002.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3010.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3033.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3045.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3046.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3054.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3066.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3074.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3086.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3094.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3106.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3114.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 3157.5095 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3162.5095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3167.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3168.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3178.9262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3179.6493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3179.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3180.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3181.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3191.8525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3192.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3193.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3197.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3203.2692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3208.2692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3213.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3214.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3224.6858 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3225.4089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3225.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3226.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3227.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3237.6122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3238.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3239.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3243.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3249.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3254.0288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3259.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3260.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3270.4455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3271.1686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3271.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3272.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3273.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3283.3718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3284.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3285.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3289.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3294.7885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3299.7885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3305.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3306.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3316.2051 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3316.9282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3316.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3317.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3319.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3329.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3330.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3331.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3335.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3340.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 200000 | ACTION | 3352.5481 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3357.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3362.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3363.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3373.9648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3374.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3374.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3375.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3376.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3386.8911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3387.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3388.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3392.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3398.3078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3403.3078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3408.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3409.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3419.7244 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3420.4475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3420.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3421.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3422.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3432.6507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3433.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3435.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3436.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3440.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3446.0674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 3489.3107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3501.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3509.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3521.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3529.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3541.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3549.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3561.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3569.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3581.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3589.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3601.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3609.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 3652.5539 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3657.5539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3662.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3663.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3673.9706 | MonopileInstallation
| WTIV | Delay | 30 | 500000 | ACTION | 3703.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3704.6936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3704.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3705.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3706.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3716.8969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3717.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3718.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3722.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3728.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3733.3136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3738.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3739.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3749.7302 | MonopileInstallation
| WTIV | Delay | 19 | 316666.6667 | ACTION | 3768.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3769.4533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3769.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3770.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3771.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3781.6565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3782.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3783.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3787.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3793.0732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3798.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3803.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3804.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3814.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3815.2129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3815.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3816.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3817.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3827.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3828.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 3831.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3832.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3834.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3838.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3843.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3848.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3854.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3855.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3865.2495 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3866.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3866.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3866.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3867.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3869.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3879.1758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3880.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3881.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3885.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3890.5925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3895.5925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3901.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3902.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3912.0092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3912.7322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3912.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3913.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3914.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3924.9355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3925.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3926.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3930.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3936.3521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3941.3521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3946.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3947.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3957.7688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3958.4919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3958.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3959.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3960.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3970.6951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3971.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3972.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3976.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3982.1118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 36 | 600000 | ACTION | 4018.1118 | MonopileInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4019.1118 | MonopileInstallation
| WTIV | Transit | 7 | 116666.6667 | ACTION | 4026.1118 | MonopileInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4040.1118 | MonopileInstallation
| WTIV | Transit | 0.24324 | 4054.0541 | ACTION | 4040.355 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 4052.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 4060.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 4072.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 4080.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 4123.5983 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4128.5983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4134.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 4135.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 4145.0149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 4145.738 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 4145.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4146.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 4147.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 4157.9413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4158.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 4159.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 4163.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4169.3579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4174.3579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4179.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 4180.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 4190.7746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 4191.4977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 4191.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4192.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 4193.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 4203.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 4204.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 4205.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 4209.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 4215.1176 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4215.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4217.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4219.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4221.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4223.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4225.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4225.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4226.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4227.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4229.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4231.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4233.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4235.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4237.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4238.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4238.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4239.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4241.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4243.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4245.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4247.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4249.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4250.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4251.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4251.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4253.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4255.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4257.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4259.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4261.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4262.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4263.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4264.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4266.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4268.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4270.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4272.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4274.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4274.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4275.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4276.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4277.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4279.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4281.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4283.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4285.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4287.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4288.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4288.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4289.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 4332.8608 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4337.8608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4343.2775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4344.2775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4344.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4346.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4347.6575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4348.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4350.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4351.4175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4352.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4354.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4355.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4357.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4359.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4360.0775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4361.0775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4362.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4364.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4365.5775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4366.0775 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4371.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4372.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4374.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4374.5775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4376.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4377.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4378.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4379.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4381.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4386.4942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4391.4942 | TurbineInstallation
| WTIV | Delay | 11 | 183333.3333 | ACTION | 4402.4942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4407.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4408.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4409.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4411.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4412.2908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4413.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4415.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4416.0508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4417.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4419.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4420.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4421.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4423.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4424.7108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4425.7108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4427.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4429.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4430.2108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4430.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4432.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4433.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4434.2108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4435.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4437.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4437.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4439.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4440.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4446.1275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4451.1275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4456.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4457.5442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4457.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4459.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4460.9242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4461.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4463.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4464.6842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4465.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4467.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4468.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4470.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4472.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4473.3442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4474.3442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4475.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4477.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4478.8442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4479.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4480.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4482.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4482.8442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4484.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4485.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4486.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4487.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4489.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4555.7608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4560.7608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4566.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4567.1775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4567.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4569.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4570.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4571.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4573.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4574.3175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4575.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4577.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4578.4575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4579.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4581.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4582.9775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4583.9775 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 4586.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4588.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4605.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4607.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4608.4775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4608.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4610.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4611.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4612.4775 | TurbineInstallation
| WTIV | Delay | 86 | 1433333.3333 | ACTION | 4698.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4699.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4702.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4704.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4704.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4706.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4707.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4713.3942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4718.3942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4723.8108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4724.8108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4725.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4727.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4728.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4728.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4730.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4731.9508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4733.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4735.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4736.0908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4737.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4739.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4740.6108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4741.6108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4743.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4745.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4746.1108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4746.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4748.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4749.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4750.1108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4751.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4753.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4753.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4755.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4756.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4762.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4767.0275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4772.4442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4773.4442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4773.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4775.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4776.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4777.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4779.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4780.5842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4781.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4783.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4784.7242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4786.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4788.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4789.2442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4790.2442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4791.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4793.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4794.7442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4795.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4796.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4798.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4798.7442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4800.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4801.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4802.2442 | TurbineInstallation
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4834.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4835.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4837.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4842.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 4885.9041 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4887.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4889.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4891.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4893.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4895.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4896.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4897.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4898.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4900.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4902.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4904.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4906.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4908.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4908.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4909.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4910.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4912.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4914.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4916.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4918.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4920.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4921.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4921.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4922.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4924.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4926.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4928.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4930.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4932.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4933.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4934.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4934.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4936.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4938.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4940.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4942.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4944.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4945.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4946.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4947.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4949.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4951.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4953.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4955.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4957.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4957.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4958.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4959.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 5002.6473 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5007.6473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5013.064 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5014.064 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5014.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5016.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5017.444 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5018.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5020.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5021.204 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5022.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5024.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5025.344 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5030.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5031.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5033.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5034.864 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5035.864 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5037.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5039.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5040.364 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5040.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5042.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5043.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5044.364 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5045.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5047.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5047.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5049.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5050.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5056.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5061.2806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5066.6973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5067.6973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5068.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5070.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5071.0773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5071.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5073.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5074.8373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5075.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5077.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5078.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5080.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5082.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5083.4973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5084.4973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5085.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5087.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5088.9973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5089.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5090.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5092.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5092.9973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5094.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5095.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5096.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5097.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5099.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5104.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5109.914 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5115.3306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5116.3306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5116.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5118.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5119.7106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5120.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5122.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5123.4706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5124.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5126.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5127.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5129.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5131.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5132.1306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5133.1306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5134.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5136.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5137.6306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5138.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5139.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5141.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5141.6306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5143.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5144.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5145.1306 | TurbineInstallation
| WTIV | Delay | 1264 | 21066666.6667 | ACTION | 6409.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6410.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6412.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6417.5473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6422.5473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6427.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6428.964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6429.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6431.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6433.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6434.344 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6435.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6437.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6438.104 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6439.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6441.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6442.244 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6443.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6445.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6446.764 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6447.764 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6449.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6451.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6452.264 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6452.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6454.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6455.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6456.264 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6457.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6459.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6459.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6461.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6462.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6468.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6473.1806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6478.5973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6479.5973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6479.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6481.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6482.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6483.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6485.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6486.7373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6487.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6489.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6490.8773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6492.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6494.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6495.3973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6496.3973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6497.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6499.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6500.8973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6501.3973 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 6516.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6517.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6519.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6519.8973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6521.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6522.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6523.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6524.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6526.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6531.814 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6536.814 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6542.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6543.2306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6543.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6545.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6546.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6547.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6549.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6550.3706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6551.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6553.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6554.5106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6556.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6558.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6559.0306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6560.0306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6561.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6563.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6564.5306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6565.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6566.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6568.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6568.5306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6570.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6571.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6572.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6573.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6575.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6580.4473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 6623.6906 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6625.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6627.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6629.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6631.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6633.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6634.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6635.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6635.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6637.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6639.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6641.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6643.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6645.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6646.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6647.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6648.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6650.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6652.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6654.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6656.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6658.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6658.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6659.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6660.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6662.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6664.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6666.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6668.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6670.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6672.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6673.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6673.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6674.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6676.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6678.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6680.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6682.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6684.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6685.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6686.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6686.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6688.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6690.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6692.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6694.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6696.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6697.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6698.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6699.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 6742.4338 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6745.4338 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6750.4338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6755.8505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6756.8505 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6757.8505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6758.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6760.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6761.2305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6761.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6763.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6764.9905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6766.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6768.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6769.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6770.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6772.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6773.6505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6774.6505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6776.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6778.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6779.1505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6779.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6781.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6782.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6783.1505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6784.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6786.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6786.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6788.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6789.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6795.0671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6800.0671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6805.4838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6806.4838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6806.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6808.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6809.8638 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6823.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6824.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6826.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6827.6238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6828.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6830.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6831.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6833.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6835.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6836.2838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6837.2838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6838.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6840.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6841.7838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6842.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6843.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6845.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6845.7838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6847.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6848.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6849.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6850.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6852.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6857.7005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6862.7005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6868.1171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6869.1171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6869.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6871.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6872.4971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6873.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6875.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6876.2571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6877.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6879.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6880.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6881.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6883.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6884.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6885.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6887.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6889.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6890.4171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6890.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6892.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6893.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6894.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6895.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6897.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6897.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6899.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6900.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6906.3338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 6911.3338 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6916.3338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6921.7505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6922.7505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6923.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6925.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6926.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6926.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6928.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6929.8905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6931.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6933.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6934.0305 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 6976.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6977.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 6983.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6985.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6986.5505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6987.5505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6989.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6991.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6992.0505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6992.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6994.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6995.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6996.0505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6997.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6999.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6999.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7001.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7002.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7007.9671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7012.9671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7018.3838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7019.3838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7019.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7021.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7022.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7023.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7025.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7026.5238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7027.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7029.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7030.6638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7032.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7034.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7035.1838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7036.1838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7037.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7039.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7040.6838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7041.1838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7042.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7044.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7044.6838 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7049.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7051.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7052.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7053.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7054.1838 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7055.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7056.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 36 | 600000 | ACTION | 7092.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7094.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7099.6005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7104.6005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7110.0171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7111.0171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7111.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7113.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7114.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7115.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7117.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7118.1571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7119.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7121.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7122.2971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7123.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7125.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7126.8171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7127.8171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7129.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7131.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7132.3171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7132.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7134.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7135.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7136.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7137.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7139.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7139.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7141.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7142.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7148.2338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 7191.477 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7193.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7195.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7197.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7199.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7201.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7202.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7202.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7203.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7205.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7207.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7209.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7211.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7213.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 133333.3333 | ACTION | 7221.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7222.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7223.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7223.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7225.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7227.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7229.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7231.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7233.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7234.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7235.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7236.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7238.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7240.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7242.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7244.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7246.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7246.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7247.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7248.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7250.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7252.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7254.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7256.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7258.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7259.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7259.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7260.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7262.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7264.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7266.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7268.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7270.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7271.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7272.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7272.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 14 | 233333.3333 | ACTION | 7286.977 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7288.977 | TurbineInstallation
| WTIV | Transit | 1 | 16666.6667 | ACTION | 7289.977 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 7295.977 | TurbineInstallation
| WTIV | Transit | 28.2432 | 470720.7207 | ACTION | 7324.2203 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7329.2203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7334.6369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7335.6369 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7338.6369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7339.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7341.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7342.0169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7342.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 7348.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7350.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7351.7769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7352.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7354.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7355.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7357.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7359.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7360.4369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7361.4369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7362.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7364.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7365.9369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7366.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7367.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7369.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7369.9369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7371.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7372.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7373.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7374.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7376.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7381.8536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7386.8536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7392.2703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7393.2703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7393.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7395.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7396.6503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7397.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7399.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7400.4103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7401.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7403.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7404.5503 | TurbineInstallation
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 7465.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7467.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7469.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7470.0703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7471.0703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7472.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7474.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7475.5703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7476.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7477.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7479.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7479.5703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7481.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7482.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7483.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7484.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7486.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7491.4869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7496.4869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7501.9036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7502.9036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7503.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7505.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7506.2836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7507.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7509.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7510.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7511.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7513.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7514.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7515.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7517.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7518.7036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7519.7036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7521.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7523.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7524.2036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7524.7036 | TurbineInstallation
| WTIV | Delay | 25 | 416666.6667 | ACTION | 7549.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7551.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7552.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7553.2036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7554.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7556.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7556.7036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7558.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7559.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7565.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7570.1203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7575.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7576.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7576.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7578.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7579.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7580.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7582.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7583.6769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7584.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7586.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7587.8169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7589.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7591.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7592.3369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7593.3369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7594.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7596.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7597.8369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7598.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7599.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7601.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7601.8369 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7603.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7605.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7606.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7607.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7608.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7610.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7615.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7620.7536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7626.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7627.1703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7627.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7629.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7630.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7631.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7633.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7634.3103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7635.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7637.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7638.4503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7639.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7641.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7642.9703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7643.9703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7645.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7647.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7648.4703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7648.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7650.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7651.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7652.4703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7653.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7655.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7655.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7657.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7658.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7664.3869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7669.3869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7674.8036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7675.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7676.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7678.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7679.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7679.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7681.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7682.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7684.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7686.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7687.0836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7688.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7690.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7691.6036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7692.6036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7694.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7696.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7697.1036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7697.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7699.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7700.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7701.1036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7702.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7704.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7704.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7706.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7707.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7713.0203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 7756.2635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7758.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7760.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7762.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7764.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7766.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7767.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7767.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7768.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7770.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7772.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7774.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7776.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7778.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7779.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7780.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7780.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7782.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7784.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7786.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7788.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7790.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7791.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7792.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7793.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7795.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7797.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7799.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7801.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7803.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7803.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7804.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7805.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7807.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7809.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7811.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7813.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7815.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7816.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7816.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7817.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7819.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7821.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7823.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7825.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7827.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7828.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7829.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7829.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 7873.0068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7878.0068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7883.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7884.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7884.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7886.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7887.8034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7888.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7890.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7891.5634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7892.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7894.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7895.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7897.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7899.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7900.2234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7901.2234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7902.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7904.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7905.7234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7906.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7907.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7909.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7909.7234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7911.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7912.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7913.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7914.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7916.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7921.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7926.6401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7932.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7933.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7933.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7935.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7936.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7937.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7939.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7940.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7941.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7943.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7944.3368 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7945.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7946.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7948.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7949.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7950.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7952.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7954.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7955.3568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7955.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7957.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7958.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7959.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7960.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7962.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7962.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7964.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7965.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7971.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7976.2734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7981.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7982.6901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7983.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7985.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7986.0701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7986.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7988.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7989.8301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7990.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7992.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7993.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7995.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7997.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7998.4901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7999.4901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8000.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8002.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8003.9901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8004.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8005.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8007.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8007.9901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8009.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8010.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8011.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8012.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8014.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8019.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8024.9068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8030.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8031.3234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8031.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8033.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8034.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8035.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8037.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8038.4634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8039.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8041.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8042.6034 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 8051.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8053.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8055.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8056.1234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8057.1234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8058.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8060.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8061.6234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8062.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8063.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8065.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8065.6234 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8066.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8068.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8072.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8073.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8074.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8075.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8077.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8082.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8087.5401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8092.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8093.9568 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8094.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8095.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8097.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8098.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8099.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8101.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8102.0968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8103.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8105.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8106.2368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8107.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8109.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8110.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8111.7568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8113.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8115.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8116.2568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8116.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8118.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8119.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8120.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8121.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8123.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8123.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8125.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8126.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 45 | 750000 | ACTION | 8171.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8177.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8182.1734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8187.5901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8188.5901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8188.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8190.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8191.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8192.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8194.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8195.7301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8196.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8198.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8199.8701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8201.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8203.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8204.3901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8205.3901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8206.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8208.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8209.8901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8210.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8211.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8213.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8213.8901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8215.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8216.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8217.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8218.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8220.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8225.8068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 8269.05 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8271.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8273.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8275.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8277.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8279.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8279.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8280.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8281.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8283.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8285.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8287.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8289.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8291.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8292.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8292.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8293.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8295.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8297.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8299.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8301.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8302.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8304.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8314.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8315.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8316.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8316.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8317.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8319.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8321.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8323.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8325.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8327.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8328.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8329.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8330.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8332.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8334.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8336.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 8339.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8341.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8343.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8343.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8344.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8345.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8347.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8349.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8351.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8353.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8355.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8356.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8356.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8357.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 8400.7933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8405.7933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8411.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8412.2099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8412.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8414.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8415.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8416.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 35 | 583333.3333 | ACTION | 8451.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8453.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8454.3499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8455.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8457.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8458.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8460.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8462.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8463.0099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8464.0099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8465.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8467.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8468.5099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8469.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8470.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8472.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8472.5099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8474.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8475.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8476.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8477.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8479.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8484.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8489.4266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8494.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8495.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8496.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8498.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8499.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8499.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8501.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8502.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8504.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8506.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8507.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8508.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8510.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8511.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8512.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8514.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8516.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8517.1433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8517.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8519.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8520.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8521.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8522.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8524.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8524.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8526.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8527.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8533.0599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8538.0599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8543.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8544.4766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8544.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8546.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8547.8566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8548.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8550.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8551.6166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8552.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8554.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8555.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8557.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8559.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8560.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8561.2766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8562.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8564.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8565.7766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8566.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8567.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8569.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8569.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8571.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8572.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8573.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8574.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8576.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8581.6933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8586.6933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8592.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8593.1099 | TurbineInstallation
| WTIV | Delay | 10 | 166666.6667 | ACTION | 8603.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8603.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8605.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8606.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8607.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8609.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8610.2499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8611.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8613.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8614.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8615.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8617.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8618.9099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8619.9099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8621.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8623.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8624.4099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8624.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8626.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8627.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8628.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8629.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8631.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8631.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8633.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8634.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8640.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8645.3266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8650.7433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8651.7433 | TurbineInstallation
| WTIV | Delay | 21 | 350000 | ACTION | 8672.7433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8673.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 44 | 733333.3333 | ACTION | 8717.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8719.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8720.1233 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8721.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8721.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8723.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8724.8833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8726.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8728.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8729.0233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8730.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8732.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8733.5433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8734.5433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8736.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8738.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8739.0433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8739.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8741.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8742.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8743.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8744.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8746.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8746.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8748.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8749.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8754.9599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8759.9599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8765.3766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8766.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8766.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8768.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8769.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8770.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8772.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8773.5166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8774.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8776.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8777.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8779.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8781.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8782.1766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8783.1766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8784.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8786.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8787.6766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8788.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8789.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8791.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8791.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8793.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8794.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8795.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8796.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8798.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8803.5933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 8846.8365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8848.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8850.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8852.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8854.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8856.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8857.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8858.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8859.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8861.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8863.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8865.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8867.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8869.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8869.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8870.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8871.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8873.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8875.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8877.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8879.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8881.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8882.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8882.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8883.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8885.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8887.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8889.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8891.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8893.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8894.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8895.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8895.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8897.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8899.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8901.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8903.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8905.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8906.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8907.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8908.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8910.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8912.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8914.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8916.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8918.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8918.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8919.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8920.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 8963.5797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8968.5797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8973.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8974.9964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8975.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8977.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8978.3764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8979.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8980.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8982.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8983.1364 | TurbineInstallation
| WTIV | Delay | 15 | 250000 | ACTION | 8998.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8999.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9001.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9002.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9003.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9005.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9006.7964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9007.7964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9009.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9011.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9012.2964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9012.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9014.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 116666.6667 | ACTION | 9021.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9022.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9023.2964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9024.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9026.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9026.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9028.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9029.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9035.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9040.2131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9045.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9046.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9047.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9049.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9050.0097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9050.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9052.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9053.7697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9054.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9056.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9057.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9059.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9061.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9062.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9063.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9064.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9066.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9067.9297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9068.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9069.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9071.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9071.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9073.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9074.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9075.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9076.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9078.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9083.8464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9088.8464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9094.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9095.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9095.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9097.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9098.6431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9099.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9101.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9102.4031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9103.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9105.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9106.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9108.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9110.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9111.0631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9112.0631 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9113.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9114.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9116.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9117.5631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9118.0631 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9119.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9120.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9122.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9122.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9124.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9125.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9126.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9127.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9129.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9134.4797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9139.4797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9144.8964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9145.8964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9146.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9148.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9149.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9150.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9152.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9153.0364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9154.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9156.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9157.1764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9158.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9160.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9161.6964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9162.6964 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9164.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9166.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9168.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9169.1964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9169.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9171.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9172.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9173.1964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9174.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9176.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9176.6964 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9180.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9182.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9183.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9189.1131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9194.1131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9199.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9200.5297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9200.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9202.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9203.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9204.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9206.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9207.6697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9208.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9210.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9211.8097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9213.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9215.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9216.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9217.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9218.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9220.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9221.8297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9222.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9223.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9225.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9225.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9227.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9228.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9229.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9230.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9232.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9237.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9242.7464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9248.1631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9249.1631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9249.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9251.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9252.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9253.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9255.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9256.3031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9257.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9259.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9260.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9261.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9263.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9264.9631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9265.9631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9267.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9269.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9270.4631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9270.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9272.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9273.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9274.4631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9275.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9277.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9277.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9279.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9280.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9286.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 9329.623 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9331.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9333.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9335.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9337.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9339.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9340.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9341.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9341.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9343.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9345.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9347.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9349.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9351.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9352.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9353.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9354.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9356.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9358.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9360.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9362.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9364.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9364.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9365.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9366.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9368.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9370.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9372.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9374.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9376.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9377.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9377.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9378.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9380.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9382.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9384.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9386.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9388.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9389.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9390.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9390.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9392.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9394.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9396.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9398.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9400.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9401.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9402.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9403.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 9446.3662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9451.3662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9456.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9457.7829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9458.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9460.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9461.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9461.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9463.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9464.9229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9466.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9468.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9469.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9470.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9472.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9473.5829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9474.5829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9476.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9478.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9479.0829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9479.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9481.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9482.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9483.0829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9484.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9486.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9486.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9488.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9489.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9494.9996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9499.9996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9505.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9506.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9506.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9508.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9509.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9510.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9512.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9513.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9514.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9516.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9517.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9519.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 216666.6667 | ACTION | 9532.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9534.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9535.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9536.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9537.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9539.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9540.7162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9541.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9542.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9544.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9544.7162 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9546.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9548.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9549.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9550.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9551.2162 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9553.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9554.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9556.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9561.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9566.6329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9572.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9573.0496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9573.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9575.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9576.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9577.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9579.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9580.1896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9581.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9583.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9584.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9585.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9587.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9588.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9589.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9591.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9593.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9594.3496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9594.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9596.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9597.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9598.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9599.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9601.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9601.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9603.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9604.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9610.2662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9615.2662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9620.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9621.6829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9622.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9624.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9625.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9625.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9627.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9628.8229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9629.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9631.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9632.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9634.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9636.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9637.4829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9638.4829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9639.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9641.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9642.9829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9643.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9644.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9646.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9646.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9648.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9649.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9650.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9651.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9653.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9658.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9663.8996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9669.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9670.3162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9670.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9674.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9676.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9677.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9678.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9680.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9681.4562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9682.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9684.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9685.5962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9687.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9689.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9690.1162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9691.1162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9692.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9694.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9695.6162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9696.1162 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9698.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9699.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9701.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9701.6162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9703.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9704.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9705.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9706.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9708.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9713.5329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9718.5329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9723.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9724.9496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9725.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9727.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9728.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9729.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9731.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9732.0896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9733.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9735.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9736.2296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9737.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9739.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9740.7496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9741.7496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9743.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9745.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9746.2496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9746.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9748.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9749.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9750.2496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9751.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9753.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9753.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9755.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9756.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9762.1662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 9805.4095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9807.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9809.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9811.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9813.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9815.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9816.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9816.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9817.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9819.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9821.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9823.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 9825.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 9827.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9828.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9829.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 9829.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 720720.7207 | ACTION | 9873.1527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9878.1527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9883.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9884.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9884.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9886.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9887.9494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9888.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9890.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9891.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9892.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9894.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9895.8494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9897.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9899.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9900.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9901.3694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9902.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9904.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9905.8694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9906.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9907.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 9909.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9911.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9911.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9913.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9914.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9915.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9916.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9918.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9923.786 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9928.786 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 9934.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9935.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9935.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9937.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9938.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9939.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9941.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9942.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9943.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9945.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 9946.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9948.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 9950.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 9951.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9952.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9953.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 9955.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9956.5027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9957.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9958.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9960.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9960.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9962.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9963.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 9964.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9965.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 9967.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 9972.4194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5