## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 83.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 83.2441 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 80.0008 | 833342.0226 | ACTION | 83.2441 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 133.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 138.6607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 139.6607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 149.6607 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 150.3838 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 150.3871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 151.3871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 152.5871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 162.5871 | MonopileInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 163.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 163.2441 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 163.5871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 164.5871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 168.5871 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 174.0037 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 203.0037 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 253.0037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 258.4204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 259.4204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 269.4204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 270.1435 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 270.1467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 271.1467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 272.3467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 282.3467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 283.3467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 284.3467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 288.3467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 293.7634 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 343.7634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 349.18 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 350.18 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 360.18 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 360.9031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 360.9064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 361.9064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 363.1064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 373.1064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 374.1064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 375.1064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 379.1064 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 384.523 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 434.523 | MonopileInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 439.523 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 444.9397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 445.9397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 453.9397 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 463.9397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 464.6628 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 464.666 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 465.666 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 466.866 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 476.866 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 393.6219 | 1968109.644 | ACTION | 476.866 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 476.8668 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 477.866 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 478.866 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 480.1101 | MonopileInstallation
| Feeder 1 | Queue | 316.866 | 1584330.0311 | ACTION | 480.1101 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 482.866 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 488.2827 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 492.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 500.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 512.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 520.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 532.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 538.2827 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 540.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 543.6993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 544.6993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 552.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 554.6993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 555.4224 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 555.4257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 556.4257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 557.6257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 560.1101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 563.3533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 563.3542 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 567.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 568.6257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 569.6257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 573.6257 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 579.0423 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 629.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 634.459 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 635.459 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 645.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 646.1821 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 646.1853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 647.1853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 648.3853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 658.3853 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 659.3853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 660.3853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 664.3853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 669.802 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 719.802 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 725.2186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 726.2186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 736.2186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 736.9417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 736.945 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 737.945 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 739.145 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 749.145 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 750.145 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 751.145 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 755.145 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 760.5616 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 810.5616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 815.9783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 816.9783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 826.9783 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 827.7014 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 827.7046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 828.7046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 829.9046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 839.9046 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 359.7945 | 1798972.5903 | ACTION | 839.9046 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 839.9054 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 840.9046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 841.9046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 843.1487 | MonopileInstallation
| Feeder 0 | Queue | 279.7945 | 1398972.5903 | ACTION | 843.1487 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 845.9046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 851.3213 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 855.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 863.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 875.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 883.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 885.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 34 | 354166.6667 | ACTION | 885.3213 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 897.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 905.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 917.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 925.1487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 928.3919 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 928.3928 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 935.3213 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 940.7379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 941.7379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 951.7379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 952.461 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 952.4643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 953.4643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 954.6643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 964.6643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 965.6643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 966.6643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 970.6643 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 976.0809 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1026.0809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1031.4976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1032.4976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1042.4976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1043.2206 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1043.2239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1044.2239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1045.4239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1055.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1056.4239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1057.4239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1061.4239 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1066.8406 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1116.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1122.2572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1123.2572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1133.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1133.9803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1133.9835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1134.9835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1136.1835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1146.1835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1147.1835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1148.1835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1152.1835 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1157.6002 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1207.6002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1213.0169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1214.0169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1224.0169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1224.7399 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1224.7432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1225.7432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1226.9432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1236.9432 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 393.7945 | 1968972.5903 | ACTION | 1236.9432 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1236.944 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1237.9432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1238.9432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1240.1873 | MonopileInstallation
| Feeder 1 | Queue | 311.7945 | 1558972.5903 | ACTION | 1240.1873 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1242.9432 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1248.3599 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1252.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1260.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1272.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1280.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1292.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1298.3599 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1300.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1303.7765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1304.7765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1312.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1314.7765 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1317.7765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1318.4996 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1318.5028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1319.5028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1320.1873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1320.7028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1323.4305 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1323.4314 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1330.7028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1331.7028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1332.7028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1336.7028 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1342.1195 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1392.1195 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1397.5362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1398.5362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1408.5362 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 1416.5362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1417.2592 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1417.2625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1418.2625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1419.4625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1429.4625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1430.4625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1431.4625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1435.4625 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1440.8792 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1490.8792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1496.2958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1497.2958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1507.2958 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1508.0189 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1508.0221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1509.0221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1510.2221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1520.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1521.2221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1522.2221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1526.2221 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1531.6388 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1581.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1587.0555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1588.0555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1598.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1598.7785 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1598.7818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1599.7818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1600.9818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1610.9818 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 370.7945 | 1853972.5903 | ACTION | 1610.9818 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1610.9826 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1611.9818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1612.9818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1614.2259 | MonopileInstallation
| Feeder 0 | Queue | 290.7945 | 1453972.5903 | ACTION | 1614.2259 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1616.9818 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1622.3985 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1626.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1634.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1646.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1654.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1666.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1672.3985 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1674.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1677.8151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1678.8151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1686.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1688.8151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1689.5382 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1689.5414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1690.5414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1691.7414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1694.2259 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1697.4691 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1697.4699 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1701.7414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1702.7414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1703.7414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1707.7414 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1713.1581 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1763.1581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1768.5748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1769.5748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1779.5748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1780.2978 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1780.3011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1781.3011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1782.5011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1792.5011 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1793.5011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1794.5011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1798.5011 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1803.9178 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1853.9178 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1859.3344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1860.3344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1870.3344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1871.0575 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1871.0607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1872.0607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1873.2607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1883.2607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1884.2607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1885.2607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1889.2607 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1894.6774 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1944.6774 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1950.0941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1951.0941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1961.0941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1961.8171 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1961.8204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1962.8204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1964.0204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1974.0204 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 359.7945 | 1798972.5903 | ACTION | 1974.0204 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1974.0212 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1975.0204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1976.0204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1977.2645 | MonopileInstallation
| Feeder 1 | Queue | 279.7945 | 1398972.5903 | ACTION | 1977.2645 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1980.0204 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1985.4371 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1989.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1997.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2009.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2017.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2029.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2035.4371 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2037.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2040.8537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2041.8537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2049.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2051.8537 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2052.5768 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2052.58 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2053.58 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2054.78 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2057.2645 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2060.5077 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2060.5085 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2064.78 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2065.78 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2066.78 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2070.78 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2076.1967 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2126.1967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2131.6134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2132.6134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2142.6134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2143.3364 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2143.3397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2144.3397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2145.5397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2155.5397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2156.5397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2157.5397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2161.5397 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2166.9564 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2216.9564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2222.373 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2223.373 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2233.373 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2234.0961 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2234.0993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2235.0993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2236.2993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2246.2993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2247.2993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2248.2993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2252.2993 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2257.716 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2307.716 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2313.1327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2314.1327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2324.1327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2324.8557 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2324.859 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2325.859 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2327.059 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2337.059 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 359.7945 | 1798972.5903 | ACTION | 2337.059 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2337.0598 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2338.059 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2339.059 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2340.3031 | MonopileInstallation
| Feeder 0 | Queue | 279.7945 | 1398972.5903 | ACTION | 2340.3031 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2343.059 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2348.4757 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2352.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2360.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2372.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2380.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2392.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2398.4757 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2400.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2403.8923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2404.8923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2412.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2414.8923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2415.6154 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2415.6186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2416.6186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2417.8186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2420.3031 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2423.5463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2423.5471 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2427.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2428.8186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2429.8186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2433.8186 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2439.2353 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2489.2353 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2494.652 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2495.652 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2505.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2506.375 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2506.3783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2507.3783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2508.5783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2518.5783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2519.5783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2520.5783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2524.5783 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2529.9949 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2579.9949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2585.4116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2586.4116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2596.4116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2597.1347 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2597.1379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2598.1379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2599.3379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2609.3379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2610.3379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2611.3379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2615.3379 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2620.7546 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2670.7546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2676.1713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2677.1713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2687.1713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2687.8943 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2687.8976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2688.8976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2690.0976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2700.0976 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 359.7945 | 1798972.5903 | ACTION | 2700.0976 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2700.0984 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2701.0976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2702.0976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2703.3417 | MonopileInstallation
| Feeder 1 | Queue | 279.7945 | 1398972.5903 | ACTION | 2703.3417 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2706.0976 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2711.5142 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2715.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2723.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2735.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 54 | 562500 | ACTION | 2765.5142 | MonopileInstallation
| Feeder 0 | Delay | 36 | 180000 | ACTION | 2771.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2779.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2791.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2799.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2811.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2815.5142 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2819.3417 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2820.9309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2821.9309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2822.5849 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2822.5857 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2831.9309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2832.654 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2832.6572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2833.6572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2834.8572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2844.8572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2845.8572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2846.8572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2850.8572 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2856.2739 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2906.2739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2911.6906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2912.6906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2922.6906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2923.4136 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2923.4169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2924.4169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2925.6169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2935.6169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2936.6169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2937.6169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2941.6169 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2947.0335 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2997.0335 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3002.4502 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3003.4502 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3013.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3014.1733 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 3033.1733 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3033.1765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3034.1765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3035.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3045.3765 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3046.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3047.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3048.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 3051.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3055.3765 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3060.7932 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3110.7932 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3116.2099 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3117.2099 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3127.2099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3127.9329 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3127.9362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3128.9362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3130.1362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3140.1362 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 436.7945 | 2183972.5903 | ACTION | 3140.1362 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3140.137 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3141.1362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3142.1362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3143.3803 | MonopileInstallation
| Feeder 0 | Queue | 320.7945 | 1603972.5903 | ACTION | 3143.3803 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3146.1362 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3151.5528 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3155.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3163.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3175.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3183.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3195.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3201.5528 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3203.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3206.9695 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3207.9695 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3215.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3217.9695 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3218.6926 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3218.6958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3219.6958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3220.8958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3223.3803 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3226.6235 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3226.6243 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3230.8958 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3231.8958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3232.8958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3236.8958 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3242.3125 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3292.3125 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3297.7292 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3298.7292 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3308.7292 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3309.4522 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3309.4555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3310.4555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3311.6555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3321.6555 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3322.6555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3323.6555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3327.6555 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3333.0721 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 3352.0721 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3402.0721 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3407.4888 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3408.4888 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3418.4888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3419.2119 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3419.2151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3420.2151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3421.4151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3431.4151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3432.4151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3433.4151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3435.4151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3439.4151 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3444.8318 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3494.8318 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3500.2485 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3501.2485 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3511.2485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3511.9715 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3511.9748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3512.9748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3514.1748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3524.1748 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 380.7945 | 1903972.5903 | ACTION | 3524.1748 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3524.1756 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3525.1748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3526.1748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3527.4188 | MonopileInstallation
| Feeder 1 | Queue | 300.7945 | 1503972.5903 | ACTION | 3527.4188 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3530.1748 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3535.5914 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3539.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3547.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3559.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3567.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3579.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3585.5914 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3587.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3591.0081 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3592.0081 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3599.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3602.0081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3602.7312 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3602.7344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3603.7344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3604.9344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3607.4188 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3610.6621 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3610.6629 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3614.9344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3615.9344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3616.9344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 14 | 145833.3333 | ACTION | 3630.9344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3634.9344 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3640.3511 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 63 | 656250 | ACTION | 3703.3511 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3753.3511 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3761.3511 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3766.7678 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3767.7678 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3777.7678 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3778.4908 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3778.4941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3779.4941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3780.6941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3790.6941 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3791.6941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3792.6941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3796.6941 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3802.1107 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 3834.1107 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3884.1107 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3889.5274 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3890.5274 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3900.5274 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3901.2505 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3901.2537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3902.2537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3903.4537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3913.4537 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3914.4537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3915.4537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3919.4537 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3924.8704 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3974.8704 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3980.287 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3981.287 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3991.287 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3992.0101 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3992.0134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3993.0134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3994.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4004.2134 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 476.7945 | 2383972.5903 | ACTION | 4004.2134 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4004.2142 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4005.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4006.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4007.4574 | MonopileInstallation
| Feeder 0 | Queue | 396.7945 | 1983972.5903 | ACTION | 4007.4574 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4013.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4017.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4019.2134 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4024.63 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 16 | 166666.6667 | ACTION | 4040.63 | MonopileInstallation
| Feeder 1 | Delay | 41 | 205000 | ACTION | 4048.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4060.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4068.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4080.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4088.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4090.63 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4096.0467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4097.0467 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4100.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4107.0467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4107.7698 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4107.773 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4108.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4108.773 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4109.973 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4119.973 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4120.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4120.973 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4121.973 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4125.973 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4128.4574 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4131.3897 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4131.7007 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4131.7015 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4181.3897 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4186.8063 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4187.8063 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4197.8063 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4198.5294 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4203.5294 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4203.5327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4204.5327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4205.7327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4215.7327 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4216.7327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4217.7327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4221.7327 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4227.1493 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4277.1493 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4278.1493 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4283.566 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4284.566 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4294.566 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4295.2891 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4295.2923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4296.2923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4297.4923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4307.4923 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4308.4923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 20 | 208333.3333 | ACTION | 4328.4923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4329.4923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4333.4923 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4338.909 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4388.909 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4394.3256 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 9 | 93750 | ACTION | 4403.3256 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4404.3256 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4414.3256 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4415.0487 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4415.052 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4416.052 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4417.252 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4427.252 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 419.7945 | 2098972.5903 | ACTION | 4427.252 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4427.2528 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4428.252 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4429.252 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4430.496 | MonopileInstallation
| Feeder 1 | Queue | 298.7945 | 1493972.5903 | ACTION | 4430.496 | MonopileInstallation | [14 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4433.252 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4438.6686 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4442.496 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4450.496 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4462.496 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4470.496 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4488.6686 | MonopileInstallation
| WTIV | Delay | 63 | 656250 | ACTION | 4551.6686 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4557.0853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4558.0853 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4568.0853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4568.8084 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4568.8116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4569.8116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4571.0116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4581.0116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4582.0116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4583.0116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 23 | 239583.3333 | ACTION | 4606.0116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4610.0116 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4615.4283 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 88 | 916666.6667 | ACTION | 4703.4283 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4753.4283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4758.8449 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4759.8449 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4769.8449 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4770.568 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4770.5713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4771.5713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4772.7713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4782.7713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4783.7713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4784.7713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4788.7713 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4794.1879 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 40 | 416666.6667 | ACTION | 4834.1879 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4884.1879 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4889.6046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4890.6046 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4900.6046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4901.3277 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4901.3309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4902.3309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4903.5309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4913.5309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4914.5309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4915.5309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4919.5309 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4924.9476 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4974.9476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4980.3642 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4981.3642 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4991.3642 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4992.3642 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4993.0873 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4993.0906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4994.0906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4995.2906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5005.2906 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 574.7945 | 2873972.5903 | ACTION | 5005.2906 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5005.2914 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5006.2906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5007.2906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5008.5346 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5011.2906 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5016.7072 | MonopileInstallation | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 5016.7072 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 5016.7072 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 5016.7072 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5018.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 5019.9505 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5020.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5022.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5024.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5026.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5027.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5028.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5028.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5030.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5032.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 4 | 20000 | ACTION | 5036.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5038.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5040.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5042.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5043.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5044.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5045.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5047.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5049.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5051.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5053.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5055.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5055.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5056.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5057.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 40.75 | 203750 | ACTION | 5057.4572 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5059.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 5060.7005 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 5060.7013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 40.7508 | 424487.8559 | ACTION | 5060.7013 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5061.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5063.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5065.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5067.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5068.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5068.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5069.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5071.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5073.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5075.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5077.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5079.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5080.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5081.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5081.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5083.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5085.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5087.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5089.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5091.9572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5092.7072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5093.4572 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5094.2072 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 5097.4505 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 5097.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 5110.7013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5116.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5117.118 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5117.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5119.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5120.498 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5121.258 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5123.258 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5124.258 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5125.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5127.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5128.398 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5129.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5131.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5132.918 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5133.918 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5135.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5137.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5138.418 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5138.918 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5140.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5141.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5142.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5143.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5145.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5145.918 | TurbineInstallation
| WTIV | Delay | 1264 | 13166666.6667 | ACTION | 6409.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6411.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6412.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6418.3346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6468.3346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6473.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6474.7513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6475.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6477.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6478.1313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6478.8913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6480.8913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6481.8913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6483.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6485.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6486.0313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6487.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6489.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6490.5513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6491.5513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6493.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6495.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6496.0513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6496.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6498.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6499.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6500.0513 | TurbineInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6517.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6518.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6520.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6520.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6522.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6523.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6528.968 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6578.968 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6584.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6585.3846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6585.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6587.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6588.7646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6589.5246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6591.5246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6592.5246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6593.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6595.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6596.6646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6598.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6600.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6601.1846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6602.1846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6603.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6605.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6606.6846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6607.1846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6608.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6610.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6610.6846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6612.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6613.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6614.1846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 1553.4833 | 7767416.6667 | ACTION | 6614.1846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 1516.7333 | 7583666.6667 | ACTION | 6614.1846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6614.1855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6615.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6617.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6617.4287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6619.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6621.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6622.6013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6623.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6625.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6627.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6628.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6628.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6629.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6631.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6633.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6635.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6637.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6639.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6640.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6641.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6641.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6643.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6645.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6647.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6649.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6651.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6652.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6653.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6654.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6657.422 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6657.4228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 43 | 447916.6667 | ACTION | 6665.6013 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6715.6013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6721.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6722.018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6722.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6724.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6725.398 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6726.158 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6728.158 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6729.158 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6730.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6732.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6733.298 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6734.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6736.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6737.818 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6738.818 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6740.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6742.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6743.318 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6743.818 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 6757.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6759.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6760.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6761.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6762.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6764.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6764.818 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6766.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6767.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6773.2346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 48 | 500000 | ACTION | 6821.2346 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6871.2346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6876.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6877.6513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6878.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6880.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6881.0313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6881.7913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6883.7913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6884.7913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6885.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6887.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6888.9313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6890.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6892.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6893.4513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6894.4513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6895.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6897.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6898.9513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6899.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6900.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6902.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6902.9513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6904.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6905.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6906.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6907.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 8 | 83333.3333 | ACTION | 6915.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6917.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6922.868 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 46 | 479166.6667 | ACTION | 6968.868 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7018.868 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7024.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7025.2846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7025.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7027.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7028.6646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7029.4246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7031.4246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7032.4246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7033.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7035.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7036.5646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7038.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7040.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7041.0846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7042.0846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7043.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7045.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7046.5846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7047.0846 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7050.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7051.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7053.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7055.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7055.5846 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7056.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7058.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 35 | 364583.3333 | ACTION | 7093.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7094.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7095.0846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 480.9 | 2404500 | ACTION | 7095.0846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 437.6618 | 2188309.2259 | ACTION | 7095.0846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7095.0855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7096.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7098.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7098.3287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7100.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7102.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7103.5013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7104.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7106.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7108.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7109.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7109.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7110.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7112.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7114.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7116.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7118.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7120.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7121.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7122.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7122.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7124.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7126.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7128.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7130.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7132.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7133.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7134.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7135.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7138.322 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7138.3228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7153.5013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7158.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7159.918 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7160.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7162.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7163.298 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7164.058 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7166.058 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7167.058 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7168.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7170.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7171.198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7172.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7174.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7175.718 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7176.718 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7178.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7180.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7181.218 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7181.718 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7183.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7184.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7185.218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7186.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7188.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7188.718 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7190.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7191.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7197.1346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 25 | 260416.6667 | ACTION | 7222.1346 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7272.1346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7277.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7278.5513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7278.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7280.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7281.9313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7282.6913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7284.6913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7285.6913 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 7299.6913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7300.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 6 | 62500 | ACTION | 7306.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7308.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7309.8313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7311.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7313.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7314.3513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7315.3513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7316.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7318.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7319.8513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7320.3513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7321.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7323.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7323.8513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7325.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7326.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7327.3513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7328.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7330.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7335.768 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7385.768 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7391.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7392.1846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7392.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7394.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7395.5646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7396.3246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7398.3246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7399.3246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7400.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7402.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7403.4646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7404.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 61 | 635416.6667 | ACTION | 7465.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7467.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7468.9846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7469.9846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7471.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7473.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7474.4846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7474.9846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7476.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7477.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7478.4846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7479.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7481.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7481.9846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 386.9 | 1934500 | ACTION | 7481.9846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 343.6618 | 1718309.2259 | ACTION | 7481.9846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7481.9855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7483.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7484.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7485.2287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7487.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7489.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7490.4013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7491.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7493.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7495.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7495.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7496.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7497.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7499.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7501.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7503.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7505.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7507.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7508.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7508.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7509.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7511.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7513.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7515.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7517.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7519.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7520.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7521.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7521.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 7 | 35000 | ACTION | 7528.9787 | TurbineInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 7532.222 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7532.2228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7540.4013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7545.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7546.818 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7549.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7550.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7552.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7553.198 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7553.958 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7555.958 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7556.958 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7558.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7560.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7561.098 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7562.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7564.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7565.618 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7566.618 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7568.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7570.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7571.118 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7571.618 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7573.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7574.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7575.118 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7576.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7578.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7578.618 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7580.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7582.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7583.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7589.0346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7639.0346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7644.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7645.4513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7645.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7647.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7648.8313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7649.5913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7651.5913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7652.5913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7653.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7655.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7656.7313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7658.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7660.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7661.2513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7662.2513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7663.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7665.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7666.7513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7667.2513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7668.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7670.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7670.7513 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 7674.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7676.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7677.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7678.2513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7679.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7681.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7686.668 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7736.668 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7742.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7743.0846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7743.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7745.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7746.4646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7747.2246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7749.2246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7750.2246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7751.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7753.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7754.3646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7755.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7757.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7758.8846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7759.8846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7761.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7763.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7764.3846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7764.8846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7766.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7767.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7768.3846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7769.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7771.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7771.8846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 289.9 | 1449500 | ACTION | 7771.8846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 239.6618 | 1198309.2259 | ACTION | 7771.8846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7771.8855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7773.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7774.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7775.1287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7777.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7779.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7780.3013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7781.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7783.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7785.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7785.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7786.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7787.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7789.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7791.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7793.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7795.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7797.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7798.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7798.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7799.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7801.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7803.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7805.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7807.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7809.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7810.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7811.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7811.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 7815.122 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7815.1228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7830.3013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7835.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7836.718 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7837.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7839.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7840.098 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7840.858 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7842.858 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7843.858 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7844.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7846.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7847.998 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7849.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7851.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7852.518 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7853.518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7855.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7857.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7858.018 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7858.518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7860.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7861.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7862.018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7863.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7865.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7865.518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7867.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7868.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7873.9346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7923.9346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7929.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7930.3513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7930.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7932.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7933.7313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7934.4913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7936.4913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7937.4913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7938.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7940.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7941.6313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7943.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7945.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7946.1513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7947.1513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7948.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7950.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7951.6513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7952.1513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7953.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7955.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7955.6513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7957.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7958.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7959.1513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7960.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7962.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7967.568 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8017.568 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8022.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8023.9846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8024.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8026.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8027.3646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8028.1246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8030.1246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8031.1246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8032.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8034.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8035.2646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8036.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8038.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8039.7846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8040.7846 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 8051.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8053.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8055.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8056.2846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8056.7846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8058.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8059.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8060.2846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8061.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8063.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8063.7846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 291.9 | 1459500 | ACTION | 8063.7846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 248.6618 | 1243309.2259 | ACTION | 8063.7846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8063.7855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8065.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8067.0287 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8067.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8068.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8069.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8071.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8073.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8074.2013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8075.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8077.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8077.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8078.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8079.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8081.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8083.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8085.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8087.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8089.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8090.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8090.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8091.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8093.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8095.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8097.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8099.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8101.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8102.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8103.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8103.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8107.022 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8107.0228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8124.2013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8129.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8130.618 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 8172.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8172.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8174.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8175.998 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8176.758 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8178.758 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8179.758 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8181.758 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8182.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8184.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8185.898 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8187.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8189.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8190.418 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8191.418 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8192.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8194.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8195.918 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8196.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8197.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8199.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8199.918 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8201.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8202.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8203.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8204.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8206.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8211.8346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8261.8346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8267.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8268.2513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8268.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8270.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8271.6313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8272.3913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8274.3913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8275.3913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8276.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8278.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8279.5313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8281.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8283.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8284.0513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8285.0513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8286.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8288.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8289.5513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8290.0513 | TurbineInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 8315.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8316.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8318.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8320.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8320.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8322.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8323.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8324.0513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8325.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8327.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8332.468 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 7 | 72916.6667 | ACTION | 8339.468 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8389.468 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8394.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8395.8846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8396.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8398.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8399.2646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8400.0246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8402.0246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8403.0246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8404.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8406.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8407.1646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8408.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8410.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8411.6846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8412.6846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8414.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8416.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8417.1846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8417.6846 | TurbineInstallation
| WTIV | Delay | 35 | 364583.3333 | ACTION | 8452.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8454.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8455.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8456.1846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8457.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8459.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8459.6846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 395.9 | 1979500 | ACTION | 8459.6846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 352.6618 | 1763309.2259 | ACTION | 8459.6846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Delay | 1 | 5000 | ACTION | 8460.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8460.6855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8461.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8462.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8463.9287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8465.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8467.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8468.1013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8469.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8471.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8473.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8474.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8475.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8476.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8478.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8480.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8482.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8484.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8486.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8486.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8487.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8488.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8490.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8492.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8494.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8496.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8498.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8499.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8499.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8500.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8503.922 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8503.9228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8518.1013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8523.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8524.518 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8524.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8526.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8527.898 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8528.658 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8530.658 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8531.658 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8532.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8534.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8535.798 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8537.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8539.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8540.318 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8541.318 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8542.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8543.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8545.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8546.818 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8547.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8548.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8550.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8550.818 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8552.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8553.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8554.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8555.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8557.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8562.7346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 36 | 375000 | ACTION | 8598.7346 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8648.7346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8654.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8655.1513 | TurbineInstallation
| WTIV | Delay | 18 | 187500 | ACTION | 8673.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8673.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8675.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8676.5313 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 8680.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8681.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 37 | 385416.6667 | ACTION | 8718.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8720.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8721.2913 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8722.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8723.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8725.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8726.4313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8727.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8729.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8730.9513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8731.9513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8733.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8735.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8736.4513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8736.9513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8738.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8739.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8740.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8741.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8743.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8743.9513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8745.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8746.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8752.368 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8802.368 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8807.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8808.7846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8809.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8811.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8812.1646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8812.9246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8814.9246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8815.9246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8817.0646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8819.0646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8820.0646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8821.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8823.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8824.5846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8825.5846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8827.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8829.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8830.0846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8830.5846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8832.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8833.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8834.0846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8835.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8837.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8837.5846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 377.9 | 1889500 | ACTION | 8837.5846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 333.6618 | 1668309.2259 | ACTION | 8837.5846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8837.5855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8839.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8840.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8840.8287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8842.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8844.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8846.0013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8846.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8848.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8850.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8851.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8852.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8853.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8855.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8857.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8859.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8861.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8863.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8863.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8864.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8865.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8867.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8869.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8871.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8873.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8875.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8876.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8876.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8877.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8880.822 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8880.8228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8896.0013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8901.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8902.418 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8902.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8904.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8905.798 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8906.558 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8908.558 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8909.558 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8910.698 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8912.698 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8913.698 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8915.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8917.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8918.218 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8919.218 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8920.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8922.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8923.718 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8924.218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8925.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8927.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8927.718 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8929.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8930.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8931.218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8932.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8934.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8939.6346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8989.6346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8995.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8996.0513 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 8999.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8999.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9001.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9002.4313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9003.1913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9005.1913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9006.1913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9007.3313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9009.3313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9010.3313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9011.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9013.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9014.8513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9015.8513 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 9021.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9023.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9025.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9026.3513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9026.8513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9028.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9029.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9030.3513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9031.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9033.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9033.8513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9035.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9036.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9042.268 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9092.268 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9097.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9098.6846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9099.0646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9101.0646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9102.0646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9102.8246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9104.8246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9105.8246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9106.9646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9108.9646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9109.9646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9111.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9113.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9115.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9116.4846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9117.4846 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9119.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9120.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9122.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9123.9846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9124.4846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9125.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9127.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9127.9846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9129.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9130.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9131.4846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 293.9 | 1469500 | ACTION | 9131.4846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 250.6618 | 1253309.2259 | ACTION | 9131.4846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9131.4855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9132.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9134.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9134.7287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9136.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9138.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9139.9013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9140.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9142.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9144.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9145.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9146.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9146.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9148.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9150.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9152.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9154.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9156.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9157.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9158.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9159.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9161.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9163.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9165.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9167.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9169.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9169.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9170.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9171.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9174.722 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9174.7228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9189.9013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9195.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9196.318 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9196.698 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9198.698 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9199.698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9200.458 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9202.458 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9203.458 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9204.598 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9206.598 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9207.598 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9209.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9211.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9212.118 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9213.118 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9214.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9216.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9217.618 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9218.118 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9219.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9221.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9221.618 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9223.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9224.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9225.118 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9226.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9228.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9233.5346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9283.5346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9288.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9289.9513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9290.3313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9292.3313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9293.3313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9294.0913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9296.0913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9297.0913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9298.2313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9300.2313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9301.2313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9302.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9304.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9305.7513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9306.7513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9308.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9310.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9311.2513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9311.7513 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 9319.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9321.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 8 | 83333.3333 | ACTION | 9329.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9330.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9331.2513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9332.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9334.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9334.7513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9336.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9337.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9343.168 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9393.168 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9398.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9399.5846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9399.9646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9401.9646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9402.9646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9403.7246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9405.7246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9406.7246 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9408.7246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9409.8646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9411.8646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9412.8646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9414.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9416.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9417.3846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9418.3846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9419.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9421.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9422.8846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9423.3846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9424.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9426.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9426.8846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9428.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9429.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9430.3846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 298.9 | 1494500 | ACTION | 9430.3846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 255.6618 | 1278309.2259 | ACTION | 9430.3846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9430.3855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9431.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9433.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9433.6287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9435.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9437.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9438.8013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9439.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9441.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9443.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9444.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9445.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9445.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9447.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9449.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9451.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9453.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9455.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9456.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9457.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9458.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9460.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9462.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9464.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9466.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9468.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9468.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9469.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9470.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9473.622 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9473.6228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9488.8013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9494.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9495.218 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9495.598 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9497.598 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9498.598 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9499.358 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9501.358 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9502.358 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9503.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9505.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9506.498 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9508.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9510.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9511.018 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9512.018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9513.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9515.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9516.518 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9517.018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9518.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9520.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9520.518 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 9533.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9535.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9536.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9537.018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9538.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9540.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9545.4346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9595.4346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9600.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9601.8513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9602.2313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9604.2313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9605.2313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9605.9913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9607.9913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9608.9913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9610.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9612.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9613.1313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9614.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9616.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9617.6513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9618.6513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9620.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9622.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9623.1513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9623.6513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9625.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9626.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9627.1513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9628.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9630.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9630.6513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9632.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9633.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9639.068 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9689.068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9694.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9695.4846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9695.8646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9697.8646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9699.8646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9700.8646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9701.6246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9703.6246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9704.6246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9705.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9707.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9708.7646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9710.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9712.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9713.2846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9714.2846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9715.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9717.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9718.7846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9719.2846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9720.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9721.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9723.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9723.7846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9725.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9726.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9727.2846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 296.9 | 1484500 | ACTION | 9727.2846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 253.6618 | 1268309.2259 | ACTION | 9727.2846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9727.2855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9728.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9730.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9730.5287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9732.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9734.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9735.7013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9736.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9738.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9740.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9741.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9742.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9742.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9744.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9746.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9748.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9750.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9752.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9753.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9754.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9755.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9757.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9759.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9761.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9763.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9765.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9765.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9766.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9767.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9770.522 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9770.5228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9785.7013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9791.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9792.118 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9792.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9794.498 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9795.498 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9796.258 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9798.258 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9799.258 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9800.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9802.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9803.398 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9804.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9806.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9807.918 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9808.918 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9810.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9812.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9813.418 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9813.918 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9815.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9816.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9817.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9818.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9820.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9820.918 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9822.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9823.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9829.3346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9879.3346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9884.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9885.7513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9886.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9888.1313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9889.1313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9889.8913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9891.8913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9892.8913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9894.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9896.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9897.0313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9898.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9900.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9901.5513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9902.5513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9904.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9906.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9907.0513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9907.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9909.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9910.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9911.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9912.0513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9913.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9915.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9915.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9917.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9918.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9923.968 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9973.968 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9979.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9980.3846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9980.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9982.7646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9983.7646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9984.5246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9986.5246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9987.5246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9988.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9990.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9991.6646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9993.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9995.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9996.1846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9997.1846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9998.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10000.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10001.6846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10002.1846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10003.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10005.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10005.6846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10007.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10008.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10009.1846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 281.9 | 1409500 | ACTION | 10009.1846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 238.6618 | 1193309.2259 | ACTION | 10009.1846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10009.1855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10010.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10012.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10012.4287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10014.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10016.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10017.6013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10018.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10020.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10022.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10023.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10023.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10024.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10026.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10028.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10030.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10032.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10034.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10035.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10036.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10036.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10038.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10040.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10042.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10044.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10046.9287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10047.6787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10048.4287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10049.1787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10052.422 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10052.4228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10067.6013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10073.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10074.018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10074.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10076.398 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10077.398 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10078.158 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10080.158 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10081.158 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10082.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10084.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10085.298 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10086.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10088.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10089.818 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10090.818 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10092.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10094.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10095.318 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10095.818 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10097.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10098.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10099.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10100.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10102.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10102.818 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10104.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10105.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10111.2346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10161.2346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10166.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10167.6513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10168.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10170.0313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10171.0313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10171.7913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10173.7913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10174.7913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10175.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10177.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10178.9313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10180.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10182.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10183.4513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10184.4513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10185.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10187.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10188.9513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10189.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10190.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10192.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10192.9513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10194.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10195.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10196.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10197.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10199.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10204.868 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10254.868 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10260.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10261.2846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10261.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10263.6646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10264.6646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10265.4246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10267.4246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10268.4246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10269.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10271.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10272.5646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10274.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10276.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10277.0846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10278.0846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10279.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10281.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10282.5846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10283.0846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10284.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10286.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10286.5846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10288.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10289.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10290.0846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 280.9 | 1404500 | ACTION | 10290.0846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 237.6618 | 1188309.2259 | ACTION | 10290.0846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10290.0855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10291.5846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10293.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10293.3287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10295.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10297.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10298.5013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10299.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10301.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10303.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10304.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10304.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10305.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10307.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10309.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10311.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10313.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10315.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10316.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10317.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10317.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10319.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10321.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10323.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10325.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10327.8287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10328.5787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10329.3287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10330.0787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10333.322 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10333.3228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10348.5013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10353.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10354.918 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10355.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10357.298 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10358.298 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10359.058 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10361.058 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10362.058 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10363.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10365.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10366.198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10367.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10369.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10370.718 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10371.718 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10373.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10375.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10376.218 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10376.718 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10378.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10379.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10380.218 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10381.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10383.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10383.718 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10385.218 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10386.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10392.1346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10442.1346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10447.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10448.5513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10448.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10450.9313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10451.9313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10452.6913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10454.6913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10455.6913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10456.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10458.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10459.8313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10461.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10463.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10464.3513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10465.3513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10466.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10468.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10469.8513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10470.3513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10471.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10473.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10473.8513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10475.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10476.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10477.3513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10478.8513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10480.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10485.768 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10535.768 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10541.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10542.1846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10542.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10544.5646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10545.5646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10546.3246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10548.3246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10549.3246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10550.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10552.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10553.4646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10554.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10556.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10557.9846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10558.9846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10560.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10562.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10563.4846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10563.9846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10565.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10566.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10567.4846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10568.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10570.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10570.9846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 280.9 | 1404500 | ACTION | 10570.9846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 237.6618 | 1188309.2259 | ACTION | 10570.9846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10570.9855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10572.4846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10573.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10574.2287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10576.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10578.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10579.4013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10580.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10582.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10584.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10584.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10585.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10586.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10588.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10590.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10592.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10594.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10596.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10597.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10597.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10598.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10600.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10602.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10604.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10606.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10608.7287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10609.4787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10610.2287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10610.9787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10614.222 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10614.2228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10629.4013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10634.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10635.818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10636.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10638.198 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10639.198 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10639.958 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10641.958 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10642.958 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10644.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10646.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10647.098 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10648.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10650.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10651.618 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10652.618 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 10654.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10656.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10658.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10659.118 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10659.618 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10661.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10662.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10663.118 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10664.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10666.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10666.618 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10668.118 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10669.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10675.0346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10725.0346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10730.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10731.4513 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 10733.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10733.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10735.8313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10736.8313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10737.5913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10739.5913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10740.5913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10741.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10743.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10744.7313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10746.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10748.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10749.2513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10750.2513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10751.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10753.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10754.7513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10755.2513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10756.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10758.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10758.7513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10760.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10761.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10762.2513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10763.7513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10765.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10770.668 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10820.668 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10826.0846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10827.0846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10827.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10829.4646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10830.4646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10831.2246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10833.2246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10834.2246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10835.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10837.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10838.3646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10839.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10841.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10842.8846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10843.8846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10845.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10847.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10848.3846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10848.8846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10850.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10851.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10852.3846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10853.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10855.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10855.8846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 284.9 | 1424500 | ACTION | 10855.8846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 241.6618 | 1208309.2259 | ACTION | 10855.8846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10855.8855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10857.3846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10858.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10859.1287 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10861.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10863.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10864.3013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10865.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10867.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10869.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10869.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10870.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10871.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10873.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10875.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10877.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10879.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10881.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10882.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10882.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10883.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10885.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10887.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10889.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10891.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10893.6287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10894.3787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10895.1287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10895.8787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 10899.122 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10899.1228 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10914.3013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10919.718 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10920.718 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10921.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10923.098 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10924.098 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10924.858 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10926.858 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10927.858 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10928.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10930.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10931.998 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10933.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10935.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10936.518 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10937.518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10939.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10941.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10942.018 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10942.518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10944.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10945.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10946.018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10947.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10949.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10949.518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10951.018 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10952.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10957.9346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11007.9346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11013.3513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11014.3513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11014.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11016.7313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11017.7313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11018.4913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11020.4913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11021.4913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11022.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11024.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11025.6313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11027.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11029.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11030.1513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11031.1513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11032.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11034.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11035.6513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11036.1513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11037.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11039.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11039.6513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11041.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11042.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11043.1513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11044.6513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11046.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11051.568 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11101.568 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11106.9846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11107.9846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11108.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11110.3646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11111.3646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11112.1246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11114.1246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11115.1246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11116.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11118.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11119.2646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11120.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11122.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11123.7846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11124.7846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11126.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11128.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11129.2846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11129.7846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11131.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11132.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11133.2846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11134.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11136.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11136.7846 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 280.9 | 1404500 | ACTION | 11136.7846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 237.6618 | 1188309.2259 | ACTION | 11136.7846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11136.7855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11138.2846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11139.7846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11140.0287 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11142.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11144.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11145.2013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11146.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11148.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11150.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11150.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11151.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11152.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11154.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11156.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11158.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11160.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11162.2787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11163.0287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11163.7787 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11164.5287 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11167.772 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11167.7728 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11195.2013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11200.618 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11201.618 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11201.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11203.998 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11204.998 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11205.758 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11207.758 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11208.758 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11209.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11211.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11212.898 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11214.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11216.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11217.418 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11218.418 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11219.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11221.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11222.918 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11223.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11224.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11226.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11226.918 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11228.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11229.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11230.418 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11231.918 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11233.418 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11238.8346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11288.8346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11294.2513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11295.2513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11295.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11297.6313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11298.6313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11299.3913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11301.3913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11302.3913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11303.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11305.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11306.5313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11308.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11310.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11311.0513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11312.0513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11313.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11315.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11316.5513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11317.0513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11318.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11320.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11320.5513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11322.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11323.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11324.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11325.0513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11326.5513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11328.0513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11333.468 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11383.468 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11388.8846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11389.8846 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11390.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11392.2646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11393.2646 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11394.0246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11396.0246 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11397.0246 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11398.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11400.1646 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11401.1646 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11402.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11404.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11405.6846 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11406.6846 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11408.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11410.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11411.1846 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11411.6846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11413.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11414.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11415.1846 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11416.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11418.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11418.6846 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 281.9 | 1409500 | ACTION | 11418.6846 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 250.9118 | 1254559.2259 | ACTION | 11418.6846 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11418.6855 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11420.1846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11421.6846 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11421.9287 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11427.1013 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11477.1013 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11482.518 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11483.518 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11483.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11485.898 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11486.898 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11487.658 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11489.658 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11490.658 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11491.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11493.798 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11494.798 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11496.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11498.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11499.318 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11500.318 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11501.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11503.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11504.818 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11505.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11506.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11508.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11508.818 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11510.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11511.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11512.318 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11513.818 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11515.318 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11520.7346 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11570.7346 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11576.1513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11577.1513 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11577.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11579.5313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11580.5313 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11581.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11583.2913 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11584.2913 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11585.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11587.4313 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11588.4313 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11589.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11591.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11592.9513 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11593.9513 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11595.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11597.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11598.4513 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11598.9513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11600.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11601.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11602.4513 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11603.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11605.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11605.9513 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 187.2667 | 936333.3333 | ACTION | 11605.9513 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11605.9521 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11607.4513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11608.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11609.1954 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 11650.9513 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11656.368 | TurbineInstallation | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 11659.6112 | TurbineInstallation