## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 92 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 100 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 112 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 120 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 123.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 128.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 133.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 134.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 144.6599 | MonopileInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 147.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 148.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 148.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 149.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 150.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 160.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 161.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 162.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 166.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 172.0029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 177.0029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 182.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 183.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 193.4196 | MonopileInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 196.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 197.1426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 208.1426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 208.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 209.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 214.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 215.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 225.3459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 226.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 227.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 231.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 236.7625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 241.7625 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 247.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 248.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 258.1792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 258.9023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 258.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 259.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 261.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 271.1055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 272.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 273.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 277.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 282.5222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 287.5222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 292.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 293.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 303.9389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 304.6619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 304.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 305.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 306.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 316.8652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 317.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 318.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 322.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 328.2818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 333.2818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 338.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 339.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 349.6985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 350.4216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 350.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 351.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 352.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 353.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 363.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 364.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 365.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 369.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 375.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 380.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 385.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 386.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 396.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 397.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 397.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 398.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 399.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 409.3845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 410.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 411.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 415.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 420.8011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 424.0444 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 436.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 439.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 447.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 453.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 465.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 473.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 485.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 493.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 505.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 513.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 525.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 533.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 545.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 553.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 556.2876 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 561.2876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 566.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 567.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 577.7043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 578.4274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 578.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 579.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 580.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 590.6306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 591.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 592.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 596.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 602.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 607.0473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 612.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 613.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 623.4639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 624.187 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 624.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 625.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 626.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 636.3903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 637.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 638.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 642.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 647.8069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 652.8069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 658.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 659.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 669.2236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 669.9467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 669.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 670.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 672.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 682.1499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 683.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 684.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 688.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 693.5666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 698.5666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 703.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 704.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 714.9832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 715.7063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 715.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 716.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 717.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 727.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 728.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 729.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 733.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 739.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 744.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 749.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 750.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 760.7429 | MonopileInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 766.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 767.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 767.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 768.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 769.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 779.6692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 780.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 781.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 785.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 791.0859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 796.0859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 801.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 802.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 812.5025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 813.2256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 813.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 814.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 815.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 825.4288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 826.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 827.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 831.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 836.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 840.0888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 852.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 860.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 872.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 880.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 885.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 897.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 905.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 917.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 925.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 937.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 945.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 957.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 965.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 968.332 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 973.332 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 978.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 979.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 989.7487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 990.4717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 990.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 991.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 992.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1002.675 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1003.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1004.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1008.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1014.0917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1019.0917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1024.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1025.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1035.5083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1036.2314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1036.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1037.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1038.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1048.4346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1049.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1050.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1054.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1059.8513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1064.8513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1070.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1071.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1081.268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1081.991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1081.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1082.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1084.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1094.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1095.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1096.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1100.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1105.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1110.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1116.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1117.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1127.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1127.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1127.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1128.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1129.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1139.9539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1140.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1141.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1145.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1151.3706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1156.3706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1161.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1162.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1172.7873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1173.5103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1173.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1174.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1175.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1185.7136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1186.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1187.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1191.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1197.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1202.1302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1207.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1208.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1218.5469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1219.27 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1219.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1220.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1221.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1231.4732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1232.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1233.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1237.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1242.8899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1246.1331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1258.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1266.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1278.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1286.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1298.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1306.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1318.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1326.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1338.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1346.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1358.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1366.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1369.3764 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1374.3764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1379.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1380.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1390.793 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1391.5161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1391.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1392.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1393.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1403.7194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1404.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1405.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 1416.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1420.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1426.136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1431.136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1436.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1437.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1447.5527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1448.2758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1448.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1449.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1450.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1460.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1461.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1462.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1466.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1471.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1476.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1482.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1483.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1493.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1494.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1494.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1495.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1496.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1506.2387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1507.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1508.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1512.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1517.6553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1522.6553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1528.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1529.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1539.072 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1539.7951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1539.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1540.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1541.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1551.9983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1552.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1553.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1557.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1563.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1568.415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1573.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1574.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1584.8316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1585.5547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1585.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1586.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1587.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1597.758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1598.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1599.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1603.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1609.1746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1614.1746 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1619.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1620.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1630.5913 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1631.3144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1631.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1632.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1633.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1643.5176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1644.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1645.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1649.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1654.9343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1658.1775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1670.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1678.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1690.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1698.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1710.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1718.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1730.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1738.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1750.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1758.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1770.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1778.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1781.4208 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1786.4208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1791.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1792.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1802.8374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1803.5605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1803.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1804.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1805.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1815.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1816.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1817.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1821.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1827.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1832.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1837.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1838.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1848.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1849.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1849.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1850.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1851.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1861.5234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1862.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1863.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1867.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1872.9401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1877.9401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1883.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1884.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1894.3567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1895.0798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1895.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1896.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1897.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1907.283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1908.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1909.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1913.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1918.6997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1923.6997 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1929.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1930.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1940.1164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1940.8394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1940.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1941.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1943.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1953.0427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1954.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1955.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1959.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 1964.4594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1969.4594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 1974.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1975.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 1985.876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1986.5991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1986.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1987.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 1988.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 1998.8023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1999.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2000.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2004.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2010.219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2015.219 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2020.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2021.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2031.6357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2032.3587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2032.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2033.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2034.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2044.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2045.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2046.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2050.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2055.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2059.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2071.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2079.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2091.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2099.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2111.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2119.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2131.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2139.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2151.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2159.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2171.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2179.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2182.4651 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2187.4651 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2192.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2193.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2203.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2204.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2204.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2205.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2206.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2216.8081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2217.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2218.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2222.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2228.2248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2233.2248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2238.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2239.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2249.6415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2250.3645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2250.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2251.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2252.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2262.5678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2263.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2264.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2268.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2273.9844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2278.9844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2284.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2285.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2295.4011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2296.1242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2296.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2297.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2298.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2308.3274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2309.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2310.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2314.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2319.7441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2324.7441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2330.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2331.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2341.1608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2341.8838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2341.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2342.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2344.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2354.0871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2355.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2356.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2360.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2365.5037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2370.5037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2375.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2376.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2386.9204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2387.6435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2387.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2388.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2389.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2399.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2400.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2401.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2405.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2411.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2416.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2421.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2422.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2432.6801 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2433.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2433.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2434.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2435.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2445.6064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2446.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2447.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2451.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2457.023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2460.2663 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2472.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2480.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2492.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2500.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2512.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2520.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2532.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2540.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2552.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2560.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2572.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2580.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2583.5095 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2588.5095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2593.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2594.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2604.9262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2605.6493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2605.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2606.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2607.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2617.8525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2618.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2619.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2623.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2629.2692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2634.2692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2639.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2640.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2650.6858 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2651.4089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2651.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2652.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2653.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2663.6122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2664.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2665.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2669.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2675.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2680.0288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2685.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2686.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2696.4455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2697.1686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2697.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2698.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2699.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2709.3718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2710.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2711.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2715.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2720.7885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2725.7885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2731.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2732.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 33 | 550000 | ACTION | 2765.2051 | MonopileInstallation
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2775.2051 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2777.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2777.9282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2777.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2778.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 2780.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2782.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2792.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2793.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2794.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2798.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2803.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2808.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2813.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2814.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2824.9648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2825.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2825.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2826.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2827.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2837.8911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2838.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2839.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2843.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2849.3078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2854.3078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 2859.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2860.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 2870.7244 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2871.4475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2871.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2872.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 2873.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 2883.6507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2884.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2885.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2889.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 2895.0674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2898.3107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2910.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2918.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2930.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2938.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2950.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2958.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2970.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2978.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2990.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2998.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3010.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 383333.3333 | ACTION | 3033.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3041.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3044.5539 | MonopileInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3046.5539 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3051.5539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3056.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3057.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3067.9706 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3068.6936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3068.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3069.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3070.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3080.8969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3081.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3082.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3086.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3092.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3097.3136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3102.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3103.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3113.7302 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3114.4533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3114.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3115.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3116.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3126.6565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3127.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3128.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3132.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3138.0732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3143.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3148.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3149.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3159.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3160.2129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3160.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3161.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3162.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3172.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3173.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3174.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3178.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3183.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3188.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3194.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3195.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3205.2495 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3205.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3205.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3206.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3208.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3218.1758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3219.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3220.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3224.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3229.5925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3234.5925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3240.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3241.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3251.0092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3251.7322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3251.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3252.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3253.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3263.9355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3264.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3265.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3269.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3275.3521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3280.3521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3285.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3286.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3296.7688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3297.4919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3297.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3298.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3299.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3309.6951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3310.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3311.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3315.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3321.1118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3324.355 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3336.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3352.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3360.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 3372.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 3380.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3383.5983 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3388.5983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3394.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3395.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3405.0149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3405.738 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3405.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3406.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3407.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3417.9413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3418.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3419.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3423.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3429.3579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3434.3579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3439.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 3440.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 166666.6667 | ACTION | 3450.7746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 3451.4977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 3451.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3452.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 20000 | ACTION | 3453.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 166666.6667 | ACTION | 3463.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 3464.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 3465.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 3469.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3475.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 3475.1176 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3477.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3479.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3481.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3483.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3485.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3485.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3486.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3487.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3489.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3491.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3493.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3495.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3497.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3498.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3498.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3499.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3501.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3503.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3505.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3507.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3509.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3510.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3511.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3511.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3513.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3515.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3517.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3519.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3521.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3522.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3523.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3524.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3526.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3528.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3530.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3532.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3534.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3534.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3535.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3536.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3538.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3540.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3542.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3544.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3546.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3547.1176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3547.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3548.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3551.8608 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3556.8608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3562.2775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3563.2775 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3563.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3565.6575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3566.6575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3567.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3569.4175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3570.4175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3571.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3573.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3574.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3576.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3578.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3579.0775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3580.0775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3581.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3583.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3584.5775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3585.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3586.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3588.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3588.5775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3590.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3591.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3592.0775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3593.5775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3595.0775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3600.4942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3605.4942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3610.9108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3611.9108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3612.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3614.2908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3615.2908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3616.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 183333.3333 | ACTION | 3627.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3629.0508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3630.0508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3631.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3633.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3634.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3635.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3637.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3638.7108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3639.7108 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3641.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3643.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3644.2108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3644.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3646.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3647.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3648.2108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3649.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3651.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3651.7108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3653.2108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3654.7108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3660.1275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3665.1275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3670.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3671.5442 | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 3702.5442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3702.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3704.9242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3705.9242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3706.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3708.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3709.6842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3710.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3712.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3713.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3715.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3717.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3718.3442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3719.3442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3720.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3722.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3723.8442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3724.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3725.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3727.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3727.8442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3729.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3730.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3731.3442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3732.8442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3734.3442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3739.7608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3744.7608 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3750.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3751.1775 | TurbineInstallation
| WTIV | Delay | 16 | 266666.6667 | ACTION | 3767.1775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3767.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3769.5575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3770.5575 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3771.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3773.3175 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3774.3175 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3775.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3777.4575 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3778.4575 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3779.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3781.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3782.9775 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3783.9775 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3785.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3787.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3788.4775 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3788.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3790.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3791.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3792.4775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3793.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3795.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3795.9775 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3797.4775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3798.9775 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3804.3942 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3809.3942 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3814.8108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3815.8108 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3816.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3818.1908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3819.1908 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3819.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3821.9508 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3822.9508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3824.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3826.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3827.0908 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3831.0908 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3832.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3833.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3835.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3836.6108 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3837.6108 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3839.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3841.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3843.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3844.1108 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3844.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3846.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3847.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3848.1108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3849.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3851.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3851.6108 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3853.1108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3854.6108 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3860.0275 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3865.0275 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3870.4442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3871.4442 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3871.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3873.8242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3874.8242 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3875.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3877.5842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3878.5842 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3879.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3881.7242 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 3882.7242 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3884.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 3886.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 3887.2442 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3888.2442 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3889.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 3891.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3892.7442 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3893.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3894.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3896.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3896.7442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3898.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3899.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 3900.2442 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3901.7442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 3903.2442 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 3908.6608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3911.9041 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3913.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3915.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3917.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3919.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3921.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3922.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3923.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3924.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3926.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3928.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3930.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3932.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3934.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3934.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3935.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3936.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3938.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3940.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3942.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3944.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3946.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3947.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3947.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3948.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3950.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3952.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3954.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3956.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3958.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3959.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3960.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3960.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3962.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3964.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3966.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3968.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3970.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3971.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3972.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3973.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3975.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3977.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3979.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 3981.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 3983.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3983.9041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3984.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 3985.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3988.6473 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3993.6473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 3999.064 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4000.064 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4000.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4002.444 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4003.444 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4004.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4006.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4007.204 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4009.204 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4010.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4012.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4014.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4015.344 | TurbineInstallation
| WTIV | Delay | 45 | 750000 | ACTION | 4060.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4061.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4063.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4064.864 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4065.864 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4067.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4069.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4070.364 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4070.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4072.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4073.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4074.364 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4075.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4077.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4077.864 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4079.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4082.364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4083.864 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4089.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4094.2806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4099.6973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4100.6973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4101.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4103.0773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4104.0773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4104.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4106.8373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4107.8373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4108.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4110.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4111.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4113.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4115.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4116.4973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4117.4973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4118.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4120.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4121.9973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4122.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4123.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4125.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4125.9973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4127.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4128.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4129.4973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4130.9973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4132.4973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4137.914 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4142.914 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4148.3306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4149.3306 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4149.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4151.7106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4152.7106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4153.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4155.4706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4156.4706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4157.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4159.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4160.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4162.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4164.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4165.1306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4166.1306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4167.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4169.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4170.6306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4171.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4172.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4174.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4174.6306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4176.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4177.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4178.1306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4179.6306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4181.1306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4186.5473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4191.5473 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4196.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4197.964 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4202.964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4203.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4205.344 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4206.344 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4207.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4209.104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4210.104 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4211.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4213.244 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4214.244 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4215.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4217.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4218.764 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4219.764 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4221.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4223.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4224.264 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4224.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4226.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4227.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4228.264 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4229.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4231.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4231.764 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4233.264 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4234.764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4240.1806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4245.1806 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4250.5973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4251.5973 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4251.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4253.9773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4254.9773 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4255.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4257.7373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4258.7373 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4259.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4261.8773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4262.8773 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4264.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4266.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4267.3973 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4268.3973 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4269.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4279.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4281.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4282.8973 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4283.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4284.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4286.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4286.8973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4288.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4289.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4290.3973 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4291.8973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4293.3973 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4298.814 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4303.814 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4309.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4310.2306 | TurbineInstallation
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4327.2306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4327.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4329.6106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4330.6106 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4331.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4333.3706 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4334.3706 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4335.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4337.5106 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4338.5106 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4340.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4342.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4343.0306 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4344.0306 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4345.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4347.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4348.5306 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4349.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4350.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4352.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4352.5306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4354.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4355.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4356.0306 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4357.5306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4359.0306 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4364.4473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4367.6906 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4369.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4371.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4373.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4375.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4377.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4378.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4379.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4381.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4383.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4385.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4387.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4389.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4390.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4391.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4392.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 166666.6667 | ACTION | 4402.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4404.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4406.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4408.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4410.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4412.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4412.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4413.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4414.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4416.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4418.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4420.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4422.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4424.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4425.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4425.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4426.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4428.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4430.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4432.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4434.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4436.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4437.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4438.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4438.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4440.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4442.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4444.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4446.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4448.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4449.6906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4450.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4451.1906 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4454.4338 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4459.4338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4464.8505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4465.8505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4466.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4468.2305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4469.2305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4469.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4471.9905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4472.9905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4474.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4476.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4477.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4478.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4480.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4481.6505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4482.6505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4484.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4486.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4487.1505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4487.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4489.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4551.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4552.1505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4553.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4555.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4555.6505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4557.1505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4558.6505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4564.0671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4569.0671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4574.4838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4575.4838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4575.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4577.8638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4578.8638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4579.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4581.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4582.6238 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4586.6238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4587.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 300000 | ACTION | 4605.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4607.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4608.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4610.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4612.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4613.2838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4614.2838 | TurbineInstallation
| WTIV | Delay | 84 | 1400000 | ACTION | 4698.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4699.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 50000 | ACTION | 4702.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4704.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4705.7838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4706.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4707.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4709.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4709.7838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4711.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4712.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4713.2838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4714.7838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4716.2838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4721.7005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4726.7005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4732.1171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4733.1171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4733.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4735.4971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4736.4971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4737.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4739.2571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4740.2571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4741.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4743.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4744.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4745.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4747.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4748.9171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4749.9171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4751.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4753.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4754.4171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4754.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4756.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4757.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4758.4171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4759.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4761.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4761.9171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4763.4171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4764.9171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4770.3338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4775.3338 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4780.7505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4781.7505 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4782.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4784.1305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4785.1305 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4785.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4787.8905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4788.8905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4790.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4792.0305 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4793.0305 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4794.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4796.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4797.5505 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4798.5505 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4800.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4802.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4803.0505 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4803.5505 | TurbineInstallation
| WTIV | Delay | 31 | 516666.6667 | ACTION | 4834.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4836.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4837.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4838.0505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4839.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4841.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4841.5505 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4843.0505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4844.5505 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4849.9671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4854.9671 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4860.3838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4861.3838 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4861.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4863.7638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4864.7638 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4865.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4867.5238 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4868.5238 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4869.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4871.6638 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4872.6638 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4874.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4876.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4877.1838 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4878.1838 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4879.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4881.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4882.6838 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4883.1838 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 4888.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4889.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4891.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4891.6838 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4893.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4894.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4895.1838 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 4896.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4897.6838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4899.1838 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4904.6005 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4909.6005 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 4915.0171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4916.0171 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4916.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4918.3971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4919.3971 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4920.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4922.1571 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4923.1571 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4924.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4926.2971 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 4927.2971 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4928.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 4930.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 4931.8171 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4932.8171 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4934.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 4936.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4937.3171 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4937.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4939.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4940.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4941.3171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4942.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4944.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 4944.8171 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4946.3171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 4947.8171 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 4953.2338 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4956.477 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4958.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4960.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4962.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4964.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4966.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4967.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4967.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4968.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4970.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4972.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4974.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4976.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4978.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4979.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4980.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4980.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4982.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4984.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4986.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4988.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 4990.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4991.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4992.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 4993.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4995.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4997.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 4999.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5001.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5003.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5003.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5004.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5005.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5007.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5009.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5011.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5013.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5015.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5016.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5016.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5017.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5019.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5021.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5023.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 5025.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 5027.727 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5028.477 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5029.227 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 5029.977 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 5033.2203 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5038.2203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5043.6369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5044.6369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5045.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5047.0169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5048.0169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5048.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5050.7769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5051.7769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5052.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5054.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5055.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5057.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5059.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5060.4369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5061.4369 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 5065.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5066.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5068.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5069.9369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5070.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5071.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5073.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5073.9369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5075.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5076.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5077.4369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5078.9369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5080.4369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5085.8536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5090.8536 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5096.2703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5097.2703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5097.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5099.6503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5100.6503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5101.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5103.4103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5104.4103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5105.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5107.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5108.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5110.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 5112.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 5113.0703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5114.0703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5115.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 5117.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5118.5703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5119.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5120.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5122.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5122.5703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5124.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5125.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 5126.0703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5127.5703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 5129.0703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 5134.4869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5139.4869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 5144.9036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 5145.9036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5146.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1263 | 21050000 | ACTION | 6409.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6411.2836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6412.2836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6413.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6415.0436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6416.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6417.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6419.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6420.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6421.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6423.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6424.7036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6425.7036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6427.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6429.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6430.2036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6430.7036 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6431.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6433.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6434.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6435.2036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6436.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6438.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6438.7036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6440.2036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6441.7036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6447.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6452.1203 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6457.5369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6458.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6458.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6460.9169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6461.9169 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6462.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6464.6769 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6465.6769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6466.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6468.8169 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6469.8169 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6471.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6473.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6474.3369 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6475.3369 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6476.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6478.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6479.8369 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6480.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6481.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6483.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6483.8369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6485.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6486.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6487.3369 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6488.8369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6490.3369 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6495.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6500.7536 | TurbineInstallation
| WTIV | Delay | 12 | 200000 | ACTION | 6512.7536 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6518.1703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6519.1703 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6519.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6521.5503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6522.5503 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6523.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6525.3103 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6526.3103 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6527.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6529.4503 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6530.4503 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6531.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6533.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6534.9703 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6535.9703 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6537.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6539.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6540.4703 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6540.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6542.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6543.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6544.4703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6545.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6547.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6547.9703 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6549.4703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6550.9703 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6556.3869 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6561.3869 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6566.8036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6567.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6568.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6570.1836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6571.1836 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6571.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6573.9436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6574.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6576.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6578.0836 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6579.0836 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6580.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6582.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6583.6036 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6584.6036 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6586.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6588.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6589.1036 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6589.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6591.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6592.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6593.1036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6594.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6596.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6596.6036 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6598.1036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6599.6036 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6605.0203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6608.2635 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6610.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6612.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6614.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6616.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6618.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6619.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6619.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6620.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6622.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6624.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6626.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6628.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6630.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6631.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6632.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6632.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6634.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6636.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6638.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6640.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6642.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6643.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6644.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6645.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6647.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6649.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6651.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6653.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6655.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6655.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6656.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6657.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6659.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6661.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6663.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6664.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6666.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6668.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6669.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6669.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6670.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6672.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6674.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6676.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 6678.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 6680.5135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6681.2635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6682.0135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 6682.7635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6686.0068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6691.0068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6696.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6697.4234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6697.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6699.8034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6700.8034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6701.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6703.5634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6704.5634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6705.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6707.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6708.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6710.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6712.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6713.2234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6714.2234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6715.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6717.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6718.7234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6719.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6720.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6722.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6722.7234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6724.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6725.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6726.2234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6727.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6729.2234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6734.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6739.6401 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6745.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6751.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6752.0568 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 6758.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6758.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6760.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6761.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6762.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6764.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6765.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6766.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6768.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6769.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6770.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6772.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6773.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6774.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6776.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6778.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6779.3568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6779.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6781.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6782.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6783.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6784.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6786.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6786.8568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6788.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6789.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6795.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6800.2734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6805.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6806.6901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6807.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6809.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6810.0701 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6824.0701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6824.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6826.8301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6827.8301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6828.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6830.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6831.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6833.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6835.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6836.4901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6837.4901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6838.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6840.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6841.9901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6842.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6843.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6845.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6845.9901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6847.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6848.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6849.4901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6850.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6852.4901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6857.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6862.9068 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6868.3234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6869.3234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6869.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6871.7034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6872.7034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6873.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6875.4634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6876.4634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6877.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6879.6034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6880.6034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6882.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6884.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6885.1234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6886.1234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6887.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6889.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6890.6234 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6891.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6892.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6894.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6894.6234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6896.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6897.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6898.1234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6899.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6901.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 6906.5401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 6911.5401 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6916.5401 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 6921.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6922.9568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6923.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6925.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6926.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6927.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6929.0968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6930.0968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6931.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6933.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 6934.2368 | TurbineInstallation
| WTIV | Delay | 41 | 683333.3333 | ACTION | 6975.2368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6976.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 6978.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 6979.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6980.7568 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 6983.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6985.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 6987.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6988.2568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6988.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6990.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6991.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6992.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6993.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6995.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 6995.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6997.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 6998.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7004.1734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7009.1734 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7014.5901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7015.5901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7015.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7017.9701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7018.9701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7019.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7021.7301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7022.7301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7023.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7025.8701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7026.8701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7028.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7030.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7031.3901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7032.3901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7033.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7035.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7036.8901 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7037.3901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7038.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7040.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7040.8901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7042.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7043.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7044.3901 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7049.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7050.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 33333.3333 | ACTION | 7052.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7054.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7059.3901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7064.8068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 1 | 16666.6667 | ACTION | 7065.8068 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7066.8068 | TurbineInstallation
| WTIV | Transit | 2.2432 | 37387.3874 | ACTION | 7069.05 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7071.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7073.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7075.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7077.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7079.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7079.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7080.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7081.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7083.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7085.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7087.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7089.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7091.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7092.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7092.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7093.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7095.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7097.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7099.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7101.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7103.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7104.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7105.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7105.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7107.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7109.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7111.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7113.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7115.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7116.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7117.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7118.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7120.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7122.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7124.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7126.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7128.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7128.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7129.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7130.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7132.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7134.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7136.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7138.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7140.3 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7141.05 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7141.8 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7142.55 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7145.7933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7150.7933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7156.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7157.2099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7157.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7159.5899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7160.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7161.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7163.3499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7164.3499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7165.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7167.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7168.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7170.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7172.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7173.0099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7174.0099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7175.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7177.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7178.5099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7179.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7180.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7182.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7182.5099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7184.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7185.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7186.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7187.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7189.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7194.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7199.4266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7204.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7205.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7206.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7208.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7209.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7209.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7211.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7212.9833 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 7221.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7223.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 100000 | ACTION | 7229.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7231.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7232.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7233.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7235.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7236.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7237.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7239.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7241.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7242.1433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7242.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7244.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7245.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7246.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7247.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7249.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7249.6433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7251.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7252.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7258.0599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7263.0599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7268.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7269.4766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7269.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7271.8566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7272.8566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7273.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7275.6166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7276.6166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7277.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7279.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7280.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7282.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 266666.6667 | ACTION | 7298.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7300.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7301.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7302.2766 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 7306.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7307.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7309.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7310.7766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7311.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7312.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7314.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7314.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7316.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7317.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7318.2766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7319.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7321.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7326.6933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7331.6933 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7337.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7338.1099 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7339.1099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7339.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 150000 | ACTION | 7348.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7350.4899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7351.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7352.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7354.2499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7355.2499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7356.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7358.3899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7359.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7360.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7362.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7363.9099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7364.9099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7366.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7368.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7369.4099 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7369.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7371.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7372.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7373.4099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7374.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7376.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7376.9099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7378.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7379.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7385.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7390.3266 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7395.7433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7396.7433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7397.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7399.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7400.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7400.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7402.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7403.8833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7405.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 7466.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7468.0233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7469.0233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7470.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7472.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7473.5433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7474.5433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7476.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7478.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7479.0433 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7479.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7481.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7482.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7483.0433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7484.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7486.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7486.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7488.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7489.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7494.9599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7499.9599 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7505.3766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7506.3766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7506.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7508.7566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7509.7566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7510.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7512.5166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7513.5166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7514.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7516.6566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7517.6566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7519.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7521.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7522.1766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7523.1766 | TurbineInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 7549.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7550.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7552.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7553.6766 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7554.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7555.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7557.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7557.6766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7559.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7560.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7561.1766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7562.6766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7564.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7569.5933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7572.8365 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7574.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7576.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7578.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7580.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7582.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7583.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7584.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7585.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7587.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7589.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7591.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7593.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7595.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7595.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7596.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7597.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7599.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7601.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7603.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7605.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7607.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7608.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7608.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7609.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7611.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7613.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7615.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7617.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7619.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7620.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7621.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7621.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7623.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7625.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7627.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7629.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7631.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7632.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7633.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7634.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7636.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7638.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7640.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7642.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7644.0865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7644.8365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7645.5865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7646.3365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7649.5797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7654.5797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7659.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7660.9964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7661.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7663.3764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7664.3764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7665.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7667.1364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7668.1364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7669.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 7674.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7676.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7677.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7678.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7680.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7681.7964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7682.7964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7684.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7686.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7687.2964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7687.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7689.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7690.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7691.2964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7692.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7694.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7694.7964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7696.2964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7697.7964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7703.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7708.2131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7713.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7714.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7715.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7717.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7718.0097 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7725.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7725.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7727.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7728.7697 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 7731.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7732.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7734.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7735.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7737.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7739.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7740.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7741.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7742.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7744.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7745.9297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7746.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7747.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7749.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7749.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7751.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7752.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7753.4297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7754.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7756.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7761.8464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7766.8464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7772.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7773.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7773.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7775.6431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7776.6431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7777.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7779.4031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7780.4031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7781.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7783.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7784.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7786.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7788.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7789.0631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7790.0631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7791.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7793.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7794.5631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7795.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7796.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7798.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7798.5631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7800.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7801.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7802.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7803.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7805.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7810.4797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7815.4797 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7820.8964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7821.8964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7822.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7824.2764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7825.2764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7826.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7828.0364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7829.0364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7830.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7832.1764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7833.1764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7834.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7836.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7837.6964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7838.6964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7840.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7842.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7843.1964 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7843.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7845.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7846.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7847.1964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7848.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7850.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7850.6964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7852.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7853.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7859.1131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7864.1131 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7869.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7870.5297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7870.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7872.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7873.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7874.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7876.6697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7877.6697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7878.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7880.8097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7881.8097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7883.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7885.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7886.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7887.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7888.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7890.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7891.8297 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7892.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7893.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7895.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7895.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7897.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7898.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7899.3297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7900.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7902.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7907.7464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7912.7464 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 7918.1631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7919.1631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7919.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7921.5431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7922.5431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7923.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7925.3031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7926.3031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7927.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7929.4431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 7930.4431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7931.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 7933.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 7934.9631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7935.9631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7937.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 7939.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7940.4631 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7940.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7942.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7943.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7944.4631 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 7945.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7946.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7948.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 7948.9631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7950.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 7951.9631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 7957.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7960.623 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7962.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7964.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7966.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7968.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7970.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7971.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7972.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7972.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7974.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7976.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7978.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7980.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7982.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7983.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7984.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7985.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7987.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7989.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7991.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7993.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 7995.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7995.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7996.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 7997.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 7999.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8001.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8003.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8005.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8007.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8008.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8008.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8009.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8011.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8013.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8015.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8017.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8019.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8020.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8021.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8021.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8023.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8025.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8027.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8029.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8031.873 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8032.623 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8033.373 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8034.123 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8037.3662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8042.3662 | TurbineInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 8051.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8056.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8057.7829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8058.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8060.1629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8061.1629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8061.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8063.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8064.9229 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8066.9229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8068.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8073.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8075.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8076.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8077.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8079.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8080.5829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8081.5829 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 8085.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8087.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8089.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8090.0829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8090.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8092.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8093.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8094.0829 | TurbineInstallation
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8095.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8096.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8098.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8098.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8100.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8101.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8106.9996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8111.9996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8117.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8118.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8118.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8120.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8121.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8122.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8124.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8125.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8126.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8128.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8129.6962 | TurbineInstallation
| WTIV | Delay | 42 | 700000 | ACTION | 8171.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8173.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8175.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8176.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8177.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8178.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8180.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8181.7162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8182.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8183.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8185.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8185.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8187.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8188.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8189.2162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8190.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8192.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8197.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8202.6329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8208.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8209.0496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8209.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8211.4296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8212.4296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8213.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8215.1896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8216.1896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8217.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8219.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8220.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8221.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8223.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8224.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8225.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8227.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8229.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8230.3496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8230.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8232.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8233.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8234.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8235.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8237.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8237.8496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8239.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8240.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8246.2662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8251.2662 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8256.6829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8257.6829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8258.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8260.0629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8261.0629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8261.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8263.8229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8264.8229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8265.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8267.9629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8268.9629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8270.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8272.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8273.4829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8274.4829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8275.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8277.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8278.9829 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8279.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8280.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8282.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8282.9829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8284.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8285.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8286.4829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8287.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 27 | 450000 | ACTION | 8314.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8316.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 16666.6667 | ACTION | 8317.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8322.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8327.8996 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8333.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8334.3162 | TurbineInstallation
| WTIV | Delay | 7 | 116666.6667 | ACTION | 8341.3162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8341.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8343.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8344.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8345.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8347.4562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8348.4562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8349.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8351.5962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8352.5962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8354.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8356.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8357.1162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8358.1162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8359.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8361.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8362.6162 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8363.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8364.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8366.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8366.6162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8368.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8369.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8370.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8371.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8373.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8378.5329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8383.5329 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8388.9496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8389.9496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8390.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8392.3296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8393.3296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8394.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8396.0896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8397.0896 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8398.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8400.2296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8401.2296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8402.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8404.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8405.7496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8406.7496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8408.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8410.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8411.2496 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8411.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8413.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8414.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8415.2496 | TurbineInstallation
| WTIV | Delay | 36 | 600000 | ACTION | 8451.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8452.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8454.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8454.7496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8456.2496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8457.7496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8463.1662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8466.4095 | TurbineInstallation
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8468.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8470.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8472.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8474.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8476.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8477.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8477.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8478.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8480.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8482.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8484.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Tower Section | 2 | 33333.3333 | ACTION | 8486.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Nacelle | 2 | 33333.3333 | ACTION | 8488.6595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8489.4095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8490.1595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Blade | 0.75 | 12500 | ACTION | 8490.9095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8494.1527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8499.1527 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8504.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8505.5694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8505.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8507.9494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8508.9494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8509.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8511.7094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8512.7094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8513.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8515.8494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8516.8494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8518.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8520.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8521.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8522.3694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8523.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8525.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8526.8694 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8527.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8528.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8530.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8530.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8532.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8533.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8534.3694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8535.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8537.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8542.786 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8547.786 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 90277.7778 | ACTION | 8553.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8554.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8554.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8556.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8557.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8558.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8560.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8561.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8562.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8564.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 16666.6667 | ACTION | 8565.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8567.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 33333.3333 | ACTION | 8569.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 16666.6667 | ACTION | 8570.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8571.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8572.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 33333.3333 | ACTION | 8574.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8575.5027 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8576.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8577.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8579.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8579.5027 | TurbineInstallation
| WTIV | Delay | 23 | 383333.3333 | ACTION | 8602.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8604.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8605.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 8333.3333 | ACTION | 8606.0027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8607.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 25000 | ACTION | 8609.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 90277.7778 | ACTION | 8614.4194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5