## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 92 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 100 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 112 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 120 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 163.2432 | MonopileInstallation
| WTIV | Delay | 40 | 416666.6667 | ACTION | 203.2432 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 253.2432 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 258.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 259.6599 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 269.6599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 270.383 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 270.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 271.3862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 272.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 282.5862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 283.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 284.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 288.5862 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 294.0029 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 344.0029 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 349.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 350.4196 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 360.4196 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 361.1426 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 361.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 362.1459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 363.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 373.3459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 374.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 375.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 379.3459 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 384.7625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 434.7625 | MonopileInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 439.7625 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 445.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 446.1792 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 453.1792 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 463.1792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 463.9023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 463.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 464.9055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 466.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 476.1055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 477.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 478.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 482.1055 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 487.5222 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 537.5222 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 542.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 543.9389 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 553.9389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 554.6619 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 554.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 555.6652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 556.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 566.8652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 567.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 568.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 572.8652 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 578.2818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 628.2818 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 633.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 634.6985 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 644.6985 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 645.4216 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 645.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 646.4248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 647.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 657.6248 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 658.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 659.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 663.6248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 669.0415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 719.0415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 724.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 725.4582 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 735.4582 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 736.1812 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 736.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 737.1845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 738.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 748.3845 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 749.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 750.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 754.3845 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 759.8011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 803.0444 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 815.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 823.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 835.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 843.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 855.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 863.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 875.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 883.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 885.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 897.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 905.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 917.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 925.0444 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 968.2876 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1018.2876 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1023.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1024.7043 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1034.7043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1035.4274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1035.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1036.4306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1037.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1047.6306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1048.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1049.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1053.6306 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1059.0473 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1109.0473 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1114.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1115.4639 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1125.4639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1126.187 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1126.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1127.1903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1128.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1138.3903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1139.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1140.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1144.3903 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1149.8069 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1199.8069 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1205.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1206.2236 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1216.2236 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1216.9467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1216.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1217.9499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1219.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1229.1499 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1230.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1231.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1235.1499 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1240.5666 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1290.5666 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1295.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1296.9832 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1306.9832 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1307.7063 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1307.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1308.7096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1309.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1319.9096 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1320.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1321.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1325.9096 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1331.3262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1381.3262 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1386.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1387.7429 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1397.7429 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1398.466 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1398.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1399.4692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1400.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1410.6692 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1411.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1416.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1417.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1421.6692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1427.0859 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1477.0859 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1482.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1483.5025 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1493.5025 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1494.2256 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1494.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1495.2288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1496.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1506.4288 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1507.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1508.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1512.4288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1517.8455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1561.0888 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1573.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1581.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1593.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1601.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1613.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1621.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1633.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1641.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1653.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1661.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1673.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1681.0888 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1724.332 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1774.332 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1779.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1780.7487 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1790.7487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1791.4717 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1791.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1792.475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1793.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1803.675 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1804.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1805.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1809.675 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1815.0917 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1865.0917 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1870.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1871.5083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1881.5083 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1882.2314 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1882.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1883.2346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1884.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1894.4346 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1895.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1896.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1900.4346 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1905.8513 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 1955.8513 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1961.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1962.268 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1972.268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1972.991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1972.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1973.9943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1975.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1985.1943 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1986.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1987.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1991.1943 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1996.6109 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2046.6109 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2052.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2053.0276 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2063.0276 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2063.7507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2063.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2064.7539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2065.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2075.9539 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2076.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2077.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2081.9539 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2087.3706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2137.3706 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2142.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2143.7873 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2153.7873 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2154.5103 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2154.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2155.5136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2156.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2166.7136 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2167.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2168.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2172.7136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2178.1302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2228.1302 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2233.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2234.5469 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2244.5469 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2245.27 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2245.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2246.2732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2247.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2257.4732 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2258.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2259.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2263.4732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2268.8899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2312.1331 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2324.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2332.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2344.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2352.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2364.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2372.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2384.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2392.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2404.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2412.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2424.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2432.1331 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2475.3764 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2525.3764 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2530.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2531.793 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2541.793 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2542.5161 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2542.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2543.5194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2544.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2554.7194 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2555.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2556.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2560.7194 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2566.136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2616.136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2621.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2622.5527 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2632.5527 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2633.2758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2633.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2634.279 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2635.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2645.479 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2646.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2647.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2651.479 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2656.8957 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2706.8957 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2712.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2713.3123 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2723.3123 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2724.0354 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2724.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2725.0387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2726.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2736.2387 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2737.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 2750.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2751.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 2780.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2784.2387 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2789.6553 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2839.6553 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2845.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2846.072 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2856.072 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2856.7951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2856.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2857.7983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2858.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2868.9983 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2869.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2870.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2874.9983 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2880.415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 2930.415 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2935.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2936.8316 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2946.8316 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2947.5547 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2947.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2948.558 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2949.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2959.758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2960.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2961.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2965.758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2971.1746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 75 | 781250 | ACTION | 3046.1746 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3096.1746 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3101.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3102.5913 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3112.5913 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3113.3144 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3113.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3114.3176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3115.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3125.5176 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3126.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3127.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3131.5176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3136.9343 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3180.1775 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3192.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3200.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3212.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3220.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3232.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3240.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3252.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3260.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3272.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3280.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3292.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3300.1775 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43 | 447916.6667 | ACTION | 3343.1775 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 3352.1775 | MonopileInstallation
| WTIV | Transit | 0.24324 | 2533.7838 | ACTION | 3352.4208 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3402.4208 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3407.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3408.8374 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3418.8374 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3419.5605 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3419.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3420.5637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3421.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3431.7637 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3432.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3433.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3435.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3439.7637 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3445.1804 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3495.1804 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3500.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3501.5971 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3511.5971 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3512.3201 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3512.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3513.3234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3514.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3524.5234 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3525.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3526.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3530.5234 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3535.9401 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3585.9401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3591.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3592.3567 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3602.3567 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3603.0798 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3603.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3604.083 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3605.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3615.283 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3616.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3617.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 3630.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3634.283 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3639.6997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 64 | 666666.6667 | ACTION | 3703.6997 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3753.6997 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3761.6997 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3767.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3768.1164 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3778.1164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3778.8394 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3778.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3779.8427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3781.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3791.0427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3792.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3793.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3797.0427 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3802.4594 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 32 | 333333.3333 | ACTION | 3834.4594 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3884.4594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3889.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3890.876 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3900.876 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3901.5991 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3901.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3902.6023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3903.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3913.8023 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3914.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3915.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3919.8023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3925.219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 3975.219 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3980.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3981.6357 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3991.6357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3992.3587 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3992.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3993.362 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3994.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4004.562 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4005.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4006.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4013.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4017.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4019.562 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4024.9787 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 2 | 20833.3333 | ACTION | 4026.9787 | MonopileInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 4040.9787 | MonopileInstallation
| WTIV | Transit | 41.2432 | 429617.1171 | ACTION | 4082.2219 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4094.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4102.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4114.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4122.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4134.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4142.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4154.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4162.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4174.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4182.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4194.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4202.2219 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4245.4651 | MonopileInstallation
| WTIV | Delay | 33 | 343750 | ACTION | 4278.4651 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4328.4651 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4333.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4334.8818 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4344.8818 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4345.6049 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4345.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4346.6081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4347.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4357.8081 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4358.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4359.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4363.8081 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4369.2248 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 34 | 354166.6667 | ACTION | 4403.2248 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4453.2248 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4458.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4459.6415 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4469.6415 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4470.3645 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4470.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4471.3678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4472.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4482.5678 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4483.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4484.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4488.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 63 | 656250 | ACTION | 4551.5678 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4556.9844 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 147 | 1531250 | ACTION | 4703.9844 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4753.9844 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4759.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4760.4011 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4770.4011 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4771.1242 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4771.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4772.1274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4773.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4783.3274 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4784.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4785.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4789.3274 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4794.7441 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 40 | 416666.6667 | ACTION | 4834.7441 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4884.7441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4890.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4891.1608 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4901.1608 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4901.8838 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4901.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4902.8871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4904.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 4914.0871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4915.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4916.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4920.0871 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4925.5037 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 4975.5037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4980.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4981.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 4991.9204 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4992.9204 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4993.6435 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4993.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4994.6467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 4995.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5005.8467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5006.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5007.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5011.8467 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5017.2634 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 5067.2634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5072.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5073.6801 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 5083.6801 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5084.4031 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5084.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5085.4064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 5086.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 5096.6064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5097.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5098.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5102.6064 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5108.023 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5151.2663 | MonopileInstallation
| WTIV | Delay | 1259 | 13114583.3333 | ACTION | 6410.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6422.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6430.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6442.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6450.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6462.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6470.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6482.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6490.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6502.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 11 | 114583.3333 | ACTION | 6513.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6521.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6533.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6541.2663 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6584.5095 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6634.5095 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6639.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6640.9262 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 6650.9262 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6651.6493 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6651.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6652.6525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 6653.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 6663.8525 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6664.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6665.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6666.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6670.8525 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6676.2692 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6726.2692 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6731.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6732.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 6742.6858 | MonopileInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6758.6858 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6759.4089 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6759.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6760.4122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 6761.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 6771.6122 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6772.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6773.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6777.6122 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6783.0288 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 38 | 395833.3333 | ACTION | 6821.0288 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 6871.0288 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6876.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6877.4455 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 6887.4455 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6888.1686 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6888.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6889.1718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 6890.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 6900.3718 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6901.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6902.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6906.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 6912.3718 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6917.7885 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 52 | 541666.6667 | ACTION | 6969.7885 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7019.7885 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7025.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7026.2051 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7036.2051 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7036.9282 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7036.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7037.9315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7039.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7049.1315 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7050.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7051.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 42 | 437500 | ACTION | 7093.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7097.1315 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7102.5481 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7152.5481 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7157.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7158.9648 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7168.9648 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7169.6878 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7169.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7170.6911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7171.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7181.8911 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7182.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7183.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7187.8911 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7193.3078 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 7222.3078 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7272.3078 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7277.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7278.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 187500 | ACTION | 7296.7244 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7306.7244 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7307.7244 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7308.4475 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7308.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7309.4507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7310.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7320.6507 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7321.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7322.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7326.6507 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7332.0674 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7375.3107 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7387.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7395.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7407.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7415.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7427.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7435.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 31 | 322916.6667 | ACTION | 7466.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7478.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7486.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7498.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7506.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 7518.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 7526.3107 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7569.5539 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7619.5539 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7624.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7625.9706 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7635.9706 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7636.6936 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7636.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7637.6969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7638.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7648.8969 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7649.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7650.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7654.8969 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7660.3136 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7710.3136 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7715.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7716.7302 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7726.7302 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7727.4533 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7727.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7728.4565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7729.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7739.6565 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7740.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7741.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7745.6565 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7751.0732 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7801.0732 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7806.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7807.4899 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7817.4899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7818.2129 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7818.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7819.2162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7820.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7830.4162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7831.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7832.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7836.4162 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7841.8328 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7891.8328 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7897.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7898.2495 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7908.2495 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7908.9726 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7908.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7909.9758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 7911.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 7921.1758 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 7922.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 7923.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 7927.1758 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7932.5925 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 7982.5925 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7988.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 7989.0092 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 7999.0092 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 7999.7322 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 7999.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8000.7355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8001.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8011.9355 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8012.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8013.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8017.9355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8023.3521 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 8052.3521 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8102.3521 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8107.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 8108.7688 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 8118.7688 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 8119.4919 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 8119.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8120.4951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8121.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8131.6951 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8132.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 40 | 416666.6667 | ACTION | 8172.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8173.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8177.6951 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8183.1118 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8226.355 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 8238.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 8246.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 8258.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 8266.355 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 36 | 375000 | ACTION | 8302.355 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8303.355 | MonopileInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 8305.355 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 8315.355 | MonopileInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 8317.355 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8318.355 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8321.5983 | MonopileInstallation
| WTIV | Delay | 18 | 187500 | ACTION | 8339.5983 | MonopileInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8389.5983 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8395.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 8396.0149 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 8406.0149 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 8406.738 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 8406.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8407.7413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8408.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8418.9413 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8419.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 33 | 343750 | ACTION | 8452.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8453.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8457.9413 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8463.3579 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8513.3579 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8518.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 8519.7746 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 8529.7746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 8530.4977 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 8530.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8531.5009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 8532.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 8542.7009 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 8543.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8544.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 8545.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 8549.7009 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8555.1176 | MonopileInstallation | 22.5 | 150 | 6 | MonopileInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 8555.1176 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 8555.1176 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 8555.1176 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8557.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8558.3608 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8559.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8561.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8563.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8565.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8565.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8566.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8567.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8569.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8571.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8573.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8575.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8577.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8578.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8578.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8579.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8581.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8583.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8585.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8587.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8589.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8590.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8591.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8591.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 13 | 65000 | ACTION | 8604.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8606.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8608.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8610.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8612.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8614.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8615.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8616.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8617.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8619.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8621.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8623.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8625.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8627.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8627.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8628.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8629.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8631.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8633.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8635.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8637.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8639.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8640.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8640.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8641.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 86.5 | 432500 | ACTION | 8641.6176 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8643.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 8644.8608 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8644.8617 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 86.5008 | 901050.3559 | ACTION | 8644.8617 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8645.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8647.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8649.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8651.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8652.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8653.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8653.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8655.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8657.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8659.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8661.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8663.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8664.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8665.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8666.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 8668.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8670.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8672.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8674.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8676.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8678.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8678.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8679.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8680.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8682.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8684.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8686.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8688.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8690.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8691.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8691.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8692.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 77 | 802083.3333 | ACTION | 8721.8617 | TurbineInstallation
| Feeder 1 | Delay | 36 | 180000 | ACTION | 8728.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8730.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8732.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 3 | 15000 | ACTION | 8735.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8737.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8739.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8741.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8742.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8743.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8743.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8745.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8747.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8749.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8751.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8753.8676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8754.6176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8755.3676 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8756.1176 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 8759.3608 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8759.3617 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8771.8617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8777.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8778.2783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8778.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8780.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8781.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8782.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8784.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8785.4183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8786.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8788.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8789.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8791.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8793.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8794.0783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8795.0783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8796.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8798.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8799.5783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8800.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8801.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8803.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8803.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8805.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8806.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8807.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8808.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8810.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8815.495 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8865.495 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8870.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8871.9117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8872.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8874.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8875.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8876.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8878.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8879.0517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8880.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8882.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8883.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8884.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8886.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8887.7117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8888.7117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8890.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8892.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8893.2117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8893.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8895.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8896.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8897.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8898.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8900.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8900.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8902.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8903.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8909.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 8959.1283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8964.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8965.545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8965.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8967.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8968.925 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8969.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8971.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8972.685 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8974.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8975.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8977.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8978.825 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8980.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8982.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 16 | 166666.6667 | ACTION | 8998.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9000.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9001.345 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9002.345 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9003.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9005.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9006.845 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9007.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9008.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9010.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9010.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9012.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9013.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9014.345 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 9021.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9022.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9024.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9029.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9079.7617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9085.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9086.1783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9086.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9088.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9089.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9090.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9092.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9093.3183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9094.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9096.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9097.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9098.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9100.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9101.9783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9102.9783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9104.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9106.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9107.4783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9107.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9109.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9110.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9111.4783 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9112.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9113.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9115.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9115.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9117.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9118.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9119.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9125.395 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9175.395 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9180.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9181.8117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9182.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9184.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9185.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9185.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9187.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9188.9517 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 9192.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9194.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9196.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9197.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9198.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9200.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9201.6117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9202.6117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9204.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9206.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9207.1117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9207.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9209.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9210.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9211.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9212.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9214.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9214.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9216.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9217.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9223.0283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9273.0283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9278.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9279.445 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9279.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9281.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9282.825 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9283.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9285.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9286.585 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9287.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9289.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9290.725 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9292.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9294.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9295.245 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9296.245 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9297.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9299.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9300.745 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9301.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9302.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9304.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9304.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9306.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9307.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9308.245 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 663.3833 | 3316916.6667 | ACTION | 9308.245 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Queue | 548.8833 | 2744416.6667 | ACTION | 9308.245 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9308.2458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9309.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9311.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9311.4891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9313.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9315.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9316.6617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9317.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9319.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9321.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9322.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9322.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9323.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9325.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9327.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9329.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9331.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9333.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9334.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9335.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9335.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9337.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9339.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9341.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9343.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9345.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9346.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9347.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9348.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9350.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9352.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9354.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9356.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9358.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9358.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9359.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9360.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9362.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9364.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9366.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9366.6617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9368.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9370.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9371.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9371.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9372.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9372.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9373.0783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9373.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9374.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9375.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9376.4583 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9376.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9377.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9378.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9379.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9380.2183 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9380.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9381.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9382.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9383.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9383.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9384.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9384.3583 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9384.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9385.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9387.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 9388.2323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9388.2331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9388.8783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9389.8783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9391.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9393.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9394.3783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9394.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9396.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9397.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9398.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9399.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9401.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9401.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9403.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9404.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9410.295 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9460.295 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9465.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9466.7117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9467.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9469.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9470.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9470.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9472.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9473.8517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9474.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9476.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9477.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9479.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9481.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9482.5117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9483.5117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9485.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9487.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9488.0117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9488.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9490.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9491.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9492.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9493.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9495.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9495.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9497.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9498.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9503.9283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 22 | 229166.6667 | ACTION | 9525.9283 | TurbineInstallation
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9575.9283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9581.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9582.345 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9582.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9584.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9585.725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9586.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9588.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9589.485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9590.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9592.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9593.625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9595.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9597.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9598.145 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9599.145 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9600.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9602.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9603.645 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9604.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9605.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9607.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9607.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9609.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9610.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9611.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9612.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9614.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9619.5617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9669.5617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9674.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9675.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9676.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9678.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9679.3583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9680.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9682.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9683.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9684.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9686.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9687.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9688.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9690.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9691.7783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9692.7783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9694.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9696.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9697.2783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9697.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9699.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9700.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9701.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9702.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9704.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9704.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9706.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9707.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9713.195 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9763.195 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9768.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9769.6117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9769.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9771.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9772.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9773.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9775.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9776.7517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9777.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9779.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9780.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9782.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9784.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9785.4117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9786.4117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9787.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9789.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9790.9117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9791.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9792.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9794.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9794.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9796.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9797.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9798.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9799.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9801.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9806.8283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9856.8283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9862.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9863.245 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9863.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9865.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9866.625 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9867.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9869.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9870.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9871.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9873.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9874.525 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9876.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9878.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9879.045 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9880.045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9881.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9883.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9884.545 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9885.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9886.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9888.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9888.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9890.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9891.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9892.045 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 583.8 | 2919000 | ACTION | 9892.045 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Queue | 503.8118 | 2519059.2259 | ACTION | 9892.045 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9892.0458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9893.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9895.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9895.2891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9897.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9899.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9900.4617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9901.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9903.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9905.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9906.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9906.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9907.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9909.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9911.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9913.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9915.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9917.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9918.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9919.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9919.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9921.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9923.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9925.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9927.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9929.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9930.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9931.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9932.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9934.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9936.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9938.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9940.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9942.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9942.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9943.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9944.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9946.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9948.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9950.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 9950.4617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9952.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9954.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9955.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9955.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9955.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9956.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9956.8783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9957.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9958.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9959.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9960.2583 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9960.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9961.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9962.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9963.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9964.0183 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9964.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9965.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9966.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9967.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9967.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9968.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9968.1583 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9968.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9969.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9971.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 9972.0323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9972.0331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9972.6783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9973.6783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9975.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9977.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9978.1783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9978.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9980.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9981.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9982.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9983.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9985.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9985.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9987.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9988.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9994.095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10044.095 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10049.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10050.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10050.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10052.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10053.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10054.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10056.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10057.6517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10058.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10060.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10061.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10063.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10065.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10066.3117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10067.3117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10068.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10070.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10071.8117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10072.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10073.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10075.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10075.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10077.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10078.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10079.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10080.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10082.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10087.7283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10137.7283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10143.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10144.145 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10144.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10146.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10147.525 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10148.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10150.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10151.285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10152.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10154.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10155.425 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10156.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10158.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10159.945 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10160.945 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10162.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10164.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10165.445 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10165.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10167.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10168.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10169.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10170.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10172.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10172.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10174.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10175.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10181.3617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10231.3617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10236.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10237.7783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10238.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10240.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10241.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10241.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10243.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10244.9183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10246.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10248.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10249.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10250.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10252.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10253.5783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10254.5783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10256.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10258.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10259.0783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10259.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10261.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10262.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10263.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10264.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10266.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10266.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10268.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10269.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10274.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10324.995 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10330.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10331.4117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10331.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10333.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10334.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10335.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10337.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10338.5517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10339.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10341.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10342.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10344.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10346.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10347.2117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10348.2117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10349.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10351.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10352.7117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10353.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10354.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10356.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10356.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10358.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10359.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10360.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10361.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10363.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10368.6283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10418.6283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10424.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10425.045 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10425.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10427.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10428.425 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10429.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10431.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10432.185 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10433.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10435.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10436.325 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10437.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10439.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10440.845 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10441.845 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10443.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10445.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10446.345 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10446.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10448.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10449.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10450.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10451.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10453.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10453.845 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 561.8 | 2809000 | ACTION | 10453.845 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Queue | 481.8118 | 2409059.2259 | ACTION | 10453.845 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10453.8458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10455.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10456.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10457.0891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10459.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10461.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10462.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10463.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10465.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10467.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10467.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10468.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10469.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10471.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10473.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10475.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10477.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10479.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10480.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10480.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10481.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10483.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10485.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10487.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10489.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10491.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10492.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10493.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10493.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10495.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10497.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10499.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10501.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10503.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10504.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10505.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10506.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10508.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10510.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10512.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10512.2617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10514.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10516.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10516.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10517.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10517.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10518.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10518.6783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10519.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10520.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10521.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10522.0583 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10522.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10522.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10524.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10524.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10525.8183 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10526.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10526.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10528.3391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10528.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10529.0891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10529.8391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10529.9583 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10530.5891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10531.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10533.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 10533.8323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10533.8331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10534.4783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10535.4783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10536.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10538.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10539.9783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10540.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10541.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10543.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10543.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10545.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10546.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10547.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10548.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10550.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10555.895 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10605.895 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10611.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10612.3117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10612.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10614.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10615.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10616.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10618.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10619.4517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10620.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10622.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10623.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10625.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10627.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10628.1117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10629.1117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10630.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10632.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10633.6117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10634.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10635.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10637.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10637.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10639.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10640.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10641.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10642.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10644.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10649.5283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10699.5283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10704.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10705.945 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10706.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10708.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10709.325 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10710.085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10712.085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10713.085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10714.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10716.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10717.225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10718.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10720.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10721.745 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10722.745 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 10732.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10734.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10736.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10737.245 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10737.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10739.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10740.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10741.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10742.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10744.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10744.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10746.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10747.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10753.1617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10803.1617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10808.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10809.5783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10809.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10811.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10812.9583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10813.7183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10815.7183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10816.7183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10817.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10819.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10820.8583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10822.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10824.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10825.3783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10826.3783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10827.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10829.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10830.8783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10831.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10832.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10834.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10834.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10836.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10837.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10838.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10839.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10841.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10846.795 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10896.795 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10902.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10903.2117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10903.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10905.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10906.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10907.3517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10909.3517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10910.3517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10911.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10913.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10914.4917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10916.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10918.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10919.0117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10920.0117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10921.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10923.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10924.5117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10925.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10926.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10928.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10928.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10930.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10931.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10932.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10933.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10935.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10940.4283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 10990.4283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10995.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10996.845 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10997.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10999.225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11000.225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11000.985 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11002.985 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11003.985 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11005.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11007.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11008.125 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11009.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11011.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11012.645 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11013.645 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11015.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11017.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11018.145 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11018.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11020.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11021.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11022.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11023.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11025.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11025.645 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 571.8 | 2859000 | ACTION | 11025.645 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Queue | 491.8118 | 2459059.2259 | ACTION | 11025.645 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11025.6458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11027.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11028.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11028.8891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11030.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11032.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11034.0617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11034.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11036.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11038.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11039.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11040.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11041.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11043.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11045.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11047.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11049.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11051.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11051.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11052.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11053.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11055.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11057.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11059.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11061.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11063.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11064.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11064.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11065.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11067.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11069.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11071.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11073.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11075.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11076.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11077.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11077.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11079.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11081.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11083.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11084.0617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11085.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11087.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11088.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11089.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11089.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11090.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11090.4783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11090.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11092.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11092.8583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11093.8583 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11094.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11094.6183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11096.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11096.6183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11097.6183 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 11098.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11098.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 11100.1391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11100.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11100.8891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11101.6391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11101.7583 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 11102.3891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11103.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11105.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 11105.6323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 11105.6331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11106.2783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11107.2783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11108.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11110.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11111.7783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11112.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11113.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11115.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11115.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11117.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11118.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11119.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11120.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11122.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11127.695 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11177.695 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11183.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11184.1117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11184.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11186.4917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11187.4917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11188.2517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11190.2517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11191.2517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11192.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11194.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11195.3917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11196.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11198.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11199.9117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11200.9117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11202.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11204.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11205.4117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11205.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11207.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11208.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11209.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11210.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11212.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11212.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11214.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11215.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11221.3283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11271.3283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11276.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11277.745 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11278.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11280.125 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11281.125 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11281.885 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11283.885 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11284.885 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11286.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11288.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11289.025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11290.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11292.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11293.545 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11294.545 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11296.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11298.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11299.045 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11299.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11301.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11302.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11303.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11304.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11306.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11306.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11308.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11309.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11314.9617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11364.9617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11370.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11371.3783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11371.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11373.7583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11374.7583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11375.5183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11377.5183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11378.5183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11379.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11381.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11382.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11384.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11386.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11387.1783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11388.1783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11389.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11391.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11392.6783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11393.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11394.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11396.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11396.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11398.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11399.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11400.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11401.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11403.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11408.595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11458.595 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11464.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11465.0117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11465.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11467.3917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11468.3917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11469.1517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11471.1517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11472.1517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11473.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11475.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11476.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11477.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11479.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11480.8117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11481.8117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11483.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11485.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11486.3117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11486.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11488.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11489.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11490.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11491.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11493.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11493.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11495.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11496.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11502.2283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11552.2283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11557.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11558.645 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11559.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11561.025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11562.025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11562.785 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11564.785 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11565.785 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11566.785 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11567.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11569.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11570.925 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11572.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11574.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11575.445 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11576.445 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11577.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11579.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11580.945 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11581.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11582.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11584.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11584.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11586.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11587.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11588.445 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 562.8 | 2814000 | ACTION | 11588.445 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Queue | 482.8118 | 2414059.2259 | ACTION | 11588.445 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11588.4458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11589.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11591.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11591.6891 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11593.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11595.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11596.8617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11597.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11599.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11601.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11602.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11603.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11603.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11605.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11607.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11609.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 54 | 562500 | ACTION | 11650.8617 | TurbineInstallation
| Feeder 0 | Delay | 41 | 205000 | ACTION | 11650.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11652.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11654.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11655.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11656.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11657.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11659.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11661.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11663.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11665.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11667.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11667.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11668.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11669.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11671.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11673.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11675.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11677.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11679.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11680.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11680.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11681.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11683.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11685.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11687.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11689.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11691.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11692.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11693.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11693.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11695.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11697.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11699.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11700.8617 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 11701.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 11703.9391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11704.6891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11705.4391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 11706.1891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11706.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11707.2783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11707.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 11709.4323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 11709.4331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11709.6583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11710.6583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11711.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11713.4183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11714.4183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11715.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11717.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11718.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11720.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11722.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11723.0783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11724.0783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11725.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11727.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11728.5783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11729.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11730.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11732.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11732.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11734.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11735.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11736.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11737.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11739.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11744.495 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11794.495 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11799.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11800.9117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11801.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11803.2917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11804.2917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11805.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11807.0517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11808.0517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11809.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11811.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11812.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11813.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11815.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11816.7117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11817.7117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11819.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11821.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11822.2117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11822.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11824.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11825.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11826.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11827.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11829.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11829.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11831.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11832.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11838.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11888.1283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11893.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11894.545 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11894.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11896.925 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11897.925 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11898.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11900.685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11901.685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11902.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11904.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11905.825 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11907.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11909.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11910.345 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 11919.345 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11920.345 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11921.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11923.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11924.845 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11925.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11926.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11928.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11928.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11930.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11931.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11932.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11933.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11935.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11940.7617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 11990.7617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11996.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11997.1783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11997.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11999.5583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12000.5583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12001.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12003.3183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12004.3183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12005.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12007.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12008.4583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12009.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12011.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12012.9783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12013.9783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12015.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12017.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12018.4783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12018.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12020.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12021.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12022.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12023.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12025.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12025.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12027.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12028.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12034.395 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12084.395 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12089.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12090.8117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12091.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12093.1917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12094.1917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12094.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12096.9517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12097.9517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12099.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12101.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12102.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12103.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12105.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12106.6117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12107.6117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12109.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12111.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12112.1117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12112.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12114.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12115.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12116.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12117.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12119.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12119.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12121.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12122.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12128.0283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12178.0283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12183.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12184.445 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12184.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12186.825 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12187.825 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12188.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12190.585 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12191.585 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12192.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12194.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12195.725 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12197.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12199.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12200.245 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12201.245 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12202.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12204.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12205.745 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12206.245 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12207.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12209.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12209.745 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12211.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12212.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12213.245 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 624.8 | 3124000 | ACTION | 12213.245 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Queue | 503.8118 | 2519059.2259 | ACTION | 12213.245 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 12213.2458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12214.745 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12216.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 12216.4891 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12218.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12220.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12221.6617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12222.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12224.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12226.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12227.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12227.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12228.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12230.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12232.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12234.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12236.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12238.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12239.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12240.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12240.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12242.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12244.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12246.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12248.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12250.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12251.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12252.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12253.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12255.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12257.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12259.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12261.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12263.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12263.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12264.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12265.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12267.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12269.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12271.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12271.6617 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12273.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12275.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12276.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12276.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12277.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12277.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12278.0783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12278.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12279.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12280.4583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12281.4583 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12281.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12282.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12283.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12284.2183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12285.2183 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 12285.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12286.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 12287.7391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12288.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12288.4891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12289.2391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12289.3583 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 12289.9891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12290.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12292.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 12293.2323 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 12293.2331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12293.8783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12294.8783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12296.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12298.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12299.3783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12299.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12301.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12302.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12303.3783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12304.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12306.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12306.8783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12308.3783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12309.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12315.295 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12365.295 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12370.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12371.7117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12372.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12374.0917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12375.0917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12375.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12377.8517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12378.8517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12379.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12381.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12382.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12384.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12386.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12387.5117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12388.5117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12390.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12392.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12393.0117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12393.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12395.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12396.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12397.0117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12398.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12400.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12400.5117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12402.0117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12403.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12408.9283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12458.9283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12464.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12465.345 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12465.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12467.725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12468.725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12469.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12471.485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12472.485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12473.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12475.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12476.625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12478.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12480.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12481.145 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12482.145 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12483.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12485.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12486.645 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12487.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12488.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12490.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12490.645 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12492.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12493.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12494.145 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12495.645 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12497.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12502.5617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12552.5617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12557.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12558.9783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12559.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12561.3583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12562.3583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12563.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12565.1183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12566.1183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12567.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12569.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12570.2583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12571.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12573.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12574.7783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12575.7783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12577.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12579.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12580.2783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12580.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12582.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12583.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12584.2783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12585.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12587.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12587.7783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12589.2783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12590.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12596.195 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12646.195 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12651.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12652.6117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12652.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12654.9917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12655.9917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12656.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12658.7517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12659.7517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12660.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12662.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12663.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12665.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12667.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12668.4117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12669.4117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12670.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12672.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12673.9117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12674.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12675.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12677.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12677.9117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12679.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12680.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12681.4117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12682.9117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12684.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12689.8283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12739.8283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12745.245 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12746.245 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12746.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12748.625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12749.625 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12750.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12752.385 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12753.385 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12754.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12756.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12757.525 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12759.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12761.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12762.045 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12763.045 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12764.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12766.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12767.545 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12768.045 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12769.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 31 | 322916.6667 | ACTION | 12800.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12802.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12802.545 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12804.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12805.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12806.045 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 592.8 | 2964000 | ACTION | 12806.045 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Queue | 512.8118 | 2564059.2259 | ACTION | 12806.045 | TurbineInstallation | [17 empty] | Site
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12807.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 12813.545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12815.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12820.4617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12870.4617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12875.8783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12876.8783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12877.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12879.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12880.2583 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12881.2583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12882.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12884.0183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12885.0183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12886.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12888.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12889.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 12890.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 12897.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12899.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 12900.6783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12901.6783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12903.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 12 | 125000 | ACTION | 12915.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 12917.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12918.1783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12918.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12920.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12921.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12922.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12923.1783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12924.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12926.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 12926.6783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12928.1783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 12929.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 12935.095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 12985.095 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 12990.5117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12991.5117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 12991.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12993.8917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12994.8917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 12995.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 12997.6517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 12998.6517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 12999.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13001.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13002.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13004.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13006.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13007.3117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13008.3117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13009.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13011.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13012.8117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13013.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13014.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13016.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13016.8117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13018.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 13020.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13021.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13022.3117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13023.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 13025.8117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13027.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13032.7283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13082.7283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13088.145 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13089.145 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13089.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13091.525 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13092.525 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13093.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13095.285 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13096.285 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13097.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13099.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13100.425 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13101.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13103.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13104.945 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13105.945 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13107.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13109.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13110.445 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13110.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13112.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13113.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13114.445 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13115.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13117.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13117.945 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13119.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 26 | 270833.3333 | ACTION | 13145.445 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13146.945 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13152.3617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13202.3617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13207.7783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13208.7783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13209.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13211.1583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13212.1583 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13212.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13214.9183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13215.9183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13217.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13219.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13220.0583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13221.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13223.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13224.5783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13225.5783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13227.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13229.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13230.0783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13230.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13232.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13233.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 428 | 2140000 | ACTION | 13234.045 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13234.0458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13234.0783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13235.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13237.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 13237.2891 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13237.5783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13239.0783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13239.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13240.5783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13241.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13243.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13245.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13245.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 13247.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13248.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13248.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13249.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13251.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13253.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13255.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 13257.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 13259.5391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13260.2891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13261.0391 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 13261.7891 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 13265.0323 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 13265.0331 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13295.995 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13301.4117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13302.4117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13302.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13304.7917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13305.7917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13306.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13308.5517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13309.5517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13310.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13312.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13313.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13315.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13317.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13318.2117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13319.2117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13320.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13322.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13323.7117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13324.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13325.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13327.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13327.7117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13329.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13330.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13331.2117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13332.7117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13334.2117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13339.6283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13389.6283 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13395.045 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13396.045 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13396.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13398.425 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13399.425 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13400.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13402.185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13403.185 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13404.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13406.325 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13407.325 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13408.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13410.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13411.845 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13412.845 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13414.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13416.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13417.345 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13417.845 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13419.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13420.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13421.345 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13422.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13424.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13424.845 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 618.8 | 3094000 | ACTION | 13424.845 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Queue | 159.8118 | 799059.2259 | ACTION | 13424.845 | TurbineInstallation | [17 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13424.8458 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13426.345 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13427.845 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 13428.0891 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13433.2617 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13483.2617 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13488.6783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13489.6783 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13490.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13492.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13493.0583 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 13494.0583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13494.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13496.8183 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13497.8183 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13498.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13500.9583 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13501.9583 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13503.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13505.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13506.4783 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13507.4783 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13508.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13510.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13511.9783 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13512.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13513.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 93750 | ACTION | 13522.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13524.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13524.9783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13526.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13527.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13528.4783 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13529.9783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13531.4783 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13536.895 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 50 | 520833.3333 | ACTION | 13586.895 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 13592.3117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13593.3117 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 13593.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13595.6917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13596.6917 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 13597.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13599.4517 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13600.4517 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 13601.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13603.5917 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 13604.5917 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 13606.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 13608.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 13609.1117 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13610.1117 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13611.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 13613.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13614.6117 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13615.1117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13616.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13618.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13618.6117 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13620.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13621.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 13622.1117 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 197.2667 | 986333.3333 | ACTION | 13622.1117 | TurbineInstallation | [17 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 13622.1125 | TurbineInstallation |  |  |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13623.6117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 13625.1117 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 13625.3557 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 13630.5283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 50 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 13633.7716 | TurbineInstallation