## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name | site_position_time | mono_drive_rate
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 32 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 40 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 52 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 60 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 72 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 80 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 83.2432 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 88.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 88.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 89.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 92.5599 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 93.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 93.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 94.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 7 | 116666.6667 | ACTION | 101.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 116.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 118.2862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 119.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 120.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 124.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 124.6029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 129.6029 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 129.9196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 130.9196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 133.9196 | MonopileInstallation
| WTIV | Delay | 9 | 150000 | ACTION | 142.9196 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 143.6426 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 143.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 144.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 3 | 50000 | ACTION | 147.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 162.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 164.6459 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 165.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 166.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 170.6459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 170.9625 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 175.9625 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 176.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 177.2792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 180.2792 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 181.0023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 183.0023 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 183.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 184.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 36 | 600000 | ACTION | 220.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 235.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 237.0055 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 238.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 239.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 243.0055 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 243.3222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 248.3222 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 248.6389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 249.6389 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 252.6389 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 253.3619 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 253.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 254.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 269.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 271.3652 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 272.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 273.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 277.3652 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 277.6818 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 280.9251 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 292.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 300.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 312.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 320.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 332.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 340.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 352.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 360.9251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 364.1683 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 369.1683 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 369.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 370.485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 373.485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 374.2081 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 374.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 375.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 390.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 392.2113 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 393.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 394.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 398.2113 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 398.528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 403.528 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 403.8446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 404.8446 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 407.8446 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 408.5677 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 408.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 409.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 424.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 426.571 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 427.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 428.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 11 | 183333.3333 | ACTION | 439.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 443.571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 443.8876 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 448.8876 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 449.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 450.2043 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 3 | 50000 | ACTION | 453.2043 | MonopileInstallation
| WTIV | Release Monopile | 3 | 50000 | ACTION | 456.2043 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 456.9274 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 456.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 457.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 472.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 474.9306 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 475.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 476.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 480.9306 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 481.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 486.2473 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 486.5639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 487.5639 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 490.5639 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 491.287 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 491.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 492.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 507.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 509.2903 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 510.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 511.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 515.2903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 515.6069 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 518.8502 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 530.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 538.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 550.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 558.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 570.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 578.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 590.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 598.8502 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 602.0934 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 607.0934 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 607.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 608.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 611.4101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 612.1331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 612.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 613.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 628.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 630.1364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 631.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 632.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 636.1364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 636.4531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 641.4531 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 641.7697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 642.7697 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 645.7697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 646.4928 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 646.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 647.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 662.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 664.496 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 665.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 666.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 670.496 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 670.8127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 675.8127 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 676.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 677.1294 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 680.1294 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 680.8524 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 680.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 681.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 696.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 698.8557 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 699.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 700.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 704.8557 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 705.1724 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 710.1724 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 710.489 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 711.489 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 714.489 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 715.2121 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 715.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 716.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 731.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 733.2153 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 734.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 735.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 739.2153 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 739.532 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 742.7752 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 754.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 762.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 774.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 782.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 794.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 802.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 814.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 822.7752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 826.0185 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 831.0185 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 831.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 832.3352 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 835.3352 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 836.0582 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 836.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 837.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 852.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 854.0615 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 855.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 856.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 860.0615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 860.3781 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 865.3781 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 865.6948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 866.6948 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 869.6948 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 870.4179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 870.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 871.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 16 | 266666.6667 | ACTION | 887.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 902.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 904.4211 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 905.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 906.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 910.4211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 910.7378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 915.7378 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 916.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 917.0545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 920.0545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 920.7775 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 920.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 921.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 936.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 938.7808 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 939.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 940.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 944.7808 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 945.0974 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 950.0974 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 950.4141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 951.4141 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 954.4141 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 955.1372 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 955.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 956.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 971.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 973.1404 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 974.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 975.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 979.1404 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 979.4571 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 982.7003 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 994.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1002.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1014.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1022.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1034.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1042.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1054.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1062.7003 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1065.9436 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1070.9436 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1071.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1072.2602 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1075.2602 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1075.9833 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1075.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1076.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1091.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1093.9866 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1094.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1095.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1099.9866 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1100.3032 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1105.3032 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1105.6199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1106.6199 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1109.6199 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1110.343 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1110.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1111.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1126.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1128.3462 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1129.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1130.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1134.3462 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1134.6629 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1139.6629 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1139.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1140.9795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1143.9795 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1144.7026 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1144.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1145.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1160.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1162.7059 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1163.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1164.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1168.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1169.0225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1174.0225 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1174.3392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1175.3392 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1178.3392 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1179.0622 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1179.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1180.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1195.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1197.0655 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1198.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1199.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1203.0655 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1203.3822 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1206.6254 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1218.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1226.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1238.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1246.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1258.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1266.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1278.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1286.6254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1289.8687 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1294.8687 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1295.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1296.1853 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1299.1853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1299.9084 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1299.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1300.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 17 | 283333.3333 | ACTION | 1317.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1332.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1334.9116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1335.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1336.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1340.9116 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1341.2283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1346.2283 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1346.545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1347.545 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1350.545 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1351.268 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1351.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1352.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1367.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1369.2713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1370.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1371.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1375.2713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1375.588 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1380.588 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1380.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1381.9046 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1384.9046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1385.6277 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1385.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1386.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1401.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1403.6309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1404.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1405.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 11 | 183333.3333 | ACTION | 1416.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1420.6309 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1420.9476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1425.9476 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1426.2643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1427.2643 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1430.2643 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1430.9873 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1430.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1431.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1446.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1448.9906 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1449.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1450.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1454.9906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1455.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1458.5505 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1470.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1478.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1490.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1498.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1510.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1518.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1530.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1538.5505 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1541.7937 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1546.7937 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1547.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1548.1104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1551.1104 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1551.8335 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1551.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1552.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 8 | 133333.3333 | ACTION | 1560.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1575.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1577.8367 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1578.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1579.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1583.8367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1584.1534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1589.1534 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1589.4701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1590.4701 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1593.4701 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1594.1931 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1594.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1595.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1610.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1612.1964 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1613.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1614.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1618.1964 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1618.513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1623.513 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1623.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1624.8297 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1627.8297 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1628.5528 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1628.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1629.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1644.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1646.556 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1647.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1648.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1652.556 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1652.8727 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1657.8727 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1658.1893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1659.1893 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1662.1893 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1662.9124 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1662.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1663.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1678.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1680.9157 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1681.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1682.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1686.9157 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1687.2323 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1690.4756 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1702.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1710.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1722.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1730.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1742.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1750.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1762.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1770.4756 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1773.7188 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1778.7188 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1779.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1780.0355 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1783.0355 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1783.7585 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1783.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1784.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1799.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1801.7618 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1802.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1803.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1807.7618 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1808.0785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1813.0785 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1813.3951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1814.3951 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1817.3951 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1818.1182 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1818.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1819.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1834.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1836.1214 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1837.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1838.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1842.1214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1842.4381 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1847.4381 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1847.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1848.7548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1851.7548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1852.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1852.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1853.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1868.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1870.4811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1871.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1872.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1876.4811 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1876.7978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 1881.7978 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 1882.1144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 1883.1144 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 1886.1144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 1886.8375 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 1886.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1887.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 1902.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 1904.8407 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 1905.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 1906.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 1910.8407 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 1911.1574 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1914.4007 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1926.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1934.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1946.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1954.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1966.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1974.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 1986.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 1994.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 1997.6439 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2002.6439 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2002.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2003.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2006.9606 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2007.6836 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2007.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2008.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 13 | 216666.6667 | ACTION | 2021.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2036.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2038.6869 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2039.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2040.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2044.6869 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2045.0035 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2050.0035 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2050.3202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2051.3202 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2054.3202 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2055.0433 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2055.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2056.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2071.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2073.0465 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2074.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2075.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2079.0465 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2079.3632 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2084.3632 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2084.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2085.6799 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2088.6799 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2089.4029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2089.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2090.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2105.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2107.4062 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2108.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2109.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2113.4062 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2113.7228 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2118.7228 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2119.0395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2120.0395 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2123.0395 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2123.7626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2123.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2124.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2139.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2141.7658 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2142.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2143.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2147.7658 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2148.0825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2151.3257 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2163.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2171.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2183.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2191.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2203.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2211.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2223.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2231.3257 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2234.569 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2239.569 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2239.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2240.8856 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2243.8856 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2244.6087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2244.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2245.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2260.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2262.612 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2263.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2264.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2268.612 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2268.9286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2273.9286 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2274.2453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2275.2453 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2278.2453 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2278.9684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2278.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2279.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2294.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2296.9716 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2297.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2298.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2302.9716 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2303.2883 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2308.2883 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2308.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2309.6049 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2312.6049 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2313.328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2313.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2314.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2329.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2331.3313 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2332.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2333.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2337.3313 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2337.6479 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2342.6479 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2342.9646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2343.9646 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2346.9646 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2347.6877 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2347.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2348.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2363.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2365.6909 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2366.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2367.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2371.6909 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2372.0076 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2375.2508 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2387.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2395.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2407.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2415.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2427.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2435.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2447.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2455.2508 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2458.4941 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2463.4941 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2463.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2464.8107 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2467.8107 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2468.5338 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2468.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2469.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2484.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2486.537 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2487.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2488.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2492.537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2492.8537 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2497.8537 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2498.1704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2499.1704 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2502.1704 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2502.8934 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2502.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2503.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2518.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2520.8967 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2521.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2522.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2526.8967 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2527.2134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2532.2134 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2532.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2533.53 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2536.53 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2537.2531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2537.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2538.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2553.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2555.2563 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2556.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2557.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2561.2563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2561.573 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2566.573 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2566.8897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2567.8897 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2570.8897 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2571.6127 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2571.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2572.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2587.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2589.616 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2590.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2591.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2595.616 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2595.9327 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2599.1759 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2611.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2619.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2631.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2639.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2651.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2659.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2671.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2679.1759 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2682.4191 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2687.4191 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2687.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2688.7358 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2691.7358 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2692.4589 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2692.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2693.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2708.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2710.4621 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2711.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2712.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2716.4621 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2716.7788 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2721.7788 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2722.0955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2723.0955 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2726.0955 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2726.8185 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2726.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2727.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Delay | 53 | 883333.3333 | ACTION | 2780.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2795.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2797.8218 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2798.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2799.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2803.8218 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2804.1384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2809.1384 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2809.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2810.4551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2813.4551 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2814.1782 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2814.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2815.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2830.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2832.1814 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2833.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2834.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2838.1814 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2838.4981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2843.4981 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2843.8148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2844.8148 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2847.8148 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2848.5378 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2848.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2849.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2864.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2866.5411 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2867.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2868.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2872.5411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2872.8577 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2876.101 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2888.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2896.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Monopile | 12 | 200000 | ACTION | 2908.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Fasten Transition Piece | 8 | 133333.3333 | ACTION | 2916.101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 2919.3442 | MonopileInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2924.3442 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2924.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2925.6609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2928.6609 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2929.384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2929.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2930.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2945.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2947.3872 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2948.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2949.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2953.3872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2953.7039 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 2958.7039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 2959.0205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | RovSurvey | 1 | 16666.6667 | ACTION | 2960.0205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Monopile | 3 | 50000 | ACTION | 2963.0205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 12051.0923 | ACTION | 2963.7436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower Monopile | 0.00325 | 54.1667 | ACTION | 2963.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2964.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Drive Monopile | 15 | 250000 | ACTION | 2979.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Release Transition Piece | 2 | 33333.3333 | ACTION | 2981.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 16666.6667 | ACTION | 2982.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Lower TP | 1 | 16666.6667 | ACTION | 2983.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Bolt TP | 4 | 66666.6667 | ACTION | 2987.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 2988.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation | 5 | 2
1 | WTIV | Mobilize | 168 | 2800000 | ACTION | 2988.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2992.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 2996.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3000.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3004.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3008.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3009.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3011.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3012.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 20 | 333333.3333 | ACTION | 3032.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3036.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3040.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3044.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3045.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3049.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3053.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3055.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3056.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3058.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3062.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3066.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3070.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3074.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3078.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3079.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3081.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3082.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3085.8068 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3090.8068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3091.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3094.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3094.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3100.5034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3103.5034 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3104.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3110.2634 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3113.2634 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3114.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3120.4034 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3123.4034 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3124.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3130.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3133.9234 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3134.9234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3136.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3142.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3143.4234 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3144.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3145.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3149.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3150.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3151.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3155.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3156.4234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3157.9234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3161.4234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3161.7401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3166.7401 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3167.0568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3170.0568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3170.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3176.4368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3179.4368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3180.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3186.1968 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3189.1968 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3190.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3196.3368 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3199.3368 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3200.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3206.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3209.8568 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3210.8568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3212.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3218.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3219.3568 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3220.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3221.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3225.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3226.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3227.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3231.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3232.3568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3233.8568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3237.3568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3237.6734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3242.6734 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3242.9901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3245.9901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3246.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3252.3701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3255.3701 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3256.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3262.1301 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3265.1301 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3266.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3272.2701 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3275.2701 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3276.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3282.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3285.7901 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3286.7901 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3288.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3294.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3295.2901 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3296.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3297.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3301.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3302.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3303.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3307.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3308.2901 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3309.7901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3313.2901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3313.6068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3316.85 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3320.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3324.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3328.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3332.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3336.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3338.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3339.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3341.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 10 | 166666.6667 | ACTION | 3351.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3355.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3359.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3363.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3367.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3371.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3372.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3374.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3375.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3379.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3383.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3387.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3391.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3395.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3397.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3398.85 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3400.35 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3403.5933 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3408.5933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3408.9099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3411.9099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3412.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3418.2899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3421.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3422.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3428.0499 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3431.0499 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3432.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3434.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3440.1899 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3443.1899 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3444.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3450.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3453.7099 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3454.7099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3456.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3462.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3463.2099 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3464.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3465.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3469.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3470.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3471.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3475.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3476.2099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3477.7099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3481.2099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3481.5266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3486.5266 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3486.8433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3489.8433 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3490.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3496.2233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3499.2233 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3499.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3505.9833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3508.9833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3510.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3516.1233 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3519.1233 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3520.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3526.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3529.6433 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3530.6433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3532.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 6 | 100000 | ACTION | 3538.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3544.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3545.1433 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3546.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3547.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3551.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3552.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3553.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3557.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3558.1433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3559.6433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3563.1433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3563.4599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3568.4599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3568.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3571.7766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3572.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3578.1566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3581.1566 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3581.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3587.9166 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3590.9166 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3592.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3598.0566 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3601.0566 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3602.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3608.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3611.5766 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3612.5766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3614.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 15 | 250000 | ACTION | 3629.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3635.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3636.0766 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3637.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3638.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3642.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3643.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3644.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3648.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3649.0766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3650.5766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3654.0766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3654.3933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 3657.6365 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3661.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3665.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3669.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3673.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3677.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 25 | 416666.6667 | ACTION | 3702.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3704.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3705.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3707.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3711.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3715.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3719.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3723.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3727.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3728.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3730.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3731.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3735.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3739.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3743.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 3747.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 3751.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3753.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3754.6365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 3756.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 1 | 16666.6667 | ACTION | 3757.1365 | TurbineInstallation
| WTIV | Delay | 3 | 50000 | ACTION | 3760.1365 | TurbineInstallation
| WTIV | Transit | 2.2432 | 37387.3874 | ACTION | 3762.3797 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3767.3797 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3767.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3770.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3771.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3777.0764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3780.0764 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3780.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3786.8364 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3789.8364 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3790.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3796.9764 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3799.9764 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3801.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3807.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3810.4964 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3811.4964 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3812.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3818.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3819.9964 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3820.9964 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3822.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3825.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3826.9964 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 3830.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3832.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 1 | 16666.6667 | ACTION | 3833.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3836.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3837.9964 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3839.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3841.4964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3844.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3845.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3850.3131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3850.6297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3853.6297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3854.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3860.0097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3863.0097 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3863.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 3865.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3871.7697 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3874.7697 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3875.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3881.9097 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3884.9097 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3886.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3892.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3895.4297 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3896.4297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3897.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3903.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3904.9297 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3905.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3907.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3910.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3911.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3913.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3916.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3917.9297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3919.4297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3922.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3923.2464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 3928.2464 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 3928.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3931.5631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 3931.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3937.9431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3940.9431 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 3941.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3947.7031 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3950.7031 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 3951.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3957.8431 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 3960.8431 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 3962.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 3968.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 3971.3631 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3972.3631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 3973.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 3979.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 3980.8631 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3981.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3983.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3986.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3987.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3989.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3992.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 3993.8631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 3995.3631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 3998.8631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 3999.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4002.423 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4006.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4010.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4014.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4018.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4022.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 17 | 283333.3333 | ACTION | 4039.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4043.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4044.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4046.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4047.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4051.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4055.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4059.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4063.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4067.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4069.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4070.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4072.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4076.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4080.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4084.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4088.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4092.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4093.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4095.423 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4096.923 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4100.1662 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4105.1662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4105.4829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4108.4829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4108.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4114.8629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4117.8629 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4118.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4124.6229 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4127.6229 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4128.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4134.7629 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4137.7629 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4139.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4145.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4148.2829 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4149.2829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4150.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4156.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4157.7829 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4158.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4160.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4163.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4164.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4166.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4169.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4170.7829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4172.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4175.7829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4176.0996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4181.0996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4181.4162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4184.4162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4184.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4190.7962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4193.7962 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4194.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 8 | 133333.3333 | ACTION | 4202.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4208.5562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4211.5562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4212.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4218.6962 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4221.6962 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4223.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4229.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4232.2162 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4233.2162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4234.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4240.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4241.7162 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4242.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4244.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4247.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4248.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4250.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4253.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4254.7162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4256.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4259.7162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4260.0329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4265.0329 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4265.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4268.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4268.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 14 | 233333.3333 | ACTION | 4282.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4288.7296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4291.7296 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4292.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4298.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4301.4896 | TurbineInstallation
| WTIV | Delay | 26 | 433333.3333 | ACTION | 4327.4896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4328.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4334.6296 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4337.6296 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4339.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4345.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4348.1496 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4349.1496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4350.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4356.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4357.6496 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4358.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4360.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4363.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4364.6496 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 4370.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4372.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4375.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4376.6496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4378.1496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4381.6496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4381.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4385.2095 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4389.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4393.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 9 | 150000 | ACTION | 4402.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4406.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4410.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4414.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4415.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4417.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4418.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4422.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4426.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4430.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4434.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4438.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4440.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4441.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4443.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4447.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4451.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4455.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4459.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4463.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4464.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4466.2095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4467.7095 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4470.9527 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4475.9527 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4476.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4479.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4479.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4485.6494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4488.6494 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4489.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 4550.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4556.4094 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4559.4094 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4560.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4566.5494 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4569.5494 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4571.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4577.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4580.0694 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4581.0694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4582.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 23 | 383333.3333 | ACTION | 4605.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4611.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4612.5694 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4613.5694 | TurbineInstallation
| WTIV | Delay | 85 | 1416666.6667 | ACTION | 4698.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4700.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4702.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4705.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4706.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4708.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4711.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4712.5694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4714.0694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4717.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4717.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4722.886 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4723.2027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4726.2027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4726.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4732.5827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4735.5827 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4736.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4742.3427 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4745.3427 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4746.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4752.4827 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4755.4827 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4757.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4763.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4766.0027 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4767.0027 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4768.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4774.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4775.5027 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4776.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4778.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4781.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4782.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4784.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4787.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4788.5027 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4790.0027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4793.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4793.8194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4798.8194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4799.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4802.136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4802.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 32 | 533333.3333 | ACTION | 4834.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4840.516 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4843.516 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 4844.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4850.276 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4853.276 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 4854.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4860.416 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4863.416 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 4864.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 4870.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 4873.936 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4874.936 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 4876.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 4882.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 4883.436 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4884.436 | TurbineInstallation
| WTIV | Delay | 4 | 66666.6667 | ACTION | 4888.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4889.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4893.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4894.436 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 4896.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4897.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4901.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 4902.436 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 4903.936 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 4907.436 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 4907.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4910.996 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4914.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4918.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4922.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4926.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4930.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4932.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4933.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4935.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4939.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4943.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4947.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4951.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4955.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4956.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4958.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4959.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4963.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4967.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4971.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 4975.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 4979.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4981.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4982.996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 4984.496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 4987.7392 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 4992.7392 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 4993.0559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 4996.0559 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 4996.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5002.4359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5005.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5006.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5012.1959 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5015.1959 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5016.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5022.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5025.3359 | TurbineInstallation
| WTIV | Delay | 5 | 83333.3333 | ACTION | 5030.3359 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5031.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5037.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5040.8559 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5041.8559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5043.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5049.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5050.3559 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5051.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5052.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5056.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5057.3559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5058.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5062.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5063.3559 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 5065.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5066.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5070.3559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5070.6725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5075.6725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5075.9892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5078.9892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 5079.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5085.3692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5088.3692 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 5089.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5095.1292 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5098.1292 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 5099.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5105.2692 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5108.2692 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 5109.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 5115.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 5118.7892 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5119.7892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 5121.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 5127.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 5128.2892 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5129.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5130.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5134.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5135.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5136.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5140.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 5141.2892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 5142.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 5146.2892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 5146.6059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 5151.6059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 5151.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 5154.9225 | TurbineInstallation
| WTIV | Delay | 1255 | 20916666.6667 | ACTION | 6409.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6410.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6416.3025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6419.3025 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6420.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6426.0625 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6429.0625 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6430.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 1 | 16666.6667 | ACTION | 6431.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6437.2025 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6440.2025 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6441.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6447.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6450.7225 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6451.7225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6453.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6459.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6460.2225 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6461.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6462.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6466.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6467.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6468.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6472.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6473.2225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6474.7225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6478.2225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6478.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6481.7824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6485.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6489.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6493.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6497.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6501.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6503.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6504.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6506.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6508.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 6512.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6516.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6520.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6524.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6528.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6532.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6533.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6535.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6536.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6540.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6544.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6548.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6552.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6556.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6558.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6559.7824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6561.2824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6564.5257 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6569.5257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6569.8424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6572.8424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6573.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6579.2224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6582.2224 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6582.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6588.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6591.9824 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6593.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6599.1224 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6602.1224 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6603.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6609.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6612.6424 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6613.6424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6615.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6621.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6622.1424 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6623.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6624.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6628.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6629.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6630.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6634.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6635.1424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6636.6424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6640.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6640.459 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6645.459 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6645.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6648.7757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6649.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6655.1557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6658.1557 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6658.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 6 | 100000 | ACTION | 6664.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6670.9157 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6673.9157 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6675.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6681.0557 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6684.0557 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6685.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6691.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6694.5757 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6695.5757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6697.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6703.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6704.0757 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6705.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6706.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6710.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6711.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6712.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6716.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6717.0757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6718.5757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6722.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6722.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6727.3924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6727.709 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6730.709 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6731.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6737.089 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6740.089 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6740.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 17 | 283333.3333 | ACTION | 6757.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6763.849 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6766.849 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6767.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6773.989 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6776.989 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 6778.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6784.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 6787.509 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6788.509 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 6790.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 6796.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 6797.009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6798.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6799.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6803.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6804.009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6805.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6809.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 6810.009 | TurbineInstallation
| WTIV | Delay | 14 | 233333.3333 | ACTION | 6824.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 6825.509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 6829.009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 6829.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6832.5689 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6836.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6840.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6844.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6848.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6852.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6854.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6855.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6857.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6861.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6865.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6869.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6873.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6877.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6878.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6880.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6881.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6885.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6889.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6893.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 6897.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 6901.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6903.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6904.5689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 6906.0689 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 6909.3122 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 6911.3122 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 6916.3122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 6916.6288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6919.6288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 6920.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6926.0088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6929.0088 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 6929.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 54 | 900000 | ACTION | 6983.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6989.7688 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 6992.7688 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 6993.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 6999.9088 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7002.9088 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7004.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7010.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7013.4288 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7014.4288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7015.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7021.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7022.9288 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7023.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7025.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7028.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7029.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7031.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7034.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7035.9288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7037.4288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7040.9288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7041.2455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7046.2455 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7046.5622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7049.5622 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7049.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 43 | 716666.6667 | ACTION | 7092.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7098.9422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7101.9422 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7102.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7108.7022 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7111.7022 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7112.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7118.8422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7121.8422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7123.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7129.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7132.3622 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7133.3622 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7134.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7140.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7141.8622 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7142.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7144.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7147.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7148.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7150.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7153.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7154.8622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7156.3622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7159.8622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7160.1788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7165.1788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7165.4955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7168.4955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7168.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7174.8755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7177.8755 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7178.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7184.6355 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7187.6355 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7188.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7194.7755 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7197.7755 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7199.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7205.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7208.2955 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7209.2955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7210.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 19 | 316666.6667 | ACTION | 7229.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7235.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7236.7955 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7237.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7239.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7242.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7243.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7245.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7248.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7249.7955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7251.2955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7254.7955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7255.1122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7258.3554 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7262.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7266.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7270.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7274.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7278.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7279.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7281.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7282.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7286.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 9 | 150000 | ACTION | 7295.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7299.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7303.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7307.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7311.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7313.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7314.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7316.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7320.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7324.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7328.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7332.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7336.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7337.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7339.3554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7340.8554 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7344.0987 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7349.0987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7349.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7352.4153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7352.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7358.7953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7361.7953 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7362.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7368.5553 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7371.5553 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7372.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7378.6953 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7381.6953 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7383.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7389.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7392.2153 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7393.2153 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7394.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7400.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7401.7153 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7402.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7404.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 61 | 1016666.6667 | ACTION | 7465.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7468.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7469.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7471.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7474.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7475.7153 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7477.2153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7480.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7481.032 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7486.032 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7486.3487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7489.3487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7489.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7495.7287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7498.7287 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7499.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7505.4887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7508.4887 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7509.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7515.6287 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7518.6287 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7520.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 29 | 483333.3333 | ACTION | 7549.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7555.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7558.1487 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7559.1487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7560.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7566.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7567.6487 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7568.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7570.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7573.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7574.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7576.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 3 | 50000 | ACTION | 7579.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7582.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7583.6487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7585.1487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7588.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7588.9653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7593.9653 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7594.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7597.282 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7597.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 6 | 100000 | ACTION | 7603.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7609.662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7612.662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7613.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7619.422 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7622.422 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7623.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7629.562 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7632.562 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7634.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7640.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7643.082 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7644.082 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7645.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7651.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7652.582 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7653.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7655.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7658.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7659.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7661.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7664.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7665.582 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7667.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 7 | 116666.6667 | ACTION | 7674.082 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7677.582 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7677.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7681.1419 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7685.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7689.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7693.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7697.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7701.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7702.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7704.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7705.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7709.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7713.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7717.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7721.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7725.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7727.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7728.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7730.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7734.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7738.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7742.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7746.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 7750.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7751.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7753.1419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 7754.6419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7757.8851 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7762.8851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7763.2018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7766.2018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7766.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7772.5818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7775.5818 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7776.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7782.3418 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7785.3418 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7786.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7792.4818 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7795.4818 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7797.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7803.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7806.0018 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7807.0018 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7808.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7814.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7815.5018 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7816.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7818.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7821.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7822.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7824.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7827.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7828.5018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7830.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7833.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7833.8185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7838.8185 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7839.1351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7842.1351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7842.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7848.5151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7851.5151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7852.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7858.2751 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7861.2751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7862.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7868.4151 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7871.4151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7872.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7878.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7881.9351 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7882.9351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7884.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7890.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7891.4351 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7892.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7893.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7897.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7898.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7899.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7903.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7904.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7905.9351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7909.4351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7909.7518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 7914.7518 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 7915.0685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7918.0685 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 7918.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7924.4485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7927.4485 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 7928.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7934.2085 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7937.2085 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 7938.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7944.3485 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 7947.3485 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 7948.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 7954.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 7957.8685 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7958.8685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 7960.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 7966.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 7967.3685 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7968.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7969.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7973.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7974.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7975.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7979.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 7980.3685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 7981.8685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 7985.3685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 7985.6851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 7988.9284 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7992.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 7996.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8000.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8004.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8008.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8010.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8011.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8013.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8017.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8021.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8025.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8029.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8033.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8034.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8036.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8037.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8041.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8045.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 6 | 100000 | ACTION | 8051.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8055.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8059.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8063.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8065.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8066.9284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8068.4284 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8071.6716 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8076.6716 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8076.9883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8079.9883 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8080.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8085.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8091.3683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8094.3683 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8095.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8101.1283 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8104.1283 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8105.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8111.2683 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8114.2683 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8115.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8121.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8124.7883 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8125.7883 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8127.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 44 | 733333.3333 | ACTION | 8171.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8177.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8178.2883 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8179.2883 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8181.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8182.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8186.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8187.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8188.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8192.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8193.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8194.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8198.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8198.605 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8203.605 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8203.9216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8206.9216 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8207.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8213.3016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8216.3016 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8217.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8223.0616 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8226.0616 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8227.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8233.2016 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8236.2016 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8237.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8243.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8246.7216 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8247.7216 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8249.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8255.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8256.2216 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8257.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8258.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8262.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8263.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8264.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8268.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8269.2216 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8270.7216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8274.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8274.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8279.5383 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8279.855 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8282.855 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8283.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 34 | 566666.6667 | ACTION | 8317.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8323.235 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8326.235 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8326.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 15 | 250000 | ACTION | 8341.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8347.995 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8350.995 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8352.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8358.135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8361.135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8362.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8368.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8371.655 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8372.655 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8374.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 5 | 83333.3333 | ACTION | 8379.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8385.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8386.155 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8387.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8388.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8392.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8393.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8394.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8398.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8399.155 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8400.655 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8404.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8404.4716 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8407.7149 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8411.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8415.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8419.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 29 | 483333.3333 | ACTION | 8448.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8452.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8456.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8458.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8459.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8461.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8465.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8469.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8473.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8477.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8481.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8482.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8484.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8485.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8489.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8493.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8497.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8501.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8505.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8507.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8508.7149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8510.2149 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8513.4581 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8518.4581 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8518.7748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8521.7748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8522.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8528.1548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8531.1548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8531.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8537.9148 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8540.9148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8542.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8544.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8550.0548 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8553.0548 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8554.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8560.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8563.5748 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8564.5748 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8566.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8572.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8573.0748 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8574.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8575.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8579.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8580.0748 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8602.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8603.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8607.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8608.0748 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8609.5748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8613.0748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8613.3915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8618.3915 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8618.7081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8621.7081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8622.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8628.0881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8631.0881 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8631.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8637.8481 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8640.8481 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8641.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8647.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8650.9881 | TurbineInstallation
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8672.9881 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8674.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 47 | 783333.3333 | ACTION | 8721.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8727.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8730.5081 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8731.5081 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8733.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8739.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8740.0081 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8741.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8742.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8746.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8747.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8748.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8752.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8753.0081 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8754.5081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8758.0081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8758.3248 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8763.3248 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8763.6415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8766.6415 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8767.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8773.0215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8776.0215 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8776.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8782.7815 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8785.7815 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8786.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8792.9215 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8795.9215 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8797.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8803.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8806.4415 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8807.4415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8808.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8814.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8815.9415 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8816.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8818.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8821.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8822.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8824.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8827.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8828.9415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8830.4415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 8833.9415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 8834.2581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8837.5014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8841.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8845.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8849.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8853.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8857.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8859.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8860.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8862.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8866.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8870.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8874.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8878.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8882.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8883.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8885.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8886.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8890.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8894.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8898.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 8902.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 8906.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8908.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8909.5014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 8911.0014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 8914.2446 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 8919.2446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 8919.5613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8922.5613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 8922.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8928.9413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8931.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 8932.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8938.7013 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8941.7013 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 8942.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8948.8413 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 8951.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 8953.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 8959.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 8962.3613 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8963.3613 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 8964.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 8970.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 8971.8613 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 8972.8613 | TurbineInstallation
| WTIV | Delay | 2 | 33333.3333 | ACTION | 8974.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 8976.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 22 | 366666.6667 | ACTION | 8998.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9001.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9002.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9004.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9007.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9008.8613 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9010.3613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9013.8613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9014.1779 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9019.1779 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9019.4946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9022.4946 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9022.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9028.8746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9031.8746 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9032.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9038.6346 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9041.6346 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9042.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9048.7746 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9051.7746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9053.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9059.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9062.2946 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9063.2946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9064.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9070.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9071.7946 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9072.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9074.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9077.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9078.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9080.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9083.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9084.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9086.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9089.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9090.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9095.1113 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9095.4279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9098.4279 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9098.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9104.8079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9107.8079 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9108.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 10 | 166666.6667 | ACTION | 9118.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9124.5679 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9127.5679 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9128.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9134.7079 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9137.7079 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9139.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9145.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9148.2279 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9149.2279 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9150.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9156.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9157.7279 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9158.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9160.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9164.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9167.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9168.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9170.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9173.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9174.7279 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9176.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9180.2279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9183.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9184.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9187.2878 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9191.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9195.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9199.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9203.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9207.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9208.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9210.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9211.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9215.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9219.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9223.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9227.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9231.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9233.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9234.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9236.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9240.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9244.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9248.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9252.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9256.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9257.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9259.2878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9260.7878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9264.0311 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9269.0311 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9269.3478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9272.3478 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9272.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9278.7278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9281.7278 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9282.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9288.4878 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9291.4878 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9292.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9298.6278 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9301.6278 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9303.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9309.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9312.1478 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9313.1478 | TurbineInstallation
| WTIV | Delay | 6 | 100000 | ACTION | 9319.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9320.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 8 | 133333.3333 | ACTION | 9328.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9334.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9335.6478 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9336.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9338.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9341.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9342.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9344.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9347.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9348.6478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9350.1478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9353.6478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9353.9644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9358.9644 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9359.2811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9362.2811 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9362.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9368.6611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9371.6611 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9372.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9378.4211 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9381.4211 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9382.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9388.5611 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9391.5611 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9393.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9399.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9402.0811 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9403.0811 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9404.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9408.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9414.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9415.5811 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9416.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9418.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9421.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9422.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9424.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9427.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9428.5811 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9430.0811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9433.5811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9433.8978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9438.8978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9439.2144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9442.2144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9442.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9448.5944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9451.5944 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9452.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9458.3544 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9461.3544 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9462.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9468.4944 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9471.4944 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9473.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9479.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9482.0144 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9483.0144 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9484.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9490.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9491.5144 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9492.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9494.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9497.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9498.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9500.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9503.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9504.5144 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9506.0144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9509.5144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9509.8311 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9513.0743 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9517.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9521.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 4 | 66666.6667 | ACTION | 9525.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9529.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9533.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9537.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9538.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9540.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9541.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9545.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9549.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9553.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9557.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9561.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9563.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9564.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9566.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9570.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9574.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9578.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9582.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9586.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9587.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9589.0743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9590.5743 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9593.8176 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9598.8176 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9599.1342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9602.1342 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9602.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9608.5142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9611.5142 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9612.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9618.2742 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9621.2742 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9622.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9628.4142 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9631.4142 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9632.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9638.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9641.9342 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9642.9342 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9644.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9650.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9651.4342 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9652.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9653.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9657.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9658.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9659.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9663.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9664.4342 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9665.9342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9669.4342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9669.7509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9674.7509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9675.0676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9678.0676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9678.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9684.4476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9687.4476 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9688.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9694.2076 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9697.2076 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9698.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9704.3476 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9707.3476 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9708.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9714.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9717.8676 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9718.8676 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9720.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Delay | 1 | 16666.6667 | ACTION | 9721.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9727.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9728.3676 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9729.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9730.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9734.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9735.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9736.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9740.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9741.3676 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9742.8676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9746.3676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9746.6842 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9751.6842 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9752.0009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9755.0009 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9755.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9761.3809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9764.3809 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9765.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9771.1409 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9774.1409 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9775.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9781.2809 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9784.2809 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9785.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9791.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9794.8009 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9795.8009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9797.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9803.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9804.3009 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9805.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9806.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9810.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9811.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9812.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9816.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9817.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9818.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9822.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9822.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9825.8608 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9829.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9833.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9837.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9841.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9845.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9847.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9848.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9850.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9854.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9858.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9862.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9866.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9870.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9871.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9873.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9874.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9878.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9882.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9886.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 9890.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 9894.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9896.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9897.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 9899.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 9902.6041 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9907.6041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9907.9207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9910.9207 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9911.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9917.3007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9920.3007 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9921.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9927.0607 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9930.0607 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 9931.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9937.2007 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9940.2007 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 9941.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9947.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 9950.7207 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9951.7207 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 9953.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 9959.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 9960.2207 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9961.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9962.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9966.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9967.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9968.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9972.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 9973.2207 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 9974.7207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 9978.2207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 9978.5374 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 9983.5374 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 9983.8541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9986.8541 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 9987.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 9993.2341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 9996.2341 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 9996.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10002.9941 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10005.9941 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10007.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10013.1341 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10016.1341 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10017.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10023.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10026.6541 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10027.6541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10029.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10035.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10036.1541 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10037.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10038.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10042.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10043.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10044.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10048.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10049.1541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10050.6541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10054.1541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10054.4707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 10059.4707 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 10059.7874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10062.7874 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10063.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10069.1674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10072.1674 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10072.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10078.9274 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10081.9274 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10083.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10089.0674 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10092.0674 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10093.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10099.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10102.5874 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10103.5874 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10105.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10111.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10112.0874 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10113.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10114.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10118.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10119.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10120.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10124.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10125.0874 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10126.5874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10130.0874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10130.4041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10133.6473 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10137.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10141.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10145.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10149.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 10153.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10155.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10156.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10158.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10162.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10166.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10170.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Tower Section | 4 | 66666.6667 | ACTION | 10174.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Nacelle | 4 | 66666.6667 | ACTION | 10178.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10179.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10181.1473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Fasten Blade | 1.5 | 25000 | ACTION | 10182.6473 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Transit | 3.2432 | 54054.0541 | ACTION | 10185.8906 | TurbineInstallation
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 10190.8906 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 10191.2072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10194.2072 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10194.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10200.5872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10203.5872 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10204.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10210.3472 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10213.3472 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10214.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10220.4872 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10223.4872 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10225.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10231.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10234.0072 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10235.0072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10236.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10242.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10243.5072 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10244.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10246.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10249.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10250.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10252.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10255.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10256.5072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10258.0072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10261.5072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10261.8239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Position Onsite | 5 | 83333.3333 | ACTION | 10266.8239 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 5277.7778 | ACTION | 10267.1406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10270.1406 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 6333.3333 | ACTION | 10270.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10276.5206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10279.5206 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 12666.6667 | ACTION | 10280.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10286.2806 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10289.2806 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 19000 | ACTION | 10290.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10296.4206 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Tower Section | 3 | 50000 | ACTION | 10299.4206 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 25333.3333 | ACTION | 10300.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Tower Section | 6 | 100000 | ACTION | 10306.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Nacelle | 3 | 50000 | ACTION | 10309.9406 | TurbineInstallation
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10310.9406 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 25000 | ACTION | 10312.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Nacelle | 6 | 100000 | ACTION | 10318.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Reequip | 1 | 16666.6667 | ACTION | 10319.4406 | TurbineInstallation
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10320.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10321.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10325.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10326.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10327.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10331.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Release Blade | 1 | 16666.6667 | ACTION | 10332.4406 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 25000 | ACTION | 10333.9406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Attach Blade | 3.5 | 58333.3333 | ACTION | 10337.4406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2
| WTIV | Jackdown | 0.31667 | 5277.7778 | ACTION | 10337.7572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation | 5 | 2