## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 43.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 123.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 80.0008 | 833342.0226 | ACTION | 123.2441 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 163.2441 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 168.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 169.6607 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 172.6607 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 173.3838 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 173.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 174.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 51 | 255000 | ACTION | 211 | MonopileInstallation
| WTIV | Delay | 46 | 479166.6667 | ACTION | 220.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 235.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 237.3871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 238.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 239.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 243.3871 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 248.8037 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 254.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 254.2441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 288.8037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 294.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 295.2204 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 298.2204 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 298.9435 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 298.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 299.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 314.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 316.9467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 317.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 318.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 322.9467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 328.3634 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 368.3634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 373.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 374.78 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 377.78 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 378.5031 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 378.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 379.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 394.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 396.5064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 397.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 398.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 402.5064 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 407.923 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 46 | 479166.6667 | ACTION | 453.923 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 493.923 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 499.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 500.3397 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 503.3397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 504.0628 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 504.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 505.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 520.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 522.066 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 398.8219 | 1994109.644 | ACTION | 522.066 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 522.0668 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 523.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 524.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 528.066 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 533.4827 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 565.3101 | MonopileInstallation
| Feeder 1 | Queue | 311.066 | 1555330.0311 | ACTION | 565.3101 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 565.3101 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 577.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 585.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 597.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 605.3101 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 605.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 610.7268 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 611.7268 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 614.7268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 615.4498 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 615.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 616.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 617.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 625.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 631.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 633.4531 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 634.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 635.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 637.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 639.4531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 644.8697 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 645.3101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 684.8697 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 688.5533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 688.5542 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 690.2864 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 691.2864 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 694.2864 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 695.0095 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 695.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 696.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 711.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 713.0127 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 714.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 715.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 719.0127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 724.4294 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 764.4294 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 769.846 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 770.846 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 773.846 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 774.5691 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 774.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 775.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 790.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 792.5724 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 793.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 794.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 798.5724 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 803.989 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 843.989 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 849.4057 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 850.4057 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 853.4057 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 854.1288 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 854.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 855.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 862.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 877.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 879.132 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 313.8219 | 1569109.644 | ACTION | 879.132 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 879.1328 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 880.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 881.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 6 | 30000 | ACTION | 885.1328 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 887.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 891.132 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 896.5487 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 928.3761 | MonopileInstallation
| Feeder 0 | Queue | 239.8219 | 1199109.644 | ACTION | 928.3761 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 928.3761 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 940.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 948.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 960.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 968.3761 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 968.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 973.7928 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 974.7928 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 977.7928 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 978.5158 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 978.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 979.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 980.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 988.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 994.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 996.5191 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 997.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 998.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1000.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1002.5191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1007.9357 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1008.3761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1047.9357 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1051.6193 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1051.6202 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1053.3524 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1054.3524 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1057.3524 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1058.0755 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1058.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1059.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1074.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1076.0787 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1077.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1078.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1082.0787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1087.4954 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1127.4954 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1132.9121 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1133.9121 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1136.9121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1137.6351 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1137.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1138.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1153.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1155.6384 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1156.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1157.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1161.6384 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1167.055 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1207.055 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1212.4717 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1213.4717 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1216.4717 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1217.1948 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1217.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1218.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1233.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1235.198 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 306.8219 | 1534109.644 | ACTION | 1235.198 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1235.1989 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1236.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1237.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1241.198 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1246.6147 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1278.4421 | MonopileInstallation
| Feeder 1 | Queue | 226.8219 | 1134109.644 | ACTION | 1278.4421 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1278.4421 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1290.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1298.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1310.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1318.4421 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1318.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1323.8588 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1324.8588 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1327.8588 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1328.5818 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1328.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1329.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1330.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1338.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1344.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1346.5851 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1347.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1348.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1350.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1352.5851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1358.0017 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1358.4421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1398.0017 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1401.6853 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1401.6862 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1403.4184 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1404.4184 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1407.4184 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 1416.4184 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1417.1415 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1417.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1418.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1433.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1435.1447 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1436.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1437.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1441.1447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1446.5614 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1486.5614 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1491.9781 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1492.9781 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1495.9781 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1496.7011 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1496.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1497.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1512.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1514.7044 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1515.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1516.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1520.7044 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1526.121 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1566.121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1571.5377 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1572.5377 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1575.5377 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1576.2608 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1576.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1577.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1592.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1594.264 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 315.8219 | 1579109.644 | ACTION | 1594.264 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1594.2649 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1595.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1596.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1600.264 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1605.6807 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1637.5081 | MonopileInstallation
| Feeder 0 | Queue | 235.8219 | 1179109.644 | ACTION | 1637.5081 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1637.5081 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1649.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1657.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1669.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1677.5081 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1677.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1682.9248 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1683.9248 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1686.9248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1687.6478 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1687.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1688.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1689.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1697.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1703.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1705.6511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1706.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1707.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1709.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1711.6511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1717.0678 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1717.5081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1757.0678 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1760.7513 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1760.7522 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1762.4844 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1763.4844 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1766.4844 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1767.2075 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1767.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1768.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1783.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1785.2107 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1786.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1787.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1791.2107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1796.6274 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1836.6274 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1842.0441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1843.0441 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1846.0441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1846.7671 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1846.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1847.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1862.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1864.7704 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1865.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1866.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1870.7704 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1876.187 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 1916.187 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1921.6037 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1922.6037 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1925.6037 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1926.3268 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1926.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1927.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1942.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1944.33 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 306.8219 | 1534109.644 | ACTION | 1944.33 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1944.3309 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1945.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1946.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1950.33 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1955.7467 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1987.5741 | MonopileInstallation
| Feeder 1 | Queue | 226.8219 | 1134109.644 | ACTION | 1987.5741 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1987.5741 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1999.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2007.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2019.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2027.5741 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2027.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2032.9908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2033.9908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2036.9908 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2037.7138 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2037.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2038.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2039.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2047.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2053.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2055.7171 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2056.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2057.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2059.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2061.7171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2067.1338 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2067.5741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2107.1338 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2110.8174 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2110.8182 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2112.5504 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2113.5504 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2116.5504 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2117.2735 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2117.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2118.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2133.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2135.2767 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2136.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2137.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2141.2767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2146.6934 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2186.6934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2192.1101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2193.1101 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2196.1101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2196.8331 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2196.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2197.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2212.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2214.8364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2215.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2216.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2220.8364 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2226.2531 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2266.2531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2271.6697 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2272.6697 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2275.6697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2276.3928 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2276.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2277.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2292.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2294.396 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 306.8219 | 1534109.644 | ACTION | 2294.396 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2294.3969 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2295.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2296.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2300.396 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2305.8127 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2337.6401 | MonopileInstallation
| Feeder 0 | Queue | 226.8219 | 1134109.644 | ACTION | 2337.6401 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2337.6401 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2349.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2357.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2369.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2377.6401 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2377.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2383.0568 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2384.0568 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2387.0568 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2387.7798 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2387.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2388.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2389.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2397.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2403.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2405.7831 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2406.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2407.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2409.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2411.7831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2417.1998 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2417.6401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2457.1998 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2460.8834 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2460.8842 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2462.6164 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2463.6164 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2466.6164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2467.3395 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2467.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2468.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2483.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2485.3427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2486.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2487.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2491.3427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2496.7594 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2536.7594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2542.1761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2543.1761 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2546.1761 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2546.8991 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2546.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2547.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2562.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2564.9024 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2565.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2566.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2570.9024 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2576.3191 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2616.3191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2621.7357 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2622.7357 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2625.7357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2626.4588 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2626.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2627.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2642.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2644.462 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 306.8219 | 1534109.644 | ACTION | 2644.462 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2644.4629 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2645.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2646.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2650.462 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2655.8787 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2687.7061 | MonopileInstallation
| Feeder 1 | Queue | 226.8219 | 1134109.644 | ACTION | 2687.7061 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2687.7061 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2699.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2707.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2719.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2727.7061 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2727.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2733.1228 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2734.1228 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2737.1228 | MonopileInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 2750.1228 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2750.8459 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2750.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2751.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 44 | 220000 | ACTION | 2771.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 2780.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2783.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2791.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2795.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2797.8491 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2798.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2799.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2803.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2803.8491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2809.2658 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2811.7061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2849.2658 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2854.6824 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2854.9494 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2854.9502 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2855.6824 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2858.6824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2859.4055 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2859.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2860.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2875.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2877.4088 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2878.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2879.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2883.4088 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2888.8254 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 2928.8254 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2934.2421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2935.2421 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2938.2421 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2938.9652 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2938.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2939.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2954.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2956.9684 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2957.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2958.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2962.9684 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2968.3851 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3008.3851 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3013.8017 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3014.8017 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 19 | 197916.6667 | ACTION | 3033.8017 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3036.8017 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3037.5248 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3037.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3038.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 3051.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3066.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3068.528 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 380.8219 | 1904109.644 | ACTION | 3068.528 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3068.5289 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3069.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3070.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3074.528 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3079.9447 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3111.7721 | MonopileInstallation
| Feeder 0 | Queue | 256.8219 | 1284109.644 | ACTION | 3111.7721 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 3111.7721 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3123.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3131.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3143.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3151.7721 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3151.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3157.1888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3158.1888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3161.1888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3161.9119 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3161.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3162.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3163.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3171.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3177.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3179.9151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3180.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3181.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3183.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3185.9151 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3191.3318 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3191.7721 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3231.3318 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3235.0154 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3235.0162 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3236.7484 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3237.7484 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3240.7484 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3241.4715 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3241.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3242.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3257.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3259.4748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3260.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3261.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3265.4748 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3270.8914 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3310.8914 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3316.3081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3317.3081 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3320.3081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3321.0312 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3321.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3322.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 30 | 312500 | ACTION | 3352.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3367.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3369.0344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3370.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3371.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3375.0344 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3380.4511 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3420.4511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3425.8677 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3426.8677 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3429.8677 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3430.5908 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3430.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3431.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 3435.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3450.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3452.5941 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 340.8219 | 1704109.644 | ACTION | 3452.5941 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3452.5949 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3453.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3454.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3458.5941 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3464.0107 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3495.8381 | MonopileInstallation
| Feeder 1 | Queue | 260.8219 | 1304109.644 | ACTION | 3495.8381 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 3495.8381 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3507.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3515.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3527.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3535.8381 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3535.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3541.2548 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3542.2548 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3545.2548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3545.9779 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3545.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3546.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3547.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3555.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3561.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3563.9811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3564.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3565.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3567.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3569.9811 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3575.3978 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3575.8381 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3615.3978 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3619.0814 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3619.0822 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3620.8144 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3621.8144 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3624.8144 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 3627.8144 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3628.5375 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3628.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3629.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3630.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3645.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3647.5408 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3648.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3649.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3653.5408 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3658.9574 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 45 | 468750 | ACTION | 3703.9574 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3743.9574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3749.3741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3750.3741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3753.3741 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 3768.3741 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3769.0972 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3769.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3770.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3785.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3787.1004 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3788.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3789.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3793.1004 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3798.5171 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 36 | 375000 | ACTION | 3834.5171 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3874.5171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3879.9337 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3880.9337 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3883.9337 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3884.6568 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3884.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3885.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 3900.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3902.6601 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 406.8219 | 2034109.644 | ACTION | 3902.6601 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3902.6609 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3903.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3904.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3908.6601 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3914.0767 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3945.9041 | MonopileInstallation
| Feeder 0 | Queue | 326.8219 | 1634109.644 | ACTION | 3945.9041 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 3945.9041 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3957.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3965.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3977.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 3985.9041 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 3985.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3991.3208 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3992.3208 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3995.3208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3996.0439 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3996.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3997.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 3997.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4005.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 43 | 215000 | ACTION | 4048.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 4060.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 64 | 666666.6667 | ACTION | 4061.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 4068.9041 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4076.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4078.0471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4079.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4080.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 4083.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4087.0471 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4092.4638 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4112.1474 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4112.1482 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4132.4638 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4137.8805 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4138.8805 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4141.8805 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4142.6035 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4142.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4143.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4158.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4160.6068 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4161.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4162.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4166.6068 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4172.0234 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4212.0234 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4217.4401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4218.4401 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4221.4401 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4222.1632 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4222.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4223.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4238.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4240.1664 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4241.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4242.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4246.1664 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4251.5831 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 27 | 281250 | ACTION | 4278.5831 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4318.5831 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4323.9998 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4324.9998 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4327.9998 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4328.9998 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4329.7228 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4329.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4330.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4345.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4347.7261 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 401.8219 | 2009109.644 | ACTION | 4347.7261 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4347.7269 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4348.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4349.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4353.7261 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4359.1427 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4390.9701 | MonopileInstallation
| Feeder 1 | Queue | 278.8219 | 1394109.644 | ACTION | 4390.9701 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 4390.9701 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay | 13 | 135416.6667 | ACTION | 4403.9701 | MonopileInstallation
| Feeder 0 | Delay | 17 | 85000 | ACTION | 4407.9701 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4419.9701 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4427.9701 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 4439.9701 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4443.9701 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 4447.9701 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4449.3868 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4450.3868 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4453.3868 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4454.1099 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4454.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4455.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4470.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4472.1131 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4473.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4474.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4478.1131 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4483.5298 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 68 | 708333.3333 | ACTION | 4551.5298 | MonopileInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4591.5298 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4596.9465 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4597.9465 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4598.9465 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4601.9465 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 4604.9465 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4605.6695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4606.6695 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4606.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4607.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 96 | 1000000 | ACTION | 4703.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4718.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4720.6728 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4721.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4722.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4726.6728 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4732.0894 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4772.0894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4777.5061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4778.5061 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4781.5061 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4782.2292 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4782.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4783.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4798.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4800.2324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4801.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4802.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 33 | 343750 | ACTION | 4835.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4839.2324 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4844.6491 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 4884.6491 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4890.0658 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4891.0658 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4894.0658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4894.7888 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4894.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4895.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4897.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 4912.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4914.7921 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 523.8219 | 2619109.644 | ACTION | 4914.7921 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4914.7929 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4915.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4916.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4920.7921 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4926.2087 | MonopileInstallation | MonopileInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 4958.0362 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 4958.0362 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 4958.0362 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4958.0362 | MonopileInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4960.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4962.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4964.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4966.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4968.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4968.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4969.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4970.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4972.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4974.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4976.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4978.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4980.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4981.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4981.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4982.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4984.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4986.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4988.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4990.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4992.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4993.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4994.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4994.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 36.75 | 183750 | ACTION | 4994.7862 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4996.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4998.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5000.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5001.2794 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5002.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5004.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5005.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5006.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5007.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5009.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5011.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5013.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5015.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5017.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5017.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5018.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5019.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5021.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5023.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5025.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5027.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5029.2862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5030.0362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5030.7862 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5031.5362 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 5 | 25000 | ACTION | 5036.5362 | TurbineInstallation
| Feeder 0 | Delay | 42 | 210000 | ACTION | 5036.7862 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 5079.7794 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 5079.7802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 78.5008 | 817717.0226 | ACTION | 5079.7802 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 5080.0294 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 5080.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 5119.7802 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5125.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5126.1969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5126.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5128.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5129.5769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5130.3369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5132.3369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5133.3369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5134.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5136.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5137.4769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5138.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5140.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5141.9969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5142.9969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5144.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5146.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5147.4969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5147.9969 | TurbineInstallation
| WTIV | Delay | 1262 | 13145833.3333 | ACTION | 6409.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6411.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6412.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6413.4969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6414.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6416.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6416.9969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6418.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6419.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6425.4136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6465.4136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6470.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6471.8302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6472.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6474.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6475.2102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6475.9702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6477.9702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6478.9702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6480.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6482.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6483.1102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6484.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6486.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6487.6302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6488.6302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6490.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6492.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6493.1302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6493.6302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6495.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6496.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6497.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6498.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6500.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6500.6302 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6516.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6518.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6519.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6525.0469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6565.0469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6570.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6571.4636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6571.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6573.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6574.8436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6575.6036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6577.6036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6578.6036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6579.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6581.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6582.7436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6584.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6586.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6587.2636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6588.2636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6589.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6591.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6592.7636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6593.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6594.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6596.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6596.7636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6598.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6599.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6600.2636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 1520.4833 | 7602416.6667 | ACTION | 6600.2636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 1520.2333 | 7601166.6667 | ACTION | 6600.2636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6600.2644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6601.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6603.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6608.6802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6643.5076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6645.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6647.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6648.6802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6649.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6651.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6653.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6654.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6654.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6655.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6655.0969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6655.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6655.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6657.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6657.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6658.4769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6659.2369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6659.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6661.2369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6661.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6662.2369 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6663.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6664.2369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 1 | 5000 | ACTION | 6664.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6665.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6666.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6667.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6667.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6668.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6668.3769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6669.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6669.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6671.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6671.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6672.8969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6673.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6673.8969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6675.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6675.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6677.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6677.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6678.3969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6678.8969 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6679.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6679.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6680.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6680.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6681.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6681.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6682.3969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6683.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6685.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6685.8969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6687.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6688.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6694.3136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6724.5009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6724.5017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6734.3136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6739.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6740.7302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6741.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6757.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6759.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6760.1102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6760.8702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6762.8702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6763.8702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6765.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6767.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6768.0102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6769.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6771.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6772.5302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6773.5302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6775.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6777.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6778.0302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6778.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6780.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6781.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6782.0302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6783.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6785.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6785.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6787.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6788.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6793.9469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 27 | 281250 | ACTION | 6820.9469 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6860.9469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6866.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6867.3636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6867.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6869.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6870.7436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6871.5036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6873.5036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6874.5036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6875.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6877.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6878.6436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6880.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6882.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6883.1636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6884.1636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6885.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6887.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6888.6636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6889.1636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6890.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6892.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6892.6636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6894.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6895.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6896.1636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 295.9 | 1479500 | ACTION | 6896.1636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 171.6618 | 858309.2259 | ACTION | 6896.1636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6896.1644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6897.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6899.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6904.5802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 15 | 75000 | ACTION | 6911.1644 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 6911.5802 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 6951.5802 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6954.4076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6956.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6956.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6957.9969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6958.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6960.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6962.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6964.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 1 | 5000 | ACTION | 6965.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6966.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 2 | 10000 | ACTION | 6968.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6968.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6969.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6971.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6973.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6975.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 18 | 187500 | ACTION | 6975.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6976.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6977.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6978.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6979.3769 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6979.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6980.1369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6980.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6981.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6981.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 6983.1369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6983.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6985.1369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6985.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6986.1369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6987.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6987.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6989.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6989.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6990.2769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6991.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6991.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6992.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6993.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6993.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6994.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6994.7969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6995.7969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6997.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6999.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7000.2969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7000.7969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7002.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7003.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7004.2969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7005.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7007.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7007.7969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7009.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7010.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7016.2136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7037.4009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7037.4017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7056.2136 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7059.2136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7064.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7065.6302 | TurbineInstallation
| WTIV | Delay | 27 | 281250 | ACTION | 7092.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7093.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7095.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7096.0102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7096.7702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7098.7702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7099.7702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7100.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7102.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7103.9102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7105.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7107.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7108.4302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7109.4302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7110.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7112.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7113.9302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7114.4302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7115.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7117.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7117.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7119.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7120.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7121.4302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7122.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7124.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7129.8469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7169.8469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7175.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7176.2636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7176.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7178.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7179.6436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7180.4036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7182.4036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7183.4036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7184.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7186.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7187.5436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7189.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7191.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7192.0636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7193.0636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7194.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7196.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7197.5636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7198.0636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7199.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7201.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7201.5636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7203.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7204.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7205.0636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 308.9 | 1544500 | ACTION | 7205.0636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 167.6618 | 838309.2259 | ACTION | 7205.0636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7205.0644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7206.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7208.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 13 | 135416.6667 | ACTION | 7221.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 16 | 80000 | ACTION | 7221.0644 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7226.4802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7264.3076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7266.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7266.4802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7268.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7270.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7271.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7272.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7272.8969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7273.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7274.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7275.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7275.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7275.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7276.2769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7276.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7277.0369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7278.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7279.0369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7280.0369 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7280.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7281.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7282.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7283.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7284.1769 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7284.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7286.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 7288.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7289.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 6 | 30000 | ACTION | 7295.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7296.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7296.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 14 | 145833.3333 | ACTION | 7298.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7298.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7299.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7300.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7302.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7304.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7306.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7306.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7307.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7308.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7308.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7309.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7309.6969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7310.6969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7312.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7314.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7315.1969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7315.6969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7317.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7318.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7319.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7320.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7322.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7322.6969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7324.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7325.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7331.1136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7352.3009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7352.3017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7371.1136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7376.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7377.5302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7377.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7379.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7380.9102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7381.6702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7383.6702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7384.6702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7385.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7387.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7388.8102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7390.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7392.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7393.3302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7394.3302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7395.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7397.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7398.8302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7399.3302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7400.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7402.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7402.8302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7404.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 61 | 635416.6667 | ACTION | 7465.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7466.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7467.3302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7468.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7470.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7475.7469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7515.7469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7521.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7522.1636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7522.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7524.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7525.5436 | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 7549.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7550.3036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7552.3036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7553.3036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7554.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7556.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7557.4436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7558.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7560.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7561.9636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7562.9636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7564.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7566.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7567.4636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7567.9636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7569.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7570.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7571.4636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7572.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7574.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7574.9636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 369.9 | 1849500 | ACTION | 7574.9636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 222.6618 | 1113309.2259 | ACTION | 7574.9636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7574.9644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7576.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7577.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7583.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 14 | 70000 | ACTION | 7588.9644 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7623.3802 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7628.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7629.7969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7630.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7632.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7632.2076 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7633.1769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7633.9369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7634.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7635.9369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7636.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7636.9369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7638.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7638.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7640.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7640.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7641.0769 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7642.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7642.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7642.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7643.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7644.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7644.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7645.5969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7646.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7646.5969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7648.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7648.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7650.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7650.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7651.0969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7651.5969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7652.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7653.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7654.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7654.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7655.0969 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7655.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7655.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7656.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7656.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7658.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7658.5969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7658.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7660.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7660.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7661.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7662.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7664.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7666.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7667.0136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7667.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7668.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7668.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7707.0136 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7712.2009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7712.2017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7712.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7713.4302 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7714.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7714.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7716.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7717.8102 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7724.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7725.5702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7727.5702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7728.5702 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7731.5702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7732.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7734.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7735.7102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7737.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7739.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7740.2302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7741.2302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7742.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7744.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7745.7302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7746.2302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7747.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7749.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7749.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7751.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7752.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7753.2302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7754.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7756.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7761.6469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7801.6469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7807.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7808.0636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7808.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7810.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7811.4436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7812.2036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7814.2036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7815.2036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7816.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7818.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7819.3436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7820.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7822.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7823.8636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7824.8636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7826.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7828.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7829.3636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7829.8636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7831.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7832.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7833.3636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7834.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7836.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7836.8636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 261.9 | 1309500 | ACTION | 7836.8636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 124.6618 | 623309.2259 | ACTION | 7836.8636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7836.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7838.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7839.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7845.2802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7880.1076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7882.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7884.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7885.2802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7886.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7888.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7890.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7890.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7890.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7891.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7891.6969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7892.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7892.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7894.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7894.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7895.0769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7895.8369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7896.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7897.8369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7898.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7898.8369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7899.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7900.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7901.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7902.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7902.9769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7903.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7903.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7904.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7904.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7906.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7906.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7907.4969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7908.4969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7908.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7909.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7910.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7911.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7912.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7912.9969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7913.4969 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7914.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7914.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7915.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7916.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7916.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7916.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7916.9969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7918.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7919.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7920.4969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7921.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7923.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7928.9136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7960.1009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7960.1017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 7968.9136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7974.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7975.3302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7975.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7977.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7978.7102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7979.4702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7981.4702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7982.4702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7983.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7985.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7986.6102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7988.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7990.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7991.1302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7992.1302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7993.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7995.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7996.6302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7997.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7998.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8000.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8000.6302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8002.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8003.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8004.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8005.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8007.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8012.5469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 39 | 406250 | ACTION | 8051.5469 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8091.5469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8096.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8097.9636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8098.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8100.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8101.3436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8102.1036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8104.1036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8105.1036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8106.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8108.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8109.2436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8110.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8112.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8113.7636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8114.7636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8116.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8118.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8119.2636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8119.7636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8121.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8122.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8123.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8124.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8126.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8126.7636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 289.9 | 1449500 | ACTION | 8126.7636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 166.6618 | 833309.2259 | ACTION | 8126.7636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8126.7644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8128.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 43 | 447916.6667 | ACTION | 8171.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8172.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 50 | 250000 | ACTION | 8176.7644 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8178.1802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8218.1802 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8220.0076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8222.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8223.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8224.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8224.5969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8224.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8226.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8226.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8227.9769 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8228.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8228.7369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8230.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8230.7369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8230.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8231.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8231.7369 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8232.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8232.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8234.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8234.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8235.8769 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8236.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8237.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8238.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8239.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8240.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8240.3969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8241.3969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8242.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8242.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8243.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8243.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8244.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8244.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8245.8969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8246.3969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8246.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8247.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8248.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8249.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8249.8969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8250.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8251.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8252.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8252.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8253.3969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8254.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8254.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8255.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8256.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8256.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8256.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8261.8136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8300.0009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8300.0017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8301.8136 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 8317.8136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8323.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8324.2302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8324.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8326.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8327.6102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8328.3702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8330.3702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8331.3702 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 8341.3702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8342.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8344.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8345.5102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8347.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8349.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8350.0302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8351.0302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8352.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8354.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8355.5302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8356.0302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8357.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8359.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8359.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8361.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8362.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8363.0302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8364.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8366.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8371.4469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8411.4469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8416.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8417.8636 | TurbineInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 8451.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8452.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8454.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8455.2436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8456.0036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8458.0036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8459.0036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8460.1436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8462.1436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8463.1436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8464.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8466.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8467.6636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8468.6636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8470.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8472.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8473.1636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8473.6636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8475.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8476.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8477.1636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8478.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8480.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8480.6636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 353.9 | 1769500 | ACTION | 8480.6636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 180.6618 | 903309.2259 | ACTION | 8480.6636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8480.6644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8482.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8483.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8489.0802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 8523.9076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8525.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8527.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8529.0802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8529.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8531.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8533.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8534.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8534.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8535.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8535.4969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8535.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8536.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8537.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8538.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8538.8769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8539.6369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8540.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8541.6369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8542.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8542.6369 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8543.6369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8544.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8544.7769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8546.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8546.7769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8546.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8547.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8547.7769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8548.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8549.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8550.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8551.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8552.2969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8552.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8553.2969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8554.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8554.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 8556.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8556.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8557.7969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8558.2969 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 8558.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8559.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8559.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8559.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 8560.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8561.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8561.7969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8563.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8564.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8565.2969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8566.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8568.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8573.7136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 25 | 260416.6667 | ACTION | 8598.7136 | TurbineInstallation
| Feeder 1 | Delay | 44 | 220000 | ACTION | 8604.6576 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8638.7136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8644.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8645.1302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8645.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8647.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 8647.9009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 8647.9017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8648.5102 | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 8672.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8673.2702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 44 | 458333.3333 | ACTION | 8717.2702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8719.2702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8720.2702 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8721.2702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8722.4102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8724.4102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8725.4102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8726.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8728.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8729.9302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8730.9302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8732.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8734.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8735.4302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8735.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8737.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8738.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8739.4302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8740.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8742.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8742.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8744.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8745.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8751.3469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8791.3469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8796.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8797.7636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8798.1436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8800.1436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8801.1436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8801.9036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8803.9036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8804.9036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8806.0436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8808.0436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8809.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8810.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8812.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8813.5636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8814.5636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8816.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8818.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8819.0636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8819.5636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8821.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8822.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8823.0636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8824.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8826.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8826.5636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 345.9 | 1729500 | ACTION | 8826.5636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 178.6618 | 893309.2259 | ACTION | 8826.5636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8826.5644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8828.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8829.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8834.9802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8869.8076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8871.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8873.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8874.9802 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8875.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8877.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8879.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8880.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8880.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8881.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8881.3969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8881.7769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8882.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8883.7769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8884.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8884.7769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8885.5369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8886.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8887.5369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8888.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8888.5369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8889.6769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8890.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8891.6769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8892.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8892.6769 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8892.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8893.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8894.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8894.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8896.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8896.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8897.1969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8898.1969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8898.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8899.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8900.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8901.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8902.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8902.6969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8903.1969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8904.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8904.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8905.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8905.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8906.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8906.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8906.6969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8908.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8909.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8910.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8911.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8913.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8918.6136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8949.8009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8949.8017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 8958.6136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8964.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8965.0302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8965.4102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8967.4102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8968.4102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8969.1702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8971.1702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8972.1702 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8974.1702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8975.3102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8977.3102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8978.3102 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8980.3102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8981.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8983.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8984.8302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8985.8302 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 8998.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9000.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9002.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9003.3302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9003.8302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9005.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9006.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9007.3302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9008.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9010.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9010.8302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9012.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9013.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9019.2469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9059.2469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9064.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9065.6636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9066.0436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9068.0436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9069.0436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9069.8036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9071.8036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9072.8036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9073.9436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9075.9436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9076.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9078.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9080.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9081.4636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9082.4636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9083.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9085.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9086.9636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9087.4636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9088.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9090.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9090.9636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9092.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9093.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9094.4636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 267.9 | 1339500 | ACTION | 9094.4636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 144.6618 | 723309.2259 | ACTION | 9094.4636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9094.4644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9095.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9097.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9102.8802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9137.7076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9139.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9141.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9142.8802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9143.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9145.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9147.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9148.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9148.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9149.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9149.2969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9149.6769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9149.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9151.6769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9151.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9152.6769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9153.4369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9153.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9155.4369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9155.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9156.4369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9157.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9157.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9159.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9159.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9160.5769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9160.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9161.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9162.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9162.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9164.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9164.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9166.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9166.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9167.0969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9168.0969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9168.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9169.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9170.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9171.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9172.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9172.5969 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9172.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9173.0969 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9173.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9174.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9174.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9176.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9176.5969 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 9180.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9182.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9183.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9184.0969 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9185.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9186.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9188.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9193.5136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9217.7009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9217.7017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9233.5136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9238.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9239.9302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9240.3102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9242.3102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9243.3102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9244.0702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9246.0702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9247.0702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9248.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9250.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9251.2102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9252.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9254.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9255.7302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9256.7302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9258.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9260.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9261.2302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9261.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9263.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9264.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9265.2302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9266.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9268.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9268.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9270.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9271.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9277.1469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9317.1469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9322.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9323.5636 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 9328.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9328.9436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9330.9436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9331.9436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9332.7036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9334.7036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9335.7036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9336.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9338.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9339.8436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9341.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9343.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9344.3636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9345.3636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9346.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9348.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9349.8636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9350.3636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9351.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9353.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9353.8636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9355.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9356.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9357.3636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 262.9 | 1314500 | ACTION | 9357.3636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 139.6618 | 698309.2259 | ACTION | 9357.3636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9357.3644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9358.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9360.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9365.7802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9400.6076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9402.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9404.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9405.7802 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9406.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9408.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9410.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9411.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9411.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9412.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9412.1969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9412.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9412.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9414.5769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9414.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9415.5769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9416.3369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9416.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9418.3369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9418.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9419.3369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9420.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9420.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9422.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9422.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9423.4769 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9423.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9424.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9424.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9425.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9426.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9427.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9427.9969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9428.9969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9429.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9430.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9431.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9432.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9433.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9433.4969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9433.9969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9435.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9435.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9435.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9436.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9436.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9437.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9437.4969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9438.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9440.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9440.9969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9442.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9443.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9449.4136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9480.6009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9480.6017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9489.4136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9494.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9495.8302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9496.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9498.2102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9499.2102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9499.9702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9501.9702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9502.9702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9504.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9506.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9507.1102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9508.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9510.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9511.6302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9512.6302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9514.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9516.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9517.1302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9517.6302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9519.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 13 | 135416.6667 | ACTION | 9532.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9533.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9534.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9535.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9537.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9537.6302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9539.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9540.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9546.0469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9586.0469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9591.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9592.4636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9592.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9594.8436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9595.8436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9596.6036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9598.6036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9599.6036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9600.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9602.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9603.7436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9605.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9607.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9608.2636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9609.2636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9610.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9612.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9613.7636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9614.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9615.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9617.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9617.7636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9619.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9620.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9621.2636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 263.9 | 1319500 | ACTION | 9621.2636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 140.6618 | 703309.2259 | ACTION | 9621.2636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9621.2644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9622.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9624.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9629.6802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9664.5076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9666.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9668.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9669.6802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9670.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9672.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9674.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9675.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9675.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9676.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9676.0969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9676.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9676.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9678.4769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9678.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9679.4769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9680.2369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9680.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9682.2369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9682.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9683.2369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9684.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9684.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9686.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9686.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9687.3769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9687.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9688.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9688.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9689.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9690.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9691.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9691.8969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9692.8969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9693.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9694.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9695.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9696.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 9697.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9697.3969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9697.8969 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 9699.0076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9699.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9699.7576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9700.5076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9700.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 9701.2576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9701.3969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9702.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9704.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9704.8969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9706.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9707.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9713.3136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 9744.5009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 9744.5017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9753.3136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9758.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9759.7302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9760.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9762.1102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9763.1102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9763.8702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9765.8702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9766.8702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9768.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9770.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9771.0102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9772.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9774.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9775.5302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9776.5302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9778.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9780.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9781.0302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9781.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9783.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9784.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9785.0302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9786.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9788.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9788.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9790.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9791.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9796.9469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9836.9469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9842.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9843.3636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9843.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9845.7436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9846.7436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9847.5036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9849.5036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9850.5036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9851.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9853.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9854.6436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9856.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9858.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9859.1636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9860.1636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9861.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9863.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9864.6636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9865.1636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9866.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9868.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9868.6636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9870.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9871.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9872.1636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 250.9 | 1254500 | ACTION | 9872.1636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 127.6618 | 638309.2259 | ACTION | 9872.1636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 9872.1644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9873.6636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9875.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9880.5802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9915.4076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9917.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9919.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 9920.5802 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9921.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9923.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9925.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 9925.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9926.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9926.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9926.9969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 9927.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9927.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9929.3769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9929.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9930.3769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 9931.1369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9931.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9933.1369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9933.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9934.1369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 9935.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9935.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9937.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9937.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 9938.2769 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9938.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9939.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 9939.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9939.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 9941.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9941.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 9942.7969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9943.7969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9943.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9945.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9945.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 9947.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 9947.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9948.2969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9948.7969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 9949.9076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9950.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9950.6576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9951.4076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9951.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 9952.1576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9952.2969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9953.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9955.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 9955.7969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9957.2969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 9958.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 9964.2136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 9995.4009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 9995.4017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10004.2136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10009.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10010.6302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10011.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10013.0102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10014.0102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10014.7702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10016.7702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10017.7702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10018.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10020.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10021.9102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10023.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10025.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10026.4302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10027.4302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10028.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10030.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10031.9302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10032.4302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10033.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10035.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10035.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10037.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10038.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10039.4302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10040.9302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10042.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10047.8469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10087.8469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10093.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10094.2636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10094.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10096.6436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10097.6436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10098.4036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10100.4036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10101.4036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10102.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10104.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10105.5436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10107.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10109.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10110.0636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10111.0636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10112.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10114.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10115.5636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10116.0636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10117.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10119.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10119.5636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10121.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10122.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10123.0636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 250.9 | 1254500 | ACTION | 10123.0636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 127.6618 | 638309.2259 | ACTION | 10123.0636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10123.0644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10124.5636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10126.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10131.4802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10166.3076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10168.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10170.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10171.4802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10172.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10174.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10176.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10176.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10177.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10177.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10177.8969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10178.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10178.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10180.2769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10180.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10181.2769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10182.0369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10182.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10184.0369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10184.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10185.0369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10186.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10186.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10188.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10188.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10189.1769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10189.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10190.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10190.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10190.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10192.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10192.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10193.6969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10194.6969 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10194.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10196.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10196.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10198.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10198.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10199.1969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10199.6969 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10200.8076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10201.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10201.5576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10202.3076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10202.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10203.0576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10203.1969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10204.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10206.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10206.6969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10208.1969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10209.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10215.1136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10246.3009 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10246.3017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10255.1136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10260.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10261.5302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10261.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10263.9102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10264.9102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10265.6702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10267.6702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10268.6702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10269.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10271.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10272.8102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10274.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10276.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10277.3302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10278.3302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10279.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10281.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10282.8302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10283.3302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10284.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10286.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10286.8302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10288.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10289.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10290.3302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10291.8302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10293.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10298.7469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10338.7469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10344.1636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10345.1636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10345.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10347.5436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10348.5436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10349.3036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10351.3036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10352.3036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10353.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10355.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10356.4436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10357.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10359.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10360.9636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10361.9636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10363.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10365.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10366.4636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10366.9636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10368.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10369.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10370.4636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10371.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10373.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10373.9636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 250.9 | 1254500 | ACTION | 10373.9636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 127.6618 | 638309.2259 | ACTION | 10373.9636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10373.9644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10375.4636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10376.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10382.3802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10417.2076 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10419.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10421.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10422.3802 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10423.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10425.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10427.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10427.7969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10427.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10428.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10428.7969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10429.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10429.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10431.1769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10431.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10432.1769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10432.9369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10433.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10434.9369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10435.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10435.9369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10437.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10437.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10439.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10439.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10440.0769 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10440.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10440.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10441.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10441.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10443.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10443.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10444.5969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10445.5969 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10445.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10447.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10447.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10449.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 10449.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10450.0969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10450.5969 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 10451.7076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10452.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10452.4576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10453.2076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10453.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 10453.9576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10454.0969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10455.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10457.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10457.5969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10459.0969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10460.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10466.0136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10497.2009 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 10497.2017 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10506.0136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10511.4302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10512.4302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10512.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10514.8102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10515.8102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10516.5702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10518.5702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10519.5702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10520.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10522.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10523.7102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10525.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10527.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10528.2302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10529.2302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10530.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10532.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10533.7302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10534.2302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10535.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10537.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10537.7302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10539.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10540.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10541.2302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10542.7302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10544.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10549.6469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10589.6469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10595.0636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10596.0636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10596.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10598.4436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10599.4436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10600.2036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10602.2036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10603.2036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10604.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10606.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10607.3436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10608.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10610.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10611.8636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10612.8636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10614.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10616.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10617.3636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10617.8636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10619.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10620.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10621.3636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10622.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10624.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10624.8636 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 250.9 | 1254500 | ACTION | 10624.8636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 127.6618 | 638309.2259 | ACTION | 10624.8636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10624.8644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10626.3636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10627.8636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10633.2802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10668.1076 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10670.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10672.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10673.2802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10674.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10676.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10678.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10678.6969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10678.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10679.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10679.6969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10680.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10680.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10682.0769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10682.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10683.0769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10683.8369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10684.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10685.8369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10686.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10686.8369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10687.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 10688.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10689.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 10690.3576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10690.9769 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10691.1076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10691.8576 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10692.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 10692.6076 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10694.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10695.4969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10696.4969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10697.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10699.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10700.9969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10701.4969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10702.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10704.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10704.9969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10706.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10707.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10708.4969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10709.9969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10711.4969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10716.9136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 10735.8509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 10735.8517 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10756.9136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10762.3302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10763.3302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10763.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10765.7102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10766.7102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10767.4702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10769.4702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10770.4702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10771.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10773.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10774.6102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10776.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10778.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10779.1302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10780.1302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10781.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10783.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10784.6302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10785.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10786.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10788.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10788.6302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10790.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10791.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10792.1302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10793.6302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10795.1302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10800.5469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10840.5469 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10845.9636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10846.9636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10847.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10849.3436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10850.3436 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10851.1036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10853.1036 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10854.1036 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10855.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10857.2436 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10858.2436 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10859.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10861.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10862.7636 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10863.7636 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10865.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10867.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10868.2636 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10868.7636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10870.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10871.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10872.2636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10873.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10875.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10875.7636 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 250.9 | 1254500 | ACTION | 10875.7636 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 139.9118 | 699559.2259 | ACTION | 10875.7636 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 10875.7644 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10877.2636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10878.7636 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10884.1802 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 10919.0076 | TurbineInstallation
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 10924.1802 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 10929.5969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10930.5969 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 10930.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10932.9769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10933.9769 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 10934.7369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10936.7369 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10937.7369 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 10938.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10940.8769 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 10941.8769 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 10943.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 10945.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 10946.3969 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10947.3969 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 10948.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 10950.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 10951.8969 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10952.3969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10953.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10955.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10955.8969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10957.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10958.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 10959.3969 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10960.8969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 10962.3969 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 10967.8136 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 40 | 416666.6667 | ACTION | 11007.8136 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 11013.2302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11014.2302 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 11014.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11016.6102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11017.6102 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 11018.3702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11020.3702 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11021.3702 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 11022.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11024.5102 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 11025.5102 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 11027.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 11029.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 11030.0302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11031.0302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11032.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 11034.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11035.5302 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11036.0302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11037.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11039.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11039.5302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11041.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11042.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 11043.0302 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 167.2667 | 836333.3333 | ACTION | 11043.0302 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 11043.0311 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11044.5302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 11046.0302 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 11051.4469 | TurbineInstallation | TurbineInstallation | 40 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 11086.2743 | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11094.6901 | TurbineInstallation