## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 43.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 123.2441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 80.0008 | 833342.0226 | ACTION | 123.2441 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 128.2441 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 133.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 134.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 137.6607 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 142.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 143.3838 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 143.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 144.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 147.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 162.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 164.3871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 165.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 166.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 170.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 175.8037 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 180.8037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 186.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 187.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 190.2204 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 196.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 196.9435 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 196.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 197.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 51 | 255000 | ACTION | 211 | MonopileInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 220.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 235.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 237.9467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 238.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 239.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 243.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 249.3634 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 254.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 254.2441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 254.3634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 259.78 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 260.78 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 263.78 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 264.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 264.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 265.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 280.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 282.5064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 283.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 284.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 288.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 293.923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 298.923 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 304.3397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 305.3397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 308.3397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 309.0628 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 309.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 310.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 325.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 327.066 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 203.8219 | 1019109.644 | ACTION | 327.066 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 327.0668 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 328.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 329.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 333.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 338.4827 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 370.3101 | MonopileInstallation
| Feeder 1 | Queue | 116.066 | 580330.0311 | ACTION | 370.3101 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 370.3101 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 375.3101 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 380.7268 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 381.7268 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 382.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 384.7268 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 385.4498 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 385.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 386.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 390.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 401.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 402.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 403.4531 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 404.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 405.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 409.4531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 410.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 414.8697 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 419.8697 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 422.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 425.2864 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 426.2864 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 429.2864 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 430.0095 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 430.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 93750 | ACTION | 439.0095 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 439.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 440.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 13 | 135416.6667 | ACTION | 453.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 28 | 140000 | ACTION | 458.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 468.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 470.0127 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 470.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 471.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 472.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 476.0127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 478.3101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 481.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 486.4294 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 491.846 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 492.846 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 495.846 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 496.5691 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 496.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 497.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 512.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 514.5724 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 515.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 516.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 520.5724 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 521.5533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 521.5542 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 525.989 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 530.989 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 536.4057 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 537.4057 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 540.4057 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 541.1288 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 541.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 542.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 557.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 559.132 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 188.8219 | 944109.644 | ACTION | 559.132 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 559.1328 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 560.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 561.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 565.132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 570.5487 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 602.3761 | MonopileInstallation
| Feeder 0 | Queue | 80.8219 | 404109.644 | ACTION | 602.3761 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 602.3761 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 607.3761 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 612.7928 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 613.7928 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 614.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 616.7928 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 617.5158 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 617.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 618.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 622.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 633.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 634.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 635.5191 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 636.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 637.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 641.5191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 642.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 646.9357 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 651.9357 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 654.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 657.3524 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 658.3524 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 661.3524 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 662.0755 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 662.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 662.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 663.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 674.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 678.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 680.0787 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 681.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 682.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 682.3761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 686.0787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 691.4954 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 696.4954 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 701.9121 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 702.9121 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 705.9121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 706.6351 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 706.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 707.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 722.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 724.6384 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 725.6193 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 725.6202 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 725.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 726.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 730.6384 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 736.055 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 741.055 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 746.4717 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 747.4717 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 750.4717 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 751.1948 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 751.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 752.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 14 | 145833.3333 | ACTION | 766.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 781.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 783.198 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 180.8219 | 904109.644 | ACTION | 783.198 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 783.1989 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 784.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 785.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 789.198 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 794.6147 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 826.4421 | MonopileInstallation
| Feeder 1 | Queue | 100.8219 | 504109.644 | ACTION | 826.4421 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 826.4421 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 831.4421 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 836.8588 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 837.8588 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 838.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 840.8588 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 841.5818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 841.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 842.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 846.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 857.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 858.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 859.5851 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 860.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 861.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 862.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 866.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 866.5851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 872.0017 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 877.0017 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 878.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 882.4184 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 883.4184 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 885.4184 | MonopileInstallation
| Feeder 0 | Delay | 7 | 35000 | ACTION | 885.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 888.4184 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 889.1415 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 889.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 890.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 893.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 905.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 905.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 907.1447 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 908.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 909.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 913.1447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 913.4421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 918.5614 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 923.5614 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 928.9781 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 929.9781 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 932.9781 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 933.7011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 933.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 934.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 949.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 951.7044 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 952.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 953.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 956.6853 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 956.6862 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 957.7044 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 963.121 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 968.121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 973.5377 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 974.5377 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 977.5377 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 978.2608 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 978.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 979.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 994.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 996.264 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 169.8219 | 849109.644 | ACTION | 996.264 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 996.2649 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 997.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 998.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1002.264 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1007.6807 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1039.5081 | MonopileInstallation
| Feeder 0 | Queue | 82.8219 | 414109.644 | ACTION | 1039.5081 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1039.5081 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1044.5081 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1049.9248 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1050.9248 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1051.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1053.9248 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1054.6478 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1054.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1055.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1059.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1070.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1071.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1072.6511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1073.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1074.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1078.6511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1079.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1084.0678 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1089.0678 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1091.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1094.4844 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1095.4844 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1098.4844 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1099.2075 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1099.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1099.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1100.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1111.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1115.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1117.2107 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1118.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1119.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1119.5081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1123.2107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1128.6274 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1133.6274 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1139.0441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1140.0441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1143.0441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1143.7671 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1143.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1144.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1159.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1161.7704 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1162.7513 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1162.7522 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1162.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1163.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1167.7704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1173.187 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1178.187 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1183.6037 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1184.6037 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1187.6037 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1188.3268 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1188.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1189.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1204.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1206.33 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 166.8219 | 834109.644 | ACTION | 1206.33 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1206.3309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1207.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1208.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1212.33 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1217.7467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1249.5741 | MonopileInstallation
| Feeder 1 | Queue | 86.8219 | 434109.644 | ACTION | 1249.5741 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1249.5741 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1254.5741 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1259.9908 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1260.9908 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1261.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1263.9908 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1264.7138 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1264.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1265.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1269.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1280.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1281.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1282.7171 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1283.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1284.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1288.7171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1289.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1294.1338 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1299.1338 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1301.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1304.5504 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1305.5504 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1308.5504 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1309.2735 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1309.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1309.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1310.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 7 | 72916.6667 | ACTION | 1317.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1321.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1329.5741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1332.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1334.2767 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1335.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1336.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1340.2767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1345.6934 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1350.6934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1356.1101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1357.1101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1360.1101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1360.8331 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1360.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1361.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1372.8174 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1372.8182 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1376.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1378.8364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1379.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1380.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1384.8364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1390.2531 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1395.2531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1400.6697 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1401.6697 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1404.6697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1405.3928 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1405.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1406.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 1416.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1431.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1433.396 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 183.8219 | 919109.644 | ACTION | 1433.396 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1433.3969 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1434.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1435.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1439.396 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1444.8127 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1476.6401 | MonopileInstallation
| Feeder 0 | Queue | 103.8219 | 519109.644 | ACTION | 1476.6401 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1476.6401 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1481.6401 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1487.0568 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1488.0568 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1488.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1491.0568 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1491.7798 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1491.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1492.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1496.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1507.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1508.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1509.7831 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1510.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1511.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1515.7831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1516.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1521.1998 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1526.1998 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1528.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1531.6164 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1532.6164 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1535.6164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1536.3395 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1536.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1536.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1537.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1548.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1552.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1554.3427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1555.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1556.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1556.6401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 1560.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1564.3427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1569.7594 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1574.7594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1580.1761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1581.1761 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1584.1761 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1584.8991 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1584.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1585.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1599.8834 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1599.8842 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1600.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1602.9024 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1603.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1604.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1608.9024 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1614.3191 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1619.3191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1624.7357 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1625.7357 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1628.7357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1629.4588 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1629.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1630.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1645.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1647.462 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 170.8219 | 854109.644 | ACTION | 1647.462 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1647.4629 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1648.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1649.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1653.462 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1658.8787 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1690.7061 | MonopileInstallation
| Feeder 1 | Queue | 90.8219 | 454109.644 | ACTION | 1690.7061 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1690.7061 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1695.7061 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1701.1228 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1702.1228 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1702.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1705.1228 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1705.8459 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1705.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1706.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1710.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1721.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1722.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1723.8491 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1724.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1725.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1729.8491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1730.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1735.2658 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1740.2658 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1742.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1745.6824 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1746.6824 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1749.6824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1750.4055 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1750.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1750.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1751.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1762.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1766.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1768.4088 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1769.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1770.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1770.7061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1774.4088 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1779.8254 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1784.8254 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1790.2421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1791.2421 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1794.2421 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1794.9652 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1794.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1795.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1810.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1812.9684 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1813.9494 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1813.9502 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1813.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1814.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1818.9684 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1824.3851 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1829.3851 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1834.8017 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1835.8017 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1838.8017 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1839.5248 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1839.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1840.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1855.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1857.528 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 166.8219 | 834109.644 | ACTION | 1857.528 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1857.5289 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1858.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1859.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1863.528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1868.9447 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1900.7721 | MonopileInstallation
| Feeder 0 | Queue | 86.8219 | 434109.644 | ACTION | 1900.7721 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1900.7721 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1905.7721 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1911.1888 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1912.1888 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1912.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1915.1888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1915.9119 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1915.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1916.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1920.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1931.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1932.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1933.9151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1934.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1935.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1939.9151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1940.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1945.3318 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1950.3318 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1952.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1955.7484 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1956.7484 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1959.7484 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1960.4715 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1960.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1960.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1961.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1966.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1972.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1980.7721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1981.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1983.4748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1984.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1985.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1989.4748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1994.8914 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1999.8914 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2005.3081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2006.3081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2009.3081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2010.0312 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2010.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2011.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2021.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2024.0154 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2024.0162 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2036.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2038.0344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2039.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2040.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2044.0344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2049.4511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2054.4511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2059.8677 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2060.8677 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2063.8677 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2064.5908 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2064.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2065.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2080.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2082.5941 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 181.8219 | 909109.644 | ACTION | 2082.5941 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2082.5949 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2083.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2084.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2088.5941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2094.0107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2125.8381 | MonopileInstallation
| Feeder 1 | Queue | 101.8219 | 509109.644 | ACTION | 2125.8381 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2125.8381 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2130.8381 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2136.2548 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2137.2548 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2137.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2140.2548 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2140.9779 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2140.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2141.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2145.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2156.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2157.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2158.9811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2159.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2160.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2164.9811 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2165.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2170.3978 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2175.3978 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2177.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2180.8144 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2181.8144 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2184.8144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2185.5375 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2185.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2185.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2186.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2197.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2201.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2203.5408 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2204.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2205.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2205.8381 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2209.5408 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2214.9574 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2219.9574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2225.3741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2226.3741 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2229.3741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2230.0972 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2230.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2231.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2246.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2248.1004 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2249.0814 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2249.0822 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2249.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2250.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2254.1004 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2259.5171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2264.5171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2269.9337 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2270.9337 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2273.9337 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2274.6568 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2274.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2275.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2290.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2292.6601 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 166.8219 | 834109.644 | ACTION | 2292.6601 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2292.6609 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2293.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2294.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2298.6601 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2304.0767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2335.9041 | MonopileInstallation
| Feeder 0 | Queue | 86.8219 | 434109.644 | ACTION | 2335.9041 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2335.9041 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2340.9041 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2346.3208 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2347.3208 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2347.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2350.3208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2351.0439 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2351.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2352.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2355.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2367.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2367.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2369.0471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2370.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2371.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2375.0471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2375.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2380.4638 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2385.4638 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2387.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2390.8805 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2391.8805 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2394.8805 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2395.6035 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2395.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2395.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2396.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2407.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2411.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2413.6068 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2414.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2415.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2415.9041 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2419.6068 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2425.0234 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2430.0234 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2435.4401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2436.4401 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2439.4401 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2440.1632 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2440.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2441.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2456.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2458.1664 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2459.1474 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2459.1482 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2459.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2460.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2464.1664 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2469.5831 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2474.5831 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2479.9998 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2480.9998 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2483.9998 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2484.7228 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2484.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2485.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2500.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2502.7261 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 166.8219 | 834109.644 | ACTION | 2502.7261 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2502.7269 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2503.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2504.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2508.7261 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2514.1427 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2545.9701 | MonopileInstallation
| Feeder 1 | Queue | 86.8219 | 434109.644 | ACTION | 2545.9701 | MonopileInstallation | [12 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2545.9701 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2550.9701 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2556.3868 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2557.3868 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2557.9701 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2560.3868 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2561.1099 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2561.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2562.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2565.9701 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2577.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2577.9701 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2579.1131 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2580.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2581.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2585.1131 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2585.9701 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2590.5298 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2595.5298 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2600.9465 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2601.9465 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2604.9465 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2605.6695 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2605.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2606.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2621.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2623.6728 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2624.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2625.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2629.6728 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2635.0894 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2640.0894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2645.5061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2646.5061 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2649.5061 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2650.2292 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2650.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2651.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2666.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2668.2324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2669.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2670.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2674.2324 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2679.6491 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2684.6491 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2690.0658 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2691.0658 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2694.0658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2694.7888 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2694.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2695.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2710.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2712.7921 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 166.8219 | 834109.644 | ACTION | 2712.7921 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2712.7929 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2713.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2714.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2718.7921 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2724.2087 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 59 | 295000 | ACTION | 2771.7929 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2815.0362 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 2815.0362 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 2815.0362 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 2815.0362 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2817.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2819.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2821.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2823.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2825.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2825.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2826.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2827.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2829.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2831.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2833.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2835.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2837.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2838.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2838.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2839.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2841.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2843.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2845.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2847.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2849.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2850.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2851.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2851.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 36.75 | 183750 | ACTION | 2851.7862 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2853.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2855.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2857.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2858.2794 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2859.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2861.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2862.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2863.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2864.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2866.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2868.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2870.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2872.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2874.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2874.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2875.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2876.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2878.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2880.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2882.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2884.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2886.2862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2887.0362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2887.7862 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2888.5362 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2895.0294 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2895.0302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 36.7508 | 382821.1892 | ACTION | 2895.0302 | TurbineInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2900.0302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2905.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2906.4469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2906.8269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2908.8269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2909.8269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2910.5869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2912.5869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2913.5869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2914.7269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2916.7269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2917.7269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2919.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2921.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2922.2469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2923.2469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2924.7469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2926.7469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2927.7469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2928.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2929.7469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2931.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2931.7469 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2931.7794 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2931.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2933.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2934.7469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2935.2469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2936.7469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2938.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2943.6636 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2948.6636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2954.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2955.0802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2955.4602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2957.4602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2958.4602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2959.2202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2961.2202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2962.2202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2963.3602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2965.3602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2966.3602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2967.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2969.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2970.8802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2971.8802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2973.3802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2975.3802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2976.3802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2976.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2978.3802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2979.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2980.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2981.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2983.3802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2983.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2985.3802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2986.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2992.2969 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2997.2969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3002.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3003.7136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3004.0936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3006.0936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3007.0936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3007.8536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3009.8536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3010.8536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3011.9936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3013.9936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 19 | 197916.6667 | ACTION | 3032.9936 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3033.9936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3035.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3037.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3038.5136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3039.5136 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 3050.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3052.0136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3054.0136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3055.0136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3055.5136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3057.0136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3058.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3059.0136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3060.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3062.0136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3062.5136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 167.4833 | 837416.6667 | ACTION | 3062.5136 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 130.7333 | 653666.6667 | ACTION | 3062.5136 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3062.5144 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3064.0136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3065.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3070.9302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3075.9302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3081.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3082.3469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3082.7269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3084.7269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3085.7269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3086.4869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3088.4869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3089.4869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3090.6269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3092.6269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3093.6269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3095.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3097.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3098.1469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3099.1469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3100.6469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3102.6469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3103.6469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3104.1469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3105.6469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3105.7576 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3107.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3107.6469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3107.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3109.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3109.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3110.6469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3111.1469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3111.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3112.6469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3113.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3114.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3115.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3116.5076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3117.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3118.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3119.5636 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3120.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3122.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3124.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3124.5636 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3126.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3128.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3128.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3129.5076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3129.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3130.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3130.9802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3131.3602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3132.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3133.3602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3134.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3134.3602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3135.1202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3136.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3137.1202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3138.1202 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3138.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3139.2602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3140.2576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3141.0076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3141.2602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3141.7576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3142.2602 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3142.5076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3143.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3145.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3146.7802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3147.7802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3149.2802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3151.2802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3152.2802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3152.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3154.2802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3155.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3156.2802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3157.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3159.2802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3159.7802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3161.2802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3162.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3168.1969 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3173.1969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3178.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3179.6136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3179.9936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3181.9936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3182.9936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3183.7536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3185.7509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3185.7517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3185.7536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3186.7536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3187.8936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3189.8936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3190.8936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3192.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3194.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3195.4136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3196.4136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3197.9136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3199.9136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3200.9136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3201.4136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3202.9136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3204.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3204.9136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3206.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3207.9136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3208.4136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 145.9 | 729500 | ACTION | 3208.4136 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 22.6618 | 113309.2259 | ACTION | 3208.4136 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3208.4144 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3209.9136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3211.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3216.8302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3221.8302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3227.2469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3228.2469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3228.6269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3230.6269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3231.6269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3232.3869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3234.3869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3235.3869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3236.5269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3238.5269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3239.5269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3241.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3243.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3244.0469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3245.0469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3246.5469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3248.5469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3249.5469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3250.0469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3251.5469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3251.6576 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3253.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3253.5469 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3253.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3255.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3255.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3256.5469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3257.0469 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3257.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3258.5469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3259.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3260.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3261.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3262.4076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3263.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3263.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3265.4636 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3265.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3267.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3269.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3270.4636 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3271.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3273.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3274.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3275.4076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3275.8802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3276.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3276.8802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3277.2602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3278.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3279.2602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3280.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3280.2602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3281.0202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3282.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3283.0202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3284.0202 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3284.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3285.1602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3286.1576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3286.9076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3287.1602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3287.6576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3288.1602 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3288.4076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3289.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3291.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3292.6802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3293.6802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3295.1802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3297.1802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3298.1802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3298.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3300.1802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3301.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3302.1802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3303.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3305.1802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3305.6802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3307.1802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3308.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3314.0969 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3319.0969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3324.5136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3325.5136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3325.8936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3327.8936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3328.8936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3329.6536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3331.6509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3331.6517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3331.6536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3332.6536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3333.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 41666.6667 | ACTION | 3337.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3339.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3340.7936 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 3351.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3353.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3355.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3356.3136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3357.3136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3358.8136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3360.8136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3361.8136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3362.3136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3363.8136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3365.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3365.8136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3367.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3368.8136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3369.3136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 160.9 | 804500 | ACTION | 3369.3136 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 37.6618 | 188309.2259 | ACTION | 3369.3136 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3369.3144 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3370.8136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3372.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3377.7302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3382.7302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3388.1469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3389.1469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3389.5269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3391.5269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3392.5269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3393.2869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3395.2869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3396.2869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3397.4269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3399.4269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3400.4269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3401.9469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3403.9469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3404.9469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3405.9469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3407.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3409.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3410.4469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3410.9469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3412.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3412.5576 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3413.9469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3414.4469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3414.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3415.9469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 2 | 10000 | ACTION | 3416.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3417.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3417.9469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3418.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3419.4469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3420.9469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 3 | 15000 | ACTION | 3421.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3423.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 2 | 10000 | ACTION | 3425.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3426.3636 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3427.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3429.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3430.3076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3431.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3431.3636 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3431.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3433.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3435.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3436.7802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3437.7802 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3437.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3438.1602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3439.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3440.1602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3441.1602 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3441.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3441.9202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3442.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3443.3076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3443.9202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3444.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3444.9202 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3446.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3446.0602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3448.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3448.0602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3449.0602 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3450.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3450.5802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3452.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3452.5802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3453.5802 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3454.0576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3454.5802 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3454.8076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3455.5576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3456.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3456.3076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3458.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3459.0802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3459.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3461.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3462.5802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3463.0802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3464.5802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3466.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3466.5802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3468.0802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3469.5802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3474.9969 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3479.9969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3485.4136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3486.4136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3486.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3488.7936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3489.7936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3490.5536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3492.5536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3493.5536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3494.6936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3496.6936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3497.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3499.2136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3499.5509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3499.5517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3501.2136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3502.2136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3503.2136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3504.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3506.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3507.7136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3508.2136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3509.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3511.2136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3511.7136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3513.2136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3514.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3515.2136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 145.9 | 729500 | ACTION | 3515.2136 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 15.6618 | 78309.2259 | ACTION | 3515.2136 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3515.2144 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3516.7136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3518.2136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3523.6302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3528.6302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3534.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3535.0469 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 3538.0469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3538.4269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3540.4269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3541.4269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3542.1869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3544.1869 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3545.1869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3546.3269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3548.3269 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3549.3269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3550.8469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3552.8469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3553.8469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3554.8469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3556.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3558.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3558.4576 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3559.3469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3559.8469 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3560.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3561.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3562.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3562.8469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3563.3469 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3564.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3564.8469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3566.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3566.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3566.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3568.3469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3568.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3569.2076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3569.8469 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3569.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3570.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3572.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3574.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3575.2636 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3576.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3578.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3580.2636 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3580.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3581.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3582.2076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3582.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3584.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3585.6802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3586.6802 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3586.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3587.0602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3588.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3589.0602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3590.0602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3590.8202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3590.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3592.8202 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3592.9576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3593.7076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3593.8202 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3594.4576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3594.9602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3595.2076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3596.9602 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3597.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3599.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3601.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3602.4802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3603.4802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3604.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3606.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3607.9802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3608.4802 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3610.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3611.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3613.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3613.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3615.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 11 | 114583.3333 | ACTION | 3626.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3627.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3628.4802 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3629.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3630.9802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3632.4802 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3637.8969 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3642.8969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3648.3136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3649.3136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3649.6936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3651.6936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3652.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3653.4536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3655.4536 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3656.4536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3657.5936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3659.5936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3660.5936 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 3702.5936 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3704.1136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3706.1136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3707.1136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3708.1136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3709.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3711.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3712.6136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3713.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3714.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3716.1136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3716.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3718.1136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3719.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3720.1136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 204.9 | 1024500 | ACTION | 3720.1136 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3720.1144 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3721.6136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3723.1136 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3728.5302 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 52 | 260000 | ACTION | 3772.1144 | TurbineInstallation
| Feeder 1 | Delay | 177 | 885000 | ACTION | 3772.2076 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3815.3576 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3815.4509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3815.4517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 86.9215 | 905432.1683 | ACTION | 3815.4517 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3817.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3819.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3820.4517 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3821.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3823.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3825.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3825.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3826.1076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3826.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3826.8684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3827.2484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3827.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3829.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 3830.2484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3832.2484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3833.2484 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3834.2484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3835.0084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 7 | 35000 | ACTION | 3836.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3837.0084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3838.0084 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3838.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3840.0084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3840.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3841.1484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3842.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3843.1484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3844.1484 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3844.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3845.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3845.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3846.1076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3846.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3847.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3848.6684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3848.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3849.6684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3850.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3851.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3852.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3853.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3854.1684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3854.6684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3854.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3856.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3856.8576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3857.6076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3857.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3858.1684 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3858.3576 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3859.1076 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3859.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3861.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3861.6684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3863.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3865.1684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3866.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3872.0851 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3877.0851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3882.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3883.5017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3883.8817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3885.8817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3886.8817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3887.6417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3889.6417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3890.6417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3891.7817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3893.7817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3894.7817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3896.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3898.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3899.3017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3900.3017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3901.8017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3902.3509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3902.3517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3903.8017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3904.8017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3905.3017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3906.8017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3908.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3908.8017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3910.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3911.8017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3912.3017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3913.8017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3915.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3920.7184 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3925.7184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3931.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3932.1351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3932.5151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3934.5151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3935.5151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3936.2751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3938.2751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3939.2751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3940.4151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3942.4151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3943.4151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3944.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3946.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3947.9351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3948.9351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3950.4351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3952.4351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3953.4351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3953.9351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3955.4351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3956.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3957.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3958.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3960.4351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3960.9351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 145.4833 | 727416.6667 | ACTION | 3960.9351 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 58.5833 | 292916.6667 | ACTION | 3960.9351 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3960.9359 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3962.4351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3963.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3969.3517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3974.3517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3979.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3980.7684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3981.1484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3983.1484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3984.1484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3984.9084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3986.9084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3987.9084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3989.0484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3991.0484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3992.0484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3993.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3995.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3996.5684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3997.5684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3999.0684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4001.0684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4002.0684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4002.5684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4004.0684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4004.1791 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4005.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4006.0684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4006.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4007.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4008.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4009.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4010.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4011.0684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4011.5684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4012.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4012.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4014.0684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4014.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4015.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4018.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 6 | 30000 | ACTION | 4020.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4020.9291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4021.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 1 | 5000 | ACTION | 4022.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4023.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4023.9851 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 4039.9851 | TurbineInstallation
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4044.9851 | TurbineInstallation
| Feeder 1 | Delay | 24 | 120000 | ACTION | 4047.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4049.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4050.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4051.4017 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4051.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4053.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4055.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4057.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4058.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4058.9291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4059.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 9 | 93750 | ACTION | 4060.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4060.7817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4061.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4062.7817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4063.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4063.7817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4064.5417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4065.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4066.5417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4067.5417 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4067.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4068.6817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4069.6791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4070.4291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4070.6817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4071.1791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4071.6817 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4071.9291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4073.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4075.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4076.2017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4077.2017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4078.7017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4080.7017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4081.7017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4082.2017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4083.7017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4085.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4085.7017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4087.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4088.7017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4089.2017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4090.7017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4092.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4097.6184 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4102.6184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4108.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4109.0351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4109.4151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4111.4151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4112.4151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4113.1751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4115.1724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4115.1732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4115.1751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4116.1751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4117.3151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4119.3151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4120.3151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4121.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4123.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4124.8351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4125.8351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4127.3351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4129.3351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4130.3351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4130.8351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4132.3351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4133.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4134.3351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4135.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4137.3351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4137.8351 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 176.9 | 884500 | ACTION | 4137.8351 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 22.6618 | 113309.2259 | ACTION | 4137.8351 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4137.8359 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4139.3351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4140.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4146.2517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4151.2517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4156.6684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4157.6684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4158.0484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4160.0484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4161.0484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4161.8084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4163.8084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4164.8084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4165.9484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4167.9484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4168.9484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4170.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4172.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4173.4684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4174.4684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4175.9684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4177.9684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4178.9684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4179.4684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4180.9684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4181.0791 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4182.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4182.9684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4183.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4184.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4185.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4185.9684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4186.4684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4187.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4187.9684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4189.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4189.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4191.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4191.8291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4192.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4193.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4194.8851 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4195.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4197.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4199.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4199.8851 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4201.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4203.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4204.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4204.8291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4205.3017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4205.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4206.3017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4206.6817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4207.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4208.6817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4209.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4209.6817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4210.4417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4211.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4212.4417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4213.4417 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4213.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4214.5817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4215.5791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4216.3291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4216.5817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4217.0791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4217.5817 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4217.8291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4219.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4221.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4222.1017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4223.1017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4224.6017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4226.6017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4227.6017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4228.1017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4229.6017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4231.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4231.6017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4233.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4234.6017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4235.1017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4236.6017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4238.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4243.5184 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4248.5184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4253.9351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4254.9351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4255.3151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4257.3151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4258.3151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4259.0751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4261.0724 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4261.0732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4261.0751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4262.0751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4263.2151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4265.2151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4266.2151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4267.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4269.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4270.7351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4271.7351 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 4279.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4281.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4282.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4284.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4285.2351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4285.7351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4287.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4288.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4289.2351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4290.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4292.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4292.7351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 154.9 | 774500 | ACTION | 4292.7351 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 31.6618 | 158309.2259 | ACTION | 4292.7351 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4292.7359 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4294.2351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4295.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4301.1517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4306.1517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4311.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4312.5684 | TurbineInstallation
| Feeder 1 | Delay | 33 | 165000 | ACTION | 4325.7359 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 4327.5684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4327.9484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4329.9484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4330.9484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4331.7084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4333.7084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4334.7084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4335.8484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4337.8484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4338.8484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4340.3684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4342.3684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4343.3684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4344.3684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4345.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4347.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4348.8684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4349.3684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4350.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4352.3684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4352.8684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4354.3684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4355.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4356.3684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4357.8684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4359.3684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4364.7851 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4368.9791 | TurbineInstallation
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4369.7851 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4370.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4372.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4374.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4375.2017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4376.2017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4376.5817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4376.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4378.5817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4378.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4379.5817 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4379.7291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4380.3417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4380.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4381.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4382.3417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4383.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4383.3417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4384.4817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4385.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4386.4817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4387.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4387.4817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4389.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4389.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 14 | 145833.3333 | ACTION | 4403.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4405.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4406.0017 | TurbineInstallation
| Feeder 1 | Delay | 17 | 85000 | ACTION | 4406.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4407.0017 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4408.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4408.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4408.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4409.7291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4410.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4410.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4411.5017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4412.0017 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4412.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4413.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4414.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4415.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4415.5017 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4416.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4417.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4418.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4418.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4419.0017 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4420.4791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4420.5017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4421.2291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4421.9791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4422.0017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4422.7291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4427.4184 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4432.4184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4437.8351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4438.8351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4439.2151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4441.2151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4442.2151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4442.9751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4444.9751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4445.9751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4447.1151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4449.1151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4450.1151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4451.6351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4453.6351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4454.6351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4455.6351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4457.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4459.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4460.1351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4460.6351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4462.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4463.6351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4464.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4465.6351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4465.9724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4465.9732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4467.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4467.6351 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 174.9 | 874500 | ACTION | 4467.6351 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 1.6618 | 8309.2259 | ACTION | 4467.6351 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4467.6359 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4469.1351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4470.6351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4476.0517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4481.0517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4486.4684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4487.4684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4487.8484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4489.8484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 61 | 635416.6667 | ACTION | 4550.8484 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4551.8484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4552.6084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4554.6084 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4555.6084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4556.7484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4558.7484 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4559.7484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4561.2684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4563.2684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4564.2684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4565.2684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4566.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4568.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4569.7684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4570.2684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4571.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4573.2684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4573.7684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4575.2684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4576.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4577.2684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4578.7684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4580.2684 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4585.6851 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4590.6851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4596.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4597.1017 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4598.1017 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4603.1017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4603.4817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4605.4817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4607.4817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4608.4817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4609.2417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4611.2417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4612.2417 | TurbineInstallation
| WTIV | Delay | 86 | 895833.3333 | ACTION | 4698.2417 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4699.3817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4702.3817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4704.3817 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4705.3817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4706.9017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4708.9017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4709.9017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4710.9017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4712.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4714.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4715.4017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4715.9017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4717.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4718.9017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4719.4017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4720.9017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4722.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4722.9017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4724.4017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4725.9017 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4731.3184 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 264 | 1320000 | ACTION | 4731.6359 | TurbineInstallation
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4736.3184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4741.7351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4742.7351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4743.1151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4745.1151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4746.1151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4746.8751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4748.8751 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4749.8751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4751.0151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4753.0151 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4754.0151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4755.5351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4757.5351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4758.5351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4759.5351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4761.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4763.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4764.0351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4764.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4766.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4767.5351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4768.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4769.5351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4771.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4771.5351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 303.9 | 1519500 | ACTION | 4771.5351 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4771.5359 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4773.0351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4774.5351 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4774.8791 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4776.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4778.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4779.9517 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4780.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4782.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4784.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4785.6291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4786.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4787.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4789.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4791.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4793.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4795.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4797.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4797.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4798.6291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4799.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4801.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4803.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4805.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4807.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4809.3791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4810.1291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4810.8791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4811.6291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4814.7791 | TurbineInstallation
| Feeder 1 | Delay | 21 | 105000 | ACTION | 4835.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4837.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4839.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4841.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4843.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4845.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4846.5291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4847.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4848.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4850.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4852.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4854.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4856.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4858.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4858.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4859.5291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4860.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4862.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4864.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4866.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4868.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4870.2791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4871.0291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4871.7791 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4872.5291 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 19 | 95000 | ACTION | 4891.5291 | TurbineInstallation
| Feeder 0 | Delay | 80 | 400000 | ACTION | 4891.6291 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4934.7724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4934.7732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 154.8215 | 1612723.8349 | ACTION | 4934.7732 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4934.8724 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4934.8732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4939.7732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4945.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4946.1899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4946.5699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4948.5699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4949.5699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4950.3299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4952.3299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4953.3299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4954.4699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4956.4699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4957.4699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4958.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4960.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4961.9899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4962.9899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4964.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4966.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4967.4899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4967.9899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4969.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4970.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4971.4899 | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 4982.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4983.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4985.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4985.9899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4987.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4991.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4992.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4998.4065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5003.4065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5008.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5009.8232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5010.2032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5012.2032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5013.2032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5013.9632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5015.9632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5016.9632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5018.1032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5020.1032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5021.1032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5022.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5024.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5025.6232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5026.6232 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 5030.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5032.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5034.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5035.1232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5035.6232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5037.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5038.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5039.1232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5040.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5042.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5042.6232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5044.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5045.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5051.0399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5056.0399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5061.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5062.4565 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 5065.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5065.8365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5067.8365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5068.8365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5069.5965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5071.5965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5072.5965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5073.7365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5075.7365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5076.7365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5078.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5080.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5081.2565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5082.2565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5083.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5085.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5086.7565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5087.2565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5088.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5090.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5090.7565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5092.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5093.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5094.2565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 159.4833 | 797416.6667 | ACTION | 5094.2565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 159.3833 | 796916.6667 | ACTION | 5094.2565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 5094.2574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5095.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5097.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5102.6732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5107.6732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5113.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5114.0899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5114.4699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5116.4699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5117.4699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5118.2299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5120.2299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5121.2299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5122.3699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5124.3699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5125.3699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5126.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5128.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5129.8899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5130.8899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5132.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5134.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5135.3899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5135.8899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5137.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 5137.5006 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5138.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5139.3899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5139.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5140.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5141.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5142.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5142.8899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5143.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5144.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5145.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5145.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 5147.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5148.2506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5149.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 5149.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5151.3065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5151.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 5153.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1258 | 13104166.6667 | ACTION | 6409.3065 | TurbineInstallation
| Feeder 1 | Delay | 1256 | 6280000 | ACTION | 6409.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6411.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6413.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6414.3065 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6415.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6416.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6417.2506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6418.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6419.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6420.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6420.7232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6421.1032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6422.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6423.1032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6424.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6424.1032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6424.8632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6426.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6426.8632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6427.8632 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6428.0006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6428.7506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6429.0032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6429.5006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6430.2506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6431.0032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6432.0032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6433.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6435.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6436.5232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6437.5232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6439.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6441.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6442.0232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6442.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6444.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6445.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6446.0232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6447.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6449.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6449.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6451.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6452.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6457.9399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6462.9399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6468.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6469.3565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6469.7365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6471.7365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6472.7365 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6473.4939 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6473.4947 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6473.4965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6475.4965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6476.4965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6477.6365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6479.6365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6480.6365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6482.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6484.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6485.1565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6486.1565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6487.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6489.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6490.6565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6491.1565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6492.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6494.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6494.6565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6496.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6497.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6498.1565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 1403.9 | 7019500 | ACTION | 6498.1565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 24.6618 | 123309.2259 | ACTION | 6498.1565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6498.1574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6499.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 14 | 70000 | ACTION | 6512.1574 | TurbineInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6516.6565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6518.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6523.5732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6528.5732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6533.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6534.9899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6535.3699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6537.3699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6538.3699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6539.1299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6541.1299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6542.1299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6543.2699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6545.2699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6546.2699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6547.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6549.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6550.7899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6551.7899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6553.2899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6555.2899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6555.4006 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6556.2899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6556.7899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6557.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6558.2899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6559.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6559.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6560.2899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6561.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6561.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6563.2899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6563.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6563.7899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6565.2899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6565.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6566.1506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6566.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6566.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6567.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6569.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6571.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6572.2065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6573.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6575.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6577.2065 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6577.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6578.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6579.1506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6579.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6581.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6582.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6583.6232 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6583.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6584.0032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6585.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6586.0032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6587.0032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6587.7632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6587.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6589.7632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6589.9006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6590.6506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6590.7632 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6591.4006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6591.9032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6592.1506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6593.9032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6594.9032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6596.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6598.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6599.4232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6600.4232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6601.9232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6603.9232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6604.9232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6605.4232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6606.9232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6608.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6608.9232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6610.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6611.9232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6612.4232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6613.9232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6615.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6620.8399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6625.8399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6631.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6632.2565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6632.6365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6634.6365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6635.3939 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6635.3947 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6635.6365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6636.3965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6638.3965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6639.3965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6640.5365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6642.5365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6643.5365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6645.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6647.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6648.0565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6649.0565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6650.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6652.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6653.5565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6654.0565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6655.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6657.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6657.5565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6659.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6660.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6661.0565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 162.9 | 814500 | ACTION | 6661.0565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 25.6618 | 128309.2259 | ACTION | 6661.0565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6661.0574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6662.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 3 | 15000 | ACTION | 6664.0574 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 6664.5565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6666.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6671.4732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6676.4732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6681.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6682.8899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6683.2699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6685.2699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6686.2699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6687.0299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6689.0299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6690.0299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6691.1699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6693.1699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6694.1699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6695.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6697.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6698.6899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6699.6899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6701.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6703.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6704.1899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6704.6899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6706.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6707.3006 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6707.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6708.1899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6709.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6709.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6711.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6711.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6711.6899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6713.1899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6713.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6714.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6715.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6717.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6718.0506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6718.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6719.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6720.1065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6721.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6723.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6725.1065 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6725.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6727.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6729.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6730.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6730.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6731.0506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6731.5232 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6731.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6731.9032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6733.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6733.9032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6734.9032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6735.6632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6735.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6737.6632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6737.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6738.6632 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6739.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6739.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6741.8006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6741.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6742.5506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6742.8032 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6743.3006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6744.0506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 1 | 5000 | ACTION | 6745.0506 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 6757.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6759.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6761.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6762.3232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6763.3232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6764.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6766.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6767.8232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6768.3232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6769.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6771.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6771.8232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6773.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6774.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6775.3232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6776.8232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6778.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6783.7399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6788.2939 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6788.2947 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6788.7399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6794.1565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6795.1565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6795.5365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6797.5365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6798.5365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6799.2965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6801.2965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6802.2965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6803.4365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6805.4365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6806.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6807.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6809.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6810.9565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6811.9565 | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 6823.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6825.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6827.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6828.4565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6828.9565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6830.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6831.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6832.4565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6833.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6835.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6835.9565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 174.9 | 874500 | ACTION | 6835.9565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 47.6618 | 238309.2259 | ACTION | 6835.9565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6835.9574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6837.4565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6838.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6844.3732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6849.3732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6854.7899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6855.7899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6856.1699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6858.1699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6859.1699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6859.9299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6861.9299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6862.9299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6864.0699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6866.0699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6867.0699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6868.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6870.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6871.5899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6872.5899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6874.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6876.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6877.0899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6877.5899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6879.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6879.2006 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6880.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6881.0899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6881.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6882.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6883.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6884.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6884.5899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6885.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6886.0899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6887.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6887.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6889.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6889.9506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6890.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6891.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6893.0065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6893.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6895.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6897.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6898.0065 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6899.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6901.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6902.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6902.9506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6903.4232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6903.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6904.4232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6904.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6905.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6906.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6907.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6907.8032 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6909.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 2 | 10000 | ACTION | 6911.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6913.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 6913.8032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6914.5632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6915.5632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6915.7006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6916.4506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6917.2006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6917.5632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6917.9506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6918.5632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6919.7032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6921.7032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6922.7032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6924.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6926.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6927.2232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6928.2232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6929.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6931.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6932.7232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6933.2232 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6961.1939 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6961.1947 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 42 | 437500 | ACTION | 6975.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6976.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6978.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6978.7232 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 6983.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6985.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6986.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6987.2232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6988.7232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6990.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6995.6399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7000.6399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7006.0565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7007.0565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7007.4365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7009.4365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7010.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7011.1965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7013.1965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7014.1965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7015.3365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7017.3365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7018.3365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7019.8565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7021.8565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7022.8565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7023.8565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7025.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7027.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7028.3565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7028.8565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7030.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7031.8565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7032.3565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7033.8565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7035.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7035.8565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 199.9 | 999500 | ACTION | 7035.8565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 74.6618 | 373309.2259 | ACTION | 7035.8565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7035.8574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7037.3565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7038.8565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7044.2732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7049.2732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7054.6899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7055.6899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7056.0699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 31 | 155000 | ACTION | 7066.8574 | TurbineInstallation
| WTIV | Delay | 36 | 375000 | ACTION | 7092.0699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7094.0699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7095.0699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7095.8299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7097.8299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7098.8299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7099.9699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7101.9699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7102.9699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7104.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7106.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7107.4899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7108.4899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7109.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7110.1006 | TurbineInstallation
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7111.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7112.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7112.9899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7113.4899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7114.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7114.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7116.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7116.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7116.9899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7118.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7118.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7119.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7120.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7120.4899 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7120.8506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7121.6006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7121.9899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7122.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7123.4899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7124.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7126.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7128.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7128.9065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7130.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7132.3506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7133.1006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7133.8506 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7133.9065 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7134.6006 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7139.3232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7140.3232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7140.7032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7142.7032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7143.7032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7144.4632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7146.4632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7147.4632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7148.6032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7150.6032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7151.6032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7153.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7155.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7156.1232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7157.1232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7158.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7160.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7161.6232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7162.1232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7163.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7165.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7165.6232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7167.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7168.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7169.1232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7170.6232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7172.1232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7177.5399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7177.8439 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7177.8447 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7182.5399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7187.9565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7188.9565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7189.3365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7191.3365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7192.3365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7193.0965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7195.0965 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7196.0965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7197.2365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7199.2365 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7200.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7201.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7203.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7204.7565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7205.7565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7207.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7209.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7210.2565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7210.7565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7212.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 9 | 93750 | ACTION | 7221.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7222.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7223.2565 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 7229.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7230.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7232.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7232.7565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 196.9 | 984500 | ACTION | 7232.7565 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 54.9118 | 274559.2259 | ACTION | 7232.7565 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7232.7574 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7234.2565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7235.7565 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7241.1732 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7246.1732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7251.5899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7252.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7252.9699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7254.9699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7255.9699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7256.7299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7258.7299 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7259.7299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7260.8699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7262.8699 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7263.8699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7265.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7267.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7268.3899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7269.3899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7270.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7272.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7273.8899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7274.3899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7275.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7276.0006 | TurbineInstallation
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7277.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7277.8899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7279.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7280.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7281.3899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7282.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 7298.8899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7300.3899 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7305.8065 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 7310.8065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7316.2232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7317.2232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7317.6032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7319.6032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7320.6032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7321.3632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7323.3632 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7324.3632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7325.5032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7327.5032 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7328.5032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7330.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7332.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7333.0232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7334.0232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7335.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 7338.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7340.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7341.5232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7342.0232 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7349.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7350.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7351.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7353.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7353.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7355.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7356.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7357.0232 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 124.2667 | 621333.3333 | ACTION | 7357.0232 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7357.024 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7358.5232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7360.0232 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7365.4399 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7400.2673 | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7408.6831 | TurbineInstallation