## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 3.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 120 | 600000 | ACTION | 120 | MonopileInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 123.2441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 120.0008 | 1250008.6892 | ACTION | 123.2441 | MonopileInstallation | [12 empty] | Site
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 128.2441 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 133.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 134.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 137.6607 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 142.6607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 143.3838 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 143.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 144.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 147.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 162.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 164.3871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 165.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 166.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 170.3871 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 172 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 175.8037 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 180 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 180.8037 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 186.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 187.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 190.2204 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 192 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 6 | 62500 | ACTION | 196.2204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 196.9435 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 196.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 197.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 19 | 95000 | ACTION | 211 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 219 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 23 | 239583.3333 | ACTION | 220.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 231 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 235.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 237.9467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 238.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 239.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 243.9467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 249.3634 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 251 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 254.3634 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 259.78 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 260.78 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 262.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 262.2441 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 263.78 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 264.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 264.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 265.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 280.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 282.5064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 283.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 284.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 288.5064 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 293.923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 298.923 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 304.3397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 305.3397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 308.3397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 309.0628 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 309.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 310.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 325.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 327.066 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 328.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 329.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 333.066 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 338.4827 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 343.4827 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 348.8993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 349.8993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 352.8993 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 353.6224 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 353.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 354.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 369.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 371.6257 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 372.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 373.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 377.6257 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 383.0423 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 388.0423 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 393.459 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 394.459 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 397.459 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 398.1821 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 398.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 399.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 414.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 416.1853 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 292.9412 | 1464706.1327 | ACTION | 416.1853 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 416.1861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 417.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 418.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 419.4294 | MonopileInstallation
| Feeder 1 | Queue | 157.1853 | 785926.5198 | ACTION | 419.4294 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 422.1853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 427.602 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 431.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 432.602 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 438.0186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 439.0186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 440.0186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 443.0186 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 443.7417 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 443.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 444.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 9 | 93750 | ACTION | 453.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 27 | 135000 | ACTION | 458.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 466.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 468.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 470.745 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 471.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 472.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 476.745 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 478.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 482.1616 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 486.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 487.1616 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 492.5783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 493.5783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 496.5783 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 497.3014 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 497.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 498.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 498.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 506.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 513.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 515.3046 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 516.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 517.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 518.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 521.3046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 526.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 526.7213 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 531.7213 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 537.1379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 538.1379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 538.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 541.1379 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 541.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 541.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 542.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 546.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 557.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 558.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 559.8643 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 560.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 561.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 565.8643 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 566.4294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 569.6726 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 569.6735 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 571.2809 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 576.2809 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 581.6976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 582.6976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 585.6976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 586.4206 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 586.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 587.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 602.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 604.4239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 605.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 606.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 610.4239 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 615.8406 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 620.8406 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 626.2572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 627.2572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 630.2572 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 630.9803 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 630.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 631.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 646.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 648.9835 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 649.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 650.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 654.9835 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 660.4002 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 665.4002 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 670.8169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 671.8169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 674.8169 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 675.5399 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 675.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 676.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 691.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 693.5432 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 274.1138 | 1370569.079 | ACTION | 693.5432 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 693.544 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 694.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 695.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 696.7873 | MonopileInstallation
| Feeder 0 | Queue | 127.1138 | 635569.079 | ACTION | 696.7873 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 699.5432 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 704.9599 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 708.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 709.9599 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 715.3765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 716.3765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 716.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 719.3765 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 720.0996 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 720.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 721.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 728.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 736.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 736.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 738.1028 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 739.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 740.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 744.1028 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 748.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 749.5195 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 754.5195 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 756.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 759.9362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 760.9362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 763.9362 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 766.9362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 767.6592 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 767.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 768.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 768.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 776.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 783.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 785.6625 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 786.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 787.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 788.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 791.6625 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 796.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 797.0792 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 802.0792 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 807.4958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 808.4958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 808.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 811.4958 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 812.2189 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 812.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 813.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 816.7873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 820.0305 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 820.0314 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 828.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 830.2221 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 831.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 832.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 836.2221 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 841.6388 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 846.6388 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 852.0555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 853.0555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 856.0555 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 856.7785 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 856.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 857.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 862.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 877.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 879.7818 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 880.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 881.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 887.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 891.7818 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 897.1985 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 902.1985 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 907.6151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 908.6151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 911.6151 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 912.3382 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 912.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 913.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 928.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 930.3414 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 931.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 932.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 936.3414 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 941.7581 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 946.7581 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 952.1748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 953.1748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 956.1748 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 956.8978 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 956.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 957.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 972.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 974.9011 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 278.1138 | 1390569.079 | ACTION | 974.9011 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 974.9019 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 975.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 976.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 978.1452 | MonopileInstallation
| Feeder 1 | Queue | 158.1138 | 790569.079 | ACTION | 978.1452 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 980.9011 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 986.3178 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 990.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 991.3178 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 996.7344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 997.7344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 998.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1000.7344 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1001.4575 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1001.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1002.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1010.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1017.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1018.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1019.4607 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1020.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1021.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1025.4607 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1030.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1030.8774 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1035.8774 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1038.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1041.2941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1042.2941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1045.2941 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1046.0171 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1046.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1047.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1050.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1058.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1062.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1064.0204 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1065.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1066.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1070.0204 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1070.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1075.4371 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1078.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1080.4371 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1085.8537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1086.8537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1089.8537 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1090.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1090.5768 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1090.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1091.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1098.1452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1101.3884 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1101.3892 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1106.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1108.58 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1109.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1110.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1114.58 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1119.9967 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1124.9967 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1130.4134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1131.4134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1134.4134 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1135.1364 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1135.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1136.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1151.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1153.1397 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1154.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1155.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1159.1397 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1164.5564 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1169.5564 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1174.973 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1175.973 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1178.973 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1179.6961 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1179.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1180.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1195.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1197.6993 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1198.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1199.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1203.6993 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1209.116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1214.116 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1219.5327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1220.5327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1223.5327 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1224.2557 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1224.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1225.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1240.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1242.259 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 264.1138 | 1320569.079 | ACTION | 1242.259 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1242.2598 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1243.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1244.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1245.5031 | MonopileInstallation
| Feeder 0 | Queue | 144.1138 | 720569.079 | ACTION | 1245.5031 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1248.259 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1253.6757 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1257.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1258.6757 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1264.0923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1265.0923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1265.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1268.0923 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1268.8154 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1268.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1269.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1277.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1284.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1285.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1286.8186 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1287.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1288.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1292.8186 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1297.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1298.2353 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1303.2353 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1305.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1308.652 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1309.652 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1312.652 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1313.375 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1313.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1314.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 3 | 31250 | ACTION | 1317.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1317.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1325.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1332.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1334.3783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1335.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1336.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1337.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1340.3783 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1345.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1345.7949 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1350.7949 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1356.2116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1357.2116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1357.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1360.2116 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1360.9347 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1360.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1361.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1365.5031 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1368.7463 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1368.7471 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1376.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1378.9379 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1379.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1380.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1384.9379 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1390.3546 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1395.3546 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1400.7713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1401.7713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1404.7713 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1405.4943 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1405.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1406.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 1416.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1431.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1433.4976 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1434.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1435.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1439.4976 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1444.9142 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1449.9142 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1455.3309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1456.3309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1459.3309 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1460.054 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1460.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1461.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1476.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1478.0572 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1479.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1480.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1484.0572 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1489.4739 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1494.4739 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1499.8906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1500.8906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1503.8906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1504.6136 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1504.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1505.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1520.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1522.6169 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 277.1138 | 1385569.079 | ACTION | 1522.6169 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1522.6177 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1523.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1524.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1525.861 | MonopileInstallation
| Feeder 1 | Queue | 157.1138 | 785569.079 | ACTION | 1525.861 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1528.6169 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1534.0335 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1537.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1539.0335 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1544.4502 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1545.4502 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1545.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1548.4502 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1549.1733 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1549.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1550.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1557.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 1560.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1565.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1575.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1577.1765 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1577.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1578.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1579.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1583.1765 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1585.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1588.5932 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1593.5932 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1597.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1599.0099 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1600.0099 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1603.0099 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1603.7329 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1603.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1604.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1605.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1617.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1619.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1621.7362 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1622.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1623.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1625.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1627.7362 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1633.1528 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1637.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1638.1528 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1643.5695 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1644.5695 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1645.861 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1647.5695 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1648.2926 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1648.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 1649.1042 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1649.105 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1649.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1664.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1666.2958 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1667.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1668.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1672.2958 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1677.7125 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1682.7125 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1688.1292 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1689.1292 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1692.1292 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1692.8522 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1692.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1693.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1708.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1710.8555 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1711.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1712.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1716.8555 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1722.2721 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1727.2721 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1732.6888 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1733.6888 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1736.6888 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1737.4119 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1737.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1738.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1753.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1755.4151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1756.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1757.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1761.4151 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1766.8318 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1771.8318 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1777.2485 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1778.2485 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1781.2485 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1781.9715 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1781.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1782.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1797.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1799.9748 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 274.1138 | 1370569.079 | ACTION | 1799.9748 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1799.9756 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1800.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1801.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1803.2188 | MonopileInstallation
| Feeder 0 | Queue | 154.1138 | 770569.079 | ACTION | 1803.2188 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1805.9748 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1811.3914 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1815.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1816.3914 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1821.8081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1822.8081 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1823.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1825.8081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1826.5312 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1826.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1827.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1835.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1842.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1843.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1844.5344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1845.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1846.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1850.5344 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1855.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1855.9511 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1860.9511 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1863.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1866.3678 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1867.3678 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1870.3678 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1871.0908 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1871.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1872.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1875.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1883.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1887.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1889.0941 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1890.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1891.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1895.0941 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1895.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1900.5107 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1903.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1905.5107 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1910.9274 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1911.9274 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1914.9274 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1915.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1915.6505 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1915.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1916.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1923.2188 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 1926.4621 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1926.4629 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1931.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1933.6537 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1934.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1935.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1939.6537 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1945.0704 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1950.0704 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1955.487 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1956.487 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1959.487 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1960.2101 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1960.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1961.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 5 | 52083.3333 | ACTION | 1966.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 1981.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1983.2134 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1984.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1985.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1989.2134 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1994.63 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 1999.63 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2005.0467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2006.0467 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2009.0467 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2009.7698 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2009.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2010.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 11 | 114583.3333 | ACTION | 2021.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2036.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2038.773 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2039.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2040.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2044.773 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2050.1897 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2055.1897 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2060.6063 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2061.6063 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2064.6063 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2065.3294 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2065.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2066.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2081.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2083.3327 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 280.1138 | 1400569.079 | ACTION | 2083.3327 | MonopileInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2083.3335 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2084.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2085.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2086.5767 | MonopileInstallation
| Feeder 1 | Queue | 160.1138 | 800569.079 | ACTION | 2086.5767 | MonopileInstallation | [12 empty] | Site
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2089.3327 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2094.7493 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2098.5767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2099.7493 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2105.166 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2106.166 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2106.5767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2109.166 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2109.8891 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2109.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2110.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2118.5767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2125.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2126.5767 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2127.8923 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2128.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2129.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2133.8923 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2139.309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2144.309 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2149.7256 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2150.7256 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2153.7256 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2154.4487 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2154.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2155.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2170.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2172.452 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2173.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2174.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2178.452 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2183.8686 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2188.8686 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2194.2853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2195.2853 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2198.2853 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2199.0084 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2199.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2200.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2215.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2217.0116 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2218.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2219.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2223.0116 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2228.4283 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2233.4283 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2238.8449 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2239.8449 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2242.8449 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2243.568 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2243.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2244.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2259.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2261.5713 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2262.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2263.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2267.5713 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2272.9879 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2277.9879 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2283.4046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2284.4046 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2287.4046 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2288.1277 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2288.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2289.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2304.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2306.1309 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2307.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2308.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2312.1309 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2317.5476 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2322.5476 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2327.9642 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2328.9642 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2331.9642 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2332.6873 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2332.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2333.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 15 | 156250 | ACTION | 2348.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2350.6906 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 264.1138 | 1320569.079 | ACTION | 2350.6906 | MonopileInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2350.6914 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2351.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2352.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2353.9346 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2356.6906 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2362.1072 | MonopileInstallation | MonopileInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 2362.1072 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 2362.1072 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 2362.1072 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2364.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 2365.3505 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2366.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2368.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2370.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2372.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2372.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2373.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2374.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2376.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2378.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2380.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2382.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2384.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2385.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2385.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2386.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2388.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2390.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2392.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2394.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2396.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2397.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2398.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2398.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2400.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2402.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2404.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2406.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2408.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2409.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2410.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2411.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2413.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2415.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2417.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2419.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2421.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2421.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2422.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2423.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2425.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2427.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2429.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2431.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2433.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2434.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2434.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2435.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 73.5 | 367500 | ACTION | 2435.6072 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2437.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2438.8505 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2438.8513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 73.5008 | 765633.6892 | ACTION | 2438.8513 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2439.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2441.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2443.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2443.8513 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2445.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2446.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2447.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2447.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2449.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2449.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2450.268 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2450.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2451.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2452.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2453.648 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2453.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2454.408 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2455.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2456.408 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2457.408 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2457.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2458.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2458.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2459.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2460.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2460.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2461.548 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2462.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2463.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2464.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2465.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2466.068 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2466.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2467.068 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2468.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2468.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2470.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2470.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2470.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2471.568 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2471.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2472.068 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2472.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2473.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2474.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2475.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2475.568 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2476.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2477.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2478.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2478.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2479.068 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2480.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2480.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2482.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2482.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2483.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2483.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2484.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2486.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2487.4846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2488.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2490.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2492.4846 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2492.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2494.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2495.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2496.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2496.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2497.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2498.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2498.9013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2499.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2500.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2501.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2502.2813 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2502.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2503.0413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 2504.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2505.0413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2506.0413 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 2506.8572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2507.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2507.6072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2508.3572 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 2509.1072 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2509.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2510.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2511.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 2512.3505 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2512.3513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2513.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2514.7013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2515.7013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2517.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2519.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2520.2013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2520.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2522.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2523.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2524.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2525.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2527.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2527.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2529.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2530.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2536.118 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2541.118 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2546.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2547.5346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2547.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2549.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2550.9146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2551.6746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2553.6746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2554.6746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2555.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2557.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2558.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2560.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2562.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2563.3346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2564.3346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2565.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2567.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2568.8346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2569.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2570.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2572.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2572.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2574.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2575.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2576.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2577.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2579.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2584.7513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2589.7513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2595.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2596.168 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2596.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2598.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2599.548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2600.308 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2602.308 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2603.308 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2604.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2606.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2607.448 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2608.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2610.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2611.968 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2612.968 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2614.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2616.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2617.468 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2617.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2619.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2620.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2621.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2622.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2624.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2624.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2626.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2627.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2633.3846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2638.3846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2643.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2644.8013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2645.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2647.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2648.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2648.9413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2650.9413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2651.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2653.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2655.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2656.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2657.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2659.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2660.6013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2661.6013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2663.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2665.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2666.1013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2666.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2668.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2669.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2670.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2671.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2673.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2673.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2675.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2676.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2682.018 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2687.018 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2692.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2693.4346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2693.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2695.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2696.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2697.5746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2699.5746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2700.5746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2701.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2703.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2704.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2706.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2708.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2709.2346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2710.2346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2711.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2713.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2714.7346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2715.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2716.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2718.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2718.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2720.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2721.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2722.2346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 283.3833 | 1416916.6667 | ACTION | 2722.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 209.8833 | 1049416.6667 | ACTION | 2722.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2722.2355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2723.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2725.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2725.4787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2727.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2729.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2730.6513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2731.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2733.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2735.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2735.6513 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2736.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2736.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2737.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 29 | 302083.3333 | ACTION | 2764.6513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2770.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 33 | 165000 | ACTION | 2770.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2771.068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2771.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2772.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2774.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2776.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2778.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 2779.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2780.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2781.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2781.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2782.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2782.448 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2782.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2783.208 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2784.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2785.208 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2786.208 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2786.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2787.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2788.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2789.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2790.348 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2790.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2791.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2792.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2793.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2793.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2794.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2794.868 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2795.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2795.868 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2797.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2797.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2799.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2799.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2800.368 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2800.868 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2801.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2802.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2803.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2803.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2804.368 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2805.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2805.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2805.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2806.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2807.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2807.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2807.868 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2809.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2809.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2810.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2811.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2813.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2815.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2816.2846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2817.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2818.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2818.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2819.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2821.2846 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2821.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2823.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2825.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2826.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2827.7013 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 2827.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2828.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 2829.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2830.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2830.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2831.0813 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2831.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2831.8413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 2831.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2833.8413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2834.8413 | TurbineInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 2835.222 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2835.2228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2835.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2837.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2838.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2840.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2842.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2843.5013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2844.5013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2846.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2848.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2849.0013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2849.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2851.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2852.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2853.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2854.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2856.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2856.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2858.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2859.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2864.918 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2869.918 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2875.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2876.3346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2876.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2878.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2879.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2880.4746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2882.4746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2883.4746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2884.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2886.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2887.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2889.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2891.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2892.1346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2893.1346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2894.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2896.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2897.6346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2898.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2899.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2901.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2901.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2903.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2904.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2905.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2906.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2908.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2913.5513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2918.5513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2923.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2924.968 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2925.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2927.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2928.348 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2929.108 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2931.108 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2932.108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2933.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2935.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2936.248 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2937.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2939.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2940.768 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2941.768 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2943.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2945.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2946.268 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2946.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2948.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2949.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2950.268 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2951.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2953.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2953.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2955.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2956.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2962.1846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 2967.1846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2972.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2973.6013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 2973.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2975.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2976.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 2977.7413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2979.7413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2980.7413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 2981.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2983.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 2984.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 2986.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 2988.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 2989.4013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2990.4013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 2991.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 2993.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 2994.9013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2995.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 2996.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 2998.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 2998.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3000.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3001.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3002.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3003.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3005.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3010.818 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 22 | 229166.6667 | ACTION | 3032.818 | TurbineInstallation
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3037.818 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3043.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3044.2346 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3046.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3046.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 41666.6667 | ACTION | 3050.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3052.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3053.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3054.3746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3056.3746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3057.3746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3058.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3060.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3061.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3063.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3065.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3066.0346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3067.0346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3068.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3070.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3071.5346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3072.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3073.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3075.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3075.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3077.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3078.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3079.0346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 356.8 | 1784000 | ACTION | 3079.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 243.8118 | 1219059.2259 | ACTION | 3079.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3079.0355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3080.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3082.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3082.2787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3084.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3086.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3087.4513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3088.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3090.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3092.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3092.4513 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3093.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3093.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3094.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3096.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3097.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3098.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3098.868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3099.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3100.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3101.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3102.248 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3102.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3103.008 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3104.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3105.008 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3105.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3106.008 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3106.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3106.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3107.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3108.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3109.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3110.148 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3110.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3111.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3112.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3113.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3114.668 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3114.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3115.668 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3116.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3117.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3117.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3118.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3119.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3119.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3120.168 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3120.668 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3121.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3122.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3123.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3123.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3124.168 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3125.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3125.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3127.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3127.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3127.668 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3129.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3129.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3129.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3130.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3130.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3131.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3133.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3135.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3136.0846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3137.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3139.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3141.0846 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3141.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3142.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3142.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3143.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3145.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3146.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3147.5013 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3147.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3147.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3149.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3149.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3150.8813 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3151.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3151.6413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3153.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3153.6413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3154.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3154.6413 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3155.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3155.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3155.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3157.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3158.7813 | TurbineInstallation
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3159.022 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3159.0228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3160.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3162.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3163.3013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3164.3013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3165.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3167.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3168.8013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3169.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3170.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3172.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3172.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3174.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3175.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3176.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3177.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3179.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3184.718 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3189.718 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3195.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3196.1346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3196.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3198.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3199.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3200.2746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3202.2746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3203.2746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3204.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3206.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3207.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3208.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3210.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3211.9346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3212.9346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3214.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3216.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3217.4346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3217.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3219.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3220.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3221.4346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3222.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3224.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3224.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3226.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3227.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3233.3513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3238.3513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3243.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3244.768 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3245.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3247.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3248.148 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3248.908 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3250.908 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3251.908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3253.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3255.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3256.048 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3257.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3259.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3260.568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3261.568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3263.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3265.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3266.068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3266.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3268.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3269.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3270.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3271.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3273.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3273.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3275.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3276.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3281.9846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3286.9846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3292.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3293.4013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3293.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3295.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3296.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3297.5413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3299.5413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3300.5413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3301.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3303.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3304.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3306.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3308.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3309.2013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3310.2013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3311.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3313.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3314.7013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3315.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3316.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3318.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3318.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3320.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3321.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3322.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3323.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3325.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3330.618 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3335.618 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3341.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3342.0346 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3352.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3352.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3354.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3355.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3356.1746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3358.1746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3359.1746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3360.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3362.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3363.3146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3364.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3366.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3367.8346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3368.8346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3370.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3372.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3373.3346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3373.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3375.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3376.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3377.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3378.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3380.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3380.8346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 301.8 | 1509000 | ACTION | 3380.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 221.8118 | 1109059.2259 | ACTION | 3380.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3380.8355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3382.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3383.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3384.0787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3386.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3388.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3389.2513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3390.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3392.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3394.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3394.2513 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3394.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3395.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3396.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3398.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3399.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3400.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3400.668 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3401.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3402.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3403.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3404.048 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3404.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3404.808 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3406.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3406.808 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3407.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3407.808 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3407.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3408.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3408.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3410.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3410.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3411.948 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3412.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3413.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3414.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3415.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3416.468 | TurbineInstallation
| Feeder 0 | Delay | 2 | 10000 | ACTION | 3416.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3417.468 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3418.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3418.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3420.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 3 | 15000 | ACTION | 3421.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3421.968 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3422.468 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3423.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3423.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3424.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 1 | 5000 | ACTION | 3425.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3425.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3425.968 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3426.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3426.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3427.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3428.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3428.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3429.468 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3430.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3430.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3432.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3432.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3434.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3436.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3437.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3437.8846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3438.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3439.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3441.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3442.8846 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3443.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3445.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3447.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3448.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3449.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3449.3013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3449.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3449.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3450.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3451.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3451.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3452.6813 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3453.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3453.4413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3455.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3455.4413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3456.4413 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3457.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3457.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3459.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3459.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3460.5813 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3461.3287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3462.0787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3462.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3462.8287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3463.5787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3464.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3465.1013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3466.1013 | TurbineInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 3466.822 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3466.8228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3467.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3469.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3470.6013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3471.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3472.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3474.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3474.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3476.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3477.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3478.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3479.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3481.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3486.518 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3491.518 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3496.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3497.9346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3498.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3500.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3501.3146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3502.0746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3504.0746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3505.0746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3506.2146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3508.2146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3509.2146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3510.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3512.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3513.7346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3514.7346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3516.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3518.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3519.2346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3519.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3521.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3522.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3523.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3524.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3526.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3526.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3528.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3529.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3535.1513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3540.1513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3545.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3546.568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3546.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3548.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3549.948 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3550.708 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3552.708 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3553.708 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3554.848 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3556.848 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3557.848 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3559.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3561.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3562.368 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3563.368 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3564.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3566.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3567.868 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3568.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3569.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3571.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3571.868 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3573.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3574.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3575.368 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3576.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3578.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3583.7846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3588.7846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3594.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3595.2013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3595.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3597.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3598.5813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3599.3413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3601.3413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3602.3413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3603.4813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3605.4813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3606.4813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3608.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3610.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3611.0013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3612.0013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3613.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3615.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3616.5013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3617.0013 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3627.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3628.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3629.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3631.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3631.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3633.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3634.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3635.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3636.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3638.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3643.418 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3648.418 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3653.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3654.8346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3655.2146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3657.2146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3658.2146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3658.9746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3660.9746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3661.9746 | TurbineInstallation
| WTIV | Delay | 41 | 427083.3333 | ACTION | 3702.9746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3704.1146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3706.1146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3707.1146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3708.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3710.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3711.6346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3712.6346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3714.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3716.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3717.1346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3717.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3719.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3720.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3721.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3722.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3724.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3724.6346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 343.8 | 1719000 | ACTION | 3724.6346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 257.8118 | 1289059.2259 | ACTION | 3724.6346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3724.6355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3726.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3727.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3727.8787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3729.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3731.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3733.0513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3733.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3735.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3737.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3738.0513 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3738.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3739.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3740.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3742.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3743.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3744.468 | TurbineInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 3767.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3767.848 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3769.848 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3770.848 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3771.608 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 30 | 150000 | ACTION | 3772.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3773.608 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3774.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3774.608 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3775.748 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3776.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3777.748 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3778.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3778.748 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3780.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3780.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3780.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3781.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3782.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3782.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3783.268 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3784.268 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3784.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3785.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3786.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3787.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3788.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3788.768 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3789.268 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3790.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3790.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3792.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3792.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3792.768 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3793.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3793.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3794.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3794.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3795.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3796.268 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3796.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3797.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3798.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3799.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3800.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3802.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3804.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3804.6846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3805.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3806.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3806.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3808.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3809.6846 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3810.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3812.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3814.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3815.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3816.1013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3816.4813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3816.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3817.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3818.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3818.4813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3819.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3819.4813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3820.2413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3821.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3822.2413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3823.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3823.2413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3824.3813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3825.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3826.3813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3827.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3827.3813 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3829.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 3 | 31250 | ACTION | 3830.3813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3831.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3833.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3835.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 7 | 35000 | ACTION | 3836.1287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3836.8787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3836.9013 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3837.6287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3837.9013 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3838.3787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3839.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3841.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 3841.622 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3841.6228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3843.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3844.4013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3844.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3846.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3847.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3848.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3849.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3851.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3851.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3853.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3854.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3860.318 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3865.318 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3870.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3871.7346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3872.1146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3874.1146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3875.1146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3875.8746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3877.8746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3878.8746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3880.0146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3882.0146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3883.0146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3884.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3886.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3887.5346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3888.5346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3890.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3892.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3893.0346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3893.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3895.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3896.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3897.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3898.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3900.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3900.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3902.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3903.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3908.9513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3913.9513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3919.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3920.368 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3920.748 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3922.748 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3923.748 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3924.508 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3926.508 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3927.508 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3928.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3930.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3931.648 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3933.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3935.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3936.168 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3937.168 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3938.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3940.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3941.668 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3942.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3943.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3945.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3945.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3947.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3948.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3949.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3950.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3952.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3957.5846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 3962.5846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3968.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3969.0013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3969.3813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3971.3813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3972.3813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3973.1413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3975.1413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3976.1413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3977.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3979.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3980.2813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3981.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3983.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3984.8013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3985.8013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3987.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3989.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3990.3013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3990.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3992.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3993.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3994.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3995.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3997.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3997.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3999.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4000.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4006.218 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4011.218 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4016.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4017.6346 | TurbineInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 4060.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4061.0146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4063.0146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4064.0146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4064.7746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4066.7746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4067.7746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4068.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4070.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4071.9146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4073.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4075.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4076.4346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4077.4346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4078.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4080.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4081.9346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4082.4346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4083.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4085.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4085.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4087.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4088.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4089.4346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 364.8 | 1824000 | ACTION | 4089.4346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 247.8118 | 1239059.2259 | ACTION | 4089.4346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4089.4355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4090.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4092.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4092.6787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4094.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4096.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4097.8513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4098.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4100.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4102.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4102.8513 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4103.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4104.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4104.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4106.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4108.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4108.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4109.268 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4109.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4110.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4111.648 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4112.648 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4112.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4113.408 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4114.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4115.408 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4115.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4116.408 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4116.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4117.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4117.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4119.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4119.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4120.548 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4121.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4122.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4123.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4124.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4125.068 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4125.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4126.068 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4127.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4127.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4127.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4128.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4129.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4129.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4130.568 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4131.068 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4131.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4132.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4133.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4134.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4134.568 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4135.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4136.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4137.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4137.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4138.068 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4139.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4139.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4140.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4140.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4141.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4141.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4143.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4145.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4146.4846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4147.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4149.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4151.4846 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4151.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4152.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4153.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4153.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4155.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4156.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4157.9013 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4157.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4158.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4159.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4160.2813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4161.2813 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4161.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4162.0413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4163.9287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4164.0413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4164.6787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4165.0413 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4165.4287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4166.1787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4166.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4168.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4169.1813 | TurbineInstallation
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4169.422 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4169.4228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4170.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4172.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4173.7013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4174.7013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4176.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4178.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4179.2013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4179.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4181.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4182.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4183.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4184.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4186.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4186.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4188.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4189.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4195.118 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4200.118 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4205.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4206.5346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4206.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4208.9146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4209.9146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4210.6746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4212.6746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4213.6746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4214.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4216.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4217.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4219.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4221.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4222.3346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4223.3346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4224.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4226.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4227.8346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4228.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4229.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4231.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4231.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4233.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4234.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4235.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4236.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4238.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4243.7513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4248.7513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4254.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4255.168 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4255.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4257.548 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4258.548 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4259.308 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4261.308 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4262.308 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4263.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4265.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4266.448 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4267.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4269.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4270.968 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4271.968 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 4279.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4281.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4282.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4284.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4285.468 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4285.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4287.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4288.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4289.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4290.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4292.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4292.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4294.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4295.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4301.3846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4306.3846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4311.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4312.8013 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 4327.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4328.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4330.1813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4331.1813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4331.9413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4333.9413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4334.9413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4336.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4338.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4339.0813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4340.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4342.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4343.6013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4344.6013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4346.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4348.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4349.1013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4349.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4351.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4352.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4353.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4354.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4356.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4356.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4358.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4359.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4365.018 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4370.018 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4375.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4376.4346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4376.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4378.8146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4379.8146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4380.5746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4382.5746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4383.5746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4384.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4386.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4387.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4389.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 13 | 135416.6667 | ACTION | 4402.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4404.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4405.2346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4406.2346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4407.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4409.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4410.7346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4411.2346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4412.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4414.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4414.7346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4416.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4417.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4418.2346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 328.8 | 1644000 | ACTION | 4418.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 248.8118 | 1244059.2259 | ACTION | 4418.2346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4418.2355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4419.7346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4421.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4421.4787 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4423.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4425.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4426.6513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4427.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4429.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4431.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4431.6513 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4432.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4432.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4433.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4435.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4437.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4437.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4438.068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4438.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4439.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4440.448 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4441.448 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4441.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4442.208 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4443.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4444.208 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4444.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4445.208 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4445.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4445.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4446.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4447.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4448.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4449.348 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4449.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4450.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4451.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4452.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4453.868 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4453.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4454.868 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4455.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4456.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4456.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4457.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4458.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4458.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4459.368 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4459.868 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4460.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4461.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4462.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4462.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4463.368 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4464.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4464.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4466.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4466.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4466.868 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4468.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4468.368 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4468.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4469.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4469.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4470.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4472.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4474.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4475.2846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4476.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4478.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4480.2846 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4480.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4481.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4481.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4482.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4484.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4485.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4486.7013 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4486.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4487.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4488.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4489.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4490.0813 | TurbineInstallation
| WTIV | Delay | 61 | 635416.6667 | ACTION | 4551.0813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4551.8413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4553.8413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 66 | 330000 | ACTION | 4554.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4554.8413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4555.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4556.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4557.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4558.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4560.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4562.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4563.5013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4564.5013 | TurbineInstallation
| Feeder 1 | Delay | 8 | 40000 | ACTION | 4564.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4566.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4566.7287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4567.4787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4568.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4568.2287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4568.9787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4569.0013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4569.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4571.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 4572.222 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4572.2228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4572.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4573.0013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4574.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4576.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4576.5013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4578.0013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4579.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4584.918 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4589.918 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4595.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4596.3346 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4603.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4603.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4605.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4607.7146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4608.7146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4609.4746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4611.4746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4612.4746 | TurbineInstallation
| WTIV | Delay | 86 | 895833.3333 | ACTION | 4698.4746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4699.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4702.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4704.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4705.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4707.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4709.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4710.1346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4711.1346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4712.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4714.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4715.6346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4716.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4717.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4719.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4719.6346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4721.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4722.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4723.1346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4724.6346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4726.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4731.5513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4736.5513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4741.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4742.968 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4743.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4745.348 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4746.348 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4747.108 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4749.108 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4750.108 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4751.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4753.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4754.248 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4755.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4757.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4758.768 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4759.768 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4761.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4763.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4764.268 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4764.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4766.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4767.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4768.268 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4769.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4771.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4771.768 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4773.268 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4774.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4780.1846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4785.1846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4790.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4791.6013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4791.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4793.9813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4794.9813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4795.7413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4797.7413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4798.7413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4799.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4801.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4802.8813 | TurbineInstallation
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4834.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4836.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4838.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4839.4013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4840.4013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4841.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4843.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4844.9013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4845.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4846.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4848.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4848.9013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4850.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4851.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4852.4013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4853.9013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4855.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4860.818 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4865.818 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4871.2346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4872.2346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4872.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4874.6146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4875.6146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4876.3746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4878.3746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4879.3746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4880.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4882.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4883.5146 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 4888.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4890.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4892.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4893.0346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4894.0346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4895.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4896.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4898.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4899.5346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4900.0346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4901.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4903.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4903.5346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4905.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4906.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4907.0346 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 488.8 | 2444000 | ACTION | 4907.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Queue | 334.8118 | 1674059.2259 | ACTION | 4907.0346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4907.0355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4908.5346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4910.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4910.2787 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4912.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4914.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4915.4513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4916.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4918.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4920.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4920.4513 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4921.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4921.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4922.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4924.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4925.868 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4926.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4926.868 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4927.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4928.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4929.248 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4930.248 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4930.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4931.008 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4932.5287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4933.008 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4933.2787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4934.008 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4934.0287 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4934.7787 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4935.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4937.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 4938.022 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4938.0228 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4938.148 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4939.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4941.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4942.668 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4943.668 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4945.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4947.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4948.168 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4948.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4950.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4951.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4952.168 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4953.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4955.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4955.668 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4957.168 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4958.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4964.0846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 4969.0846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4974.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4975.5013 | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 4982.5013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4982.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4984.8813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4985.8813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4986.6413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4988.6413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4989.6413 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4991.6413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4992.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4994.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4995.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4997.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4999.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5000.3013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5001.3013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5002.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5004.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5005.8013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5006.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5007.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5009.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5009.8013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5011.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5012.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5013.3013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5014.8013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5016.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5021.718 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5026.718 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5032.1346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5033.1346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5033.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5035.5146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5036.5146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5037.2746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5039.2746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5040.2746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5041.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5043.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5044.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5045.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5047.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5048.9346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5049.9346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5051.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5053.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5054.4346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5054.9346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5056.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5057.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5058.4346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5059.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5061.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5061.9346 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 5065.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5067.4346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5068.9346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5074.3513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5079.3513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5084.768 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5085.768 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5086.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5088.148 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5089.148 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5089.908 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5091.908 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5092.908 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5094.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5096.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5097.048 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5098.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5100.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5101.568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5102.568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5104.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5106.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5107.068 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5107.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5109.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5110.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5111.068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5112.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5114.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5114.568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5116.068 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5117.568 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5122.9846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 5127.9846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5133.4013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5134.4013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5134.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5136.7813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5137.7813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5138.5413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5140.5413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5141.5413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5142.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5144.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5145.6813 | TurbineInstallation
| WTIV | Delay | 1264 | 13166666.6667 | ACTION | 6409.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6411.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6413.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6414.2013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6415.2013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6416.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6418.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6419.7013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6420.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6421.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6423.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6423.7013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6425.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6426.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6427.2013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6428.7013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6430.2013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6435.618 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6440.618 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6446.0346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6447.0346 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6447.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6449.4146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6450.4146 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6451.1746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6453.1746 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6454.1746 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6455.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6457.3146 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6458.3146 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6459.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6461.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6462.8346 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6463.8346 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6465.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6467.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6468.3346 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6468.8346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6470.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6471.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6472.3346 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6473.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6475.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6475.8346 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 1568.8 | 7844000 | ACTION | 6475.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Queue | 1537.8118 | 7689059.2259 | ACTION | 6475.8346 | TurbineInstallation | [12 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6475.8355 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6477.3346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6478.8346 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 3.2432 | 16216.2162 | ACTION | 6479.0787 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6484.2513 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6489.2513 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6494.668 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6495.668 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6496.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6498.048 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6499.048 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6499.808 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6516.808 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6518.808 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6519.808 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6520.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6522.948 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6523.948 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6525.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6527.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6528.468 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6529.468 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6530.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6532.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6533.968 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6534.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6535.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6537.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6537.968 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6539.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6540.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6541.468 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6542.968 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6544.468 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6549.8846 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 5 | 52083.3333 | ACTION | 6554.8846 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6560.3013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6561.3013 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6561.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6563.6813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6564.6813 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6565.4413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6567.4413 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6568.4413 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6569.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6571.5813 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6572.5813 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6574.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6576.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6577.1013 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6578.1013 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6579.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6581.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6582.6013 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6583.1013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6584.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6586.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6586.6013 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6588.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6589.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6590.1013 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 114.2667 | 571333.3333 | ACTION | 6590.1013 | TurbineInstallation | [12 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6590.1021 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6591.6013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6593.1013 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 3.2432 | 16216.2162 | ACTION | 6593.3454 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6598.518 | TurbineInstallation | TurbineInstallation | 5 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 6601.7612 | TurbineInstallation