## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 63.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 65.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 65.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 66.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 68.5599 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 71.5599 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 79.5599 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 80.283 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 80.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 81.2862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 82.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 84.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 85.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 88.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 89.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 93.7862 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 94.1029 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 137.3461 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 149.3461 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 157.3461 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 10 | 104166.6667 | ACTION | 167.3461 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 179.3461 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 180.3461 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 181.3461 | MonopileInstallation
| WTIV | Transit | 32.2432 | 335867.1171 | ACTION | 213.5894 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 215.5894 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 215.906 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 216.906 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 219.906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 220.6291 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 220.6324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 221.6324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 223.1324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 225.1324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 226.1324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 227.1324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 246.1324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 250.1324 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 250.449 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 293.6923 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 305.6923 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 313.6923 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 356.9355 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 358.9355 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 359.2522 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 360.2522 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 363.2522 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 363.9752 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 363.9785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 364.9785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 366.4785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 368.4785 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 369.4785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 370.4785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 374.4785 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 374.7952 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 418.0384 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 430.0384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 438.0384 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 481.2816 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 483.2816 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 483.5983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 484.5983 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 487.5983 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 488.3214 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 488.3246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 489.3246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 490.8246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 492.8246 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 493.8246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 494.8246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 498.8246 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 499.1413 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 21 | 218750 | ACTION | 520.1413 | MonopileInstallation
| WTIV | Delay | 71 | 739583.3333 | ACTION | 591.1413 | MonopileInstallation
| WTIV | Transit | 22.2432 | 231700.4505 | ACTION | 613.3845 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 625.3845 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 633.3845 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 676.6278 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 678.6278 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 678.9445 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 679.9445 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 682.9445 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 683.6675 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 683.6708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 684.6708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 686.1708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 688.1708 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 689.1708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 690.1708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 694.1708 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 694.4874 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 737.7307 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 749.7307 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 757.7307 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 800.9739 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 802.9739 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 803.2906 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 804.2906 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 807.2906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 808.0137 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 808.0169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 809.0169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 810.5169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 812.5169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 813.5169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 814.5169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 818.5169 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 818.8336 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 862.0768 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 874.0768 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 882.0768 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 7 | 72916.6667 | ACTION | 889.0768 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 913.0768 | MonopileInstallation
| WTIV | Transit | 36.2432 | 377533.7838 | ACTION | 949.3201 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 951.3201 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 951.6367 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 952.6367 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 955.6367 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 956.3598 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 956.363 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 957.363 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 958.863 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 960.863 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 961.863 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 962.863 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 966.863 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 967.1797 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1010.4229 | MonopileInstallation
| WTIV | Delay | 33 | 343750 | ACTION | 1043.4229 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1055.4229 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1063.4229 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 17 | 177083.3333 | ACTION | 1080.4229 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1081.4229 | MonopileInstallation
| WTIV | Transit | 4 | 41666.6667 | ACTION | 1085.4229 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1088.4229 | MonopileInstallation
| WTIV | Transit | 22.2432 | 231700.4505 | ACTION | 1110.6662 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1112.6662 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1112.9829 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1113.9829 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1116.9829 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1117.7059 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1117.7092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1118.7092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1120.2092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1122.2092 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1123.2092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1124.2092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1128.2092 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1128.5258 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 38 | 395833.3333 | ACTION | 1166.5258 | MonopileInstallation
| WTIV | Delay | 66 | 687500 | ACTION | 1232.5258 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 1237.7691 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1249.7691 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1257.7691 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 15 | 156250 | ACTION | 1272.7691 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 1281.7691 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 1282.7691 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1283.7691 | MonopileInstallation
| WTIV | Transit | 27.2432 | 283783.7838 | ACTION | 1311.0123 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1313.0123 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1313.329 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1314.329 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1317.329 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1318.0521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1318.0553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1319.0553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1320.5553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1322.5553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1323.5553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1324.5553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1328.5553 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1328.872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1372.1152 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1384.1152 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1392.1152 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 22 | 229166.6667 | ACTION | 1414.1152 | MonopileInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 1434.1152 | MonopileInstallation
| WTIV | Transit | 12 | 125000 | ACTION | 1446.1152 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1447.1152 | MonopileInstallation
| WTIV | Transit | 9.2432 | 96283.7838 | ACTION | 1456.3585 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1458.3585 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1458.6751 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1459.6751 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1462.6751 | MonopileInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 1479.6751 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1480.3982 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1480.4014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1481.4014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1482.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1484.9014 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1485.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1486.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 1492.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1496.9014 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1497.2181 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1540.4614 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1552.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1560.4614 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 33 | 343750 | ACTION | 1593.4614 | MonopileInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 1616.4614 | MonopileInstallation
| WTIV | Transit | 10.2432 | 106700.4505 | ACTION | 1626.7046 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1628.7046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1629.0213 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1630.0213 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1633.0213 | MonopileInstallation
| WTIV | Delay | 31 | 322916.6667 | ACTION | 1664.0213 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1664.7443 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1664.7476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1665.7476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1667.2476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1669.2476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1670.2476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1671.2476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1675.2476 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1675.5642 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1718.8075 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1730.8075 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1738.8075 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 1754.8075 | MonopileInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 1779.8075 | MonopileInstallation
| WTIV | Transit | 27.2432 | 283783.7838 | ACTION | 1807.0507 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1809.0507 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1809.3674 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1810.3674 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1813.3674 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1814.0905 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1814.0937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1815.0937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1816.5937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1818.5937 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1819.5937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1820.5937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1824.5937 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1824.9104 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1868.1536 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1880.1536 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1888.1536 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1931.3969 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1933.3969 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1933.7135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1934.7135 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1937.7135 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1938.4366 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1938.4398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1939.4398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1940.9398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1942.9398 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1943.9398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1944.9398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1948.9398 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1949.2565 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1992.4998 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2004.4998 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2012.4998 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2055.743 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2057.743 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2058.0597 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2059.0597 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2062.0597 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2062.7827 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2062.786 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2063.786 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2065.286 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2067.286 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2068.286 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2069.286 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2073.286 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2073.6027 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2116.8459 | MonopileInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 2133.8459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2145.8459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2153.8459 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2197.0891 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2199.0891 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2199.4058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2200.4058 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2203.4058 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2204.1289 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2204.1321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2205.1321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2206.6321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2208.6321 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2209.6321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2210.6321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2214.6321 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2214.9488 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2258.192 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2270.192 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2278.192 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 2294.192 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2304.192 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 2305.192 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 2335.192 | MonopileInstallation
| WTIV | Transit | 26.2432 | 273367.1171 | ACTION | 2361.4353 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2363.4353 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2363.7519 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2364.7519 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2367.7519 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2368.475 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2368.4783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2369.4783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2370.9783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2372.9783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2373.9783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2374.9783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 2408.9783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2412.9783 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2413.2949 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2456.5382 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2468.5382 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2476.5382 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2519.7814 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2521.7814 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2522.0981 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2523.0981 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2526.0981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2526.8211 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2526.8244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2527.8244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2529.3244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2531.3244 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2532.3244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2534.3244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2535.3244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2539.3244 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2539.6411 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2582.8843 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 2594.8843 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2606.8843 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2614.8843 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2658.1275 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2660.1275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2660.4442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2661.4442 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2664.4442 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2665.1673 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2665.1705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2666.1705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2667.6705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2669.6705 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2670.6705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2671.6705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2675.6705 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2675.9872 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 10 | 104166.6667 | ACTION | 2685.9872 | MonopileInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 2699.9872 | MonopileInstallation
| WTIV | Transit | 33.2432 | 346283.7838 | ACTION | 2733.2304 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2745.2304 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2753.2304 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2796.4737 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2798.4737 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2798.7903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2799.7903 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2802.7903 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2803.5134 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2803.5167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2804.5167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2806.0167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2808.0167 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2809.0167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2810.0167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2814.0167 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2814.3333 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 23 | 239583.3333 | ACTION | 2837.3333 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2839.3333 | MonopileInstallation
| WTIV | Transit | 20.2432 | 210867.1171 | ACTION | 2859.5766 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2871.5766 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2879.5766 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2922.8198 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2924.8198 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2925.1365 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2926.1365 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2929.1365 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2929.8595 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2929.8628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2930.8628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2932.3628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2934.3628 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2935.3628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2936.3628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2940.3628 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2940.6795 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2983.9227 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2995.9227 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3003.9227 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 3008.9227 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 3023.9227 | MonopileInstallation
| WTIV | Transit | 29 | 302083.3333 | ACTION | 3052.9227 | MonopileInstallation
| WTIV | Delay | 29 | 302083.3333 | ACTION | 3081.9227 | MonopileInstallation
| WTIV | Transit | 9.2432 | 96283.7838 | ACTION | 3091.166 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3093.166 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3093.4826 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3094.4826 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3097.4826 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3098.2057 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3098.2089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3099.2089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3100.7089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3102.7089 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3103.7089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3104.7089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3108.7089 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3109.0256 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3152.2688 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3164.2688 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3172.2688 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3215.5121 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3217.5121 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3217.8288 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3218.8288 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3221.8288 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3222.5518 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3224.5518 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3224.5551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3225.5551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3227.0551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3229.0551 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3230.0551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3231.0551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3235.0551 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3235.3717 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3278.615 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3290.615 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3298.615 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3341.8582 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3343.8582 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3344.1749 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3345.1749 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3348.1749 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3348.898 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3348.9012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3349.9012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3351.4012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3353.4012 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3354.4012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3355.4012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3359.4012 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3359.7179 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3402.9611 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3414.9611 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3422.9611 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 44 | 458333.3333 | ACTION | 3466.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3467.9611 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3468.9611 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 3473.9611 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3474.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3475.9611 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3477.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3478.9611 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3488.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3489.9611 | MonopileInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 3496.9611 | MonopileInstallation
| WTIV | Transit | 34.2432 | 356700.4505 | ACTION | 3531.2044 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3533.2044 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3533.521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3534.521 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3537.521 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3538.2441 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3538.2473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3539.2473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3540.7473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3542.7473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3543.7473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3544.7473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3548.7473 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3549.064 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3592.3072 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3604.3072 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3612.3072 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3655.5505 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3657.5505 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3657.8672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3658.8672 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3661.8672 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3662.5902 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3662.5935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3663.5935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3665.0935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3667.0935 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3668.0935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3669.0935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3673.0935 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3673.4101 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3716.6534 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3724.6534 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3736.6534 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3744.6534 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3787.8966 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3789.8966 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3790.2133 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3791.2133 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3794.2133 | MonopileInstallation
| WTIV | Delay | 26 | 270833.3333 | ACTION | 3820.2133 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3820.9364 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3820.9396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3821.9396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 37 | 385416.6667 | ACTION | 3858.9396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3860.4396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3862.4396 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3864.4396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3865.4396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3866.4396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3870.4396 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3870.7563 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3913.9995 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3925.9995 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3933.9995 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3977.2428 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3979.2428 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3979.5594 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3980.5594 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3983.5594 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3984.2825 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3984.2857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3985.2857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3986.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3988.7857 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3989.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3990.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3994.7857 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3995.1024 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4038.3457 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4050.3457 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4058.3457 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4101.5889 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4103.5889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4103.9056 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4104.9056 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4107.9056 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4108.6286 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4108.6319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4109.6319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4111.1319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4113.1319 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4114.1319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4115.1319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4119.1319 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4119.4485 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4162.6918 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4174.6918 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4182.6918 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4225.935 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4227.935 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4228.2517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4229.2517 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4232.2517 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4232.9748 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4232.978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4233.978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4235.478 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4237.478 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4238.478 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4239.478 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4243.478 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4243.7947 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4287.0379 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4299.0379 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4307.0379 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4350.2812 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4352.2812 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4352.5978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4353.5978 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4356.5978 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4357.3209 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4357.3242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4358.3242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4359.8242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4361.8242 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4362.8242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4363.8242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4367.8242 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4368.1408 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4411.3841 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4423.3841 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4431.3841 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4474.6273 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4476.6273 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4476.944 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4477.944 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4480.944 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4481.667 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4481.6703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4482.6703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4484.1703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4486.1703 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4487.1703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4488.1703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4492.1703 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4492.487 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4535.7302 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4547.7302 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4555.7302 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4598.9734 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4600.9734 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4601.2901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4602.2901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4605.2901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4606.0132 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4606.0164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4607.0164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4608.5164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4610.5164 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4611.5164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4612.5164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4616.5164 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4616.8331 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4660.0763 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4672.0763 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4680.0763 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4723.3196 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4725.3196 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4725.6362 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4726.6362 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4729.6362 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 4732.6362 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4733.3593 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4733.3626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4734.3626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4735.8626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4737.8626 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4738.8626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4739.8626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4743.8626 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4744.1792 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 38 | 395833.3333 | ACTION | 4782.1792 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 4788.1792 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 4793.4225 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4805.4225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4813.4225 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4856.6657 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4858.6657 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4858.9824 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4859.9824 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4862.9824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4863.7054 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4863.7087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4864.7087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4866.2087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4868.2087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4869.2087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4870.2087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4874.2087 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4874.5254 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4917.7686 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4929.7686 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4937.7686 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4981.0118 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4983.0118 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4983.3285 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4984.3285 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4987.3285 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4988.0516 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4988.0548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4989.0548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4990.5548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4992.5548 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4993.5548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4994.5548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4998.5548 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4998.8715 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 25 | 260416.6667 | ACTION | 5023.8715 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5024.8715 | MonopileInstallation
| WTIV | Transit | 13 | 135416.6667 | ACTION | 5037.8715 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5038.8715 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 5044.1147 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5056.1147 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5064.1147 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5107.358 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5109.358 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5109.6746 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5110.6746 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5113.6746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5114.3977 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5114.401 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5115.401 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5116.901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5118.901 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5119.901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5120.901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5124.901 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5125.2176 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5168.4609 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5180.4609 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5188.4609 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5231.7041 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5233.7041 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5234.0208 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5235.0208 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5238.0208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5238.7438 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5238.7471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5239.7471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5241.2471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5243.2471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5244.2471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5245.2471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5249.2471 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5249.5638 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5292.807 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5304.807 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5312.807 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5356.0503 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5358.0503 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5358.3669 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5359.3669 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5362.3669 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5363.09 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5363.0932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5364.0932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5365.5932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5367.5932 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5368.5932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5369.5932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5373.5932 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5373.9099 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5417.1531 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5429.1531 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5437.1531 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 31 | 322916.6667 | ACTION | 5468.1531 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 5470.1531 | MonopileInstallation
| WTIV | Transit | 12.2432 | 127533.7838 | ACTION | 5482.3964 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5484.3964 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5484.7131 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5485.7131 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5488.7131 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5489.4361 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5489.4394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5490.4394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5491.9394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5493.9394 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5494.9394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5495.9394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5499.9394 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5500.256 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5543.4993 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5555.4993 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5563.4993 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5606.7425 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5608.7425 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5609.0592 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5610.0592 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5613.0592 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5613.7823 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5613.7855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5614.7855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5616.2855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5618.2855 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5619.2855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5620.2855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5624.2855 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5624.6022 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5667.8454 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5679.8454 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5687.8454 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5731.0887 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5733.0887 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5733.4053 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5734.4053 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5737.4053 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5738.1284 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5738.1316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5739.1316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5740.6316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5742.6316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5743.6316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5744.6316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5748.6316 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5748.9483 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5792.1915 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5804.1915 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5812.1915 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5855.4348 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5857.4348 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5857.7515 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5858.7515 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5861.7515 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5862.4745 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5862.4778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5863.4778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5864.9778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5866.9778 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5867.9778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5868.9778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5872.9778 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5873.2944 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5916.5377 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5928.5377 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5936.5377 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5979.7809 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5981.7809 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5982.0976 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5983.0976 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5986.0976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5986.8207 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5986.8239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5987.8239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5989.3239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5991.3239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5992.3239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 6001.3239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6002.3239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6006.3239 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6006.6406 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6049.8838 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6061.8838 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6069.8838 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6113.1271 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6115.1271 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6115.4437 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6116.4437 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6119.4437 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6120.1668 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6120.17 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6121.17 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6122.67 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6124.67 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6125.67 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6126.67 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6130.67 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6130.9867 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6174.23 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6186.23 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6194.23 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6237.4732 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6239.4732 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6239.7899 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6240.7899 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6243.7899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6244.5129 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6244.5162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6245.5162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6247.0162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6249.0162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6250.0162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6251.0162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6255.0162 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6255.3328 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6298.5761 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6310.5761 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6318.5761 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6361.8193 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6363.8193 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6364.136 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6365.136 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6368.136 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6368.8591 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6368.8623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6369.8623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6371.3623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6373.3623 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6374.3623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6375.3623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6379.3623 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6379.679 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6422.9222 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6434.9222 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6442.9222 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6486.1655 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6488.1655 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6488.4821 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6489.4821 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6492.4821 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6493.2052 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6493.2085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6494.2085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6495.7085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6497.7085 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6498.7085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6499.7085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6503.7085 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6504.0251 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6547.2684 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6559.2684 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6567.2684 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6610.5116 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6612.5116 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6612.8283 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6613.8283 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6616.8283 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6617.5513 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6617.5546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6618.5546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6620.0546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6622.0546 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6623.0546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6624.0546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6628.0546 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6628.3713 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6671.6145 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6683.6145 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6691.6145 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6734.8577 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6736.8577 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6737.1744 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6738.1744 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6741.1744 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6741.8975 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6741.9007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6742.9007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6744.4007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6746.4007 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6747.4007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6748.4007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6752.4007 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6752.7174 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6795.9606 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6807.9606 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6815.9606 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6859.2039 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6861.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6861.5205 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6862.5205 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6865.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6866.2436 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6866.2469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6867.2469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6868.7469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6870.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6871.7469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6872.7469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6876.7469 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6877.0635 | MonopileInstallation | 22.5 | 150 | 2 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 6877.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6881.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6885.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6889.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6890.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6892.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6893.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6897.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6901.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6905.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6907.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6908.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6910.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6953.3068 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6955.3068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6955.6234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6958.6234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 6959.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6965.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 6968.3734 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 6969.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 6975.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 6978.8734 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6979.8734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6981.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 6987.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6988.3734 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6989.3734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6990.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 6994.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 6995.3734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6996.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7000.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7001.3734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7002.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7006.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7006.6901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7008.6901 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7009.0068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7012.0068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7012.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7018.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7021.7568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7023.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7029.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7032.2568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7033.2568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7034.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7040.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7041.7568 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7042.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7044.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7047.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7048.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7050.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7053.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7054.7568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7056.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7059.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7060.0734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7103.3167 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7107.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7111.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7115.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7116.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7118.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7119.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7123.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7127.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7131.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7133.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7134.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7136.3167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7179.5599 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7181.5599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7181.8766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7184.8766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7185.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7191.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7194.6266 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7196.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7202.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7205.1266 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7206.1266 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7207.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7213.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7214.6266 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7215.6266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7217.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7220.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7221.6266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7223.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7226.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7227.6266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7229.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7232.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7232.9433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7234.9433 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7235.2599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7238.2599 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7239.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7245.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7248.0099 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7249.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7255.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7258.5099 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7259.5099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7261.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7267.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7268.0099 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7269.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7270.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7274.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7275.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7276.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7280.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7281.0099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7282.5099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7286.0099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7286.3266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 36 | 375000 | ACTION | 7322.3266 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7323.3266 | TurbineInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 7328.3266 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 7334.3266 | TurbineInstallation
| WTIV | Transit | 2.2432 | 23367.1171 | ACTION | 7336.5698 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 7349.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7353.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7357.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7361.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7363.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7364.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7366.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7370.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7374.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7378.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7379.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7381.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7382.5698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7425.8131 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7427.8131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7428.1297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7431.1297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7431.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7437.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7440.8797 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7442.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7448.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7451.3797 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7452.3797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7453.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7459.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7460.8797 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7461.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7463.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7466.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7467.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7469.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7472.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7473.8797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7475.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7478.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7479.1964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7481.1964 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7481.5131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7484.5131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7485.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7491.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7494.2631 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7495.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7501.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7504.7631 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7505.7631 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7507.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7513.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7514.2631 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7515.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7516.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7520.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7521.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7522.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7526.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7527.2631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7528.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7532.2631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7532.5797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7575.823 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7579.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7583.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7587.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7589.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7590.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7592.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7596.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 7617.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7621.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7625.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7626.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7628.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7630.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7631.823 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7675.0662 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7677.0662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7677.3829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7680.3829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7681.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7687.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7690.1329 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7691.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7697.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7700.6329 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7701.6329 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7703.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7709.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7710.1329 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7711.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7712.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7716.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7717.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7718.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7722.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7723.1329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7724.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7728.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7728.4496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7730.4496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7730.7662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7733.7662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7734.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7740.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7743.5162 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7745.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7751.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7754.0162 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7755.0162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7756.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7762.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7763.5162 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7764.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7766.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7769.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7770.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7772.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7775.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7776.5162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7778.0162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7781.5162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7781.8329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7825.0761 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7829.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7833.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7837.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7838.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7840.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7841.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7845.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7849.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7853.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7855.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7856.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7858.0761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7901.3194 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7903.3194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7903.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7906.636 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7907.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7913.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7916.386 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7917.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 7936.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7942.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7945.886 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7946.886 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7948.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7954.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7955.386 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7956.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7957.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7961.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7962.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7963.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7967.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7968.386 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7969.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7973.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7973.7027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7975.7027 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7976.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7979.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7979.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7985.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7988.7694 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7990.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7996.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7999.2694 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8000.2694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8001.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8007.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8008.7694 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8009.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8011.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8014.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8015.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8017.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8019.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8022.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8023.7694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8025.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8028.7694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8029.086 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8072.3293 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8076.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8080.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8084.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8085.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8087.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8088.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8092.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8096.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8100.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8102.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8103.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8105.3293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8148.5725 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8150.5725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8150.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8153.8892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8154.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8160.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8163.6392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8165.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8171.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8174.1392 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8175.1392 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8176.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8182.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8183.6392 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8184.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8186.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8189.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8190.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8192.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 8195.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8198.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8199.6392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8201.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 8214.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8217.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8217.9559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8219.9559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8220.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8223.2725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8224.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8230.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8233.0225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8234.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8240.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8243.5225 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8244.5225 | TurbineInstallation
| WTIV | Delay | 43 | 447916.6667 | ACTION | 8287.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8289.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8295.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8296.0225 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8297.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8298.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8302.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8303.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8304.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8308.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8309.0225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8310.5225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8314.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8314.3392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 28 | 291666.6667 | ACTION | 8342.3392 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 8345.3392 | TurbineInstallation
| WTIV | Transit | 15.2432 | 158783.7838 | ACTION | 8360.5824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8364.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8368.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8372.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8374.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8375.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8377.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8381.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8385.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8389.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8390.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8392.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8393.5824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 21 | 218750 | ACTION | 8414.5824 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8415.5824 | TurbineInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 8417.5824 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8418.5824 | TurbineInstallation
| WTIV | Transit | 20.2432 | 210867.1171 | ACTION | 8438.8257 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8440.8257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8441.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8444.1424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8444.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 8450.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8456.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8459.8924 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8461.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8467.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8470.3924 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8471.3924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8472.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8478.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8479.8924 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8480.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8482.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8485.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8486.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8488.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8491.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8492.8924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8494.3924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8497.8924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8498.209 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8500.209 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8500.5257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8503.5257 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8504.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8510.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8513.2757 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8514.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8520.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8523.7757 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8524.7757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8526.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8532.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8533.2757 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8534.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8535.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8539.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8540.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8541.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8545.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8546.2757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8547.7757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8551.2757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8551.5924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8594.8356 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8598.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8602.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8603.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8607.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8609.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 8624.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8625.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8627.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8631.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8635.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8639.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8640.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8642.3356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8643.8356 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8687.0788 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8689.0788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8689.3955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8692.3955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8693.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8699.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8702.1455 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8703.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8709.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8712.6455 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8713.6455 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8715.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8721.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8722.1455 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8723.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8724.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8728.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8729.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8730.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8734.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8735.1455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8736.6455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8740.1455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8740.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8742.4622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8742.7788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8745.7788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8746.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8752.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8755.5288 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8757.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8763.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8766.0288 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8767.0288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8768.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8774.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8775.5288 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8776.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8778.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8781.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8782.5288 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8787.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8789.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8792.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8793.5288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8795.0288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8798.5288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8798.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8842.0887 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8846.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8850.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8854.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8855.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8857.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8858.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 8862.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8866.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8870.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8874.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8876.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8877.5887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8879.0887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8922.332 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8924.332 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8924.6487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8927.6487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8928.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8934.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8937.3987 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8938.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8944.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8947.8987 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8948.8987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8950.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8955.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8961.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8962.3987 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8963.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8964.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8968.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8969.3987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8970.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8974.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8975.3987 | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 8987.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8988.8987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8992.3987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8992.7153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8994.7153 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8995.032 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8998.032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8998.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9004.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9007.782 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9009.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9015.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9018.282 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9019.282 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9020.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9026.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9027.782 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9028.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9030.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9033.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9034.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9036.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9039.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9040.782 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9042.282 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9045.782 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9046.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 28 | 291666.6667 | ACTION | 9074.0987 | TurbineInstallation
| WTIV | Delay | 61 | 635416.6667 | ACTION | 9135.0987 | TurbineInstallation
| WTIV | Transit | 15.2432 | 158783.7838 | ACTION | 9150.3419 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9154.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9158.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9162.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9163.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9165.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9166.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9170.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9174.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9178.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9180.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9182.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9183.8419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9185.3419 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9187.3419 | TurbineInstallation
| WTIV | Transit | 13 | 135416.6667 | ACTION | 9200.3419 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9201.3419 | TurbineInstallation
| WTIV | Transit | 23 | 239583.3333 | ACTION | 9224.3419 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9225.3419 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 9226.3419 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9227.3419 | TurbineInstallation
| WTIV | Transit | 6.2432 | 65033.7838 | ACTION | 9233.5851 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 9236.5851 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9238.5851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9238.9018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9241.9018 | TurbineInstallation
| WTIV | Delay | 42 | 437500 | ACTION | 9283.9018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9284.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 9287.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9293.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9296.6518 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9298.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9304.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9307.1518 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9308.1518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9309.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9315.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9316.6518 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9317.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9319.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9322.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9323.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9325.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9328.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9329.6518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9331.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9334.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9334.9685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9336.9685 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9337.2851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9340.2851 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9341.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9347.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9350.0351 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9351.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9357.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9360.5351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9361.5351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9363.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9369.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9370.0351 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9371.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9372.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9376.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9377.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9378.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9382.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9383.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9384.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9388.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9388.3518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 9404.3518 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 9418.3518 | TurbineInstallation
| WTIV | Transit | 27.2432 | 283783.7838 | ACTION | 9445.5951 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9449.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9453.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9457.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9459.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9460.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9462.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9466.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9470.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9474.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9475.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9477.0951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9478.5951 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 9521.8383 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9523.8383 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9524.155 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9527.155 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9527.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9533.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9536.905 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9538.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9544.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9547.405 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9548.405 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9549.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9555.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9556.905 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9557.905 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 9567.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9569.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9572.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9573.905 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 9576.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9578.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9581.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9582.905 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9584.405 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9587.905 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9588.2216 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9590.2216 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9590.5383 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9593.5383 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9594.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9600.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9603.2883 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9604.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9610.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9613.7883 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9614.7883 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 9615.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9617.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9623.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9624.2883 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9625.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9626.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9630.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9631.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9632.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9636.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9637.2883 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9638.7883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9642.2883 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9642.605 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 9685.8482 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9689.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9693.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9697.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9699.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9700.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9702.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9706.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9710.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9714.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9715.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9717.3482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9718.8482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 21 | 218750 | ACTION | 9739.8482 | TurbineInstallation
| WTIV | Delay | 1255 | 13072916.6667 | ACTION | 10994.8482 | TurbineInstallation
| WTIV | Transit | 22.2432 | 231700.4505 | ACTION | 11017.0915 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11019.0915 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11019.4081 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11022.4081 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11023.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11029.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11032.1581 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11033.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11039.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11042.6581 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11043.6581 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11045.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11051.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11052.1581 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11053.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11054.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11058.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11059.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11060.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11064.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11065.1581 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11066.6581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11070.1581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11070.4748 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11072.4748 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11072.7915 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11075.7915 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11076.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11082.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11085.5415 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 11101.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11103.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11109.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11112.0415 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11113.0415 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11114.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11120.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11121.5415 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11122.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11124.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11127.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11128.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11130.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11133.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11134.5415 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11136.0415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11139.5415 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11139.8581 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11183.1014 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11187.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11191.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11195.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11196.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11198.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11199.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11203.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11207.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11211.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11213.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11214.6014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11216.1014 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 32 | 333333.3333 | ACTION | 11248.1014 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11249.1014 | TurbineInstallation
| WTIV | Transit | 11.2432 | 117117.1171 | ACTION | 11260.3446 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11262.3446 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11262.6613 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11265.6613 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11266.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11272.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11275.4113 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11276.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11282.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11285.9113 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11286.9113 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11288.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11294.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11295.4113 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11296.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11297.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11301.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11302.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11303.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11307.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11308.4113 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11309.9113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11313.4113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11313.7279 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11315.7279 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11316.0446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11319.0446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11319.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11325.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11328.7946 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 11342.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11344.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11350.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11353.2946 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11354.2946 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11355.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11361.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11362.7946 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11363.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11365.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11368.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11369.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11371.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11374.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11375.7946 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11377.2946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11380.7946 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11381.1113 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 17 | 177083.3333 | ACTION | 11398.1113 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 11403.1113 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 11404.1113 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11405.1113 | TurbineInstallation
| WTIV | Transit | 25.2432 | 262950.4505 | ACTION | 11430.3545 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11434.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11438.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11442.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11443.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11445.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11446.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11450.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11454.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11458.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11460.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11461.8545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11463.3545 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 32 | 333333.3333 | ACTION | 11495.3545 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11496.3545 | TurbineInstallation
| WTIV | Transit | 11.2432 | 117117.1171 | ACTION | 11507.5978 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11509.5978 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11509.9144 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11512.9144 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11513.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 55 | 572916.6667 | ACTION | 11568.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11574.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11577.6644 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11579.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11585.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11588.1644 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11589.1644 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11590.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11596.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11597.6644 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11598.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11600.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11603.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11604.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11606.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11609.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11610.6644 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11612.1644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11615.6644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11615.9811 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11617.9811 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11618.2978 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11621.2978 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11622.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11628.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11631.0478 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 11635.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11636.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 41 | 427083.3333 | ACTION | 11677.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11683.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11686.5478 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11687.5478 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11689.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11695.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11696.0478 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11697.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11698.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11702.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11703.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11704.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11708.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11709.0478 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11710.5478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11714.0478 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11714.3644 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11757.6077 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11761.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11765.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11769.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11771.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11772.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11774.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11778.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11782.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11786.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11787.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11789.1077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11790.6077 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 8 | 83333.3333 | ACTION | 11798.6077 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 11806.6077 | TurbineInstallation
| WTIV | Transit | 35.2432 | 367117.1171 | ACTION | 11841.8509 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11843.8509 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11844.1676 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11847.1676 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11847.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11853.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11856.9176 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11858.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11864.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11867.4176 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11868.4176 | TurbineInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 11883.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11884.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 11891.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11897.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11898.9176 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11899.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11901.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11904.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11905.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11907.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11910.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11911.9176 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11913.4176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11916.9176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11917.2342 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11919.2342 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11919.5509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11922.5509 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 11923.5509 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11924.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 11936.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11942.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11945.3009 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11946.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11952.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11955.8009 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11956.8009 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11958.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11964.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11965.3009 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11966.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11967.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11971.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11972.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11973.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11977.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11978.3009 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11979.8009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11983.3009 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11983.6176 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12026.8608 | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 12050.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12054.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12058.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12062.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12064.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12065.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12067.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12071.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12075.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12079.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12080.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12082.3608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12083.8608 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12127.1041 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12129.1041 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12129.4207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12132.4207 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 12134.4207 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12135.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12141.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12144.1707 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12145.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12151.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12154.6707 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12155.6707 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12157.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12163.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12164.1707 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12165.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12166.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12170.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12171.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12172.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12176.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12177.1707 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12178.6707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12182.1707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12182.4874 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12184.4874 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12184.8041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12187.8041 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12188.8041 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12189.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12195.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12198.5541 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12200.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12206.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12209.0541 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12210.0541 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12211.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12217.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12218.5541 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12219.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12221.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12224.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12225.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12227.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12230.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12231.5541 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12233.0541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12236.5541 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12236.8707 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12280.114 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12284.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12288.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12292.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12293.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12295.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12296.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12300.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12304.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12308.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12310.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12311.614 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12313.114 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12356.3572 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12358.3572 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12358.6739 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12361.6739 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12362.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12368.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12371.4239 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12372.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12378.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12381.9239 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12382.9239 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12384.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12390.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12391.4239 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12392.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12393.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12397.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12398.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12399.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12403.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12404.4239 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12405.9239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12409.4239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12409.7406 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12411.7406 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12412.0572 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12415.0572 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12415.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12421.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12424.8072 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12426.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12432.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12435.3072 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12436.3072 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12437.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12443.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12444.8072 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12445.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12447.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12450.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12451.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12453.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12456.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12457.8072 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12459.3072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12462.8072 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12463.1239 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12506.3671 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12510.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12514.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12518.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12519.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12521.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12522.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12526.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12530.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12534.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12536.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12537.8671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12539.3671 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12582.6104 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12584.6104 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12584.927 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12587.927 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12588.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12594.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12597.677 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12599.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12605.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12608.177 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12609.177 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12610.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12616.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12617.677 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12618.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12620.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12623.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12624.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12626.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 12636.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12639.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12640.677 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12642.177 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12645.677 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12645.9937 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12647.9937 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12648.3104 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12651.3104 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12652.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 12658.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12664.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12667.0604 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 12671.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12672.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12678.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12681.5604 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12682.5604 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12684.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12690.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12691.0604 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12692.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12693.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12697.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12698.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12699.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12703.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12704.0604 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12705.5604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12709.0604 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12709.377 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 7 | 72916.6667 | ACTION | 12716.377 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12717.377 | TurbineInstallation
| WTIV | Transit | 4 | 41666.6667 | ACTION | 12721.377 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12722.377 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 12723.377 | TurbineInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 12748.377 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 12749.377 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 12752.377 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 12753.377 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 12756.377 | TurbineInstallation
| WTIV | Transit | 29.2432 | 304617.1171 | ACTION | 12785.6203 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12789.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12793.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12797.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12799.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12800.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12802.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12806.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12810.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12814.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12815.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12817.1203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12818.6203 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12861.8635 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12863.8635 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12864.1802 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12867.1802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12867.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12873.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12876.9302 | TurbineInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 12899.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12901.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12902.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12908.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12911.4302 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12912.4302 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12913.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 12926.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12932.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12933.9302 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12934.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12936.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12939.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12940.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12942.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12945.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12946.9302 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12948.4302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12951.9302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12952.2469 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12954.2469 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12954.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12957.5635 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12958.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 12964.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12970.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12973.3135 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12974.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12980.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12983.8135 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12984.8135 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12986.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12992.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12993.3135 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12994.3135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12995.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12999.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13000.3135 | TurbineInstallation
| WTIV | Delay | 36 | 375000 | ACTION | 13036.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13037.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13041.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13042.3135 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13043.8135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13047.3135 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13047.6302 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13090.8734 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13094.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13098.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13102.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13104.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13105.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13107.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13111.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13115.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13119.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13120.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13122.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13123.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13167.1167 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13169.1167 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13169.4333 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13172.4333 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 13176.4333 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13177.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 13187.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13193.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13196.1833 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13197.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13203.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13206.6833 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13207.6833 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13209.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13215.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13216.1833 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13217.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13218.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13222.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13223.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13224.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13228.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13229.1833 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13230.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 76 | 791666.6667 | ACTION | 13306.6833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13310.1833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13310.5 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13312.5 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13312.8167 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13315.8167 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13316.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13322.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13325.5667 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13327.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13333.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13336.0667 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13337.0667 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13338.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13344.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13345.5667 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13346.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13348.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13351.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13352.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13354.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13357.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13358.5667 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13360.0667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13363.5667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13363.8833 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13407.1266 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13411.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13415.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13419.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13420.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13422.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13423.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13427.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13431.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13435.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13437.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13438.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13440.1266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13483.3698 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13485.3698 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13485.6865 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13488.6865 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13489.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13495.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13498.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13499.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13505.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13508.9365 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13509.9365 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13511.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13517.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13518.4365 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13519.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13520.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13524.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13525.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13526.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13530.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13531.4365 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13532.9365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13536.4365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13536.7532 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13538.7532 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13539.0698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13542.0698 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13542.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13548.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13551.8198 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13553.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 13583.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13589.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13592.3198 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13593.3198 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13594.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 13606.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13612.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13613.8198 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13614.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13616.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13619.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13620.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13622.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13625.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13626.8198 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13628.3198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13631.8198 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13632.1365 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13675.3797 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13679.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13683.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13687.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13688.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13690.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13691.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13695.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13699.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13703.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13705.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13706.8797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13708.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13751.623 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13753.623 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13753.9397 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13756.9397 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13757.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 13777.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13783.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13786.6897 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13788.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13794.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13797.1897 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13798.1897 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13799.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13805.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13806.6897 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13807.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13809.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13812.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13813.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13815.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13818.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13819.6897 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13821.1897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13824.6897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13825.0063 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13827.0063 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13827.323 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13830.323 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13831.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13837.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13840.073 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13841.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13847.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13850.573 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13851.573 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13853.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13859.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13860.073 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13861.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13862.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13866.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13867.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13868.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13872.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13873.073 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13874.573 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13878.073 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13878.3897 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13921.6329 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13925.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13929.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13933.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13935.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13936.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13938.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13942.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 13946.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 13950.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13951.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13953.1329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 13954.6329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 13997.8761 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13999.8761 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14000.1928 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14003.1928 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14003.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14009.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14012.9428 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14014.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14020.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14023.4428 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14024.4428 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14025.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14031.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14032.9428 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14033.9428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14035.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14038.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14039.9428 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14041.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14044.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14045.9428 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 14046.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14048.4428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14051.9428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14052.2595 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 14054.2595 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14054.5761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14057.5761 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14058.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14064.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14067.3261 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14068.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14074.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14077.8261 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14078.8261 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14080.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14086.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14087.3261 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14088.3261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14089.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14093.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14094.3261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14095.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14099.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14100.3261 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14101.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 14117.8261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14121.3261 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14121.6428 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 14164.886 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14168.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14172.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 14176.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14178.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14179.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14181.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14185.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14189.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 14193.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14194.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14196.386 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14197.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 14241.1293 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 14243.1293 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14243.446 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14246.446 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14247.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14253.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14256.196 | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 14259.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14260.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14266.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14269.696 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14270.696 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14272.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14278.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14279.196 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14280.196 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 14282.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14283.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14287.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14288.196 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14289.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14293.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14294.196 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14295.696 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14299.196 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14299.5126 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 14301.5126 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14301.8293 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14304.8293 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14305.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 14306.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14312.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14315.5793 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14317.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14323.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14326.0793 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14327.0793 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14328.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14334.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14335.5793 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14336.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14338.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14341.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14342.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14344.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14347.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14348.5793 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14350.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14353.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14353.896 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 14397.1392 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14401.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14405.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 14409.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14410.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14412.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14413.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14417.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 14421.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 14425.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14427.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14428.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 14430.1392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 14473.3824 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 14475.3824 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14475.6991 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14478.6991 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14479.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14485.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14488.4491 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14489.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 14494.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14500.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14503.9491 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14504.9491 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14506.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14512.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14513.4491 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14514.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14515.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14519.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14520.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14521.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14525.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14526.4491 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14527.9491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14531.4491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14531.7658 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 14533.7658 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 14534.0824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14537.0824 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 14537.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14543.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 14546.8324 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 14548.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 14554.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 14557.3324 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14558.3324 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 14559.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 14565.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 14566.8324 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14567.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14569.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14572.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14573.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14575.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14578.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 14579.8324 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 14581.3324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 14584.8324 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 14585.1491 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation