## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | site_depth | hub_height | per_trip | phase_name
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 12 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 20 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 63.2432 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 65.2432 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 65.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 66.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 68.5599 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 71.5599 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 79.5599 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 80.283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 80.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 81.2862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 82.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 84.7862 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 85.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 88.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 89.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 93.7862 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 94.1029 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 137.3461 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 149.3461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 157.3461 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 10 | 104166.6667 | ACTION | 167.3461 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 179.3461 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 180.3461 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 181.3461 | MonopileInstallation
| WTIV | Transit | 32.2432 | 335867.1171 | ACTION | 213.5894 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 215.5894 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 215.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 216.906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 219.906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 220.6291 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 220.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 221.6324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 223.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 225.1324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 226.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 227.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 19 | 197916.6667 | ACTION | 246.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 250.1324 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 250.449 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 293.6923 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 305.6923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 313.6923 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 356.9355 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 358.9355 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 359.2522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 360.2522 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 363.2522 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 363.9752 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 363.9785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 364.9785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 366.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 368.4785 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 369.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 370.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 374.4785 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 374.7952 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 418.0384 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 430.0384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 438.0384 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 481.2816 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 483.2816 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 483.5983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 484.5983 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 487.5983 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 488.3214 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 488.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 489.3246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 490.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 492.8246 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 493.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 494.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 498.8246 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 499.1413 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 21 | 218750 | ACTION | 520.1413 | MonopileInstallation
| WTIV | Delay | 71 | 739583.3333 | ACTION | 591.1413 | MonopileInstallation
| WTIV | Transit | 22.2432 | 231700.4505 | ACTION | 613.3845 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 625.3845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 633.3845 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 676.6278 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 678.6278 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 678.9445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 679.9445 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 682.9445 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 683.6675 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 683.6708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 684.6708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 686.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 688.1708 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 689.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 690.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 694.1708 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 694.4874 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 737.7307 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 749.7307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 757.7307 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 800.9739 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 802.9739 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 803.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 804.2906 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 807.2906 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 808.0137 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 808.0169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 809.0169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 810.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 812.5169 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 813.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 814.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 818.5169 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 818.8336 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 862.0768 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 874.0768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 882.0768 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 7 | 72916.6667 | ACTION | 889.0768 | MonopileInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 913.0768 | MonopileInstallation
| WTIV | Transit | 36.2432 | 377533.7838 | ACTION | 949.3201 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 951.3201 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 951.6367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 952.6367 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 955.6367 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 956.3598 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 956.363 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 957.363 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 958.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 960.863 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 961.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 962.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 966.863 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 967.1797 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1010.4229 | MonopileInstallation
| WTIV | Delay | 33 | 343750 | ACTION | 1043.4229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1055.4229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1063.4229 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 17 | 177083.3333 | ACTION | 1080.4229 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1081.4229 | MonopileInstallation
| WTIV | Transit | 4 | 41666.6667 | ACTION | 1085.4229 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 1088.4229 | MonopileInstallation
| WTIV | Transit | 22.2432 | 231700.4505 | ACTION | 1110.6662 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1112.6662 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1112.9829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1113.9829 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1116.9829 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1117.7059 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1117.7092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1118.7092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1120.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1122.2092 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1123.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1124.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1128.2092 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1128.5258 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 38 | 395833.3333 | ACTION | 1166.5258 | MonopileInstallation
| WTIV | Delay | 66 | 687500 | ACTION | 1232.5258 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 1237.7691 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1249.7691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1257.7691 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 15 | 156250 | ACTION | 1272.7691 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 1281.7691 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 1282.7691 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1283.7691 | MonopileInstallation
| WTIV | Transit | 27.2432 | 283783.7838 | ACTION | 1311.0123 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1313.0123 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1313.329 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1314.329 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1317.329 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1318.0521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1318.0553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1319.0553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1320.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1322.5553 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1323.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1324.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1328.5553 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1328.872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1372.1152 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1384.1152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1392.1152 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 22 | 229166.6667 | ACTION | 1414.1152 | MonopileInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 1434.1152 | MonopileInstallation
| WTIV | Transit | 12 | 125000 | ACTION | 1446.1152 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 1447.1152 | MonopileInstallation
| WTIV | Transit | 9.2432 | 96283.7838 | ACTION | 1456.3585 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1458.3585 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1458.6751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1459.6751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1462.6751 | MonopileInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 1479.6751 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1480.3982 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1480.4014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1481.4014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1482.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1484.9014 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1485.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1486.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 1492.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1496.9014 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1497.2181 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1540.4614 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1552.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1560.4614 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 33 | 343750 | ACTION | 1593.4614 | MonopileInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 1616.4614 | MonopileInstallation
| WTIV | Transit | 10.2432 | 106700.4505 | ACTION | 1626.7046 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1628.7046 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1629.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1630.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1633.0213 | MonopileInstallation
| WTIV | Delay | 31 | 322916.6667 | ACTION | 1664.0213 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1664.7443 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1664.7476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1665.7476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1667.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1669.2476 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1670.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1671.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1675.2476 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1675.5642 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1718.8075 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1730.8075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1738.8075 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 1754.8075 | MonopileInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 1779.8075 | MonopileInstallation
| WTIV | Transit | 27.2432 | 283783.7838 | ACTION | 1807.0507 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1809.0507 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1809.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1810.3674 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1813.3674 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1814.0905 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1814.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1815.0937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1816.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1818.5937 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1819.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1820.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1824.5937 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1824.9104 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1868.1536 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 1880.1536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 1888.1536 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1931.3969 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 1933.3969 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 1933.7135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1934.7135 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 1937.7135 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1938.4366 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1938.4398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1939.4398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 1940.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 1942.9398 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1943.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1944.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1948.9398 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 1949.2565 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 1992.4998 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2004.4998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2012.4998 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2055.743 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2057.743 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2058.0597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2059.0597 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2062.0597 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2062.7827 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2062.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2063.786 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2065.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2067.286 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2068.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2069.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2073.286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2073.6027 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2116.8459 | MonopileInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 2133.8459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2145.8459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2153.8459 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2197.0891 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2199.0891 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2199.4058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2200.4058 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2203.4058 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2204.1289 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2204.1321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2205.1321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2206.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2208.6321 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2209.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2210.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2214.6321 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2214.9488 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2258.192 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2270.192 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2278.192 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 16 | 166666.6667 | ACTION | 2294.192 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 2304.192 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 2305.192 | MonopileInstallation
| WTIV | Delay | 30 | 312500 | ACTION | 2335.192 | MonopileInstallation
| WTIV | Transit | 26.2432 | 273367.1171 | ACTION | 2361.4353 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2363.4353 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2363.7519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2364.7519 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2367.7519 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2368.475 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2368.4783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2369.4783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2370.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2372.9783 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2373.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2374.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 34 | 354166.6667 | ACTION | 2408.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2412.9783 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2413.2949 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2456.5382 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2468.5382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2476.5382 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2519.7814 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2521.7814 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2522.0981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2523.0981 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2526.0981 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2526.8211 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2526.8244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2527.8244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2529.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2531.3244 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2532.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2534.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2535.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2539.3244 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2539.6411 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2582.8843 | MonopileInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 2594.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2606.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2614.8843 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2658.1275 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2660.1275 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2660.4442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2661.4442 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2664.4442 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2665.1673 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2665.1705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2666.1705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2667.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2669.6705 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2670.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2671.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2675.6705 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2675.9872 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 10 | 104166.6667 | ACTION | 2685.9872 | MonopileInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 2699.9872 | MonopileInstallation
| WTIV | Transit | 33.2432 | 346283.7838 | ACTION | 2733.2304 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2745.2304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2753.2304 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2796.4737 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2798.4737 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2798.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2799.7903 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2802.7903 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2803.5134 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2803.5167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2804.5167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2806.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2808.0167 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2809.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2810.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2814.0167 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2814.3333 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 23 | 239583.3333 | ACTION | 2837.3333 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2839.3333 | MonopileInstallation
| WTIV | Transit | 20.2432 | 210867.1171 | ACTION | 2859.5766 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2871.5766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 2879.5766 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2922.8198 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 2924.8198 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 2925.1365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2926.1365 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 2929.1365 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2929.8595 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2929.8628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2930.8628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 2932.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 2934.3628 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2935.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2936.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2940.3628 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 2940.6795 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 2983.9227 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 2995.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3003.9227 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 3008.9227 | MonopileInstallation
| WTIV | Delay | 15 | 156250 | ACTION | 3023.9227 | MonopileInstallation
| WTIV | Transit | 29 | 302083.3333 | ACTION | 3052.9227 | MonopileInstallation
| WTIV | Delay | 29 | 302083.3333 | ACTION | 3081.9227 | MonopileInstallation
| WTIV | Transit | 9.2432 | 96283.7838 | ACTION | 3091.166 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3093.166 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3093.4826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3094.4826 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3097.4826 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3098.2057 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3098.2089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3099.2089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3100.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3102.7089 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3103.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3104.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3108.7089 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3109.0256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3152.2688 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3164.2688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3172.2688 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3215.5121 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3217.5121 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3217.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3218.8288 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3221.8288 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3222.5518 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3224.5518 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3224.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3225.5551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3227.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3229.0551 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3230.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3231.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3235.0551 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3235.3717 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3278.615 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3290.615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3298.615 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3341.8582 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3343.8582 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3344.1749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3345.1749 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3348.1749 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3348.898 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3348.9012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3349.9012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3351.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3353.4012 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3354.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3355.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3359.4012 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3359.7179 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3402.9611 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3414.9611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3422.9611 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 44 | 458333.3333 | ACTION | 3466.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3467.9611 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3468.9611 | MonopileInstallation
| WTIV | Transit | 5 | 52083.3333 | ACTION | 3473.9611 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3474.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3475.9611 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3477.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3478.9611 | MonopileInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3488.9611 | MonopileInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 3489.9611 | MonopileInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 3496.9611 | MonopileInstallation
| WTIV | Transit | 34.2432 | 356700.4505 | ACTION | 3531.2044 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3533.2044 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3533.521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3534.521 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3537.521 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3538.2441 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3538.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3539.2473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3540.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3542.7473 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3543.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3544.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3548.7473 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3549.064 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3592.3072 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3604.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3612.3072 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3655.5505 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3657.5505 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3657.8672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3658.8672 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3661.8672 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3662.5902 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3662.5935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3663.5935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3665.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3667.0935 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3668.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3669.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3673.0935 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3673.4101 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3716.6534 | MonopileInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 3724.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3736.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3744.6534 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3787.8966 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3789.8966 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3790.2133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3791.2133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3794.2133 | MonopileInstallation
| WTIV | Delay | 26 | 270833.3333 | ACTION | 3820.2133 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3820.9364 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3820.9396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3821.9396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 37 | 385416.6667 | ACTION | 3858.9396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3860.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3862.4396 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3864.4396 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3865.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3866.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3870.4396 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3870.7563 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3913.9995 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 3925.9995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 3933.9995 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 3977.2428 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 3979.2428 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 3979.5594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3980.5594 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 3983.5594 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3984.2825 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3984.2857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3985.2857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 3986.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 3988.7857 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3989.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3990.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3994.7857 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 3995.1024 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4038.3457 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4050.3457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4058.3457 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4101.5889 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4103.5889 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4103.9056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4104.9056 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4107.9056 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4108.6286 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4108.6319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4109.6319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4111.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4113.1319 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4114.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4115.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4119.1319 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4119.4485 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4162.6918 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4174.6918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4182.6918 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4225.935 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4227.935 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4228.2517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4229.2517 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4232.2517 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4232.9748 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4232.978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4233.978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4235.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4237.478 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4238.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4239.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4243.478 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4243.7947 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4287.0379 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4299.0379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4307.0379 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4350.2812 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4352.2812 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4352.5978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4353.5978 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4356.5978 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4357.3209 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4357.3242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4358.3242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4359.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4361.8242 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4362.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4363.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4367.8242 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4368.1408 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4411.3841 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4423.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4431.3841 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4474.6273 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4476.6273 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4476.944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4477.944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4480.944 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4481.667 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4481.6703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4482.6703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4484.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4486.1703 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4487.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4488.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4492.1703 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4492.487 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4535.7302 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4547.7302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4555.7302 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4598.9734 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4600.9734 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4601.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4602.2901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4605.2901 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4606.0132 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4606.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4607.0164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4608.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4610.5164 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4611.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4612.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4616.5164 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4616.8331 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4660.0763 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4672.0763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4680.0763 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4723.3196 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4725.3196 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4725.6362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4726.6362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4729.6362 | MonopileInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 4732.6362 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4733.3593 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4733.3626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4734.3626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4735.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4737.8626 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4738.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4739.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4743.8626 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4744.1792 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 38 | 395833.3333 | ACTION | 4782.1792 | MonopileInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 4788.1792 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 4793.4225 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4805.4225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4813.4225 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4856.6657 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4858.6657 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4858.9824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4859.9824 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4862.9824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4863.7054 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4863.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4864.7087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4866.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4868.2087 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4869.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4870.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4874.2087 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4874.5254 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4917.7686 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 4929.7686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 4937.7686 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 4981.0118 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 4983.0118 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 4983.3285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 4984.3285 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 4987.3285 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 4988.0516 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 4988.0548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4989.0548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 4990.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 4992.5548 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 4993.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 4994.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 4998.5548 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 4998.8715 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 25 | 260416.6667 | ACTION | 5023.8715 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5024.8715 | MonopileInstallation
| WTIV | Transit | 13 | 135416.6667 | ACTION | 5037.8715 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 5038.8715 | MonopileInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 5044.1147 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5056.1147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5064.1147 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5107.358 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5109.358 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5109.6746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5110.6746 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5113.6746 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5114.3977 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5114.401 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5115.401 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5116.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5118.901 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5119.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5120.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5124.901 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5125.2176 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5168.4609 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5180.4609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5188.4609 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5231.7041 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5233.7041 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5234.0208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5235.0208 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5238.0208 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5238.7438 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5238.7471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5239.7471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5241.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5243.2471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5244.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5245.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5249.2471 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5249.5638 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5292.807 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5304.807 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5312.807 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5356.0503 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5358.0503 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5358.3669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5359.3669 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5362.3669 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5363.09 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5363.0932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5364.0932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5365.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5367.5932 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5368.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5369.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5373.5932 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5373.9099 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5417.1531 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5429.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5437.1531 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 31 | 322916.6667 | ACTION | 5468.1531 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 5470.1531 | MonopileInstallation
| WTIV | Transit | 12.2432 | 127533.7838 | ACTION | 5482.3964 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5484.3964 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5484.7131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5485.7131 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5488.7131 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5489.4361 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5489.4394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5490.4394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5491.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5493.9394 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5494.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5495.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5499.9394 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5500.256 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5543.4993 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5555.4993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5563.4993 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5606.7425 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5608.7425 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5609.0592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5610.0592 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5613.0592 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5613.7823 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5613.7855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5614.7855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5616.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5618.2855 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5619.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5620.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5624.2855 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5624.6022 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5667.8454 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5679.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5687.8454 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5731.0887 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5733.0887 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5733.4053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5734.4053 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5737.4053 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5738.1284 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5738.1316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5739.1316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5740.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5742.6316 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5743.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5744.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5748.6316 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5748.9483 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5792.1915 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5804.1915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5812.1915 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5855.4348 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5857.4348 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5857.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5858.7515 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5861.7515 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5862.4745 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5862.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5863.4778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5864.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5866.9778 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5867.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 5868.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 5872.9778 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 5873.2944 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5916.5377 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 5928.5377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 5936.5377 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 5979.7809 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 5981.7809 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 5982.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 5983.0976 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 5986.0976 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 5986.8207 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 5986.8239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5987.8239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 5989.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 5991.3239 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 5992.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 6001.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6002.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6006.3239 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6006.6406 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6049.8838 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6061.8838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6069.8838 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6113.1271 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6115.1271 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6115.4437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6116.4437 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6119.4437 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6120.1668 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6120.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6121.17 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6122.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6124.67 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6125.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6126.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6130.67 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6130.9867 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6174.23 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6186.23 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6194.23 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6237.4732 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6239.4732 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6239.7899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6240.7899 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6243.7899 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6244.5129 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6244.5162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6245.5162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6247.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6249.0162 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6250.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6251.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6255.0162 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6255.3328 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6298.5761 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6310.5761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6318.5761 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6361.8193 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6363.8193 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6364.136 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6365.136 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6368.136 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6368.8591 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6368.8623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6369.8623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6371.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6373.3623 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6374.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6375.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6379.3623 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6379.679 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6422.9222 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6434.9222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6442.9222 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6486.1655 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6488.1655 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6488.4821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6489.4821 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6492.4821 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6493.2052 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6493.2085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6494.2085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6495.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6497.7085 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6498.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6499.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6503.7085 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6504.0251 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6547.2684 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6559.2684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6567.2684 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6610.5116 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6612.5116 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6612.8283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6613.8283 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6616.8283 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6617.5513 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6617.5546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6618.5546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6620.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6622.0546 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6623.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6624.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6628.0546 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6628.3713 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6671.6145 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6683.6145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6691.6145 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6734.8577 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6736.8577 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6737.1744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6738.1744 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6741.1744 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6741.8975 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6741.9007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6742.9007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6744.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6746.4007 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6747.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6748.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6752.4007 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6752.7174 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6795.9606 | MonopileInstallation
| WTIV | Fasten Monopile | 12 | 125000 | ACTION | 6807.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Fasten Transition Piece | 8 | 83333.3333 | ACTION | 6815.9606 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 6859.2039 | MonopileInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 6861.2039 | MonopileInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 6861.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 6862.5205 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Monopile | 3 | 31250 | ACTION | 6865.5205 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 6866.2436 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 6866.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6867.2469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Drive Monopile | 1.5 | 15625 | ACTION | 6868.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Release Transition Piece | 2 | 20833.3333 | ACTION | 6870.7469 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 6871.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 6872.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 6876.7469 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 6877.0635 | MonopileInstallation | 22.5 | 150 | 4 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 6877.0635 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6881.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6885.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6889.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6890.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6892.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6893.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6897.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6901.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6905.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6907.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6908.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6910.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6914.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6918.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6922.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6923.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6925.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6926.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6930.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6934.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6938.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6940.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6941.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6943.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6947.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 6951.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 6955.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6956.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6958.0635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 6959.5635 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7002.8068 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7004.8068 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7005.1234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7008.1234 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7008.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7014.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7017.8734 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7019.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7025.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7028.3734 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7029.3734 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7030.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7036.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7037.8734 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7038.8734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7040.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7043.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7044.8734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7046.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7049.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7050.8734 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7052.3734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7055.8734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7056.1901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7058.1901 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7058.5068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7061.5068 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7062.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7068.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7071.2568 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7072.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7078.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7081.7568 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7082.7568 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7084.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7090.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7091.2568 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7092.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7093.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7097.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7098.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7099.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7103.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7104.2568 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7105.7568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7109.2568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7109.5734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7111.5734 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7111.8901 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7114.8901 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7115.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7121.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7124.6401 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7126.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7132.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7135.1401 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7136.1401 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7137.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7143.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7144.6401 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7145.6401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7147.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7150.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7151.6401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7153.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7156.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7157.6401 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7159.1401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7162.6401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7162.9568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7164.9568 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7165.2734 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7168.2734 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7169.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7175.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7178.0234 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7179.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7185.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7188.5234 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7189.5234 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7191.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7197.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7198.0234 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7199.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7200.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7204.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7205.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7206.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7210.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7211.0234 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7212.5234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7216.0234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7216.3401 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7218.3401 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7218.6568 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7221.6568 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7222.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7228.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7231.4068 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7232.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7238.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7241.9068 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7242.9068 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7244.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7250.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7251.4068 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7252.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7253.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7257.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7258.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7259.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7263.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7264.4068 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7265.9068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7269.4068 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7269.7234 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7312.9667 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7316.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7320.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 3 | 31250 | ACTION | 7323.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7327.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 7334.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7336.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 7349.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7350.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7352.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7356.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7360.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7364.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7365.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7367.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7368.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7372.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7376.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7380.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7382.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7383.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7385.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7389.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7393.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7397.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7398.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7400.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7401.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7405.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7409.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7413.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7415.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7416.9667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7418.4667 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7461.7099 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7463.7099 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7464.0266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7467.0266 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7467.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7473.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7476.7766 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7478.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7484.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7487.2766 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7488.2766 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7489.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7495.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7496.7766 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7497.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7499.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7502.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7503.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7505.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7508.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7509.7766 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7511.2766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7514.7766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7515.0933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7517.0933 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7517.4099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7520.4099 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7521.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7527.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7530.1599 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7531.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7537.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7540.6599 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7541.6599 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7543.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7549.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7550.1599 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7551.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7552.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7556.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7557.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7558.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7562.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7563.1599 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7564.6599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7568.1599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7568.4766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7570.4766 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7570.7933 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7573.7933 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7574.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7580.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7583.5433 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7585.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7591.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7594.0433 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7595.0433 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7596.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 7617.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7623.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7624.5433 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7625.5433 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 7635.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7637.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7640.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7641.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7643.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7646.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7647.5433 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7649.0433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7652.5433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7652.8599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7654.8599 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7655.1766 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7658.1766 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7658.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7664.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7667.9266 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7669.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7675.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7678.4266 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7679.4266 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7680.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7686.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7687.9266 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7688.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7690.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7693.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7694.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7696.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7699.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7700.9266 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7702.4266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7705.9266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7706.2433 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7708.2433 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7708.5599 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7711.5599 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7712.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7718.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7721.3099 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7722.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7728.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7731.8099 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7732.8099 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7734.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7740.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7741.3099 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7742.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7743.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7747.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7748.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7749.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7753.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7754.3099 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7755.8099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7759.3099 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7759.6266 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 7802.8698 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7806.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7810.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7814.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7816.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7817.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7819.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7823.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7827.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7831.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7832.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7834.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7835.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7839.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7843.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7847.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7849.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7850.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7852.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7856.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7860.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7864.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7865.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7867.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7868.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7872.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 7876.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 7880.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7882.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7883.8698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 7885.3698 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 42 | 437500 | ACTION | 7927.3698 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 7936.3698 | TurbineInstallation
| WTIV | Transit | 1.2432 | 12950.4505 | ACTION | 7937.6131 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7939.6131 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7939.9297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7942.9297 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7943.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7949.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7952.6797 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 7954.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 7960.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 7963.1797 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7964.1797 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7965.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 7971.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7972.6797 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7973.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7975.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7978.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7979.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7981.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7984.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 7985.6797 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7987.1797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 7990.6797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 7990.9964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 7992.9964 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 7993.3131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 7996.3131 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 7997.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8003.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8006.0631 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8007.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8013.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8016.5631 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8017.5631 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8019.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8021.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8027.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8028.0631 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8029.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8030.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8034.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8035.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8036.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8040.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8041.0631 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8042.5631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8046.0631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8046.3797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8048.3797 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8048.6964 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8051.6964 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8052.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8058.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8061.4464 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8062.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8068.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8071.9464 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8072.9464 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8074.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8080.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8081.4464 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8082.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8083.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8087.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8088.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8089.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8093.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8094.4464 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8095.9464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8099.4464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8099.7631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8101.7631 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8102.0797 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8105.0797 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8105.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8111.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8114.8297 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8116.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 7 | 72916.6667 | ACTION | 8123.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8129.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8132.3297 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8133.3297 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8134.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8140.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8141.8297 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8142.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8144.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8147.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8148.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8150.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8153.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8154.8297 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8156.3297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8159.8297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8160.1464 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8162.1464 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8162.4631 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8165.4631 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8166.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8172.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8175.2131 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8176.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8182.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8185.7131 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8186.7131 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8188.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8194.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8195.2131 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8196.2131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8197.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8201.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8202.2131 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 8211.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8212.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8214.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8218.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8219.2131 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8220.7131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8224.2131 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8224.5297 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 38 | 395833.3333 | ACTION | 8262.5297 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8264.5297 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 8265.5297 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8266.5297 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 8267.5297 | TurbineInstallation
| WTIV | Delay | 20 | 208333.3333 | ACTION | 8287.5297 | TurbineInstallation
| WTIV | Transit | 3.2432 | 33783.7838 | ACTION | 8290.773 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8294.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8298.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8302.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8304.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8305.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8307.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8311.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8315.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8319.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8320.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8322.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8323.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8327.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8331.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8335.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8337.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8338.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8340.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 8345.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8349.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8353.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8357.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8358.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8360.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8361.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8365.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8369.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8373.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8375.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8376.773 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8378.273 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 36 | 375000 | ACTION | 8414.273 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8415.273 | TurbineInstallation
| WTIV | Transit | 2 | 20833.3333 | ACTION | 8417.273 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8418.273 | TurbineInstallation
| WTIV | Transit | 5.2432 | 54617.1171 | ACTION | 8423.5162 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8425.5162 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8425.8329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8428.8329 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8429.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8435.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8438.5829 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8440.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8446.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8449.0829 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8450.0829 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8451.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8457.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8458.5829 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8459.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8461.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8464.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8465.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8467.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8470.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8471.5829 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8473.0829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8476.5829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8476.8996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8478.8996 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8479.2162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8482.2162 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8482.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8488.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8491.9662 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8493.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8499.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8502.4662 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8503.4662 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8504.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8510.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8511.9662 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8512.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8514.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8517.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8518.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8520.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8523.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8524.9662 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8526.4662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8529.9662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8530.2829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8532.2829 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8532.5996 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8535.5996 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8536.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8542.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8545.3496 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8546.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8552.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8555.8496 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8556.8496 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8558.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8564.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8565.3496 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8566.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8567.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8571.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8572.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8573.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8577.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8578.3496 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8579.8496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8583.3496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8583.6662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8585.6662 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8585.9829 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8588.9829 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8589.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 56 | 583333.3333 | ACTION | 8645.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8651.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8654.7329 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8656.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8662.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8665.2329 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8666.2329 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8667.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8668.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8674.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8675.7329 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8676.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8678.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8681.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8682.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8684.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8687.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8688.7329 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8690.2329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8693.7329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8694.0496 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8696.0496 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8696.3662 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8699.3662 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8700.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8706.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8709.1162 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8710.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8716.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8719.6162 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8720.6162 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8722.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8728.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8729.1162 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8730.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8731.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8735.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8736.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8737.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8741.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8742.1162 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8743.6162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8747.1162 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8747.4329 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8790.6761 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8794.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8798.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8802.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8804.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8805.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8807.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8811.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8815.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8819.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8820.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8822.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8823.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8827.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8831.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8835.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8837.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8838.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8840.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8844.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8848.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8852.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8853.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8855.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8856.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8860.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8862.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 8866.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 8870.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8872.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8873.6761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 8875.1761 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 8918.4194 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8920.4194 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8920.736 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8923.736 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8924.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8930.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8933.486 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 8934.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 8940.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 8943.986 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8944.986 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8946.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 8955.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 8961.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8962.486 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8963.486 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8964.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8968.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8969.486 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8970.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8974.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 8975.486 | TurbineInstallation
| WTIV | Delay | 12 | 125000 | ACTION | 8987.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8988.986 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 8992.486 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 8992.8027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 8994.8027 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 8995.1194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 8998.1194 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 8998.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9004.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9007.8694 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9009.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9015.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9018.3694 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9019.3694 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9020.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9026.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9027.8694 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9028.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9030.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9033.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9034.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9036.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9039.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9040.8694 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9042.3694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9045.8694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9046.186 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9048.186 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9048.5027 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9051.5027 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9052.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9058.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9061.2527 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9062.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9068.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9071.7527 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9072.7527 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9074.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 61 | 635416.6667 | ACTION | 9135.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9141.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9142.2527 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9143.2527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9144.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9148.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9149.2527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9150.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9154.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9155.2527 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9156.7527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9160.2527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9160.5694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9162.5694 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9162.886 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9165.886 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9166.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 24 | 250000 | ACTION | 9190.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9196.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9199.636 | TurbineInstallation
| WTIV | Delay | 84 | 875000 | ACTION | 9283.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9285.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9287.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9293.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9296.136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9297.136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9298.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9304.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9305.636 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9306.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9308.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9311.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9312.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9314.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9317.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9318.636 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9320.136 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9323.636 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9323.9527 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9325.9527 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9326.2694 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9329.2694 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9330.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9336.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9339.0194 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9340.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9346.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9349.5194 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9350.5194 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9352.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9358.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9359.0194 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9360.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9361.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9365.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9366.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9367.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9371.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9372.0194 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9373.5194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9377.0194 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9377.336 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 27 | 281250 | ACTION | 9404.336 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 9418.336 | TurbineInstallation
| WTIV | Transit | 16.2432 | 169200.4505 | ACTION | 9434.5793 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9438.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9442.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9446.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9448.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9449.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9451.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9455.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9459.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9463.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9464.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9466.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9467.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9471.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9475.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9479.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9481.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9482.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9484.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9488.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9492.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9496.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9497.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9499.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9500.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9504.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 9508.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 9512.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9514.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9515.5793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 9517.0793 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 9560.3225 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9562.3225 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9562.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9565.6392 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 9567.6392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9568.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 9576.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9582.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9585.3892 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9586.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9592.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9595.8892 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9596.8892 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9598.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9604.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9605.3892 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9606.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9607.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 9615.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9619.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9620.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9621.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9625.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9626.3892 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9627.8892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9631.3892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9631.7059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9633.7059 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9634.0225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9637.0225 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9637.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9643.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9646.7725 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 9650.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9652.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9658.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9661.2725 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9662.2725 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9663.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9669.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9670.7725 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9671.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9673.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9676.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9677.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9679.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9682.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9683.7725 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9685.2725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9688.7725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 9689.0892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 9691.0892 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 9691.4059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9694.4059 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 9695.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9701.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 9704.1559 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 9705.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 9711.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 9714.6559 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9715.6559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 9717.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 9723.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 9724.1559 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9725.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 9726.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 9730.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 9731.1559 | TurbineInstallation
| WTIV | Delay | 1263 | 13156250 | ACTION | 10994.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 10995.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 10999.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11000.1559 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11001.6559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11005.1559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11005.4725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11007.4725 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11007.7892 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11010.7892 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11011.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 11016.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11022.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11025.5392 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11027.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11033.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11036.0392 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11037.0392 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11038.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11044.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11045.5392 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11046.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11048.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11051.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11052.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11054.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11057.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11058.5392 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11060.0392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11063.5392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11063.8559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11065.8559 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11066.1725 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11069.1725 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11069.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11075.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11078.9225 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11080.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 11101.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11107.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11110.4225 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11111.4225 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11112.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11118.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11119.9225 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11120.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11122.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11125.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11126.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11128.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11131.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11132.9225 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11134.4225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11137.9225 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11138.2392 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11181.4824 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11185.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11189.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11193.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11194.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11196.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11197.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11201.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11205.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11209.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11211.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11212.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11214.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11218.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11222.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11226.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11227.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11229.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11230.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11234.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11238.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11242.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11244.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11245.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11247.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 11249.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11253.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11257.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11261.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11262.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11264.4824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11265.9824 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11309.2257 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11311.2257 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11311.5424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11314.5424 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11315.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11321.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11324.2924 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11325.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 17 | 177083.3333 | ACTION | 11342.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11348.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11351.7924 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11352.7924 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11354.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11360.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11361.2924 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11362.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11363.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11367.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11368.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11369.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11373.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11374.2924 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11375.7924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11379.2924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11379.609 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11381.609 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11381.9257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11384.9257 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11385.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11391.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11394.6757 | TurbineInstallation
| WTIV | Delay | 14 | 145833.3333 | ACTION | 11408.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11410.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11416.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11419.1757 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11420.1757 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11421.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11427.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11428.6757 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11429.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11431.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11434.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11435.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11437.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11440.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11441.6757 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11443.1757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11446.6757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11446.9924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11448.9924 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11449.309 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11452.309 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11453.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11459.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11462.059 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11463.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11469.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11472.559 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11473.559 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11475.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11481.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11482.059 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11483.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11484.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11488.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11489.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11490.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 11500.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11504.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11505.059 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11506.559 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11510.059 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11510.3757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11512.3757 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11512.6924 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11515.6924 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11516.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 52 | 541666.6667 | ACTION | 11568.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11574.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11577.4424 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11578.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11584.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11587.9424 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11588.9424 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11590.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11596.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11597.4424 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11598.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11599.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11603.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11604.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11605.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11609.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11610.4424 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11611.9424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11615.4424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11615.759 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11617.759 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11618.0757 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11621.0757 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11621.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11627.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11630.8257 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 11634.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11636.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 41 | 427083.3333 | ACTION | 11677.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11683.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11686.3257 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11687.3257 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11688.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11694.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11695.8257 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11696.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11698.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11701.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11702.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11704.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11707.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11708.8257 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11710.3257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11713.8257 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11714.1424 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 11757.3856 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11761.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11765.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11769.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11770.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11772.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11773.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11777.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11781.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11785.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11787.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11788.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11790.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11794.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11798.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 11806.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11810.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11811.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11813.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11814.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11818.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11822.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11826.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11828.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11829.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11831.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11835.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 11839.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 11843.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11844.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11846.3856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 11847.8856 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 24 | 250000 | ACTION | 11871.8856 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 11873.8856 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 11874.8856 | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 11880.8856 | TurbineInstallation
| WTIV | Transit | 18.2432 | 190033.7838 | ACTION | 11899.1288 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11901.1288 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11901.4455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11904.4455 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11905.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11911.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11914.1955 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11915.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 11936.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11942.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 11945.6955 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11946.6955 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 11948.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 11954.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 11955.1955 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11956.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11957.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11961.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11962.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11963.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11967.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 11968.1955 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 11969.6955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 11973.1955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 11973.5122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 11975.5122 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 11975.8288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11978.8288 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 11979.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 11985.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 11988.5788 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 11990.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 60 | 625000 | ACTION | 12050.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12056.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12059.0788 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12060.0788 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12061.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12067.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12068.5788 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12069.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12071.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12074.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12075.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12077.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12080.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12081.5788 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12083.0788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12086.5788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12086.8955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12088.8955 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12089.2122 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12092.2122 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12092.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12098.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12101.9622 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12103.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12109.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12112.4622 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12113.4622 | TurbineInstallation
| WTIV | Delay | 21 | 218750 | ACTION | 12134.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12135.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12141.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12142.9622 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12143.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12145.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12148.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12149.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12151.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12154.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12155.9622 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12157.4622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12160.9622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12161.2788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12163.2788 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12163.5955 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12166.5955 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12167.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12173.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12176.3455 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12177.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12183.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12186.8455 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12187.8455 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12188.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12190.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12196.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12197.3455 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12198.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12199.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12203.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12204.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12205.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12209.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12210.3455 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12211.8455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12215.3455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12215.6622 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12217.6622 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12217.9788 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12220.9788 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12221.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12227.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12230.7288 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12232.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12238.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12241.2288 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12242.2288 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12243.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12249.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12250.7288 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12251.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12253.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 12259.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12262.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12263.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12265.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12268.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12269.7288 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12271.2288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12274.7288 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12275.0455 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12318.2887 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12322.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12326.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12330.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12331.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12333.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12334.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12338.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12342.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12346.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12348.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12349.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12351.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12355.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12359.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12363.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12364.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12366.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12367.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12371.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12375.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12379.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12381.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12382.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12384.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12388.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12392.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12396.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12397.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12399.2887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12400.7887 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12444.032 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12446.032 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12446.3487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12449.3487 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12450.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12456.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12459.0987 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12460.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12466.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12469.5987 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12470.5987 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12472.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12478.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12479.0987 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12480.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12481.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12485.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12486.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12487.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12491.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12492.0987 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12493.5987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12497.0987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12497.4153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12499.4153 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12499.732 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12502.732 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12503.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12509.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12512.482 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12513.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12519.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12522.982 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12523.982 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12525.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 12530.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12536.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12537.482 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12538.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12539.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12543.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12544.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12545.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12549.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12550.482 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12551.982 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12555.482 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12555.7987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12557.7987 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12558.1153 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12561.1153 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12561.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12567.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12570.8653 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12572.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12578.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12581.3653 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12582.3653 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12583.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12589.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12590.8653 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12591.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12593.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12596.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12597.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12599.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12602.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12603.8653 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12605.3653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12608.8653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12609.182 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12611.182 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12611.4987 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12614.4987 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12615.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12621.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12624.2487 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12625.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 11 | 114583.3333 | ACTION | 12636.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12642.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12645.7487 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12646.7487 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12648.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 12657.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12663.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12664.2487 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12665.2487 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 12670.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12671.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12675.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12676.2487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12677.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 12679.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12683.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12684.2487 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12685.7487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12689.2487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12689.5653 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12691.5653 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12691.882 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12694.882 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12695.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12701.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12704.632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12706.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12712.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 12715.132 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12716.132 | TurbineInstallation
| WTIV | Delay | 40 | 416666.6667 | ACTION | 12756.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 12757.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 12763.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 12764.632 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12765.632 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 12766.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12768.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12771.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12772.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12774.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12777.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 12778.632 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 12780.132 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 12783.632 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 12783.9487 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12827.1919 | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12831.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12835.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12839.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12840.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12842.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12843.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12847.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12851.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12855.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12857.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12858.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12860.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12864.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12868.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12872.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12873.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12875.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12876.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12880.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12884.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 18 | 187500 | ACTION | 12902.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12906.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12908.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12909.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12911.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12915.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Tower Section | 4 | 41666.6667 | ACTION | 12919.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 12923.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Nacelle | 4 | 41666.6667 | ACTION | 12927.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12928.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12930.1919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Fasten Blade | 1.5 | 15625 | ACTION | 12931.6919 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 12974.9351 | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 12976.9351 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 12977.2518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12980.2518 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 12981.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12987.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 12990.0018 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 12991.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 12997.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13000.5018 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13001.5018 | TurbineInstallation
| WTIV | Delay | 35 | 364583.3333 | ACTION | 13036.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13038.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13044.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13045.0018 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13046.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13047.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13051.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13052.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13053.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13057.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13058.0018 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13059.5018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13063.0018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13063.3185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13065.3185 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13065.6351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13068.6351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13069.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13075.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13078.3851 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13079.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13085.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13088.8851 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13089.8851 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13091.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13097.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13098.3851 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13099.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13100.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13104.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13105.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13106.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13110.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13111.3851 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13112.8851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13116.3851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13116.7018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13118.7018 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13119.0185 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13122.0185 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13122.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 6 | 62500 | ACTION | 13128.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13134.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13137.7685 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13139.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13145.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13148.2685 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13149.2685 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13150.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13156.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13157.7685 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13158.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13160.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13163.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13164.7685 | TurbineInstallation
| WTIV | Delay | 23 | 239583.3333 | ACTION | 13187.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13189.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13192.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13193.7685 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13195.2685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13198.7685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13199.0851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13201.0851 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13201.4018 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13204.4018 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13205.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13211.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13214.1518 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13215.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13221.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13224.6518 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13225.6518 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13227.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13233.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13234.1518 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13235.1518 | TurbineInstallation
| WTIV | Delay | 22 | 229166.6667 | ACTION | 13257.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13258.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Delay | 48 | 500000 | ACTION | 13306.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13310.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13311.1518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13312.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13316.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13317.1518 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13318.6518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13322.1518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13322.4685 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Position Onsite | 2 | 20833.3333 | ACTION | 13324.4685 | TurbineInstallation
| WTIV | Jackup | 0.31667 | 3298.6111 | ACTION | 13324.7851 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13327.7851 | TurbineInstallation
| WTIV | Lift Tower Section | 0.75 | 7812.5 | ACTION | 13328.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13334.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Tower Section | 3 | 31250 | ACTION | 13337.5351 | TurbineInstallation
| WTIV | Lift Tower Section | 1.5 | 15625 | ACTION | 13339.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Tower Section | 6 | 62500 | ACTION | 13345.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Nacelle | 3 | 31250 | ACTION | 13348.0351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13349.0351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 13350.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Nacelle | 6 | 62500 | ACTION | 13356.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 13357.5351 | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13358.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13360.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13363.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13364.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13366.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13369.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Release Blade | 1 | 10416.6667 | ACTION | 13370.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 13372.0351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Attach Blade | 3.5 | 36458.3333 | ACTION | 13375.5351 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation
| WTIV | Jackdown | 0.31667 | 3298.6111 | ACTION | 13375.8518 | TurbineInstallation | 22.5 | 150 |  | TurbineInstallation