## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | site_position_time | mono_drive_rate | mono_release_time | tp_release_time | tower_section_fasten_time | tower_section_release_time | tower_section_attach_time | nacelle_fasten_time | nacelle_release_time | nacelle_attach_time | blade_fasten_time | blade_release_time | blade_attach_time | location | site_depth | hub_height
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 0 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 12 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 20 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 32 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 40 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Transit | 43.2432 | 450450.4505 | ACTION | 43.2432 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 52 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 60 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 72 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 80 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 80 | 400000 | ACTION | 80 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 92 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 100 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 112 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 120 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 123.2432 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 123.2441 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for monopiles | 80.0008 | 833342.0226 | ACTION | 123.2441 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 132 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 138.2441 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 140 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 143.6607 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 144.6607 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 152 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 154.6607 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 155.3838 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 155.3871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 156.3871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 157.5871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 160 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 167.5871 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 168.5871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 169.5871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 173.5871 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 179.0037 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 194.0037 | MonopileInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 203.0037 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 208.4204 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 209.4204 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Delay | 51 | 255000 | ACTION | 211 | MonopileInstallation
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 219.4204 | MonopileInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 220.4204 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 221.1435 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 221.1467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 222.1467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 223.3467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 233.3467 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 234.3467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 235.3467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 239.3467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 244.7634 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 254.2432 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 254.2441 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 259.7634 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 265.18 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 266.18 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 276.18 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 276.9031 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 276.9064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 277.9064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 279.1064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 289.1064 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 290.1064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 291.1064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 295.1064 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 300.523 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 315.523 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 320.9397 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 321.9397 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 331.9397 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 332.6628 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 332.666 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 333.666 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 334.866 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 344.866 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 221.6219 | 1108109.644 | ACTION | 344.866 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 344.8668 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 345.866 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 346.866 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 350.866 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 356.2827 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 388.1101 | MonopileInstallation
| Feeder 1 | Queue | 133.866 | 669330.0311 | ACTION | 388.1101 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 388.1101 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 400.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 403.1101 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 408.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 408.5268 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 409.5268 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 419.5268 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 420.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 420.2498 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 420.2531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 421.2531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 422.4531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 428.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 432.4531 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 433.4531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 6 | 62500 | ACTION | 439.4531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 440.4531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 444.4531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 449.8697 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 4 | 41666.6667 | ACTION | 453.8697 | MonopileInstallation
| Feeder 0 | Delay | 30 | 150000 | ACTION | 458.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 468.8697 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 470.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 474.2864 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 475.2864 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 478.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 485.2864 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 486.0095 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 486.0127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 487.0127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 488.2127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 490.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 498.1101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 498.2127 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 499.2127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 500.2127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 504.2127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 509.6294 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 524.6294 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 530.046 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 531.046 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 541.046 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 541.3533 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 541.3542 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 541.7691 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 541.7724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 542.7724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 543.9724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 553.9724 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 554.9724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 555.9724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 559.9724 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 565.389 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 580.389 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 585.8057 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 586.8057 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 596.8057 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 597.5288 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 597.532 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 598.532 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 599.732 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 609.732 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 221.6219 | 1108109.644 | ACTION | 609.732 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 609.7328 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 610.732 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 611.732 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 615.732 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 621.1487 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 652.9761 | MonopileInstallation
| Feeder 0 | Queue | 111.6219 | 558109.644 | ACTION | 652.9761 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 652.9761 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 664.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 667.9761 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 672.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 673.3928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 674.3928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 684.3928 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 684.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 685.1158 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 685.1191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 686.1191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 687.3191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 692.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 697.3191 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 698.3191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 699.3191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 703.3191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 704.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 708.7357 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 712.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 723.7357 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 724.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 729.1524 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 730.1524 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 732.9761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 740.1524 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 740.8755 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 740.8787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 741.8787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 743.0787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 753.0787 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 754.0787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 755.0787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 759.0787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 764.4954 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 776.2193 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 776.2202 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 779.4954 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 784.9121 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 785.9121 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 795.9121 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 796.6351 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 796.6384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 797.6384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 798.8384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 808.8384 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 809.8384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 810.8384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 814.8384 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 820.255 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 835.255 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 840.6717 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 841.6717 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 851.6717 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 852.3948 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 852.398 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 853.398 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 854.598 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 864.598 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 864.598 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 864.5989 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 865.598 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 866.598 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 870.598 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 876.0147 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Delay | 21 | 105000 | ACTION | 885.5989 | MonopileInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 928.8421 | MonopileInstallation
| Feeder 1 | Queue | 152.6219 | 763109.644 | ACTION | 928.8421 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 52.8274 | 550285.5286 | ACTION | 928.8421 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 940.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 943.8421 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 948.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 949.2588 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 950.2588 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 960.2588 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 960.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 960.9818 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 960.9851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 961.9851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 963.1851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 968.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 973.1851 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 974.1851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 975.1851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 979.1851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 980.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 984.6017 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 988.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 999.6017 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1000.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1005.0184 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1006.0184 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1008.8421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1016.0184 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1016.7415 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1016.7447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1017.7447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1018.9447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1028.9447 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1029.9447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1030.9447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1034.9447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1040.3614 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1052.0853 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1052.0862 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1055.3614 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1060.7781 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1061.7781 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1071.7781 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1072.5011 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1072.5044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1073.5044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1074.7044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1084.7044 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1085.7044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1086.7044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1090.7044 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1096.121 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1111.121 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1116.5377 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1117.5377 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1127.5377 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1128.2608 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1128.264 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1129.264 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1130.464 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1140.464 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 1140.464 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1140.4649 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1141.464 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1142.464 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1146.464 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1151.8807 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1183.7081 | MonopileInstallation
| Feeder 0 | Queue | 131.6219 | 658109.644 | ACTION | 1183.7081 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1183.7081 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1195.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1198.7081 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1203.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1204.1248 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1205.1248 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1215.1248 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1215.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1215.8478 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1215.8511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1216.8511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1218.0511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1223.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1228.0511 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1229.0511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1230.0511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1234.0511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1235.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1239.4678 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1243.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1254.4678 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1255.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1259.8844 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1260.8844 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1263.7081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1270.8844 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1271.6075 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1271.6107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1272.6107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1273.8107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1283.8107 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1284.8107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1285.8107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1289.8107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1295.2274 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1306.9513 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1306.9522 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1310.2274 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1315.6441 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1316.6441 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1326.6441 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1327.3671 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1327.3704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1328.3704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1329.5704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1339.5704 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1340.5704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1341.5704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1345.5704 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1350.987 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1365.987 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1371.4037 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1372.4037 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1382.4037 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1383.1268 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1383.13 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1384.13 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1385.33 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1395.33 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 1395.33 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1395.3309 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1396.33 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1397.33 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1401.33 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1406.7467 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1438.5741 | MonopileInstallation
| Feeder 1 | Queue | 131.6219 | 658109.644 | ACTION | 1438.5741 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1438.5741 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1450.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1453.5741 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1458.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1458.9908 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1459.9908 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1469.9908 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1470.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1470.7138 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1470.7171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1471.7171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1472.9171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1478.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1482.9171 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1483.9171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1484.9171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1488.9171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1490.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1494.3338 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1498.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1509.3338 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1510.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1514.7504 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1515.7504 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1518.5741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1525.7504 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1526.4735 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1526.4767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1527.4767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1528.6767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1538.6767 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1539.6767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1540.6767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1544.6767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1550.0934 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1561.8174 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 1561.8182 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1565.0934 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1570.5101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1571.5101 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1581.5101 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1582.2331 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1582.2364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1583.2364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1584.4364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1594.4364 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1595.4364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1596.4364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1600.4364 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1605.8531 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1620.8531 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1626.2697 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1627.2697 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1637.2697 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1637.9928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1637.996 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1638.996 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1640.196 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1650.196 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 1650.196 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1650.1969 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1651.196 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1652.196 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1656.196 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1661.6127 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1693.4401 | MonopileInstallation
| Feeder 0 | Queue | 131.6219 | 658109.644 | ACTION | 1693.4401 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1693.4401 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1705.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1708.4401 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1713.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1713.8568 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1714.8568 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1724.8568 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1725.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1725.5798 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1725.5831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1726.5831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1727.7831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1733.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1737.7831 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1738.7831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1739.7831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1743.7831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1745.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1749.1998 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1753.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1764.1998 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 1765.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1769.6164 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1770.6164 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 1773.4401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1780.6164 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1781.3395 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1781.3427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1782.3427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1783.5427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1793.5427 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1794.5427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1795.5427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1799.5427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1804.9594 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 1816.6834 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 1816.6842 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1819.9594 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1825.3761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1826.3761 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1836.3761 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1837.0991 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1837.1024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1838.1024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1839.3024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1849.3024 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1850.3024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1851.3024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1855.3024 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1860.7191 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1875.7191 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1881.1357 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1882.1357 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1892.1357 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1892.8588 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1892.862 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1893.862 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1895.062 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1905.062 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 1905.062 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 1905.0629 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1906.062 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1907.062 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1911.062 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 1916.4787 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 1948.3061 | MonopileInstallation
| Feeder 1 | Queue | 131.6219 | 658109.644 | ACTION | 1948.3061 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 1948.3061 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1960.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 1963.3061 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1968.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 1968.7228 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 1969.7228 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 1979.7228 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 1980.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 1980.4459 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 1980.4491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1981.4491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 1982.6491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 1988.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 1992.6491 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 1993.6491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 1994.6491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 1998.6491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2000.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2004.0658 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2008.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2019.0658 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2020.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2024.4824 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2025.4824 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2028.3061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2035.4824 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2036.2055 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2036.2088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2037.2088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2038.4088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2048.4088 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2049.4088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2050.4088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2054.4088 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2059.8254 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2071.5494 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2071.5502 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2074.8254 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2080.2421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2081.2421 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2091.2421 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2091.9652 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2091.9684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2092.9684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2094.1684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2104.1684 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2105.1684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2106.1684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2110.1684 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2115.5851 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2130.5851 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2136.0017 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2137.0017 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2147.0017 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2147.7248 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2147.728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2148.728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2149.928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2159.928 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 2159.928 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2159.9289 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2160.928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2161.928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2165.928 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2171.3447 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2203.1721 | MonopileInstallation
| Feeder 0 | Queue | 131.6219 | 658109.644 | ACTION | 2203.1721 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2203.1721 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2215.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2218.1721 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2223.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2223.5888 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2224.5888 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2234.5888 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2235.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2235.3119 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2235.3151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2236.3151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2237.5151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2243.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2247.5151 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2248.5151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2249.5151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2253.5151 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2255.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2258.9318 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2263.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2273.9318 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2275.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2279.3484 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2280.3484 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2283.1721 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2290.3484 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2291.0715 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2291.0748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2292.0748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2293.2748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2303.2748 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2304.2748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2305.2748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2309.2748 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2314.6914 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2326.4154 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2326.4162 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2329.6914 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2335.1081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2336.1081 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2346.1081 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2346.8312 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2346.8344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2347.8344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2349.0344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2359.0344 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2360.0344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2361.0344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2365.0344 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2370.4511 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2385.4511 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2390.8677 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2391.8677 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2401.8677 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2402.5908 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2402.5941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2403.5941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2404.7941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2414.7941 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 2414.7941 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2414.7949 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2415.7941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2416.7941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2420.7941 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2426.2107 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2458.0381 | MonopileInstallation
| Feeder 1 | Queue | 131.6219 | 658109.644 | ACTION | 2458.0381 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2458.0381 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2470.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2473.0381 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2478.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2478.4548 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2479.4548 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2489.4548 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2490.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2490.1779 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2490.1811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2491.1811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2492.3811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2498.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2502.3811 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2503.3811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2504.3811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2508.3811 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2510.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2513.7978 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2518.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2528.7978 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 2530.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2534.2144 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2535.2144 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 2538.0381 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2545.2144 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2545.9375 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2545.9408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2546.9408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2548.1408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2558.1408 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2559.1408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2560.1408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2564.1408 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2569.5574 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 2581.2814 | MonopileInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 2581.2822 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2584.5574 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2589.9741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2590.9741 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2600.9741 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2601.6972 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2601.7004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2602.7004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2603.9004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2613.9004 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2614.9004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2615.9004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2619.9004 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2625.3171 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2640.3171 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2645.7337 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2646.7337 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2656.7337 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2657.4568 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2657.4601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2658.4601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2659.6601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2669.6601 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 211.6219 | 1058109.644 | ACTION | 2669.6601 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2669.6609 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2670.6601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2671.6601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2675.6601 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2681.0767 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2712.9041 | MonopileInstallation
| Feeder 0 | Queue | 131.6219 | 658109.644 | ACTION | 2712.9041 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 2712.9041 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2724.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2727.9041 | MonopileInstallation
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2732.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2733.3208 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2734.3208 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 31 | 322916.6667 | ACTION | 2765.3208 | MonopileInstallation
| Feeder 1 | Delay | 39 | 195000 | ACTION | 2771.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2775.3208 | MonopileInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2777.3208 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2778.0439 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 2780.0439 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2780.0471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2781.0471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2782.2471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2783.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2791.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2792.2471 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2793.2471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2794.2471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2798.2471 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2803.6638 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2803.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2811.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2818.6638 | MonopileInstallation
| Feeder 1 | Fasten Monopile | 12 | 60000 | ACTION | 2823.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2824.0805 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2825.0805 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Fasten Transition Piece | 8 | 40000 | ACTION | 2831.9041 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2835.0805 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2835.8035 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2835.8068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2836.8068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2838.0068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2848.0068 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2849.0068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2850.0068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2854.0068 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2859.4234 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2874.4234 | MonopileInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 2875.1474 | MonopileInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 2875.1482 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2879.8401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2880.8401 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2890.8401 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2891.5632 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2891.5664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2892.5664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2893.7664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2903.7664 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2904.7664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2905.7664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2909.7664 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2915.1831 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 2930.1831 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 2935.5998 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 2936.5998 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 2946.5998 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 2947.3228 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 2947.3261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2948.3261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 2949.5261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 2959.5261 | MonopileInstallation
| Feeder 0 | ActiveFeeder | 246.6219 | 1233109.644 | ACTION | 2959.5261 | MonopileInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 2959.5269 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 2960.5261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 2961.5261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 2965.5261 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 2970.9427 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3002.7701 | MonopileInstallation
| Feeder 1 | Queue | 127.6219 | 638109.644 | ACTION | 3002.7701 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay: Not enough vessels for monopiles | 31.8274 | 331535.5286 | ACTION | 3002.7701 | MonopileInstallation | [14 empty] | Site
| WTIV | Delay | 44 | 458333.3333 | ACTION | 3046.7701 | MonopileInstallation
| Feeder 0 | Delay | 49 | 245000 | ACTION | 3051.7701 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3061.7701 | MonopileInstallation
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3063.7701 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3067.1868 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3068.1868 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3071.7701 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3078.1868 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3078.9099 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3078.9131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3079.9131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3081.1131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 0 | Fasten Monopile | 12 | 60000 | ACTION | 3083.7701 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3091.1131 | MonopileInstallation
| Feeder 0 | Fasten Transition Piece | 8 | 40000 | ACTION | 3091.7701 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3092.1131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3093.1131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3097.1131 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3102.5298 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3117.5298 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3122.9465 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3123.9465 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3133.9465 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3134.6695 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3134.6728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3135.6728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3136.8728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3146.8728 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3147.8728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3148.8728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3152.8728 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3158.2894 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3173.2894 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3178.7061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3179.7061 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3189.7061 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3190.4292 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3190.4324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3191.4324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3192.6324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3202.6324 | MonopileInstallation
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3203.6324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3204.6324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3208.6324 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3214.0491 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3229.0491 | MonopileInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3234.4658 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | RovSurvey | 1 | 10416.6667 | ACTION | 3235.4658 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Monopile | 10 | 104166.6667 | ACTION | 3245.4658 | MonopileInstallation
| WTIV | Upend Monopile | 0.72307 | 7531.9327 | ACTION | 3246.1888 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower Monopile | 0.00325 | 33.8542 | ACTION | 3246.1921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3247.1921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Drive Monopile | 1.2 | 12500 | ACTION | 3248.3921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Release Transition Piece | 10 | 104166.6667 | ACTION | 3258.3921 | MonopileInstallation
| Feeder 1 | ActiveFeeder | 255.6219 | 1278109.644 | ACTION | 3258.3921 | MonopileInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3258.3929 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Crane Reequip | 1 | 10416.6667 | ACTION | 3259.3921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Lower TP | 1 | 10416.6667 | ACTION | 3260.3921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Bolt TP | 4 | 41666.6667 | ACTION | 3264.3921 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3269.8087 | MonopileInstallation | MonopileInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3301.6362 | MonopileInstallation
1 | WTIV | Mobilize | 168 | 1750000 | ACTION | 3301.6362 | TurbineInstallation
0.5 | Feeder 0 | Mobilize | 72 | 180000 | ACTION | 3301.6362 | TurbineInstallation
0.5 | Feeder 1 | Mobilize | 72 | 180000 | ACTION | 3301.6362 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3303.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3305.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3307.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3309.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3311.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3312.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3313.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3313.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3315.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3317.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3319.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3321.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3323.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3324.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3325.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3326.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3328.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3330.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3332.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3334.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3336.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3336.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3337.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3338.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Queue | 36.75 | 183750 | ACTION | 3338.3862 | TurbineInstallation
| WTIV | Transit | 42 | 437500 | ACTION | 3343.6362 | TurbineInstallation
| WTIV | Delay | 9 | 93750 | ACTION | 3352.6362 | TurbineInstallation
| WTIV | Transit | 1.2432 | 12950.4505 | ACTION | 3353.8794 | TurbineInstallation
| Feeder 0 | Delay | 19 | 95000 | ACTION | 3357.3862 | TurbineInstallation
| Feeder 1 | Delay | 19 | 95000 | ACTION | 3357.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3359.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3361.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3363.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3365.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3367.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3368.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3368.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3369.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3371.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3373.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3375.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3377.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3379.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3380.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3381.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3381.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3383.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3385.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3387.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3389.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3391.8862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3392.6362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3393.3862 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3394.1362 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3400.6294 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3400.6302 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 46.7508 | 486987.8559 | ACTION | 3400.6302 | TurbineInstallation | [14 empty] | Site
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3415.6302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3421.0469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3422.0469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3422.4269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3424.4269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3425.4269 | TurbineInstallation
| Feeder 1 | Delay | 32 | 160000 | ACTION | 3426.1362 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3426.1869 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3428.1869 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3429.1869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3430.3269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3432.3269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3433.3269 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3435.3269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3436.8469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3438.8469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3439.8469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3440.8469 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3442.3469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3444.3469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3445.3469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3445.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3447.3469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3448.8469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3449.3469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3450.8469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3452.3469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3452.8469 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3454.3469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3455.8469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3461.2636 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3469.3794 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3469.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3476.2636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3481.6802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3482.6802 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3483.0602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3485.0602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3486.0602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3486.8202 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3488.8202 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3489.8202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3490.9602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3492.9602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3493.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3495.4802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3497.4802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3498.4802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3499.4802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3500.9802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3502.9802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3503.9802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3504.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3505.9802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3507.4802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3507.9802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3509.4802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3510.9802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3511.4802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3512.9802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3514.4802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3519.8969 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3534.8969 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3540.3136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3541.3136 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3541.6936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3543.6936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3544.6936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3545.4536 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3547.4536 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3548.4536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3549.5936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3551.5936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3552.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3554.1136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3556.1136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3557.1136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3558.1136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3559.6136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3561.6136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3562.6136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3563.1136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3564.6136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3566.1136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3566.6136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3568.1136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3569.6136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3570.1136 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 169.4833 | 847416.6667 | ACTION | 3570.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 100.7333 | 503666.6667 | ACTION | 3570.1136 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3570.1144 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3571.6136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3573.1136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3578.5302 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3593.5302 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3598.9469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3599.9469 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3600.3269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3602.3269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3603.3269 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3604.0869 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3606.0869 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3607.0869 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3608.2269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3610.2269 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3611.2269 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3612.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3613.3576 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3614.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3615.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3615.7469 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3616.7469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3617.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3619.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3621.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3623.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3624.1076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3624.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 3626.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3628.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3630.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 7 | 35000 | ACTION | 3631.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3632.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3632.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3633.2469 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3633.7469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3634.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3635.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 1 | 5000 | ACTION | 3635.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3636.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3637.2469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3637.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3638.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3639.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3640.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3640.7469 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3641.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3642.2469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3643.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3643.7469 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3644.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3645.1076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3645.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3647.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3649.1636 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3649.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3651.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 3653.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 3655.8576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3656.6076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3657.3576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 3658.1076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3664.1636 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3669.5802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3670.5802 | TurbineInstallation
| WTIV | Delay | 33 | 343750 | ACTION | 3703.5802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3703.9602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3705.9602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3706.9602 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3707.7202 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3709.7202 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3710.7202 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3711.8602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3713.8602 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3714.8602 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3716.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3718.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3719.3802 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3720.3802 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3721.8802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3723.8802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3724.8802 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3725.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3726.8802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3728.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3728.8802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3730.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3731.8802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3732.3802 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3733.8802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3735.3802 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3740.7969 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3755.7969 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 3760.7969 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3766.2136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3767.2136 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 3768.2136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3768.5936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3770.5936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3771.5936 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3772.3536 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 115 | 575000 | ACTION | 3773.1076 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3774.3536 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3775.3536 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3776.4936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3778.4936 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3779.4936 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3781.0136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3783.0136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3784.0136 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3785.0136 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3786.5136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3788.5136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3789.5136 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3790.0136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3791.5136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3793.0136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3793.5136 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3795.0136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3796.5136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3797.0136 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 226.9 | 1134500 | ACTION | 3797.0136 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 3797.0144 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3798.5136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3800.0136 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3805.4302 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 3816.3509 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 3816.3517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 10.9215 | 113765.5016 | ACTION | 3816.3517 | TurbineInstallation | [14 empty] | Site
| WTIV | Delay | 18 | 187500 | ACTION | 3834.3517 | TurbineInstallation
| Feeder 1 | Delay | 40 | 200000 | ACTION | 3837.0144 | TurbineInstallation
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3849.3517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3854.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3855.7684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3856.1484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3858.1484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3859.1484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3859.9084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3861.9084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3862.9084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3864.0484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 3866.0484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3868.0484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3869.0484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3870.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3872.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3873.5684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3874.5684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3876.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3878.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3879.0684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3879.5684 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3880.2576 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3881.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3882.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3882.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3883.0684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3884.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3884.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3886.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3886.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3886.5684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3888.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3888.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3889.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3890.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3891.0076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3891.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3892.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3894.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3894.9851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3896.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3898.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3900.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3902.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3903.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3904.0076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3904.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3906.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3908.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3909.9851 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3910.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 3912.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 3914.7576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3915.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3915.5076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3916.2576 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3916.4017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3916.7817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 3917.0076 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3918.7817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3919.7817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3920.5417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3922.5417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3923.5417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3924.6817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3926.6817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3927.6817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3929.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3931.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3932.2017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3933.2017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3934.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3936.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3937.7017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3938.2017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3939.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3941.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3941.7017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3943.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3944.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3945.2017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3946.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3948.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 3953.6184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 3960.2509 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 3960.2517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 3968.6184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 3974.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3975.0351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 3975.4151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3977.4151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3978.4151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 3979.1751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3981.1751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3982.1751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 3983.3151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3985.3151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 3986.3151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 3987.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 3989.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 3990.8351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3991.8351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 3993.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 3995.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 3996.3351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 3996.8351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 3998.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 3999.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4000.3351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4001.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4003.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4003.8351 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 187.4833 | 937416.6667 | ACTION | 4003.8351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 43.5833 | 217916.6667 | ACTION | 4003.8351 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4003.8359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4005.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4006.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4012.2517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 28 | 291666.6667 | ACTION | 4040.2517 | TurbineInstallation
| Feeder 0 | Delay | 44 | 220000 | ACTION | 4047.8359 | TurbineInstallation
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4055.2517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4060.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4061.6684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4062.0484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4064.0484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4065.0484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4065.8084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4067.8084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4068.8084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4069.9484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4071.9484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4072.9484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4074.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4076.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4077.4684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4078.4684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4079.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4082.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4084.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4085.9684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4086.4684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4087.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4089.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4089.9684 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4091.0791 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4091.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4092.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4093.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4093.4684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4094.9684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4095.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4096.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4097.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4099.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4101.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4101.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4101.8851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4102.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4103.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4105.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4107.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4109.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4111.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4113.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4114.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4114.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4115.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4116.8851 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4117.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4119.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4121.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4122.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4123.3017 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4123.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4123.6817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4125.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4125.6817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4126.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4126.6817 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4127.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4127.4417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4127.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4129.4417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4130.4417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4131.5817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4133.5817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4134.5817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4136.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4138.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4139.1017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4140.1017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4141.6017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4143.6017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4144.6017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4145.1017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4146.6017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4148.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4148.6017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4150.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4151.6017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4152.1017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4153.6017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4155.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4160.5184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4171.0724 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4171.0732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4175.5184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4180.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4181.9351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4182.3151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4184.3151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4185.3151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4186.0751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4188.0751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4189.0751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4190.2151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4192.2151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4193.2151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4194.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4196.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4197.7351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4198.7351 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4202.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4204.2351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4206.2351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4207.2351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4207.7351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4209.2351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4210.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4211.2351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4212.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4214.2351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4214.7351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 210.9 | 1054500 | ACTION | 4214.7351 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 43.6618 | 218309.2259 | ACTION | 4214.7351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4214.7359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4216.2351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4217.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4223.1517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4238.1517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4243.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4244.5684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4244.9484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4246.9484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4247.9484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4248.7084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4250.7084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4251.7084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4252.8484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4254.8484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4255.8484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4257.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4257.9791 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4259.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4259.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4260.3684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4261.3684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4261.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4262.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4263.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4264.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4265.8684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4265.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4266.3684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4267.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4267.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4268.7291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4269.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4269.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4269.8684 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4270.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4272.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4274.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4276.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 4278.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 10 | 104166.6667 | ACTION | 4279.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4280.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4281.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4282.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4282.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4283.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4283.7291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4284.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4284.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4285.3684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4286.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4286.8684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4288.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4288.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4290.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4292.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4293.7851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4294.4791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4295.2291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4295.9791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4296.7291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4308.7851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4314.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4315.2017 | TurbineInstallation
| Feeder 1 | Delay | 29 | 145000 | ACTION | 4325.7291 | TurbineInstallation
| WTIV | Delay | 13 | 135416.6667 | ACTION | 4328.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4328.5817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4330.5817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4331.5817 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4332.3417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4334.3417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4335.3417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4336.4817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4338.4817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4339.4817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4341.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4343.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4344.0017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4345.0017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4346.5017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4348.5017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4349.5017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4350.0017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4351.5017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4353.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4353.5017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4355.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4356.5017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4357.0017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4358.5017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4360.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4365.4184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4368.9724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4368.9732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4380.4184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4385.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4386.8351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4387.2151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4389.2151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4390.2151 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4391.2151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4391.9751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 11 | 114583.3333 | ACTION | 4402.9751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4404.9751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4405.9751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4407.1151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4409.1151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4410.1151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4411.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4413.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4414.6351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4415.6351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4417.1351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4419.1351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4420.1351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4420.6351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4422.1351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4423.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4424.1351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4425.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4427.1351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4427.6351 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 212.9 | 1064500 | ACTION | 4427.6351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 58.6618 | 293309.2259 | ACTION | 4427.6351 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4427.6359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4429.1351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4430.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4436.0517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4451.0517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4456.4684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4457.4684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4457.8484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4459.8484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4460.8484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4461.6084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4463.6084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4464.6084 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4465.7484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4467.7484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4468.7484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4470.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4470.8791 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4472.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4472.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4473.2684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4474.2684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4474.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4475.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4476.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4477.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4478.7684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4478.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4479.2684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4480.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4480.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4481.6291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4482.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4482.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4482.7684 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4483.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4484.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4485.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4485.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4486.2684 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4487.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4487.7684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4489.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4489.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 62 | 645833.3333 | ACTION | 4551.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 66 | 330000 | ACTION | 4555.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4556.6851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4557.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 8 | 40000 | ACTION | 4565.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4567.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4567.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4568.6291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4569.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4571.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4571.6851 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4573.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4575.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4577.1017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 4577.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4578.1017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4578.4817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 4579.3791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4580.1291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4580.4817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4580.8791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4581.4817 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 4581.6291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4582.2417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4584.2417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4585.2417 | TurbineInstallation
| WTIV | Delay | 2 | 20833.3333 | ACTION | 4587.2417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4588.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 18 | 187500 | ACTION | 4606.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4608.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4609.3817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4610.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4612.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4613.9017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4614.9017 | TurbineInstallation
| WTIV | Delay | 84 | 875000 | ACTION | 4698.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4700.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 4703.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4705.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4706.4017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4706.9017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4708.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4709.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4710.4017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4711.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4713.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4713.9017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4715.4017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4716.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4722.3184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 151 | 755000 | ACTION | 4732.6291 | TurbineInstallation
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4737.3184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4742.7351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4743.7351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4744.1151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4746.1151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4747.1151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4747.8751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4749.8751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4750.8751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4752.0151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4754.0151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4755.0151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4756.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4758.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4759.5351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4760.5351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4762.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4764.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4765.0351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4765.5351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4767.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4768.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4769.0351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4770.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4772.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4772.5351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 344.9 | 1724500 | ACTION | 4772.5351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4772.5359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4774.0351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4775.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 4775.8724 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 4775.8732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4780.9517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4795.9517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4801.3684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4802.3684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4802.7484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4815.7791 | TurbineInstallation
| WTIV | Delay | 32 | 333333.3333 | ACTION | 4834.7484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 20 | 100000 | ACTION | 4835.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4836.7484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4837.7484 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4837.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4838.5084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4839.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4840.5084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4841.5084 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4841.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4842.6484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4843.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4844.6484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4845.6484 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4845.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4846.5291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4847.1684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4847.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4848.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4849.1684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4850.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4850.1684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4851.1684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4852.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4852.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4854.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4854.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4855.6684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4856.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4856.1684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4857.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4858.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4858.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4859.1684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4859.5291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4859.6684 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4860.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4861.1684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4862.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4862.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4863.1684 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4864.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4864.6684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4866.1684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4866.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 4868.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 4870.2791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4871.0291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4871.5851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4871.7791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 4872.5291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4886.5851 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4892.0017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 20 | 100000 | ACTION | 4892.5291 | TurbineInstallation
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4893.0017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4893.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4895.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4896.3817 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 4897.3817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4898.1417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4900.1417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4901.1417 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4902.2817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4904.2817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4905.2817 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4906.8017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4908.8017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4909.8017 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4910.8017 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4912.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4914.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4915.3017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4915.8017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4917.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4918.8017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4919.3017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4920.8017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4922.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4922.8017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4924.3017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4925.8017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 4931.2184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 4935.7724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 4935.7732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 4946.2184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 4951.6351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4952.6351 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 4953.0151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4955.0151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4956.0151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 4956.7751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4958.7751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4959.7751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 4960.9151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4962.9151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 4963.9151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 4965.4351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 4967.4351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 4968.4351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4969.4351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 4970.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 12 | 125000 | ACTION | 4982.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 4984.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 4985.9351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4986.4351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4987.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 4 | 41666.6667 | ACTION | 4991.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4993.4351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4993.9351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4995.4351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 4996.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 4997.4351 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 221.5618 | 1107809.2259 | ACTION | 4997.4351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 61.6618 | 308309.2259 | ACTION | 4997.4351 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 4997.4359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 4998.9351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5000.4351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5005.8517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 5020.8517 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5026.2684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5027.2684 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5027.6484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 5030.6484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5032.6484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5033.6484 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5034.4084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5036.4084 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5037.4084 | TurbineInstallation
| Feeder 0 | Delay | 40 | 200000 | ACTION | 5037.4359 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5038.5484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5040.5484 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5041.5484 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5043.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5045.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5046.0684 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5047.0684 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5048.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5050.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5051.5684 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5052.0684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5053.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5055.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5055.5684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5057.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5058.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5059.0684 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5060.5684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5062.0684 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5067.4851 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 5080.6791 | TurbineInstallation
| WTIV | Position Onsite | 15 | 156250 | ACTION | 5082.4851 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5082.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5084.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5086.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5087.9017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5088.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5088.9017 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 5089.2817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5090.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5091.2817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5091.4291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5092.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5092.2817 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5092.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 5093.0417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5094.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5095.0417 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5096.0417 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5096.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 5097.1817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5098.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5099.1817 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5100.1817 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5100.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 5101.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5102.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5103.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 5103.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5104.4291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 5104.7017 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5105.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5105.7017 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5107.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 5107.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5109.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 5109.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 5110.2017 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5110.7017 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5111.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5112.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 5113.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5113.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5114.2017 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 5115.1791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5115.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5115.9291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5116.6791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5117.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 5117.4291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 5117.7017 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 5119.2017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 5120.7017 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 5126.1184 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 5141.1184 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 5146.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 5147.5351 | TurbineInstallation
| Feeder 0 | Delay | 1293 | 6465000 | ACTION | 6410.4291 | TurbineInstallation
| WTIV | Delay | 1263 | 13156250 | ACTION | 6410.5351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6410.9151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6412.9151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6413.9151 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6414.6751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6416.6751 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6417.6751 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6418.8151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6420.8151 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6421.8151 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6423.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6425.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6426.3351 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6427.3351 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6428.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6430.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6431.8351 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6432.3351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6433.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6435.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6435.8351 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6437.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6438.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6439.3351 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 1441.9 | 7209500 | ACTION | 6439.3351 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6439.3359 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6440.8351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6442.3351 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6447.7517 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6453.6724 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6453.6732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay: Not enough vessels for turbines | 5.9215 | 61682.1683 | ACTION | 6453.6732 | TurbineInstallation | [14 empty] | Site
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6468.6732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6474.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6475.0899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6475.4699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6477.4699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6478.4699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6479.2299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6481.2299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6482.2299 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6482.5791 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6483.3699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6484.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6485.3699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6486.3699 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6486.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6487.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6488.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6489.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6490.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6490.8899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6491.8899 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6492.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6493.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6493.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6494.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6494.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6495.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6496.3899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6496.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6496.8899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6498.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6498.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6499.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6500.3899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6500.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6502.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6504.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6505.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6506.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 1 | 5000 | ACTION | 6507.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6508.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6510.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 3 | 15000 | ACTION | 6513.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6515.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6517.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 17 | 177083.3333 | ACTION | 6517.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6518.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6519.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6520.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6520.8899 | TurbineInstallation
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6521.0791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6521.8291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6522.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6522.5791 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6523.3291 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6523.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6529.3065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6544.3065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6549.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6550.7232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6551.1032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6553.1032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6554.1032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6554.8632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6556.8632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6557.8632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6559.0032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6561.0032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6562.0032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6563.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6565.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6566.5232 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6566.5724 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 6566.5732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6567.5232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6569.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6571.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6572.0232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6572.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6574.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6575.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6576.0232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6577.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6579.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6579.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6581.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6582.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6587.9399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6602.9399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6608.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6609.3565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6609.7365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6611.7365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6612.7365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6613.4965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6615.4965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6616.4965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6617.6365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6619.6365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6620.6365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6622.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6624.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6625.1565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6626.1565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6627.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6629.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6630.6565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6631.1565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6632.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6634.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6634.6565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6636.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6637.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6638.1565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 184.4833 | 922416.6667 | ACTION | 6638.1565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 71.5833 | 357916.6667 | ACTION | 6638.1565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6638.1574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6639.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6641.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6646.5732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6661.5732 | TurbineInstallation
| Feeder 0 | Delay | 27 | 135000 | ACTION | 6665.1574 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 6665.5732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6670.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6671.9899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6672.3699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6674.3699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6675.3699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6676.1299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6678.1299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6679.1299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6680.2699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6682.2699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6683.2699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6684.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6686.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6687.7899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6688.7899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6690.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6692.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6693.2899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6693.7899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6695.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6696.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6697.2899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6698.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6700.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6700.7899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6702.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6703.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6708.4006 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6709.2065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6710.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6712.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6714.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6716.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6718.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6719.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6719.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6720.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6722.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6724.2065 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6724.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6726.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6728.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6729.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6730.6232 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6730.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6731.0032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6731.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6732.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6732.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6733.0032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6734.0032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6734.7632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6734.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6736.7632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6736.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6737.7632 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6738.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6738.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 6740.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6740.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6741.9032 | TurbineInstallation
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 6742.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6743.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6744.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 6745.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Delay | 1 | 5000 | ACTION | 6746.1506 | TurbineInstallation
| WTIV | Delay | 16 | 166666.6667 | ACTION | 6757.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6759.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6761.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6762.4232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6763.4232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6764.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6766.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6767.9232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6768.4232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6769.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6771.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6771.9232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6773.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6774.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6775.4232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6776.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6778.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6783.8399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 6789.3939 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 6789.3947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6798.8399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6804.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6805.2565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6805.6365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6807.6365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6808.6365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6809.3965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 15 | 156250 | ACTION | 6824.3965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6826.3965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6827.3965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6828.5365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6830.5365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6831.5365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6833.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6835.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6836.0565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6837.0565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6838.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6840.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6841.5565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6842.0565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6843.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6845.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6845.5565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6847.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6848.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6849.0565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 210.9 | 1054500 | ACTION | 6849.0565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 59.6618 | 298309.2259 | ACTION | 6849.0565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 6849.0574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6850.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6852.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6857.4732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6872.4732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6877.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6878.8899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6879.2699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6881.2699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6882.2699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6883.0299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6885.0299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6886.0299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6887.1699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6889.1699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6890.1699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6891.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 6892.3006 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6893.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6894.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6894.6899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6895.6899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6896.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6897.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6898.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6899.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6900.1899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6900.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6900.6899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6902.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6902.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6903.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6903.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6903.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6904.1899 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6904.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6905.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6906.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6907.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 6907.6899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6908.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6910.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Delay | 2 | 10000 | ACTION | 6912.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6914.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 8 | 83333.3333 | ACTION | 6915.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6916.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 6917.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6917.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6918.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 6918.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6918.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6920.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6922.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 6924.1065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6924.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 6926.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 6928.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6929.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6930.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 6931.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 6939.1065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 6944.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6945.5232 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6946.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 6946.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 38 | 190000 | ACTION | 6969.0506 | TurbineInstallation
| WTIV | Delay | 29 | 302083.3333 | ACTION | 6975.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6977.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6978.9032 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 6979.9032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 6980.6632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 3 | 31250 | ACTION | 6983.6632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6985.6632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6986.6632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 6987.8032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6989.8032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 6990.8032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 6992.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 6994.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 6995.3232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 6996.3232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 6997.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 6999.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7000.8232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7001.3232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7002.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7004.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7004.8232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7006.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7007.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7008.3232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7009.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7011.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7012.2939 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7012.2947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7016.7399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7031.7399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7037.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7038.1565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7038.5365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7040.5365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7041.5365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7042.2965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7044.2965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7045.2965 | TurbineInstallation
| WTIV | Delay | 5 | 52083.3333 | ACTION | 7050.2965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7051.4365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 7053.4365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7055.4365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7056.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7057.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 35 | 364583.3333 | ACTION | 7092.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7094.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7095.9565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7096.9565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7098.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7100.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7101.4565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7101.9565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7103.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7104.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7105.4565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7106.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7108.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7108.9565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 259.9 | 1299500 | ACTION | 7108.9565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 96.6618 | 483309.2259 | ACTION | 7108.9565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7108.9574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7110.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7111.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7117.3732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7132.3732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7137.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7138.7899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7139.1699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7141.1699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7142.1699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7142.9299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7144.9299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7145.9299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7147.0699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7149.0699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7150.0699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7151.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7152.2006 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7153.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7154.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7154.5899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7155.5899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7156.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7157.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7158.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7159.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7160.0899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7160.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7160.5899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7162.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7162.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7162.9506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7163.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7163.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7164.0899 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7164.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7165.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7166.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7167.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7167.5899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7168.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7169.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7170.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7170.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7172.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7174.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7175.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7175.9506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7176.0065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7176.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7178.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7180.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7182.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7184.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7186.7006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7187.4506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7188.2006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7188.9506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7191.0065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7196.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7197.4232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7197.8032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7199.8032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7200.8032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7201.5632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7203.5632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7204.5632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7205.7032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7207.7032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7208.7032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7210.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7212.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7213.2232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7214.2232 | TurbineInstallation
| Feeder 0 | Delay | 33 | 165000 | ACTION | 7221.9506 | TurbineInstallation
| WTIV | Delay | 8 | 83333.3333 | ACTION | 7222.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7223.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 6 | 62500 | ACTION | 7229.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7231.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7232.7232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7233.2232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7234.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7236.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7236.7232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7238.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7239.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7240.2232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7241.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7243.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7248.6399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7263.6399 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7265.1939 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7265.1947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7269.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7270.0565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7270.4365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7272.4365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7273.4365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7274.1965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7276.1965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7277.1965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7278.3365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7280.3365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7281.3365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7282.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 16 | 166666.6667 | ACTION | 7298.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7300.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7301.8565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7302.8565 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 7306.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7308.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7310.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7311.3565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7311.8565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7313.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7314.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7315.3565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7316.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7318.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7318.8565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 209.9 | 1049500 | ACTION | 7318.8565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 53.6618 | 268309.2259 | ACTION | 7318.8565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7318.8574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7320.3565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7321.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7327.2732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7342.2732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7347.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7348.6899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7349.0699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7351.0699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7352.0699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7352.8299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7354.8299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7355.8299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7356.9699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7358.9699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7359.9699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7361.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7362.1006 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7363.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7364.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7364.4899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7365.4899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7366.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7366.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7368.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7368.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7369.9899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7370.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7370.4899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7371.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7372.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7372.8506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7373.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7373.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7373.9899 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7374.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7375.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7376.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7376.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7377.4899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7378.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7378.9899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7380.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7380.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7382.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7384.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7385.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7385.8506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7385.9065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7386.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7388.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7390.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7392.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7394.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7396.6006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7397.3506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7398.1006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7398.8506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7400.9065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7406.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7407.3232 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7442.0939 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7442.0947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 59 | 614583.3333 | ACTION | 7466.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7466.7032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7468.7032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7469.7032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7470.4632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7472.4632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7473.4632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7474.6032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7476.6032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7477.6032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7479.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7481.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7482.1232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7483.1232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7484.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7486.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7487.6232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7488.1232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7489.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7491.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7491.6232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7493.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7494.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7495.1232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7496.6232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7498.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7503.5399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7518.5399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7523.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7524.9565 | TurbineInstallation
| WTIV | Delay | 25 | 260416.6667 | ACTION | 7549.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7550.3365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7552.3365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7553.3365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7554.0965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7556.0965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7557.0965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7558.2365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7560.2365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7561.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7562.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7564.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7565.7565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7566.7565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7568.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7570.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7571.2565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7571.7565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7573.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7574.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7575.2565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7576.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7578.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7578.7565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 259.9 | 1299500 | ACTION | 7578.7565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 136.6618 | 683309.2259 | ACTION | 7578.7565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7578.7574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7579.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7581.2565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7582.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7588.1732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 10 | 50000 | ACTION | 7588.7574 | TurbineInstallation
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7603.1732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7608.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7609.5899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7609.9699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7611.9699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7612.9699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7613.7299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7615.7299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7616.7299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7617.8699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7619.8699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7620.8699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7622.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7624.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7625.3899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7626.3899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7627.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7629.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7630.8899 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7631.3899 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7632.0006 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7632.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7634.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7634.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7634.8899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7636.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7636.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7637.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7638.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7638.3899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7639.8899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7640.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7641.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7642.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7642.7506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7643.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7644.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7646.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7646.8065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7648.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7650.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7652.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7654.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7655.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7655.7506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7656.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7658.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7660.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7661.8065 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7662.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7664.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7666.5006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7667.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7667.2506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7668.0006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7668.2232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7668.6032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7668.7506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7670.6032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7671.6032 | TurbineInstallation
| WTIV | Delay | 4 | 41666.6667 | ACTION | 7675.6032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7676.3632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7678.3632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7679.3632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7680.5032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7682.5032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7683.5032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7685.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7687.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7688.0232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7689.0232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7690.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7692.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7693.5232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7694.0232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7695.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7697.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7697.5232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7699.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7700.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7701.0232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7702.5232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7704.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7709.4399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7711.9939 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 7711.9947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7724.4399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7729.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7730.8565 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 7731.8565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7732.2365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7734.2365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7735.2365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7735.9965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7737.9965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7738.9965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7740.1365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7742.1365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7743.1365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7744.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7746.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7747.6565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7748.6565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7750.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7752.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7753.1565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7753.6565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7755.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7756.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7757.1565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7758.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7760.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7760.6565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 181.9 | 909500 | ACTION | 7760.6565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 48.6618 | 243309.2259 | ACTION | 7760.6565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7760.6574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7762.1565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7763.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7769.0732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7784.0732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7789.4899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7790.4899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7790.8699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7792.8699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7793.8699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7794.6299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7796.6299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7797.6299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7798.7699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7800.7699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7801.7699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7803.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7803.9006 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7805.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7805.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7806.2899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7807.2899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7807.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7808.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7809.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7810.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7811.7899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7811.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7812.2899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7813.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7813.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7814.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7815.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7815.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7815.7899 | TurbineInstallation
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7816.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7817.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7818.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7818.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7819.2899 | TurbineInstallation
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7820.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7820.7899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7822.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7822.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7824.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7826.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7826.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7827.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7827.7065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7828.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7830.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7832.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7834.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Tower Section | 2 | 10000 | ACTION | 7836.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Nacelle | 2 | 10000 | ACTION | 7838.4006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7839.1506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7839.9006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 1 | Fasten Blade | 0.75 | 3750 | ACTION | 7840.6506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7842.7065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7848.1232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7849.1232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7849.5032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7851.5032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7852.5032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7853.2632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7855.2632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7856.2632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7857.4032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7859.4032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7860.4032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7861.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7863.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7864.9232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7865.9232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7867.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7869.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7870.4232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7870.9232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7872.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7873.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7874.4232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7875.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7877.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7877.9232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7879.4232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7880.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 7883.8939 | TurbineInstallation
| Feeder 1 | Jackup | 0.00083417 | 4.1708 | ACTION | 7883.8947 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7886.3399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7901.3399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7906.7565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7907.7565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7908.1365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7910.1365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7911.1365 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7911.8965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7913.8965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7914.8965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7916.0365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7918.0365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7919.0365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7920.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7922.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7923.5565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7924.5565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7926.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7928.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7929.0565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7929.5565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7931.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7932.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7933.0565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7934.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7936.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7936.5565 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 175.9 | 879500 | ACTION | 7936.5565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Queue | 52.6618 | 263309.2259 | ACTION | 7936.5565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 7936.5574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7938.0565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7939.5565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 7944.9732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 7959.9732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 7965.3899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7966.3899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 7966.7699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7968.7699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7969.7699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 7970.5299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7972.5299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7973.5299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 7974.6699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7976.6699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 7977.6699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 7979.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 7979.8006 | TurbineInstallation
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 7981.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7981.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 7982.1899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7983.1899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7983.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 7984.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7985.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 7986.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 7987.6899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7987.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7988.1899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7989.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 7989.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7990.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7991.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7991.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7991.6899 | TurbineInstallation
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 7992.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7993.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7994.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7994.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 7995.1899 | TurbineInstallation
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7996.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 7996.6899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 7998.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 7998.1899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Tower Section | 2 | 10000 | ACTION | 8000.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Nacelle | 2 | 10000 | ACTION | 8002.0506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8002.8006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8003.5506 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8003.6065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Fasten Blade | 0.75 | 3750 | ACTION | 8004.3006 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Position Onsite | 15 | 156250 | ACTION | 8018.6065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8024.0232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8025.0232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8025.4032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8027.4032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8028.4032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8029.1632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8031.1632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8032.1632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8033.3032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8035.3032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8036.3032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8037.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8039.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8040.8232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8041.8232 | TurbineInstallation
| WTIV | Delay | 10 | 104166.6667 | ACTION | 8051.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8053.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8055.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 0 | Delay | 52 | 260000 | ACTION | 8056.3006 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8056.3232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8056.8232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8058.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8059.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8060.3232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8061.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8063.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8063.8232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8065.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 2 | 20833.3333 | ACTION | 8067.3232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8068.8232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8074.2399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 8089.2399 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8094.6565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8095.6565 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8096.0365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8098.0365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8099.0365 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8099.5439 | TurbineInstallation
| Feeder 0 | Jackup | 0.00083417 | 4.1708 | ACTION | 8099.5447 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8099.7965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8101.7965 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8102.7965 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8103.9365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8105.9365 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8106.9365 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8108.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8110.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8111.4565 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8112.4565 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8113.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8115.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8116.9565 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8117.4565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8118.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8120.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8120.9565 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8122.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8123.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8124.4565 | TurbineInstallation
| Feeder 1 | ActiveFeeder | 187.9 | 939500 | ACTION | 8124.4565 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Queue | 24.9118 | 124559.2259 | ACTION | 8124.4565 | TurbineInstallation | [14 empty] | Site
| Feeder 1 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8124.4574 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8125.9565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8127.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 45 | 468750 | ACTION | 8172.4565 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| Feeder 1 | Delay | 53 | 265000 | ACTION | 8177.4574 | TurbineInstallation
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8177.8732 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 8192.8732 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8198.2899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8199.2899 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8199.6699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8201.6699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8202.6699 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8203.4299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8205.4299 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8206.4299 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8207.5699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8209.5699 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8210.5699 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8212.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8214.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8215.0899 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8216.0899 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8217.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8219.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8220.5899 | TurbineInstallation
| Feeder 1 | Transit | 43.2432 | 216216.2162 | ACTION | 8220.7006 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8221.0899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8222.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8224.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8224.5899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8226.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8227.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8228.0899 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8229.5899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8231.0899 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8236.5065 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Position Onsite | 15 | 156250 | ACTION | 8251.5065 | TurbineInstallation
| WTIV | Jackup | 5.4167 | 56423.6111 | ACTION | 8256.9232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8257.9232 | TurbineInstallation
| WTIV | Lift Tower Section | 0.38 | 3958.3333 | ACTION | 8258.3032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8260.3032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8261.3032 | TurbineInstallation
| WTIV | Lift Tower Section | 0.76 | 7916.6667 | ACTION | 8262.0632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8264.0632 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8265.0632 | TurbineInstallation
| WTIV | Lift Tower Section | 1.14 | 11875 | ACTION | 8266.2032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8268.2032 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Tower Section | 1 | 10416.6667 | ACTION | 8269.2032 | TurbineInstallation
| WTIV | Lift Tower Section | 1.52 | 15833.3333 | ACTION | 8270.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Tower Section | 2 | 20833.3333 | ACTION | 8272.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Nacelle | 1 | 10416.6667 | ACTION | 8273.7232 | TurbineInstallation
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8274.7232 | TurbineInstallation
| WTIV | Lift Nacelle | 1.5 | 15625 | ACTION | 8276.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Nacelle | 2 | 20833.3333 | ACTION | 8278.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Reequip | 1 | 10416.6667 | ACTION | 8279.2232 | TurbineInstallation
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8279.7232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8281.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8282.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8283.2232 | TurbineInstallation
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8284.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8286.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Release Blade | 0.5 | 5208.3333 | ACTION | 8286.7232 | TurbineInstallation
| Feeder 0 | ActiveFeeder | 162.2667 | 811333.3333 | ACTION | 8286.7232 | TurbineInstallation | [14 empty] | Site
| Feeder 0 | Jackdown | 0.00083417 | 4.1708 | ACTION | 8286.724 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5
| WTIV | Lift Blade | 1.5 | 15625 | ACTION | 8288.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 27 | 281250 | ACTION | 8315.2232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Attach Blade | 1.5 | 15625 | ACTION | 8316.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8317.7232 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Jackdown | 5.4167 | 56423.6111 | ACTION | 8323.1399 | TurbineInstallation | TurbineInstallation | 15 | 25 | 10 | 10 | 2 | 1 | 2 | 2 | 1 | 2 | 0.75 | 0.5 | 1.5 |  | 22.5 | 150
| WTIV | Transit | 13 | 135416.6667 | ACTION | 8336.1399 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8337.1399 | TurbineInstallation
| WTIV | Transit | 1 | 10416.6667 | ACTION | 8338.1399 | TurbineInstallation
| WTIV | Delay | 1 | 10416.6667 | ACTION | 8339.1399 | TurbineInstallation
| Feeder 0 | Delay | 57 | 285000 | ACTION | 8343.724 | TurbineInstallation
| WTIV | Transit | 29.2432 | 304617.1171 | ACTION | 8368.3831 | TurbineInstallation
| Feeder 0 | Transit | 43.2432 | 216216.2162 | ACTION | 8386.9673 | TurbineInstallation